## Status 2026-10-26
ATIP product tracker — status 2026-10-26 (DONE / IN PROGRESS / GAP / BLOCKED)
DONE: 142 | IN PROGRESS: 188 | GAP: 14 | BLOCKED: 32 | total: 376
ID | Module | Feature | Priority | Status (2026-10-26) | Evidence (2026-10-26) | Previous tracker status | Next action | Key files
DP-02 | Data Platform | Daily OHLCV history | P0 | DONE | 9 missing sessions (8, 12-16, 19, 21, 22 Oct) backfilled from NSE 2026-10-26; 0 trading days missing since 2025-03-03; delivery filled for the same sessions | COMPLETED | Maintain | data/bhavcopy.py; data/dhan.py
DP-07 | Data Platform | Delivery data | P1 | DONE | 9 missing sessions (8, 12-16, 19, 21, 22 Oct) backfilled from NSE 2026-10-26; 0 trading days missing since 2025-03-03; delivery filled for the same sessions | COMPLETED | Maintain | data/bhavcopy.py
DP-20 | Data Platform | Trading calendar | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Add next year's holidays each December | utils/trading_calendar.py
TA-01 | Technical Analysis | Core indicators | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | data/technical.py
TA-02 | Technical Analysis | Extended oscillators | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | data/technical.py
TA-05 | Technical Analysis | Fibonacci | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Independent QA | data/technical.py; data/technical_ext.py
TA-07 | Technical Analysis | Trend features | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | data/technical.py
TA-08 | Technical Analysis | Relative strength | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Independent QA; IC research before any score use | scores/engine.py; data/technical_ext.py
SC-03 | Alpha/Factor Engine | RRI | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Institutional input improves with SC-14 | scores/engine.py
SC-04 | Alpha/Factor Engine | MRI | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/engine.py
SC-07 | Alpha/Factor Engine | ZPI | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/engine.py
SC-10 | Alpha/Factor Engine | Portfolio Health score | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py
PF-05 | Portfolio | Portfolio health | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/portfolio_health.py
SC-11 | Alpha/Factor Engine | Trade of the Day | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/engine.py
SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/engine.py
SC-17 | Alpha/Factor Engine | Configurable weights | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Regime-specific rows used by ML-05 | db/schema.py
SG-02 | Signal Engine | Signal validation | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | pipeline/scheduler.py
SG-03 | Signal Engine | Signal ranking | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/engine.py
SG-05 | Signal Engine | Trade plan | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/predictions.py
SG-06 | Signal Engine | Outcome tracking | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/signal_log.py
SG-07 | Signal Engine | Signal provenance log | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/signal_log.py
BT-01 | Backtesting | Historical backtest | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py
BT-10 | Backtesting | Win rate / profit factor / expectancy | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | strategy/backtest_aggressive.py
RK-02 | Risk Management | Max order value | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Set values in config.json | orders/risk.py
RK-03 | Risk Management | Max orders per day | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Set values in config.json | orders/risk.py
RK-04 | Risk Management | Max open positions | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Set values in config.json | orders/risk.py
RK-05 | Risk Management | Symbol exposure limit | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Set values in config.json | orders/risk.py
RK-14 | Risk Management | Crash-risk gating | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | scores/engine.py
EX-03 | Execution | Position management | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | strategy/positions.py
EX-04 | Execution | Entry/exit | P0 | IN PROGRESS | merged (PR #17) and scheduled every 2 min in market hours; cannot manage positions without Dhan quotes: alert added 2026-10-26; no open positions | COMPLETED | Maintain | strategy/live.py
EX-05 | Execution | Stop loss | P0 | IN PROGRESS | merged (PR #17) and scheduled every 2 min in market hours; cannot manage positions without Dhan quotes: alert added 2026-10-26; no open positions | COMPLETED | Maintain | strategy/aggressive.py
EX-06 | Execution | Trailing stop | P0 | IN PROGRESS | merged (PR #17) and scheduled every 2 min in market hours; cannot manage positions without Dhan quotes: alert added 2026-10-26; no open positions | COMPLETED | Maintain | strategy/aggressive.py
EX-07 | Execution | Profit booking / partial exit | P1 | IN PROGRESS | merged (PR #17) and scheduled every 2 min in market hours; cannot manage positions without Dhan quotes: alert added 2026-10-26; no open positions | COMPLETED | Maintain | strategy/aggressive.py
EX-13 | Execution | Paper trading | P0 | BLOCKED | paper fills need Dhan quotes (orders/paper.py rejects without one): 7 paper orders ever, last 2026-09-17. Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | COMPLETED | Maintain | orders/paper.py
EX-14 | Execution | Live gating | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | orders/environment.py
BR-01 | Broker Integration | Dhan | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | data/dhan.py; orders/broker.py
BR-03 | Broker Integration | Broker abstraction | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Becomes multi-broker interface in ENT-15 | orders/environment.py
DB-01 | Dashboard | Market Health panel | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-02 | Dashboard | Global Markets panel | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-03 | Dashboard | FII/DII panel | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-05 | Dashboard | Sector Rotation | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-07 | Dashboard | Top 25 VPI | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-08 | Dashboard | Buy Zone (ZPI) | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-09 | Dashboard | Recovery (RRI) | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-10 | Dashboard | Momentum Reversal (MRI) | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-12 | Dashboard | Portfolio Health panel | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-13 | Dashboard | Trade of the Day | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-15 | Dashboard | Orders/signals panel | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
DB-19 | Dashboard | Hosted read-only snapshot | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Superseded by ENT-08 web app | publish_snapshot.py
API-01 | APIs | Internal REST | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | dashboard/server.py
API-02 | APIs | Local API authentication | P0 | DONE | install token for the owner; per-session tokens for other tenants since 5ee26cb (R12, merged f6ceb25); owner pages verified to carry the install token on 2026-10-26 after the restart | COMPLETED | Replaced by per-user auth in SEC-02 | dashboard/security.py
DBS-01 | Database | Schema | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Migrations via DBS-04 | db/schema.py
DBS-02 | Database | Retention/purge | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | db/purge.py
SEC-01 | Security | Credential handling | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Move legacy plaintext keys out of config.json (owner action) | ops/secrets.py; ops/logs.py
MON-07 | Monitoring | Feed health | P1 | DONE | broker health reports Dhan market data DOWN and names the inactive Data API plan (2026-10-26 20:28) | COMPLETED | Maintain | data/dhan_ws.py
MON-08 | Monitoring | Diagnostics | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | ops/health.py; dashboard/ops_routes.py
OPS-01 | Deployment/Ops | Autostart/scheduling | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml
OPS-07 | Deployment/Ops | Snapshot publishing | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Maintain | publish_snapshot.py
DP-09 | Data Platform | India VIX | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | None for DP-09; VIX term structure/percentile features belong to later factor work | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py
DP-17 | Data Platform | Market breadth | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Survivorship-free universe (BT-15); sector-level breadth (DP-13) | scores/engine.py; db/schema.py
SC-09 | Alpha/Factor Engine | Market Health score | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | FII/DII and global history only from 2026-07 (backfilled coverage avg 0.65); determine_signal still defaults a missing MH to 50; model-based regime is ML-05 | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py
SC-08 | Alpha/Factor Engine | ACS | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | NewsConfidence stays absent until NS-02 (Anthropic key) classifies news | scores/engine.py; data/news.py; db/schema.py
MON-01 | Monitoring | Job logging | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Record failures, end time, row counts | pipeline/scheduler.py; db/schema.py
MON-02 | Monitoring | Stalled-job detection | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Expected-run table + missed-run check | pipeline/health.py; pipeline/scheduler.py
MON-03 | Monitoring | Failure alerting | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Configure Telegram; alert on failure/stall | alerts/telegram.py; dashboard/server.py
DB-14 | Dashboard | Alerts / morning brief | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Deliver digest; verify daily | alerts/telegram.py
RK-15 | Risk Management | Risk alerts | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Alert on halt, limit breach, CRI spike | orders/risk.py; orders/broker.py
MON-06 | Monitoring | Log rotation | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | RotatingFileHandler | main.py
DBS-06 | Database | Timestamp consistency | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Normalise; fix news recency | db/schema.py; data/news.py; tools/repair_news_timezone.py
NS-01 | News/Sentiment | News ingestion | P0 | IN PROGRESS | 9 RSS feeds, 5 working (3 failing 21x, MoneyControl 0 items); fetched before 09:15 on 1 of the last 10 sessions (ATIP down 13-23 Oct) | COMPLETED | Fix job; add second source; health check | data/news.py; pipeline/scheduler.py
OPS-03 | Deployment/Ops | Install/setup | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Fix requirements/setup; pin versions | setup.py; install.bat; requirements-dev.txt; docs/DEV_SETUP.md
EX-01 | Execution | Order management tests | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Independent QA | orders/rules.py
OPS-02 | Deployment/Ops | CI + end-to-end test | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Independent QA; network download steps are exercised only live | pipeline/scheduler.py; .github/workflows/tests.yml
DP-15 | Data Platform | Fundamentals | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | First full backfill (python -m data.nse_filings, ~1 h); --history for pre-2025 quarters; QA | data/nse_filings.py; data/nse_api.py; data/fundamentals.py; pipeline/scheduler.py
SC-13 | Alpha/Factor Engine | Fundamental Score | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Enable fundamentals.score_enabled after QA; IC study once history exists | scores/fundamental.py; scores/engine.py
SC-02 | Alpha/Factor Engine | SPI | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Enable after QA; measure SPI/FS correlation (QR-03) | scores/fundamental.py; scores/engine.py
SC-05 | Alpha/Factor Engine | CRI debt input | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Feed Debt/Equity | scores/engine.py
SC-01 | Alpha/Factor Engine | VPI inputs | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Real Fundamental Growth input | scores/engine.py
PF-01 | Portfolio | Portfolio ingestion | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Scheduled reliable sync + token handling | data/dhan.py; portfolio/zerodha.py
BR-04 | Broker Integration | Portfolio sync schedule | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Scheduled sync with alert on failure | pipeline/scheduler.py; pipeline/health.py
PF-02 | Portfolio | Holdings & P&L | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Realised + unrealised P&L | portfolio/pnl.py; dashboard/server.py
PF-13 | Portfolio | Daily P&L series | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Daily P&L table; EOD job | portfolio/pnl.py; db/schema.py
RK-13 | Risk Management | Risk-based sizing wired to orders | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Use size in order path | orders/risk.py; orders/rules.py
RK-07 | Risk Management | Daily loss limit | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Limit on PF-13; auto-halt | orders/risk.py
RK-08 | Risk Management | Drawdown limit | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Peak-to-trough on PF-13; auto-halt | orders/risk.py
DBS-03 | Database | Backups | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Off-machine copy of backups; restore drill | ops/backup.py; docs/BACKUP_RESTORE.md
DP-06 | Data Platform | Corporate actions open items | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py
TA-06 | Technical Analysis | Support/Resistance | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; optionally feed the Technical Score SR component | data/technical_ext.py
DP-19 | Data Platform | Data quality layer | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | DQS table; outlier and timestamp checks | data/quality.py; pipeline/scheduler.py
DBS-04 | Database | Schema migrations | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Down-migration scripts beyond rollback notes (policy: restore pre-release backup) | ops/migrations.py; db/schema.py
DP-01 | Data Platform | Live market data | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Enable and observe one live session (cannot be exercised outside market hours) | data/stock_feed.py; main.py
DP-03 | Data Platform | Intraday bars | P0 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | QA; consider 5-min bars for session VWAP | data/dhan.py; db/schema.py; db/purge.py
TA-03 | Technical Analysis | VWAP | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Owner: technical.vwap_in_score (changes scores); QA | data/technical_ext.py; data/technical.py
SC-12 | Alpha/Factor Engine | Technical Score VWAP input | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Include VWAP | data/technical.py
TA-04 | Technical Analysis | Volume Profile | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | data/technical_ext.py
TA-10 | Technical Analysis | Multi-timeframe analysis | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | data/technical_ext.py
TA-12 | Technical Analysis | Full-history indicator panel | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run the backfill (owner timing; copy first) | data/technical.py
AF-03 | Alpha/Factor Engine | Factor panel persistence | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | scores/engine.py; scores/formulas.py
AF-04 | Alpha/Factor Engine | Standalone factor families | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; research on full history | quant/factors.py
AF-02 | Alpha/Factor Engine | Normalisation contract | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | quant/normalize.py
AF-01 | Alpha/Factor Engine | Factor library/registry | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | quant/factors.py
SC-18 | Alpha/Factor Engine | Formula registry/versioning | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | scores/formulas.py
DBS-07 | Database | Research registry tables | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | quant/studies.py
QR-01 | Quant Research | Information coefficient | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run full-history backfill + report | quant/research.py
QR-02 | Quant Research | IC decay / half-life | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run on full history | quant/research.py
QR-03 | Quant Research | Factor correlation/redundancy | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run on full history | quant/research.py
QR-04 | Quant Research | Statistical toolkit | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | quant/statarb.py; quant/normalize.py; quant/volatility.py
AF-08 | Alpha/Factor Engine | Factor approval gate | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: enable after review | quant/approval.py; strategy_engine/lifecycle.py
BT-16 | Backtesting | Dated equity curve / run records | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Dated trades + equity curve + run table | backtest/store.py; db/schema.py
BT-08 | Backtesting | Portfolio-level backtest | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Portfolio simulator | backtest/engine.py
BT-09 | Backtesting | Drawdown analysis | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Compute on equity curve | backtest/metrics.py
BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Implement | backtest/metrics.py
BT-12 | Backtesting | VaR/CVaR in backtest | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | backtest/metrics.py
BT-05 | Backtesting | Itemised costs | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Indian cost model shared by backtest and paper | backtest/costs.py; backtest/config.py
BT-06 | Backtesting | Slippage in backtest | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Shared slippage model | backtest/slippage.py
BT-07 | Backtesting | Liquidity constraints | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | All engines | backtest/liquidity.py
DP-18 | Data Platform | Survivorship-free universe | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Store constituent history | data/index_constituents.py
BT-15 | Backtesting | Bias controls | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Systematic checks | backtest/data.py; backtest/engine.py
BT-03 | Backtesting | In/out-of-sample | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Formal splits | backtest/periods.py; backtest/service.py
BT-02 | Backtesting | Walk-forward | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Implement | backtest/walkforward.py
BT-13 | Backtesting | Monte Carlo | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Implement | backtest/montecarlo.py
BT-04 | Backtesting | Parameter optimisation | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | backtest/optimize.py
QR-11 | Quant Research | Parameter sensitivity | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | backtest/sensitivity.py
BT-14 | Backtesting | Robustness | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. W40: first / second-order stochastic dominance of the selected trial's out-of-sample results over a random selection (in pbo() and CPCV); CPCV on the event-driven engine (engine="event_driven") | backtest/robustness.py; backtest/cpcv.py
QR-12 | Quant Research | Reproducibility / experiment tracking | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | quant/experiments.py; quant/studies.py
QR-07 | Quant Research | Momentum/trend research | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run full-universe study; review | backtest/strategies.py; backtest/study.py
QR-08 | Quant Research | Mean-reversion research | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run full-universe study; review | backtest/strategies.py; backtest/study.py
QR-13 | Quant Research | Signal outcome research by regime | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Add regime/ACS buckets | scores/signal_log.py
TA-09 | Technical Analysis | Beta 3y / rolling 60 | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: prices_daily retention >= 1,100 days for a 3-year beta | data/technical_ext.py
SC-16 | Alpha/Factor Engine | Beta Risk Index | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; decide if it joins a composite | data/technical_ext.py
TA-11 | Technical Analysis | Extended indicator catalogue | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | data/technical_ext.py; data/technical.py
DP-08 | Data Platform | Derivatives data | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; verify NSE option-chain fields live | data/derivatives_store.py; data/derivatives.py
SC-06 | Alpha/Factor Engine | MSI | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | AI news input to MSI (W28, NS-*) | scores/engine.py; data/derivatives.py
DP-10 | Data Platform | FII/DII history | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Historical backfill source | data/bhavcopy.py
DP-11 | Data Platform | GIFT Nifty | P2 | IN PROGRESS | scheduled on the Mac since 2026-10-26; never ran before (W39 jobs not on the old Windows build); participant OI first run 2026-10-26 20:15 SUCCESS (20 rows); pre-open/GIFT due 08:45-09:09 on 27 Oct | IMPLEMENTED BUT NOT VERIFIED | Pre-open panel (DB-04) | data/market_series.py
DB-04 | Dashboard | GIFT Nifty panel | P2 | IN PROGRESS | scheduled on the Mac since 2026-10-26; never ran before (W39 jobs not on the old Windows build); participant OI first run 2026-10-26 20:15 SUCCESS (20 rows); pre-open/GIFT due 08:45-09:09 on 27 Oct | IMPLEMENTED BUT NOT VERIFIED | QA | dashboard/market_routes.py; dashboard/market_page.py
DP-12 | Data Platform | Global markets | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | India 10Y G-sec: no reliable free source via yfinance (left out, not approximated) | data/markets.py
DP-13 | Data Platform | Sector data | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run --backfill-sectors; QA | data/market_series.py; data/dhan.py
DP-16 | Data Platform | Institutional data | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Daily per-stock MF flow has no free source (quarterly SHP change used); QA | data/institutional.py
SC-14 | Alpha/Factor Engine | Institutional Score | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Enable after QA; IC study | scores/engine.py
AD-03 | Alternative Data | Bulk/block deal signal | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner decision: first study CONTRADICTS INS BulkDeals direction (net SELL deals -> +4.5% 5d abnormal, t=4.1, n=139) on 4 weeks of data -- do not up-weight; re-check as history grows | quant/deal_signal.py
SG-04 | Signal Engine | Rich decision states | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Extended states + stored reasons | strategy_engine/decisions.py
SG-01 | Signal Engine | SELL calibration | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Backtest-based SELL thresholds | scores/engine.py
SE-01 | Strategy Engine | Strategy library | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Strategy interface + registry | strategy_engine/definition.py; registry.py
SE-02 | Strategy Engine | Strategy parameters | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Param store per strategy with versions | strategy_engine/params.py; registry.py
SE-03 | Strategy Engine | Rule-based strategies | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Generic rule definition format | strategy_engine/rules.py; kinds.py
SE-06 | Strategy Engine | Multi-factor strategy | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | IC-weighted multi-factor strategy | strategy_engine/kinds.py
SE-04 | Strategy Engine | Quant strategies | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Implement first quant strategies | strategy_engine/kinds.py; features.py
SE-09 | Strategy Engine | Strategy lifecycle | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | State machine + gates | strategy_engine/lifecycle.py
SE-11 | Strategy Engine | Strategy health | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Health scoring + alerts | strategy_engine/health.py
SE-07 | Strategy Engine | Strategy combination/ranking/selection | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Allocator | strategy_engine/selection.py; kinds.py
SE-08 | Strategy Engine | Regime-aware selection | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Regime-conditional allocation | strategy_engine/selection.py; regime.py; library/regime_mapping.json
SG-08 | Signal Engine | Intraday scans | P2 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | QA; tune thresholds after a few sessions | strategy/intraday_scan.py; pipeline/scheduler.py
DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | scores/lists.py; dashboard/w28_assets.py; scores/engine.py
DB-16 | Dashboard | Strategy performance panel | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | No strategy has run (all DRAFT, no fills) -- panel populates once strategies run in PAPER | strategy_engine/performance.py; dashboard/strategy_page.py
ML-13 | AI/ML | Labels/targets | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | ml/labels.py
ML-07 | AI/ML | Feature selection | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | ml/selection.py
ML-08 | AI/ML | Model validation | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | ml/validation.py
ML-01 | AI/ML | Supervised ML | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Richer features / labels; full-universe validation | ml/trees.py; ml/presets.py
ML-12 | AI/ML | Model registry/versioning | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | ml/registry.py; ml/artifacts.py
ML-11 | AI/ML | Ensemble models | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | ml/trees.py
ML-09 | AI/ML | Model monitoring/drift | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | ml/decay.py; ops/monitor.py
ML-10 | AI/ML | Explainability | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | ml/trees.py; ml/validation.py
ML-05 | AI/ML | Regime detection | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner decides regime provider after evidence | ml/presets.py
ML-03 | AI/ML | Unsupervised learning | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | ml/unsupervised.py
ML-06 | AI/ML | Anomaly detection | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: ml.anomalies_enabled | ml/unsupervised.py
SE-05 | Strategy Engine | AI-driven strategies | P1 | BLOCKED | tracker BLOCKED | BLOCKED | Blocked on a model with edge: no ML model registered in production; W24 validation showed NO_EDGE | ml/ai_strategy.py; dashboard/ml_page.py
NS-02 | News/Sentiment | News classification | P0 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | Working ANTHROPIC_API_KEY (current key 401, KD-001), then news.ai_enabled=true | data/news_ai.py; data/news.py
NS-03 | News/Sentiment | Sentiment + confidence | P0 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | Enable the AI path; compare AI vs rule sentiment on a labelled sample | data/news_ai.py
NS-05 | News/Sentiment | Novelty/decay/source weighting | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; review effect on VPI/MRI/RRI/CRI/ZPI | data/news_weighting.py; data/news.py; scores/engine.py
NS-04 | News/Sentiment | AI news summary | P1 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | Enable AI path | data/news_ai.py; pipeline/scheduler.py
DB-06 | Dashboard | AI News Summary panel | P1 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | QA | dashboard/w28_assets.py
NS-06 | News/Sentiment | Earnings call / announcement NLP | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; verify NSE field names live; owner: news.ai_enabled for document NLP | data/announcements.py; dashboard/w28b_routes.py
ML-02 | AI/ML | Deep learning | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run benefit_check on a real dataset; adopt only if ADOPTABLE | ml/deep.py; ml/models.py; ml/registry.py
ML-04 | AI/ML | Reinforcement learning | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run on the universe; expect NO_ADVANTAGE unless proven otherwise | ml/rl.py
DB-18 | Dashboard | Quant/model panel | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Shows data once a model runs with ml.enabled (none in production) | dashboard/w28_routes.py; dashboard/ml_page.py
PF-03 | Portfolio | Exposure / sector allocation | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | portfolio/risk.py; dashboard/portfolio_risk_routes.py
PF-04 | Portfolio | Concentration/diversification | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | portfolio/risk.py
PF-09 | Portfolio | Correlation | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | portfolio/risk.py; dashboard/execution_page.py
RK-11 | Risk Management | Correlation risk | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; portfolio/limits.py
RK-12 | Risk Management | Portfolio VaR/ES | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | portfolio/risk.py; portfolio/limits.py; execution/risk_engine.py
RK-06 | Risk Management | Sector limits | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | execution/risk_engine.py; execution/positions.py
RK-09 | Risk Management | Volatility limits | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; execution/config.py; portfolio/limits.py
RK-10 | Risk Management | Liquidity limits | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; orders/risk.py; portfolio/limits.py
RK-18 | Risk Management | Strategy risk budget | P2 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Per-strategy capital budgets | execution/risk_engine.py; execution/positions.py
RK-01 | Risk Management | Kill switch scopes + auto-trigger | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Per-strategy/symbol; auto-trigger | orders/risk.py
RK-16 | Risk Management | Emergency exit | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | portfolio/emergency.py; dashboard/portfolio_risk_routes.py
PF-10 | Portfolio | Portfolio optimisation | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; expected-return model review | portfolio/optimize.py
PF-06 | Portfolio | Rebalancing | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. W39b: the event-driven engine (BT-17) now trades ADD / REDUCE too, through its own order model | portfolio/optimize.py; strategy_engine/kinds.py; backtest/engine.py; backtest/event_driven.py; strategy_engine/adapter.py
PF-07 | Portfolio | Risk attribution | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | portfolio/risk.py
PF-08 | Portfolio | Performance attribution | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. Trade-based attribution of the LIVE book now exists in the wealth performance report (PERF-001-07 / -09 / -10 on portfolio LIVE: broker_sync + PF-12 imports) | portfolio/risk.py
PF-11 | Portfolio | CAGR/XIRR analytics | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. LIVE XIRR now comes from the wealth performance ledger (PERF-001-04, portfolio LIVE: Dhan broker_sync + PF-12 broker imports) | portfolio/risk.py; wealth/perf/metrics.py
DB-17 | Dashboard | Risk dashboard | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | dashboard/execution_page.py
EX-02 | Execution | Order types | P0 | GAP | LIVE path supports MARKET / LIMIT only; SL, SL-M and modify exist in PAPER only (orders/broker.py) | IMPLEMENTED BUT NOT VERIFIED | QA; LIVE order types only with live execution (not built) | orders/paper.py; execution/order_manager.py; execution/paper_matching.py; execution/models.py
EX-08 | Execution | Order modify/cancel | P0 | GAP | modify / cancel exist in PAPER only; the LIVE path has none (orders/broker.py) | IMPLEMENTED BUT NOT VERIFIED | QA | execution/order_manager.py; execution/adapters.py; dashboard/w29_routes.py
BR-05 | Broker Integration | Execution reconciliation | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | execution/reconcile.py
BR-06 | Broker Integration | Connection health | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Observe in a live session | execution/broker_health.py
RK-17 | Risk Management | Broker/operational risk | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | execution/risk_engine.py; execution/broker_health.py
BR-08 | Broker Integration | Sandbox | P2 | BLOCKED | tracker BLOCKED | BLOCKED | Needs a Dhan-issued sandbox token (owner) -- then run the check with --place-test-order | orders/environment.py; orders/sandbox_check.py
EX-09 | Execution | Measured slippage | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Meaningful once PAPER strategies execute | execution/analytics.py
EX-10 | Execution | Execution analytics | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | execution/analytics.py; dashboard/execution_page.py
BR-02 | Broker Integration | Zerodha/Kite | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Register http://127.0.0.1:8000/zerodha/callback in the Kite developer console; Kite ORDERS not built (owner decision) | portfolio/zerodha.py; dashboard/w29_routes.py
MON-04 | Monitoring | Live strategy/P&L monitoring | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | QA in a live session | portfolio/live_pnl.py; dashboard/execution_page.py
SEC-03 | Security | Audit logging | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Set audit.offbox_dir (owner: a second drive / NAS / synced folder) | enterprise/audit_export.py
DP-04 | Data Platform | Tick data | P2 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Owner: enable stock feed + capture_ticks; QA | data/ticks.py; data/stock_feed.py
DP-05 | Data Platform | Order book / depth | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: depth.enabled; verify Dhan depth payload live; QA | data/depth.py
AF-07 | Alpha/Factor Engine | Microstructure factors | P2 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Quoted spread / depth / tick features need DP-04 / DP-05 feeds | quant/microstructure.py; quant/w30.py; data/stock_feed.py
AF-06 | Alpha/Factor Engine | Derivatives factors | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run factor IC research once F&O history accumulates | quant/factors.py; quant/engine.py
QR-10 | Quant Research | Volatility strategies | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Backfill IV history (python -m data.derivatives --backfill 250 --recompute) so iv_rank has a year; backtest the two strategies; options strategies (selling vol) not executable in cash | data/derivatives.py; quant/derivatives_features.py; strategy_engine/library/70_*,71_*
QR-05 | Quant Research | Stat-arb / pairs / cointegration | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. W40: the W2 backtest simulates SHORT / COVER as near-month stock futures (lots, margin, daily variation margin, NSE F&O costs, a roll N sessions before expiry; refused, never priced off spot, without futures history); the paper book can auto-roll (futures.auto_roll, off by default). Not modelled: physical settlement, SPAN margin | execution/futures_paper.py; backtest/futures.py; backtest/engine.py
QR-06 | Quant Research | Cross-sectional / market-neutral | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. W40: long/short portfolios backtest with their futures legs (see QR-05); lot granularity still makes small books non-neutral -- check exposure after sizing | strategy_engine/kinds.py
QR-09 | Quant Research | Event-driven research | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | MACRO / INDEX_CHANGE calendars (no free source); earnings history needs the full fundamentals backfill | quant/event_sources.py; quant/event_study.py; quant/events.py; quant/w30.py
AF-05 | Alpha/Factor Engine | Value/quality composites | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Full fundamentals backfill (W27-1) then a factor IC study | quant/factors.py
EX-11 | Execution | Execution algos | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; owner: execution.algo.enabled | execution/algos.py; execution/pipeline.py; dashboard/w34_routes.py
EX-12 | Execution | Market impact model | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; calibration needs live fills | execution/impact.py
EX-15 | Execution | Latency telemetry | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | ops/latency.py; execution/order_manager.py; data/dhan.py; data/dhan_ws.py
EX-16 | Execution | Event-driven OMS | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | execution/events.py; execution/event_handlers.py; execution/order_manager.py
BT-17 | Backtesting | Event-driven backtester | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. W40: reports the adapter's skipped decisions like W2; fix: the end-of-window close-out is now in the last day's return (chained returns overstated final equity by the close-out costs). It still does not trade SHORT (W2 does, as futures) | backtest/event_driven.py; dashboard/w34_routes.py
DP-14 | Data Platform | Macroeconomic data | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; owner: add RBI MPC dates to the calendar | data/macro.py
AD-01 | Alternative Data | Alt-data framework | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | altdata/framework.py
AD-02 | Alternative Data | Alt-data sources | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; IC research before any use | altdata/sources.py
DP-22 | Data Platform | Point-in-time data lake | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: pip install pyarrow duckdb for Parquet + SQL; QA | data/lake.py
DP-21 | Data Platform | Multi-asset data | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; MCX/CDS exchange feeds if a source is chosen | data/multi_asset.py
MON-05 | Monitoring | Model/factor decay monitoring | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Needs factor history (W22 backfill) | ml/decay.py
OPS-06 | Deployment/Ops | DR / backup automation | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: set ops.backup_offsite_dir (second drive / NAS / synced folder) and keep the data key outside it | ops/backup.py; ops/__main__.py; docs/DISASTER_RECOVERY.md
SEC-04 | Security | Encryption | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: python -m ops keygen + vault-migrate --apply; TLS only with ENT-07 (exposure blocked) | ops/vault.py; ops/crypto.py; ops/secrets.py; data/dhan.py; portfolio/zerodha.py; alerts/telegram.py
API-05 | APIs | API contracts/docs | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. Per-route schemas for the internal dashboard routes are not planned: /api/v1 is the published contract | ops/api_docs.py; docs/API_REFERENCE.md; docs/openapi.json
API-06 | APIs | Widget JSON schemas | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; extend as widgets change | dashboard/widget_schemas.py; dashboard/schemas/
OPS-05 | Deployment/Ops | Documentation set | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Refresh after W32/W33 | docs/USER_GUIDE.md; docs/API_REFERENCE.md; docs/DISASTER_RECOVERY.md; docs/ROLLBACK_PROCEDURE.md
ENT-01 | Enterprise Platform | Multi-tenant architecture | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA isolation scenarios (W32 handoff); Postgres (DBS-05) | enterprise/scoping.py; execution/tenant_books.py; execution/adapters.py
DBS-05 | Database | Scalable database | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Run the scheduler's write jobs for a few days on a PostgreSQL copy; connection pool; then decide the switch | db/postgres.py; db/dialect_scan.py; db/backend.py; tools/sqlite_to_postgres.py; docs/POSTGRESQL_MIGRATION.md
ENT-07 | Security | Secure internet exposure | P0 | BLOCKED | tracker BLOCKED | BLOCKED | Owner decision + security architecture | dashboard/security.py
SEC-02 | Security | Users / RBAC / MFA | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | WebAuthn after ENT-07 (HTTPS origin) | enterprise/w32.py; enterprise/mfa.py; enterprise/users.py
ENT-05 | Security | Session management | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | enterprise/users.py; dashboard/enterprise_routes.py
ENT-02 | User Management | User registration/onboarding | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | OAuth / Google / Apple / mobile OTP (need ENT-07) | enterprise/onboarding.py; enterprise/email_flows.py
ENT-03 | User Management | User profile + risk profile | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | enterprise/w32.py; execution/risk_engine.py; enterprise/profiles.py
ENT-06 | Security | Per-user broker credential vault | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; owner stores real credentials on /account and runs verify | enterprise/vault.py; ops/crypto.py; dashboard/w37_routes.py
ENT-14 | Compliance | Regulatory approvals | P0 | BLOCKED | tracker BLOCKED | BLOCKED | LEGAL WORK: a qualified professional must review and sign off each item | ops/regulatory.py; docs/ENT14_REGULATORY_PACK.md
SEC-05 | Security | Compliance monitoring | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: act on the first run's findings (risk_limits unset, 7 plaintext secrets, no encryption key, no restore drill); QA | ops/compliance.py; dashboard/w38_routes.py; dashboard/w38_page.py
ENT-17 | Compliance | Data privacy | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Legal review of the notice (ENT-14 DPDP item); fill saas.company_name / privacy_contact / grievance_officer | enterprise/privacy.py; dashboard/w38_page.py
ENT-08 | Channels | Multi-user web app | P0 | BLOCKED | tracker BLOCKED | BLOCKED | Blocked on ENT-07 for any exposure | dashboard/saas_page.py; dashboard/saas_routes.py
ENT-04 | User Management | Subscriptions & billing | P1 | BLOCKED | tracker BLOCKED | BLOCKED | Owner: run the flows in Razorpay test mode (docs/BILLING_RAZORPAY.md); GST tax lines are not built (ENT-14 PAYMENTS-TAX) | enterprise/payments.py; enterprise/razorpay.py; enterprise/billing.py; enterprise/w32.py; db/schema_billing.py
ENT-18 | User Management | Multi-device login | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | enterprise/users.py; dashboard/saas_routes.py
ENT-19 | Channels | Watchlists | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | enterprise/workspace.py
ENT-11 | Channels | Per-user price & AI alerts | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | enterprise/w32.py; enterprise/workspace.py
ENT-10 | Channels | Notification channels | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | SMS / push / WhatsApp (providers: owner) | enterprise/channels.py; pipeline/scheduler.py
ENT-09 | Channels | Mobile apps | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Native Android/iOS apps not built; reaching /m from a phone needs a private tunnel or the ENT-07 exposure | dashboard/w38_page.py; dashboard/w38_routes.py
API-03 | APIs | Versioned public API | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | enterprise/public_api.py; ops/http.py; ops/__main__.py; docs/API_VERSIONING_POLICY.md
API-04 | APIs | Webhooks | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; verify against real Razorpay test-mode deliveries once ENT-07 gives ATIP a public URL; a broker postback mapping when a broker offers one | enterprise/w32.py; enterprise/razorpay.py; ops/webhooks.py; dashboard/ops_routes.py
PF-12 | Portfolio | Multi-broker import | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA with the owner's real broker exports | portfolio/imports.py; dashboard/w37_page.py
BR-07 | Broker Integration | Additional brokers | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA against real accounts (read-only); live orders need owner + ENT-14 decision | brokers/base.py; brokers/connectors.py; brokers/registry.py
ENT-15 | Execution | Multi-asset trading | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: options.enabled; QA. W40: option-overlay strategies (strategy_engine/option_overlay.py) emit multi-leg OPTION intents -- covered call, protective put, spreads, iron condor and more, strikes by delta or % OTM, monthly expiry -- sized by the risk engine (max loss, margin approximation, naked short calls refused unless allowed), filled all-or-nothing in the paper options book, marked daily, exited by rule, settled at expiry; PAPER only, LIVE refused; a replay on stored daily option prices | execution/options_paper.py; execution/option_intents.py; strategy_engine/option_overlay.py
ENT-12 | Reporting | Reports | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. Tax report content is NOT built: Tax is excluded by the owner (deployment tracker, Scope Exclusions sheet); revisit only if the owner re-scopes it | enterprise/reports.py
ENT-13 | Administration | Administration console | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA | dashboard/saas_routes.py; dashboard/saas_page.py
SE-10 | Strategy Engine | No/low-code strategy builder | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | QA; backtest builder strategies before promotion | strategy_engine/builder.py; dashboard/strategy_builder_page.py
ML-16 | AI/ML | AI chat assistant | P2 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | Owner: assistant.enabled + working ANTHROPIC_API_KEY; QA | ml/chat.py; dashboard/assistant_page.py; dashboard/w36_routes.py
OPS-04 | Deployment/Ops | Cloud deployment | P0 | BLOCKED | hosting and secrets undecided (master file R10); NSE blocks cloud IPs for the Bhavcopy | IMPLEMENTED BUT NOT VERIFIED | Owner: choose a host (ENT-16) and exposure (ENT-07); Kubernetes manifests and a registry push only after that | Dockerfile; docker-compose.yml; .dockerignore; .github/workflows/docker.yml; docs/CONTAINER_DEPLOYMENT.md
ENT-16 | Deployment/Ops | Scalability, HA & observability | P1 | BLOCKED | tracker BLOCKED | BLOCKED | DBS-05 (PostgreSQL path) and OPS-04 (container packaging) are done (W38); multi-instance HA needs the runtime moved to PostgreSQL and a host | ops/shared_state.py; ops/jobs.py; db/backend.py
SEC-06 | Security | API security hardening | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Enable rate limiting in production config | ops/http.py
OPS-08 | Deployment/Ops | Configuration management | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | ops/config.py; ops/startup.py
OPS-09 | Deployment/Ops | Scheduler hardening | P1 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | ops/jobs.py; pipeline/scheduler.py
OPS-10 | Deployment/Ops | Resilience + idempotency | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Observe breaker behaviour in a real outage | data/dhan.py; data/nse_api.py; data/markets.py; data/news.py
MON-09 | Monitoring | Operational alerting | P1 | DONE | Telegram alerts sent 2026-10-26 (ops monitor, job health); new: price-hole and unmanaged-exit alerts | COMPLETED | Tune thresholds after observation | ops/monitor.py
RK-19 | Risk | Stale-data trade protection | P1 | IN PROGRESS | W4 risk engine refuses BUYs while broker health is DOWN/STALE; the W1 path values a MARKET order at 0 without a quote (GAP-2610-06) | COMPLETED | Validate | execution/risk_engine.py; execution/order_manager.py; execution/config.py
OPS-11 | Deployment/Ops | Release management & deployment | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner-authorized production deployment of W25-W33 (not done by development) | ops/rollback_drill.py; main.py; docs/ROLLBACK_PROCEDURE.md
RK-20 | Risk | Unified live-trading master switch | P0 | DONE | tracker COMPLETED; full suite 1,621 passed on merged master (912e654) | COMPLETED | Validate | orders/broker.py; ops/trading_safety.py
INV-001 | Wealth | Investor DNA | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/dna.py
WLT-001 | Wealth | Multi-asset wealth dashboard | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/holdings.py; wealth/assets.py
GOL-001 | Wealth | Goal planning engine | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/goals.py
AAL-001 | Wealth | Dynamic asset allocation | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/allocation.py
RBL-001 | Wealth | Portfolio rebalancing | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/rebalance.py
PERF-001 | Wealth | Investor performance attribution | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA + owner UAT | wealth/perf/
AIA-001 | Wealth | AI investment advisor | P1 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/advisor.py
INT-001 | Wealth | Integrated intelligence | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/integrated.py
QA-001 | Wealth | Wealth QA / security / performance | P1 | IN PROGRESS | tracker IN PROGRESS | IN PROGRESS | Independent testing (ChatGPT) per W33 handoff; the development suite now runs 820+ tests green (W39); run tools/load_test.py against the production machine | docs/W33_QA_UAT_HANDOFF.md; tests/test_wealth_*.py; enterprise/authz.py; dashboard/enterprise_page.py
UAT-001 | Wealth | Beta / UAT | P1 | BLOCKED | tracker BLOCKED | BLOCKED | Owner UAT; exit criteria W33 section 5 | docs/W33_QA_UAT_HANDOFF.md; docs/W19_UAT_PLAN.md; wealth/uat.py
REL-001 | Wealth | Wealth production hardening | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent testing (ChatGPT) + UAT; merge after authorization | ops/migrations.py; wealth/health.py
PERF-001-01 | Wealth / Performance | Performance data model | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Positions are derived from the ledger by design (no second source of truth); independent QA | wealth/perf/ledger.py; db/schema_w39.py; ops/migrations.py
PERF-001-02 | Wealth / Performance | Model Return | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/model.py
PERF-001-03 | Wealth / Performance | Executable Return | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Parity with the OMS paper fill model is not automated (different fill rule by design) | wealth/perf/model.py; execution/impact.py
PERF-001-04 | Wealth / Performance | Actual Investor Return | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/engine.py
PERF-001-05 | Wealth / Performance | Benchmark Return | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; the dividend part is an estimate (no free-float or constituent data) -- compare once with NSE's published TRI | wealth/perf/data.py; wealth/perf/report.py; data/total_return.py
PERF-001-06 | Wealth / Performance | Cost Attribution | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA with real broker contract notes | wealth/perf/engine.py; portfolio/imports.py
PERF-001-07 | Wealth / Performance | Position Attribution | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/model.py
PERF-001-08 | Wealth / Performance | Return Metrics | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/metrics.py; backtest/metrics.py
PERF-001-09 | Wealth / Performance | Signal Attribution | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/model.py; wealth/perf/report.py
PERF-001-10 | Wealth / Performance | Portfolio Attribution | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/engine.py
PERF-001-11 | Wealth / Performance | Performance Dashboard | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner UAT | dashboard/wealth_ui/performance_tab.py; dashboard/wealth_ui/overview_tab.py
PERF-001-12 | Wealth / Performance | Audit & Explainability | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/report.py
PERF-001-13 | Wealth / Performance | Report Export | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner UAT of the printed layout | wealth/perf/report.py; dashboard/wealth_routes.py; dashboard/wealth_ui/performance_tab.py
PERF-001-14 | Wealth / Performance | Regression & Edge Cases | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | wealth/perf/
OPS-12 | Deployment/Ops | Dhan token auto-renewal (TOTP) | P0 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: add dhan_pin + dhan_totp_secret (or vault them) once; run deploy/launchd/install.sh token | tools/dhan_token_refresh.py; deploy/launchd/com.atip.dhan-token-refresh.plist
DP-23 | Data Platform | Long price history (7 years) | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Owner: Dhan Data API subscription; the Nifty 500 completes in ~2 weeks of nightly runs | data/history_backfill.py; db/purge.py; data/dhan.py
DB-20 | Dashboard | Stock history like a trading platform | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner UAT | dashboard/stock_view.py
RK-21 | Risk Management | Pre-trade price band + gross leverage | P0 | IN PROGRESS | price band / circuit checks skip MARKET orders; gross exposure skipped for LIVE (orders/risk.py) | IMPLEMENTED BUT NOT VERIFIED | Independent QA; circuit fields confirmed against a live Dhan quote | execution/risk_engine.py; orders/risk.py; data/dhan.py
AF-09 | Alpha/Factor Engine | Time-series momentum + vol-adjusted 12-1 | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Factor IC research before any score use | quant/factors.py
PF-14 | Portfolio | Mean-variance with turnover penalty | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | portfolio/optimize.py
PF-15 | Portfolio | Factor neutrality | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | quant/normalize.py; portfolio/optimize.py
AF-10 | Alpha/Factor Engine | Volatility surface + term structure | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Needs F&O contract history (DP-08 store, daily) | quant/derivatives.py
ML-17 | AI/ML | Unsupervised market regime (HMM) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: choose the regime provider; research validation | ml/hmm.py; ml/regime.py
ML-18 | AI/ML | Research-to-production lineage | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | ml/registry.py
BT-18 | Backtesting | Purged walk-forward for strategies | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | backtest/walkforward.py
BT-19 | Backtesting | Transaction-cost stress sweep | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | backtest/robustness.py
EX-17 | Execution | Aggressive exit: enable flag + CRI-spike / momentum-decay exit | P1 | IN PROGRESS | merged (PR #17) and scheduled every 2 min in market hours; cannot manage positions without Dhan quotes: alert added 2026-10-26; no open positions | IMPLEMENTED BUT NOT VERIFIED | Independent QA; the owner picks a CRI threshold (e.g. 80) after reviewing CRI history before turning it on; the aggressive strategy stays unscheduled and PAPER | strategy/aggressive.py; strategy/live.py
EX-18 | Execution | Basket orders (paper) | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | LIVE placement stays behind the live-trading master switch | orders/basket.py
EX-19 | Execution | Broker-side GTT / forever orders | P2 | BLOCKED | tracker BLOCKED | BLOCKED | Place / modify / cancel broker GTT (Dhan forever-order API, Kite GTT) for LIVE positions | orders/rules.py
EX-20 | Execution | Stock SIP (recurring buys, paper) | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | LIVE SIP stays behind the live-trading master switch | orders/sip.py
UX-01 | Dashboard | Investor / Trader mode + progressive disclosure | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner UAT of which panels belong in Simple | dashboard/wealth_page.py
W39-RS | Research | Equity research reports (RS-01..10) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | No consensus estimates feed; XBRL key lines only (no 3-statement model); hit rates start from the first report and need PaRRVA review before being shown to others | research/valuation.py; research/report.py
W39-SCREENER | Research | Stock screener: fundamental + technical (SC-20) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | research/screener.py
W39-OPTIONS | Derivatives | Options strategy builder (OP-01..05) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Analysis only: one-click execution needs the live OMS and the owner's explicit go-ahead | quant/options_strategy.py
W39-TECH | Technical Analysis | Technical scans, ratings and signals (TA-01..04) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Trust a scan only after ~30 closed signals (records start on the first run) | research/technicals.py; research/tech_signals.py
W39-PULSE | Market Intelligence | Market pulse (MP-01..05) | P1 | IN PROGRESS | scheduled on the Mac since 2026-10-26; never ran before (W39 jobs not on the old Windows build); participant OI first run 2026-10-26 20:15 SUCCESS (20 rows); pre-open/GIFT due 08:45-09:09 on 27 Oct | IMPLEMENTED BUT NOT VERIFIED | Needs Nifty + global history loaded, Dhan index quotes for GIFT, NSE reachable for participant OI | research/market_pulse.py; data/participant_oi.py
W39-REGIME | Market Intelligence | Market regime gate (RG-01..04) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Thresholds are ATIP's choices (IBD tradition); evidence needs 30+ closed signals per side | research/regime_gate.py
W39-TRACK | Research | Signal track record by regime and horizon (TR-01..03) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Useful after a few months of signals | research/tech_signals.py
W39-WEEKLY | Technical Analysis | Weekly technical rating (WK-01..02) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | research/technicals.py
W39-PATTERNS | Technical Analysis | Chart patterns from swing pivots (CP-01..04) and marks on the stock chart | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Rule-based approximations; independent QA; each new scan needs 30 closed signals before its alerts start | research/patterns.py; dashboard/stock_view.py
W39-RSLINE | Technical Analysis | RS-line new highs and size-group RS ranks (RL-01..02) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | research/technicals.py
W39-DELIVERY | Technical Analysis | Delivery-% spike scan (DL-01) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA | research/technicals.py
W39-SCORECARD | Research | Explainable fundamental scorecard (FS-01..03) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Reported (not forecast) growth; banks / NBFCs miss six checks by design; record needs months | research/scorecard.py
W39-EVENTS | Market Intelligence | Macro event calendar (EV-01..03) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Seeded dates reach end-2026 (RBI Feb-2027): add next year's dates each December | research/event_calendar.py
W39-INTRADAY | Technical Analysis | Intraday scans on 15-minute bars (IN-01..03) | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Needs the Dhan Data API (15-minute bars) and 3 sessions of stored bars | research/intraday_signals.py
W39-DEPTH20 | Data Platform | 20-level depth, depth-weighted imbalance and order-flow imbalance (DP-01..03, OF-01..03) | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Owner: depth20.enabled and the Dhan Data API | data/depth20.py
W39-GLOBALSYNC | Market Intelligence | Synchronised global-cue model (GS-01..03) | P1 | IN PROGRESS | scheduled on the Mac since 2026-10-26; never ran before (W39 jobs not on the old Windows build); participant OI first run 2026-10-26 20:15 SUCCESS (20 rows); pre-open/GIFT due 08:45-09:09 on 27 Oct | IMPLEMENTED BUT NOT VERIFIED | Needs 40 mornings of snapshots (~2 months) | research/global_sync.py
W39-NLSCREEN | Research | English to screener query (NL-01..03) | P1 | BLOCKED | news.ai_enabled false and no working Anthropic key: 0 of 3,664 articles AI-classified, ai_usage_log empty; keyword classifier only | IMPLEMENTED BUT NOT VERIFIED | Claude path needs a working Anthropic key (KD-001) | research/screener_nl.py
W39-MCP | APIs | Read-only ATIP MCP server (MC-01..03) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Local stdio only (no hosted transport) | tools/atip_mcp.py
W39-ORDERBOOK | Market Intelligence | Order-book pressure and open orders (OB-01..03) | P1 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Needs the Dhan Data API; context, not a signal | data/order_pressure.py; portfolio/open_orders.py
W39B-TF75 | Technical Analysis | 75-minute technical rating and its agreement with the daily one | P2 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | IMPLEMENTED BUT NOT VERIFIED | Independent QA. W40: a 75m column on /signals and GET /api/stock/{symbol}/rating-75 (on demand from the stored 15-minute bars, completed bars only); the /signals column is still the 20:30 snapshot | research/technicals.py; research/tech_signals.py; research/screener.py
W39B-DVM | Research | DVM view: durability, valuation, momentum 0-100 and zones | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; weights are ATIP's definitions, not backtested -- record whether the zones pay before using them | research/dvm.py; research/scorecard.py; dashboard/w39_routes.py
W39B-PEAD | Research | Earnings surprise (SUE), EPS-trend proxy and a post-earnings-drift scan | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA; needs 9+ quarters of NSE XBRL history (run the history backfill); no consensus estimates (ATIP's own history only); filings arrive with the Saturday fundamentals job | research/earnings_surprise.py; research/tech_signals.py
W39B-MFA | Wealth / Mutual funds | Mutual fund analytics on stored AMFI NAVs (read-only) | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA. Holding MFs in the wealth ledger stays out of scope (owner Scope Exclusions); benchmark is a price index (the W40 Nifty 50 TR is not wired here yet); peers limited to stored schemes; tiered exit loads not modelled | data/mf_analytics.py; dashboard/w35_routes.py; dashboard/w35_page.py
W40-RISKMODEL | Risk & Portfolio | Fundamental factor risk model (Barra-style) | P1 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Independent QA on the real database; needs filed share counts for 30+ stocks; universe and industries are today's (survivorship); no free-float data | quant/risk_model.py; portfolio/risk.py; dashboard/risk_model_routes.py
W40-META | AI/ML | Meta-labelling of the technical signals (AFML ch. 3-4, 7, 10) | P2 | IN PROGRESS | built and unit-tested; not proven on live data / UAT | IMPLEMENTED BUT NOT VERIFIED | Owner: switch on after a few hundred closed signals exist and a version is ADOPTABLE; independent QA | ml/meta_label.py; ml/validation.py; dashboard/w40_routes.py
GAP-2610-01 | Market Data | Dhan Data API subscription | P0 | BLOCKED | Dhan Data API plan inactive since ~2026-09-18 (profile dataPlan=Deactive; quotes 806 'Data APIs not Subscribed'; history DH-902; last Dhan bar 2026-09-17, last live quote 2026-10-05). Owner action: subscribe. | BLOCKED | Subscribe to Dhan Data APIs (web.dhan.co); then confirm quotes, WebSocket, 15-min bars, history | data/dhan.py
GAP-2610-02 | Data Platform | Holes in prices_daily recovered automatically | P0 | DONE | fixed 2026-10-26 (ac58625): catch-up re-scores holes in the window, fills older holes from NSE; tests tests/test_catchup_price_holes.py | COMPLETED | Monitor the price_holes alert | pipeline/scheduler.py
GAP-2610-03 | Execution | Alert when scheduled exits cannot run (no/stale quotes) | P0 | DONE | fixed 2026-10-26 (63767d8): one error alert a day naming the cause; tests/test_dhan_data_plan.py | COMPLETED | - | strategy/live.py
GAP-2610-04 | Execution | LIVE fill confirmation (order/trade book polling, partial fills) | P0 | GAP | orders/broker.py books exits at the hint price on acknowledgement; strategy/live.py enter() reports a real buy as 'did not fill' when the ack has no price | YET TO START | Poll order/trade book or order-update WS; reconcile partials | strategy/live.py; orders/broker.py; orders/rules.py
GAP-2610-05 | Risk Management | Broker-side protective stop at entry (SL-M / Forever) | P0 | GAP | stops are checked by ATIP every 2 min (aggressive) / 30 s (rules) on LTP; nothing rests at the exchange | YET TO START | Place SL-M/Forever order with each entry; cancel/modify on exit | orders/broker.py; strategy/live.py
GAP-2610-06 | Risk Management | LIVE order path fails closed when price is unknown | P0 | GAP | _estimate_order_value returns 0 for a MARKET order without a quote, so funds/value checks pass | YET TO START | Refuse BUY when no price; route W1 orders through execution/risk_engine | orders/broker.py; orders/risk.py
GAP-2610-07 | Compliance | SEBI retail algo framework: order-rate cap, Algo ID, static IP | P0 | GAP | no rate limiter; execution.max_orders_per_second ignored as unknown key; no Algo ID; no static-IP design | YET TO START | Add OPS limiter + known key; tag orders; static IP via Dhan | execution/config.py; orders/broker.py; ops/compliance.py
GAP-2610-08 | Execution | LIVE reconciliation against Dhan order/trade book | P0 | GAP | execution/reconcile.py compares OMS LIVE fills (which cannot exist) with holdings; W1 order_log never matched | YET TO START | Reconcile order_log/strategy_position with Dhan books daily and at start-up | execution/reconcile.py
GAP-2610-09 | Operations | Single trading instance per broker account | P0 | GAP | flock per atip_data folder only; a second folder/worktree trades the same Dhan account | YET TO START | Account-level lock + broker position check before orders | main.py; ops/jobs.py
GAP-2610-10 | Signal Engine | Pre-market inputs (GIFT gap, pre-open IEP, global cues, overnight news) feed the morning decision | P1 | GAP | signals are fixed post-market; preopen/GIFT/market pulse are display only (scores/engine.py reads none of them) | YET TO START | Pre-open gate/re-rank at 09:10 using GIFT gap + pre-open imbalance | scores/engine.py; data/preopen.py; research/market_pulse.py
GAP-2610-11 | News/Sentiment | Stock-level news coverage | P1 | GAP | 88% of scored rows carry neutral news; 0 of 76 logged BUY signals had stock-specific news; 3 of 9 RSS feeds failing 21x, MoneyControl 0 items | YET TO START | Fix/replace feeds; NSE announcements as primary stock news | data/news.py; data/announcements.py
GAP-2610-12 | Backtesting | Out-of-sample gate + point-in-time adjusted universe | P1 | GAP | headline figures in-sample; universe = today's Nifty 500 before Sep 2026 (survivorship) | YET TO START | Walk-forward gate for any profile; point-in-time constituents incl. delisted | scores/backtest.py; backtest/data.py
GAP-2610-13 | Backtesting | One statutory cost model (DP charge, options, paper) | P1 | GAP | DP charge defaults 0; paper charges 0.05%/leg + 5 bps; options costs incomplete; 0.25% applied two ways | YET TO START | Single CostModel everywhere; set DP per sell | backtest/costs.py; orders/paper.py; execution/options_paper.py
GAP-2610-14 | Operations | Morning brief recovery after the open | P2 | GAP | auto-recovery sent the 'morning brief' at 18:49 on 2026-10-26 | YET TO START | Skip the brief after 09:15; send an evening summary instead | pipeline/recover.py
GAP-2610-15 | Portfolio | LIVE day P&L after a missing day | P2 | GAP | pnl_daily LIVE 2026-10-23 equity NULL (sync failed, DH-901) so 2026-10-26 day_pnl = 5,94,472 on 5,77,996 equity | YET TO START | Compare with the last non-null equity | portfolio/pnl.py
GAP-2610-16 | Deployment/Ops | Test and Prod hosted servers | P2 | BLOCKED | only the owner's Mac runs ATIP; test.bkesari.com receives the read-only snapshot only (R10) | BLOCKED | Decide hosting + secrets; deploy behind the owner gate (PR #11) | deploy/; Dockerfile
GAP-2610-17 | Security | Dashboard token scoped per tenant session (R12) | P2 | DONE | 5ee26cb (cloud session, merged f6ceb25): other tenants get a session-derived token, the install token is refused to them on write routes; CI green; no change with enterprise mode off (owner pages verified) | COMPLETED | Rotate the install token (delete atip_data/dashboard_token.txt) before ever enabling accept_legacy_token | dashboard/security.py; enterprise/authz.py
OPS-01 | Dashboard | Merge pending UI/UX changes (UXR-01..03) | P1 | DONE | Uncommitted UXR delta reviewed and merged into master; halt-route date.today() replaced with an IST clock; 4 other dashboard branches reviewed and NOT merged (hosting/stale) | COMPLETED | Owner decision on central-auth owner gate + /ATIP base path (hosting) | dashboard/command_page.py; dashboard/command_routes.py; orders/sessions.py
OPS-02 | Pipeline | Operating schedule STOPPED 21:00-06:00 IST | P1 | DONE | pipeline/operating_schedule.py gates the schedule loop + run_job; orders.risk.halted() closes every order path; feed window + order monitor check is_stopped() | COMPLETED | Watch the first real 21:00 stop on the Mac (atip.log + /api/status) | pipeline/operating_schedule.py; pipeline/scheduler.py; orders/risk.py; data/dhan_ws.py; dashboard/server.py
OPS-03 | Dashboard | Read-only dashboard + STOPPED banner | P1 | DONE | Banner on /, /command, /m, /global-asia (polls /api/status 60s); writes -> HTTP 423 except override, halt, sign-in | COMPLETED |  | dashboard/global_asia.py; pipeline/operating_schedule.py
OPS-04 | Pipeline | scheduler_status table + /api/status | P1 | DONE | scheduler_status, scheduler_override, resume_runs, deferred_jobs; GET /api/status | COMPLETED |  | pipeline/operating_schedule.py; dashboard/global_asia.py
OPS-05 | Pipeline | 06:00 resume sequence (6 steps, logged) | P1 | DONE | Steps logged as resume_1..6 in pipeline_log + resume_runs.steps_json; real end-to-end run on the Prod-profile snapshot | COMPLETED | Confirm on the Mac at a real 06:00 with Dhan + Anthropic keys present | pipeline/operating_schedule.py; pipeline/premarket_report.py
OPS-06 | Pipeline | Missed-resume catch-up + run lock | P1 | DONE | tick() at start-up, every 15 s and on wake; resume_runs per IST date + job_lock; crashed run re-run after 2 h | COMPLETED |  | pipeline/operating_schedule.py; pipeline/scheduler.py
OPS-07 | Pipeline | Weekends / NSE holidays | P1 | DONE | Step 6 SKIPPED on non-trading days; status live_feeds false | COMPLETED |  | pipeline/operating_schedule.py
OPS-08 | Dashboard | Manual start/stop override (logged) | P1 | DONE | POST /api/status/override stop¦start¦auto (token, owner-only); CLI too; scheduler_status + alert_log | COMPLETED | Add buttons on /command (API + banner done) | dashboard/global_asia.py; enterprise/authz.py
OPS-09 | AI/News | Loud alert on keyword-classifier fallback | P1 | DONE | Resume step 3 DEGRADED + critical alert 'NEWS SENTIMENT FALLBACK' | COMPLETED |  | pipeline/operating_schedule.py
OPS-10 | Technical | Null-EMA gap for small/mid-caps | P1 | IN PROGRESS | data/ema_gap.py fills missing sessions from the NSE Bhavcopy archive (insert-only), recomputes indicators; resume step 4 | COMPLETED | Reaches SMA-200 after ~1 week of 06:00 runs; verify on live DB | data/ema_gap.py
OPS-11 | Docs | Scheduler mechanism decision documented | P1 | DONE | Kept ONE mechanism (in-process schedule loop) — deviation from the two named options, reasons in scheduler.py header + docs | N/A | Owner to confirm the decision | pipeline/scheduler.py; docs/OPERATING_SCHEDULE_AND_ASIA_2026-10.md
ASIA-01 | Data | Asia markets data module (6 indices, primary + fallback) | P1 | DONE | data/asia_markets.py; 14 sources probed: 11 OK, 3 FLAGGED (TOPIX Yahoo, KSE-100 PSX DPS HTTP 462, KSE-100 Yahoo); Stooq rejected (JS wall) ¦ BLOCKER: TOPIX / KSE-100 fallback sources fail from India | COMPLETED | TOPIX and KSE-100 have one working source from this network | data/asia_markets.py; data/asia_exchanges.json
ASIA-02 | Data | global_indices_daily + 600-day retention | P1 | DONE | global_indices_daily, asia_signals, asia_sentiment in LONG (600 d) purge; data-inventory classified | COMPLETED |  | data/asia_markets.py; db/purge.py; enterprise/privacy.py
ASIA-03 | Data | Exchange hours + holidays from config; 3 Asia runs | P1 | IN PROGRESS | data/asia_exchanges.json (JPX/KRX/TWSE/PSX) + config override; runs 06:00, 10:45, 17:15 IST; calendar self-check | COMPLETED | 2026 holiday lists unverified (lunar dates for PSX); confirm against exchange notices | data/asia_exchanges.json
ASIA-04 | Signals | Per-market BULLISH/NEUTRAL/BEARISH + confidence | P1 | DONE | compute_signal; defect fixed in testing: no dead band made sideways tapes BULLISH | COMPLETED | Back-test the thresholds on 1y of history | data/asia_markets.py
ASIA-05 | Signals | Asia Sentiment Score -> Market Health + pre-market report | P1 | DONE | weights in asia_exchanges.json; MH weight_config ('MH','Asia') 0.05; pre-market report + 08:30 brief line | COMPLETED | Owner to confirm the 0.05 MH weight | data/asia_markets.py; scores/engine.py; pipeline/premarket_report.py; alerts/telegram.py
ASIA-06 | Signals | Pakistan geopolitical / risk-event flag | P1 | DONE | pakistan_risk(): NONE/ELEVATED/HIGH from classified news + Google News Pakistan feed; PK_GEO_RISK weight 0.10 | COMPLETED |  | data/asia_markets.py; data/news.py
ASIA-07 | Dashboard | Global & Asia tab | P1 | DONE | Tab on /, page /global-asia, screen on /m; informational only | COMPLETED |  | dashboard/global_asia.py; dashboard/server.py; dashboard/w38_page.py
MOB-01 | Mobile | Android app: merged UI, status banner, Global & Asia | P1 | IN PROGRESS | New Kotlin shell (mobile/android): tabs Today/Command/Global & Asia + native /api/status banner ¦ BLOCKER: No Android SDK / JDK installed | IN PROGRESS | Build + install: no Android SDK/Java on the Mac; needs Android Studio | mobile/android
MOB-02 | Mobile | iOS app: merged UI, status banner, Global & Asia | P1 | IN PROGRESS | New SwiftUI shell (mobile/ios, XcodeGen spec): same tabs + native banner; swiftc -parse OK ¦ BLOCKER: Xcode not installed | IN PROGRESS | Build: needs Xcode (only Command Line Tools installed); App Store needs a developer account | mobile/ios
QA-01 | Testing | Test + Prod server testing + report | P1 | IN PROGRESS | Run on local Test (ATIP_ENV=test, seeded DB, :8765) and Prod-profile (ATIP_ENV=production, live-DB snapshot, :8766) instances; full suite ¦ BLOCKER: No hosted Test/Prod servers exist | IN PROGRESS | Repeat on real hosted servers once they exist (GAP-2610-16) | docs/TEST_REPORT_2026-10-26_OPS_ASIA.md
NI-01 | Data Platform | News impact module: fetch + analyse | P1 | DONE | data/news_impact.run(): RSS_FEEDS + GLOBAL_FEEDS through run_news_pipeline (dedup, classify, store), then assess, combine, track | COMPLETED | Maintain | data/news_impact.py; data/news.py
NI-02 | AI/News | Per-headline impact assessment | P1 | IN PROGRESS | Claude (news model + daily cap, purpose news_impact) with JSON schema; keyword-rule fallback reads crude/yield/dollar moves for India, keeps company news off the Nifty; recaps skipped ¦ BLOCKER: ANTHROPIC_API_KEY (owner) | IN PROGRESS | Owner adds ANTHROPIC_API_KEY; then verify a live Claude run (only stubbed so far) | data/news_impact.py
NI-03 | AI/News | Session estimate: score, bias, sectors, drivers, brief | P1 | DONE | 0-100 score, POSITIVE/NEUTRAL/NEGATIVE + strength, per-sector scores for 11 NSE indices, top 8 drivers, Claude brief (rules fallback); informational only | COMPLETED | Maintain | data/news_impact.py
NI-04 | AI/News | Tracking check vs Nifty close | P1 | DONE | news_impact_eval vs index_levels 15:30; pre-open call per session; baselines (commonest outcome, yesterday again); per-sector and per-headline hits; scheduled 07:40/12:20/15:50/20:15 + 06:00 resume, scored 16:20 | COMPLETED | Read the track record after 20+ sessions before relying on it | data/news_impact.py; pipeline/scheduler.py; pipeline/operating_schedule.py
NI-05 | Dashboard | News impact panel + API | P1 | DONE | /api/news-impact, /accuracy, /refresh (owner token); panel on / News + Global & Asia tabs, /global-asia, /m (Android/iOS apps load it); pre-market report section; Telegram brief line | COMPLETED | Maintain | dashboard/news_impact_view.py; dashboard/global_asia.py; dashboard/server.py; dashboard/w38_page.py; pipeline/premarket_report.py; alerts/telegram.py

## Sheet1
Sum of Phase | Column Labels
Row Labels | COMPLETED | IN PROGRESS | UNCLEAR | YET TO START | Grand Total
P0 | 10 | 73 | 6 | 146 | 235
AI/ML |  | 20 |  | 8 | 28
Delivered baseline (maintain) | 0 |  |  |  | 0
Enterprise SaaS (final objective) |  |  |  | 117 | 117
Execution |  | 12 | 6 |  | 18
Broker Integration |  | 6 |  |  | 6
Execution |  | 6 | 6 |  | 12
Foundation | 2 | 14 |  | 4 | 20
Alpha/Factor Engine |  | 4 |  |  | 4
Broker Integration |  | 1 |  |  | 1
Data Platform |  | 3 |  |  | 3
Deployment/Ops | 1 |  |  |  | 1
Execution | 1 |  |  |  | 1
Monitoring |  | 2 |  | 1 | 3
News/Sentiment |  | 1 |  |  | 1
Portfolio |  | 2 |  | 1 | 3
Risk Management |  | 1 |  | 2 | 3
Quant Research (data, factors, backtesting) |  | 18 |  | 12 | 30
Alpha/Factor Engine |  | 6 |  | 2 | 8
Backtesting |  | 6 |  | 8 | 14
Data Platform |  | 2 |  |  | 2
Database |  | 2 |  |  | 2
Quant Research |  |  |  | 2 | 2
Technical Analysis |  | 2 |  |  | 2
Risk & Portfolio | 5 |  |  | 5 | 10
Risk Management | 5 |  |  | 5 | 10
Strategy Engine | 3 | 9 |  |  | 12
Signal Engine | 3 | 3 |  |  | 6
Strategy Engine |  | 6 |  |  | 6
P1 | 8 | 99 | 1 | 234 | 342
AI/ML |  | 12 |  | 20 | 32
Delivered baseline (maintain) | 0 |  |  |  | 0
Enterprise SaaS (final objective) |  |  |  | 99 | 99
Execution |  | 30 |  | 6 | 36
Broker Integration |  | 6 |  |  | 6
Execution |  | 6 |  | 6 | 12
Monitoring |  | 6 |  |  | 6
Risk Management |  | 6 |  |  | 6
Security |  | 6 |  |  | 6
Foundation | 2 | 6 | 1 | 1 | 10
Alpha/Factor Engine | 2 |  |  |  | 2
Dashboard |  | 1 |  |  | 1
Data Platform |  | 1 |  |  | 1
Database |  | 2 |  |  | 2
Deployment/Ops |  | 1 |  |  | 1
Monitoring |  |  |  | 1 | 1
Risk Management |  | 1 |  |  | 1
Technical Analysis |  |  | 1 |  | 1
Production Hardening |  | 8 |  | 24 | 32
Deployment/Ops |  | 8 |  | 8 | 16
Monitoring |  |  |  | 8 | 8
Security |  |  |  | 8 | 8
Quant Research (data, factors, backtesting) | 6 | 24 |  | 24 | 54
Alpha/Factor Engine | 2 | 6 |  | 2 | 10
Backtesting |  | 8 |  | 6 | 14
Data Platform | 2 | 4 |  | 2 | 8
Database |  |  |  | 2 | 2
Quant Research | 2 | 6 |  | 8 | 16
Technical Analysis |  |  |  | 4 | 4
Risk & Portfolio |  | 10 |  | 45 | 55
Dashboard |  |  |  | 5 | 5
Portfolio |  | 10 |  | 15 | 25
Risk Management |  |  |  | 25 | 25
Strategy Engine |  | 9 |  | 15 | 24
Dashboard |  | 3 |  | 3 | 6
Strategy Engine |  | 6 |  | 12 | 18
P2 | 3 | 38 |  | 236 | 277
Advanced Quant |  |  |  | 133 | 133
Alpha/Factor Engine |  |  |  | 21 | 21
Alternative Data |  |  |  | 14 | 14
Backtesting |  |  |  | 7 | 7
Data Platform |  |  |  | 35 | 35
Execution |  |  |  | 28 | 28
Quant Research |  |  |  | 28 | 28
AI/ML |  |  |  | 24 | 24
Delivered baseline (maintain) | 0 |  |  |  | 0
Enterprise SaaS (final objective) |  |  |  | 45 | 45
Execution |  | 12 |  |  | 12
Broker Integration |  | 12 |  |  | 12
Foundation | 1 |  |  |  | 1
Data Platform | 1 |  |  |  | 1
Production Hardening |  | 8 |  | 8 | 16
APIs |  | 8 |  | 8 | 16
Quant Research (data, factors, backtesting) | 2 | 12 |  | 6 | 20
Alpha/Factor Engine |  |  |  | 2 | 2
Alternative Data |  | 2 |  |  | 2
Dashboard |  | 2 |  |  | 2
Data Platform | 2 | 6 |  |  | 8
Technical Analysis |  | 2 |  | 4 | 6
Risk & Portfolio |  |  |  | 20 | 20
Portfolio |  |  |  | 15 | 15
Risk Management |  |  |  | 5 | 5
Strategy Engine |  | 6 |  |  | 6
Signal Engine |  | 3 |  |  | 3
Strategy Engine |  | 3 |  |  | 3
Grand Total | 21 | 210 | 7 | 616 | 854

## ATIP_MASTER_TRACKER
Seq | Phase | Phase Name | ID | Module | Feature | Target Requirement | Scope Source | Priority | Status | Completion % | Depends On | Current Implementation | Next Action / Missing Work | Key Files | Evidence | Owner | Target Date | Started On | Completed On | Last Updated | Notes
1 | 0 | Delivered baseline (maintain) | DP-02 | Data Platform | Daily OHLCV history | Clean daily bars for universe | Agreed-Spec | P0 | COMPLETED | 90 |  | NSE Bhavcopy + Dhan; coverage/freshness/duplicate guards | Maintain | data/bhavcopy.py; data/dhan.py | prices_daily ~234k rows / 426 sessions |  |  |  |  | 2026-09-24
2 | 0 | Delivered baseline (maintain) | DP-07 | Data Platform | Delivery data | Delivery qty and % | Code-Derived | P1 | COMPLETED | 90 |  | Full Bhavcopy nightly + backfill | Maintain | data/bhavcopy.py | 223,854 rows |  |  |  |  | 2026-09-24
3 | 0 | Delivered baseline (maintain) | DP-20 | Data Platform | Trading calendar | NSE holidays/special sessions | Code-Derived | P0 | COMPLETED | 90 |  | 2025-26 holidays + budget sessions | Add next year's holidays each December | utils/trading_calendar.py | 7132017 |  |  |  |  | 2026-09-24
4 | 0 | Delivered baseline (maintain) | TA-01 | Technical Analysis | Core indicators | RSI; MACD; EMA; SMA; ATR; ADX; Bollinger | Agreed-Spec | P0 | COMPLETED | 90 |  | Computed and stored; MACD fixed and normalised | Maintain | data/technical.py | a7d92a7; bbd0540 |  |  |  |  | 2026-09-24
5 | 0 | Delivered baseline (maintain) | TA-02 | Technical Analysis | Extended oscillators | Stoch; Williams %R; CCI; OBV; relative volume | Agreed-Spec | P1 | COMPLETED | 80 |  | Computed and stored | Maintain | data/technical.py | technical.py:47-54 |  |  |  |  | 2026-09-24
6 | 0 | Delivered baseline (maintain) | TA-05 | Technical Analysis | Fibonacci | Retracement levels | Agreed-Spec | P1 | COMPLETED | 80 |  | 52-week 23.6/38.2/50/61.8 levels | Optional: swing-anchored levels | data/technical.py | technical.py:262-268 |  |  |  |  | 2026-09-24
7 | 0 | Delivered baseline (maintain) | TA-07 | Technical Analysis | Trend features | Crosses; 200DMA; gap % | Agreed-Spec | P1 | COMPLETED | 80 |  | Computed and stored | Maintain | data/technical.py | technical.py:291 |  |  |  |  | 2026-09-24
8 | 0 | Delivered baseline (maintain) | TA-08 | Technical Analysis | Relative strength | RS vs NIFTY | Agreed-Spec | P1 | COMPLETED | 80 |  | 20-day RS with date-matched benchmark | Sector-relative RS later (TA-08b in Phase 2 if wanted) | scores/engine.py | 8dd04fb |  |  |  |  | 2026-09-24
9 | 0 | Delivered baseline (maintain) | SC-03 | Alpha/Factor Engine | RRI | Recovery & Rebound Index per QRH | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented | Institutional input improves with SC-14 | scores/engine.py | engine.py:260 |  |  |  |  | 2026-09-24
10 | 0 | Delivered baseline (maintain) | SC-04 | Alpha/Factor Engine | MRI | Momentum Reversal Index per QRH | Agreed-Spec | P0 | COMPLETED | 85 |  | Implemented; MACD corrected | Maintain | scores/engine.py | engine.py:241 |  |  |  |  | 2026-09-24
11 | 0 | Delivered baseline (maintain) | SC-07 | Alpha/Factor Engine | ZPI | Zone Probability Index per QRH | Agreed-Spec | P0 | COMPLETED | 80 |  | Implemented + delivery component | Maintain | scores/engine.py | 969f570 |  |  |  |  | 2026-09-24
12 | 0 | Delivered baseline (maintain) | SC-10 | Alpha/Factor Engine | Portfolio Health score | PHS formula | Agreed-Spec | P1 | COMPLETED | 75 |  | Implemented | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py | portfolio_health.py |  |  |  |  | 2026-09-24
13 | 0 | Delivered baseline (maintain) | PF-05 | Portfolio | Portfolio health | Portfolio Health score + panel | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented + dashboard | Maintain | scores/portfolio_health.py | portfolio_health.py |  |  |  |  | 2026-09-24
14 | 0 | Delivered baseline (maintain) | SC-11 | Alpha/Factor Engine | Trade of the Day | TOD formula | Agreed-Spec | P1 | COMPLETED | 80 |  | Implemented; one TOD per session | Maintain | scores/engine.py | d74e595 |  |  |  |  | 2026-09-24
15 | 0 | Delivered baseline (maintain) | SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | Master ranking | Agreed-Spec | P0 | COMPLETED | 80 |  | Implemented; rank stored | Maintain | scores/engine.py | engine.py:508 |  |  |  |  | 2026-09-24
16 | 0 | Delivered baseline (maintain) | SC-17 | Alpha/Factor Engine | Configurable weights | Weights in configuration | Agreed-Spec | P1 | COMPLETED | 80 |  | weight_config table | Regime-specific rows used by ML-05 | db/schema.py | seed_weights |  |  |  |  | 2026-09-24
17 | 0 | Delivered baseline (maintain) | SG-02 | Signal Engine | Signal validation | Data gates before signals | Code-Derived | P0 | COMPLETED | 75 |  | EOD coverage guard; FII/DII hold | Maintain | pipeline/scheduler.py | a4a508b; 969f570 |  |  |  |  | 2026-09-24
18 | 0 | Delivered baseline (maintain) | SG-03 | Signal Engine | Signal ranking | Top-25 lists | Agreed-Spec | P0 | COMPLETED | 85 |  | Implemented | Maintain | scores/engine.py | dashboard lists |  |  |  |  | 2026-09-24
19 | 0 | Delivered baseline (maintain) | SG-05 | Signal Engine | Trade plan | Entry/stop/targets/R:R/horizon | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented | Maintain | scores/predictions.py | predictions.py |  |  |  |  | 2026-09-24
20 | 0 | Delivered baseline (maintain) | SG-06 | Signal Engine | Outcome tracking | Hit rate and P&L per signal | Agreed-Spec | P0 | COMPLETED | 80 |  | Implemented; corrected denominator | Maintain | scores/signal_log.py | cc8ce46 |  |  |  |  | 2026-09-24
21 | 0 | Delivered baseline (maintain) | SG-07 | Signal Engine | Signal provenance log | Immutable signal log | Code-Derived | P1 | COMPLETED | 80 |  | Append-only signal_log | Maintain | scores/signal_log.py | signal_log.py |  |  |  |  | 2026-09-24
22 | 0 | Delivered baseline (maintain) | BT-01 | Backtesting | Historical backtest | Bar-level backtest | Agreed-Spec | P0 | COMPLETED | 80 |  | 3 bar engines | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py | — |  |  |  |  | 2026-09-24
23 | 0 | Delivered baseline (maintain) | BT-10 | Backtesting | Win rate / profit factor / expectancy | Trade metrics | Agreed-Spec | P0 | COMPLETED | 90 |  | Implemented | Maintain | strategy/backtest_aggressive.py | metrics() |  |  |  |  | 2026-09-24
24 | 0 | Delivered baseline (maintain) | RK-02 | Risk Management | Max order value | Pre-trade limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
25 | 0 | Delivered baseline (maintain) | RK-03 | Risk Management | Max orders per day | Pre-trade limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
26 | 0 | Delivered baseline (maintain) | RK-04 | Risk Management | Max open positions | Position limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
27 | 0 | Delivered baseline (maintain) | RK-05 | Risk Management | Symbol exposure limit | Concentration limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
28 | 0 | Delivered baseline (maintain) | RK-14 | Risk Management | Crash-risk gating | CRI gate | Agreed-Spec | P0 | COMPLETED | 75 |  | SELL_CRI_DANGER + strategy use | Maintain | scores/engine.py | — |  |  |  |  | 2026-09-24
29 | 0 | Delivered baseline (maintain) | EX-03 | Execution | Position management | Persistent idempotent positions | Code-Derived | P0 | COMPLETED | 75 |  | reserve -> place -> apply | Maintain | strategy/positions.py | — |  |  |  |  | 2026-09-24
30 | 0 | Delivered baseline (maintain) | EX-04 | Execution | Entry/exit | Automated entry and exit | Agreed-Spec | P0 | COMPLETED | 70 |  | strategy/live.py | Maintain | strategy/live.py | — |  |  |  |  | 2026-09-24
31 | 0 | Delivered baseline (maintain) | EX-05 | Execution | Stop loss | Hard/ATR stops | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented | Maintain | strategy/aggressive.py | — |  |  |  |  | 2026-09-24
32 | 0 | Delivered baseline (maintain) | EX-06 | Execution | Trailing stop | ATR trailing stop | Quant-Research | P0 | COMPLETED | 80 |  | Implemented (4.0x ATR) | Maintain | strategy/aggressive.py | aggressive.py:57-66 |  |  |  |  | 2026-09-24
33 | 0 | Delivered baseline (maintain) | EX-07 | Execution | Profit booking / partial exit | Checkpoints and partial exits | Agreed-Spec | P1 | COMPLETED | 70 |  | Implemented in aggressive strategy | Maintain | strategy/aggressive.py | — |  |  |  |  | 2026-09-24
34 | 0 | Delivered baseline (maintain) | EX-13 | Execution | Paper trading | Virtual trading (FR-PT) | Agreed-Spec | P0 | COMPLETED | 85 |  | Paper broker with slippage | Maintain | orders/paper.py | tests/test_paper_broker.py |  |  |  |  | 2026-09-24
35 | 0 | Delivered baseline (maintain) | EX-14 | Execution | Live gating | PAPER default; explicit confirm | Agreed-Spec | P0 | COMPLETED | 85 |  | Implemented | Maintain | orders/environment.py | environment.py:37-57 |  |  |  |  | 2026-09-24
36 | 0 | Delivered baseline (maintain) | BR-01 | Broker Integration | Dhan | Data + orders | Agreed-Spec | P0 | COMPLETED | 80 |  | dhanhq integration | Maintain | data/dhan.py; orders/broker.py | — |  |  |  |  | 2026-09-24
37 | 0 | Delivered baseline (maintain) | BR-03 | Broker Integration | Broker abstraction | Routed execution clients | Quant-Research | P0 | COMPLETED | 75 |  | PAPER/SANDBOX/LIVE routing | Becomes multi-broker interface in ENT-15 | orders/environment.py | — |  |  |  |  | 2026-09-24
38 | 0 | Delivered baseline (maintain) | DB-01 | Dashboard | Market Health panel | Dashboard section | Agreed-Spec | P0 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
39 | 0 | Delivered baseline (maintain) | DB-02 | Dashboard | Global Markets panel | Dashboard section | Agreed-Spec | P1 | COMPLETED | 75 |  | Rendered; snapshot bug fixed | Maintain | dashboard/server.py | db7f506 |  |  |  |  | 2026-09-24
40 | 0 | Delivered baseline (maintain) | DB-03 | Dashboard | FII/DII panel | Dashboard section | Agreed-Spec | P1 | COMPLETED | 75 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
41 | 0 | Delivered baseline (maintain) | DB-05 | Dashboard | Sector Rotation | Dashboard section | Agreed-Spec | P1 | COMPLETED | 70 |  | Heatmap rendered | Maintain | dashboard/server.py | server.py:489 |  |  |  |  | 2026-09-24
42 | 0 | Delivered baseline (maintain) | DB-07 | Dashboard | Top 25 VPI | Dashboard section | Agreed-Spec | P0 | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | /api/scores |  |  |  |  | 2026-09-24
43 | 0 | Delivered baseline (maintain) | DB-08 | Dashboard | Buy Zone (ZPI) | Dashboard section | Agreed-Spec | P0 | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
44 | 0 | Delivered baseline (maintain) | DB-09 | Dashboard | Recovery (RRI) | Dashboard section | Agreed-Spec | P1 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
45 | 0 | Delivered baseline (maintain) | DB-10 | Dashboard | Momentum Reversal (MRI) | Dashboard section | Agreed-Spec | P1 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
46 | 0 | Delivered baseline (maintain) | DB-12 | Dashboard | Portfolio Health panel | Dashboard section | Agreed-Spec | P0 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | /api/portfolio |  |  |  |  | 2026-09-24
47 | 0 | Delivered baseline (maintain) | DB-13 | Dashboard | Trade of the Day | Dashboard section | Agreed-Spec | P0 | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | /api/tod |  |  |  |  | 2026-09-24
48 | 0 | Delivered baseline (maintain) | DB-15 | Dashboard | Orders/signals panel | Orders tab | Code-Derived | P1 | COMPLETED | 70 |  | Rendered with PAPER status | Maintain | dashboard/server.py | /api/orders |  |  |  |  | 2026-09-24
49 | 0 | Delivered baseline (maintain) | DB-19 | Dashboard | Hosted read-only snapshot | bkesari viewer | Code-Derived | P1 | COMPLETED | 80 |  | publish_snapshot.py | Superseded by ENT-08 web app | publish_snapshot.py | — |  |  |  |  | 2026-09-24
50 | 0 | Delivered baseline (maintain) | API-01 | APIs | Internal REST | Dashboard API | Agreed-Spec | P1 | COMPLETED | 70 |  | 15 FastAPI routes | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
51 | 0 | Delivered baseline (maintain) | API-02 | APIs | Local API authentication | Auth on mutating routes | Agreed-Spec | P0 | COMPLETED | 80 |  | 127.0.0.1 bind + X-ATIP-Token | Replaced by per-user auth in SEC-02 | dashboard/security.py | 7191c71 |  |  |  |  | 2026-09-24
52 | 0 | Delivered baseline (maintain) | DBS-01 | Database | Schema | Operational schema | Agreed-Spec | P1 | COMPLETED | 75 |  | 19 SQLite tables | Migrations via DBS-04 | db/schema.py | — |  |  |  |  | 2026-09-24
53 | 0 | Delivered baseline (maintain) | DBS-02 | Database | Retention/purge | Data retention | Code-Derived | P2 | COMPLETED | 70 |  | db/purge.py | Maintain | db/purge.py | — |  |  |  |  | 2026-09-24
54 | 0 | Delivered baseline (maintain) | SEC-01 | Security | Credential handling | Secrets outside code | Agreed-Spec | P0 | COMPLETED | 70 |  | config.json outside repo | Vault in ENT-06 | atip_data/config.json | — |  |  |  |  | 2026-09-24
55 | 0 | Delivered baseline (maintain) | MON-07 | Monitoring | Feed health | WebSocket stall detection | Code-Derived | P1 | COMPLETED | 70 |  | Implemented | Maintain | data/dhan_ws.py | b303d7a |  |  |  |  | 2026-09-24
56 | 0 | Delivered baseline (maintain) | MON-08 | Monitoring | Diagnostics | Diagnostic tool | Code-Derived | P2 | COMPLETED | 65 |  | diagnose.py | Maintain | diagnose.py | — |  |  |  |  | 2026-09-24
57 | 0 | Delivered baseline (maintain) | OPS-01 | Deployment/Ops | Autostart/scheduling | Windows autostart | Code-Derived | P1 | COMPLETED | 75 |  | Task Scheduler + VBS | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml | — |  |  |  |  | 2026-09-24
58 | 0 | Delivered baseline (maintain) | OPS-07 | Deployment/Ops | Snapshot publishing | Hosted read-only view | Code-Derived | P2 | COMPLETED | 80 |  | Implemented | Maintain | publish_snapshot.py | — |  |  |  |  | 2026-09-24
59 | 1 | Foundation | DP-09 | Data Platform | India VIX | Real VIX series as MH/MSI/CRI input | Agreed-Spec | P0 | COMPLETED | 40 |  | Read from index snapshot with 15.0 fallback | Store daily VIX; remove silent default; flag missing | scores/engine.py; data/markets.py | engine.py:358 |  |  |  |  | 2026-09-24
60 | 1 | Foundation | DP-17 | Data Platform | Market breadth | Advance/decline; new highs/lows | Agreed-Spec | P0 | COMPLETED | 30 | DP-02 | Breadth input frozen (25.93) | Compute A/D and 52w highs/lows from prices_daily | scores/engine.py | Phase status Tier 3 |  |  |  |  | 2026-09-24
61 | 1 | Foundation | SC-09 | Alpha/Factor Engine | Market Health score | MH formula + regime label | Agreed-Spec | P0 | COMPLETED | 65 | DP-09; DP-17 | Implemented; breadth/VIX inputs frozen | Use real inputs; backfill market_health history | scores/engine.py | engine.py:354 |  |  |  |  | 2026-09-24
62 | 1 | Foundation | SC-08 | Alpha/Factor Engine | ACS | AI Confidence Score | Agreed-Spec | P0 | COMPLETED | 55 | SC-09 | Implemented; accuracy query leak; NewsConfidence frozen | Bound feedback query by date; real news confidence | scores/engine.py | engine.py:389 |  |  |  |  | 2026-09-24
63 | 1 | Foundation | MON-01 | Monitoring | Job logging | Accurate pipeline_log | Code-Derived | P0 | IN PROGRESS | 50 |  | Swallows exceptions; no end time; SUCCESS with 0 rows | Record failures, end time, row counts | pipeline/scheduler.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
64 | 1 | Foundation | MON-02 | Monitoring | Stalled-job detection | Heartbeat per job | Code-Derived | P0 | YET TO START | 5 | MON-01 | None | Expected-run table + missed-run check | pipeline/scheduler.py | news job silent 11 days |  |  |  |  | 2026-09-24
65 | 1 | Foundation | MON-03 | Monitoring | Failure alerting | Alerts on failure | Agreed-Spec | P0 | IN PROGRESS | 30 | MON-02 | Telegram path exists; unconfigured | Configure Telegram; alert on failure/stall | alerts/telegram.py | run_job |  |  |  |  | 2026-09-24
66 | 1 | Foundation | DB-14 | Dashboard | Alerts / morning brief | Telegram + 08:30 digest | Agreed-Spec | P1 | IN PROGRESS | 50 | MON-03 | Digest scheduled; channel unconfigured | Deliver digest; verify daily | alerts/telegram.py | scheduler.py:1032 |  |  |  |  | 2026-09-24
67 | 1 | Foundation | RK-15 | Risk Management | Risk alerts | Alerts on risk events | Agreed-Spec | P1 | IN PROGRESS | 40 | MON-03 | CRI alerts coded; channel unconfigured | Alert on halt, limit breach, CRI spike | alerts/telegram.py | — |  |  |  |  | 2026-09-24
68 | 1 | Foundation | MON-06 | Monitoring | Log rotation | Rotating logs | Code-Derived | P1 | YET TO START | 0 |  | None | RotatingFileHandler | main.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
69 | 1 | Foundation | DBS-06 | Database | Timestamp consistency | One timezone convention | Code-Derived | P1 | IN PROGRESS | 30 |  | IST and UTC mixed in same rows | Normalise; fix news recency | db/schema.py; data/news.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
70 | 1 | Foundation | NS-01 | News/Sentiment | News ingestion | Reliable daily news feed | Agreed-Spec | P0 | IN PROGRESS | 50 | MON-02 | ~1,249 rows; job stalled as of 09-21 | Fix job; add second source; health check | data/news.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
71 | 1 | Foundation | OPS-03 | Deployment/Ops | Install/setup | Reproducible install | Code-Derived | P1 | IN PROGRESS | 50 |  | setup.py lists pandas-ta; omits ta | Fix requirements/setup; pin versions | setup.py; requirements.txt | Phase status Tier 3 |  |  |  |  | 2026-09-24
72 | 1 | Foundation | EX-01 | Execution | Order management tests | Tested order rule engine | Agreed-Spec | P0 | COMPLETED | 70 |  | orders/rules.py (944 lines) without tests | Unit tests for rules.py | orders/rules.py; tests/ | Phase status Phase 11 |  |  |  |  | 2026-09-24
73 | 1 | Foundation | OPS-02 | Deployment/Ops | CI + end-to-end test | Data->score->signal->order->P&L test | Code-Derived | P0 | COMPLETED | 70 | EX-01 | GitHub Actions; ~270 test functions; no E2E | Add E2E pipeline test | .github/workflows/tests.yml; tests/ | — |  |  |  |  | 2026-09-24
74 | 1 | Foundation | DP-15 | Data Platform | Fundamentals | ROE; ROCE; EPS; PEG; FCF; D/E | Agreed-Spec | P0 | IN PROGRESS | 30 |  | Screener.in fetcher; ingestion disabled | Your decision; enable; quarterly store; no 50.0 default | data/fundamentals.py; pipeline/scheduler.py | FUNDAMENTALS_ENABLED=False |  |  |  |  | 2026-09-24
75 | 1 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | FS formula per concept document | Agreed-Spec | P0 | IN PROGRESS | 20 | DP-15 | Default 50 when unparsed | Implement FS formula on real data | data/fundamentals.py | — |  |  |  |  | 2026-09-24
76 | 1 | Foundation | SC-02 | Alpha/Factor Engine | SPI | Stability Profit Index per QRH | Agreed-Spec | P0 | IN PROGRESS | 30 | SC-13 | = fundamental_score (double-weighted) | Implement SPI formula separately from FS | scores/engine.py | engine.py:503 |  |  |  |  | 2026-09-24
77 | 1 | Foundation | SC-05 | Alpha/Factor Engine | CRI debt input | CRI per QRH incl. Debt | Agreed-Spec | P1 | COMPLETED | 75 | DP-15 | Implemented; Debt input missing | Feed Debt/Equity | scores/engine.py | engine.py:276 |  |  |  |  | 2026-09-24
78 | 1 | Foundation | SC-01 | Alpha/Factor Engine | VPI inputs | VPI per QRH | Agreed-Spec | P1 | COMPLETED | 80 | DP-15 | Implemented; FG/IS inputs weak | Real Fundamental Growth input | scores/engine.py | engine.py:222 |  |  |  |  | 2026-09-24
79 | 1 | Foundation | PF-01 | Portfolio | Portfolio ingestion | Zerodha/Dhan holdings sync | Agreed-Spec | P0 | IN PROGRESS | 60 |  | Kite holdings sync; Dhan holdings | Scheduled reliable sync + token handling | portfolio/zerodha.py; data/dhan.py | — |  |  |  |  | 2026-09-24
80 | 1 | Foundation | BR-04 | Broker Integration | Portfolio sync schedule | Real-time/daily sync (FR-BI-002) | Agreed-Spec | P0 | IN PROGRESS | 50 | PF-01 | Partial | Scheduled sync with alert on failure | pipeline/scheduler.py | — |  |  |  |  | 2026-09-24
81 | 1 | Foundation | PF-02 | Portfolio | Holdings & P&L | Holdings and P&L | Agreed-Spec | P0 | IN PROGRESS | 60 | PF-01 | portfolio_holdings with pnl | Realised + unrealised P&L | portfolio/ | zerodha.py:64 |  |  |  |  | 2026-09-24
82 | 1 | Foundation | PF-13 | Portfolio | Daily P&L series | Stored daily P&L (paper + live) | Code-Derived | P0 | YET TO START | 0 | PF-02 | None; realized_pnl cumulative only | Daily P&L table; EOD job | orders/paper.py | orders/risk.py docstring |  |  |  |  | 2026-09-24
83 | 1 | Foundation | RK-13 | Risk Management | Risk-based sizing wired to orders | FR-RM-001 position size | Agreed-Spec | P0 | IN PROGRESS | 25 |  | position_size_pct computed; not read | Use size in order path | scores/predictions.py; orders/rules.py | predictions.py:84 |  |  |  |  | 2026-09-24
84 | 1 | Foundation | RK-07 | Risk Management | Daily loss limit | Circuit breaker | Quant-Research | P0 | YET TO START | 0 | PF-13 | Deliberately absent | Limit on PF-13; auto-halt | orders/risk.py | — |  |  |  |  | 2026-09-24
85 | 1 | Foundation | RK-08 | Risk Management | Drawdown limit | Drawdown halt | Quant-Research | P0 | YET TO START | 0 | PF-13 | None | Peak-to-trough on PF-13; auto-halt | orders/risk.py | — |  |  |  |  | 2026-09-24
86 | 1 | Foundation | DBS-03 | Database | Backups | Automated backups | Agreed-Spec | P1 | IN PROGRESS | 40 |  | Manual pre-repair backups | Nightly integrity-checked backup + retention | db/ | atip_data/*.bak |  |  |  |  | 2026-09-24
87 | 1 | Foundation | DP-06 | Data Platform | Corporate actions open items | Split/bonus/demerger adjustment | Code-Derived | P2 | COMPLETED | 85 |  | NSE CA calendar; reconciliation; volume re-base | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py | 4416ac7 |  |  |  |  | 2026-09-24
88 | 1 | Foundation | TA-06 | Technical Analysis | Support/Resistance | S/R levels (ZPI/RRI inputs) | Agreed-Spec | P1 | UNCLEAR | 30 |  | Not verified statically | Confirm what ZPI/RRI use; implement pivot-based S/R | scores/engine.py | — |  |  |  |  | 2026-09-24
89 | 1 | Foundation | DP-19 | Data Platform | Data quality layer | Validation + DataQualityScore | Quant-Research | P1 | IN PROGRESS | 35 | MON-01 | Coverage/identical-bar/OHLC guards; no DQS | DQS table; outlier and timestamp checks | pipeline/scheduler.py | ba31981; 8526a9b |  |  |  |  | 2026-09-24
90 | 2 | Quant Research (data, factors, backtesting) | DBS-04 | Database | Schema migrations | Versioned migrations | Code-Derived | P0 | IN PROGRESS | 20 |  | CREATE IF NOT EXISTS only | Migration mechanism before new tables | db/schema.py | — |  |  |  |  | 2026-09-24
91 | 2 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | Live quotes + index feed (FR-MD-001) | Agreed-Spec | P1 | IN PROGRESS | 60 |  | Index WebSocket 09:00-15:45 + quote cache; stock tick feed never run | Stock-level live feed in production; failover | data/dhan_ws.py; data/dhan.py | dhan_ws.py session window/backoff |  |  |  |  | 2026-09-24
92 | 2 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | Stored 1/5/15-min bars | Agreed-Spec | P0 | IN PROGRESS | 20 | DBS-04 | Fetched every 30 min; nothing stored | Persist bars; retention policy | data/dhan.py; pipeline/scheduler.py | — |  |  |  |  | 2026-09-24
93 | 2 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | VWAP (TS weight 0.08) | Agreed-Spec | P1 | YET TO START | 5 | DP-03 | Weight seeded; never computed | Compute from intraday bars | data/technical.py | schema.py:322 |  |  |  |  | 2026-09-24
94 | 2 | Quant Research (data, factors, backtesting) | SC-12 | Alpha/Factor Engine | Technical Score VWAP input | TS formula complete | Agreed-Spec | P1 | COMPLETED | 75 | TA-03 | Implemented; VWAP weight dead | Include VWAP | data/technical.py | technical.py:307 |  |  |  |  | 2026-09-24
95 | 2 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | Volume by price; POC | Agreed-Spec | P1 | YET TO START | 0 | DP-03 | None | Implement on intraday bars | data/technical.py | — |  |  |  |  | 2026-09-24
96 | 2 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | Daily/weekly/intraday confluence | Agreed-Spec | P2 | YET TO START | 5 | DP-03 | Daily only | Resample timeframes | data/technical.py | — |  |  |  |  | 2026-09-24
97 | 2 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | Indicators for every history date | Quant-Research | P0 | IN PROGRESS | 30 |  | ~15 sessions deep | Backfill 426 sessions | data/technical.py | Phase status Phase 3 |  |  |  |  | 2026-09-24
98 | 2 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | (date, symbol, factor, value) | Quant-Research | P0 | IN PROGRESS | 30 | TA-12 | Composites stored; sub-components discarded | Persist sub-factors | scores/engine.py | — |  |  |  |  | 2026-09-24
99 | 2 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | Momentum; MR; trend; vol; volume; liquidity | Quant-Research | P0 | IN PROGRESS | 50 | AF-03 | Embedded inside composites | Extract as standalone factors | scores/engine.py | — |  |  |  |  | 2026-09-24
100 | 2 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | z-score; robust; winsorise; percentile | Quant-Research | P0 | IN PROGRESS | 15 | AF-03 | Min-max only | Per-factor normalisation config | scores/engine.py | — |  |  |  |  | 2026-09-24
101 | 2 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | ID; formula; lookback; version | Quant-Research | P0 | YET TO START | 5 | AF-03 | None | Registry table + API | — | — |  |  |  |  | 2026-09-24
102 | 2 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | Versioned score formulas | Agreed-Spec | P1 | IN PROGRESS | 25 | AF-01 | model_version + weights_hash on signal_log | Formula registry table | scores/signal_log.py | signal_log.py:144 |  |  |  |  | 2026-09-24
103 | 2 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | Factor/model/experiment tables | Quant-Research | P1 | YET TO START | 0 | DBS-04 | None | Create schema | db/schema.py | — |  |  |  |  | 2026-09-24
104 | 2 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | Rank IC; ICIR; hit-rate of IC | Quant-Research | P0 | YET TO START | 10 | AF-03 | Ad hoc only | IC engine vs forward returns | — | — |  |  |  |  | 2026-09-24
105 | 2 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | Decay by horizon | Quant-Research | P1 | YET TO START | 0 | QR-01 | None | Implement | — | — |  |  |  |  | 2026-09-24
106 | 2 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | Correlation matrix | Quant-Research | P1 | YET TO START | 0 | AF-03 | None | Implement | — | — |  |  |  |  | 2026-09-24
107 | 2 | Quant Research (data, factors, backtesting) | QR-04 | Quant Research | Statistical toolkit | Correlation; covariance; regression | Quant-Research | P1 | YET TO START | 5 | AF-03 | Univariate beta only | Stats module | — | technical.py:99 |  |  |  |  | 2026-09-24
108 | 2 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | Validation before production | Quant-Research | P1 | YET TO START | 0 | QR-01; QR-03 | Factor enters via seed code | Gate workflow + approval record | — | — |  |  |  |  | 2026-09-24
109 | 2 | Quant Research (data, factors, backtesting) | BT-16 | Backtesting | Dated equity curve / run records | Run registry with dated equity | Quant-Research | P0 | YET TO START | 5 |  | None | Dated trades + equity curve + run table | strategy/; scores/backtest.py | — |  |  |  |  | 2026-09-24
110 | 2 | Quant Research (data, factors, backtesting) | BT-08 | Backtesting | Portfolio-level backtest | Shared capital; sizing | Quant-Research | P0 | YET TO START | 5 | BT-16 | Independent per-trade notional | Portfolio simulator | — | backtest_history.py:139 |  |  |  |  | 2026-09-24
111 | 2 | Quant Research (data, factors, backtesting) | BT-09 | Backtesting | Drawdown analysis | Max DD on dated equity | Agreed-Spec | P0 | IN PROGRESS | 30 | BT-16 | DD in trade order (wrong) | Compute on equity curve | strategy/ | backtest_aggressive.py:206 |  |  |  |  | 2026-09-24
112 | 2 | Quant Research (data, factors, backtesting) | BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | Risk-adjusted metrics | Agreed-Spec | P0 | YET TO START | 0 | BT-16 | None | Implement | — | — |  |  |  |  | 2026-09-24
113 | 2 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | Tail metrics | Agreed-Spec | P1 | YET TO START | 0 | BT-16 | None | Implement | — | — |  |  |  |  | 2026-09-24
114 | 2 | Quant Research (data, factors, backtesting) | BT-05 | Backtesting | Itemised costs | Brokerage; STT; GST; stamp; SEBI fee; exchange fee | Agreed-Spec | P0 | IN PROGRESS | 35 |  | Single blended cost % | Indian cost model shared by backtest and paper | strategy/ | backtest_history.py:39 |  |  |  |  | 2026-09-24
115 | 2 | Quant Research (data, factors, backtesting) | BT-06 | Backtesting | Slippage in backtest | Slippage model | Agreed-Spec | P1 | IN PROGRESS | 30 | BT-05 | Paper broker only | Shared slippage model | orders/paper.py | paper.py:199 |  |  |  |  | 2026-09-24
116 | 2 | Quant Research (data, factors, backtesting) | BT-07 | Backtesting | Liquidity constraints | ADV/turnover floor + participation cap | Agreed-Spec | P1 | IN PROGRESS | 40 |  | One engine has floor | All engines | scores/backtest.py | backtest.py:61 |  |  |  |  | 2026-09-24
117 | 2 | Quant Research (data, factors, backtesting) | DP-18 | Data Platform | Survivorship-free universe | Point-in-time constituents | Agreed-Spec | P1 | COMPLETED | 80 |  | Current NIFTY 500 download | Store constituent history | data/index_constituents.py | — |  |  |  |  | 2026-09-24
118 | 2 | Quant Research (data, factors, backtesting) | BT-15 | Backtesting | Bias controls | Look-ahead; survivorship | Quant-Research | P1 | IN PROGRESS | 30 | DP-18 | Look-ahead handled in 2 places | Systematic checks | — | backtest.py:163-174 |  |  |  |  | 2026-09-24
119 | 2 | Quant Research (data, factors, backtesting) | BT-03 | Backtesting | In/out-of-sample | Split testing | Agreed-Spec | P0 | IN PROGRESS | 20 | BT-16 | Forward signal tracker only | Formal splits | — | — |  |  |  |  | 2026-09-24
120 | 2 | Quant Research (data, factors, backtesting) | BT-02 | Backtesting | Walk-forward | Rolling train/test (purged) | Agreed-Spec | P0 | YET TO START | 5 | BT-03 | None | Implement | — | — |  |  |  |  | 2026-09-24
121 | 2 | Quant Research (data, factors, backtesting) | BT-13 | Backtesting | Monte Carlo | Trade shuffle/bootstrap | Agreed-Spec | P1 | YET TO START | 0 | BT-16 | None | Implement | — | — |  |  |  |  | 2026-09-24
122 | 2 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | Optimiser | Agreed-Spec | P1 | IN PROGRESS | 20 | BT-02 | Manual sweep | Grid/Bayesian optimiser | — | aggressive.py:57 |  |  |  |  | 2026-09-24
123 | 2 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | Sensitivity analysis | Agreed-Spec | P1 | IN PROGRESS | 20 | BT-04 | Manual sweep | Neighbourhood analysis | strategy/aggressive.py | — |  |  |  |  | 2026-09-24
124 | 2 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | Deflated Sharpe; PBO; regime testing | Quant-Research | P1 | YET TO START | 0 | BT-02 | None | Implement | — | — |  |  |  |  | 2026-09-24
125 | 2 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | Seeded runs; experiment log | Quant-Research | P1 | YET TO START | 0 | DBS-07 | None | Experiment store | — | — |  |  |  |  | 2026-09-24
126 | 2 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | Trend strategy research | Agreed-Spec | P1 | IN PROGRESS | 30 | BT-02 | Aggressive exit + 3-policy backtest | Entry-side research | strategy/ | backtest_history.py |  |  |  |  | 2026-09-24
127 | 2 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | MR strategy research | Agreed-Spec | P1 | IN PROGRESS | 20 | BT-02 | RSI band inside VPI only | Standalone MR tests | scores/engine.py | — |  |  |  |  | 2026-09-24
128 | 2 | Quant Research (data, factors, backtesting) | QR-13 | Quant Research | Signal outcome research by regime | Hit rate by regime/ACS decile | Code-Derived | P1 | COMPLETED | 70 | ML-05 | success_report keyed on signal/threshold | Add regime/ACS buckets | scores/signal_log.py | signal_log.py:522 |  |  |  |  | 2026-09-24
129 | 2 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | 1y; 3y; rolling-60 beta (QRH) | Agreed-Spec | P2 | IN PROGRESS | 40 | TA-12 | 1y beta only | Add 3y and rolling beta | data/technical.py | technical.py:99 |  |  |  |  | 2026-09-24
130 | 2 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | Optional BRI (QRH) | Agreed-Spec | P2 | YET TO START | 0 | TA-09 | None | Define + implement | — | — |  |  |  |  | 2026-09-24
131 | 2 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | Ichimoku; Donchian; Keltner; SAR; MFI; CMF; HV | Quant-Research | P2 | YET TO START | 5 | TA-12 | None | Implement per research workbook | data/technical.py | — |  |  |  |  | 2026-09-24
132 | 2 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | Futures; options; OI; IV; PCR | Agreed-Spec | P1 | YET TO START | 0 | DBS-04 | None | NSE F&O bhavcopy + option chain store | — | — |  |  |  |  | 2026-09-24
133 | 2 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | Market Sentiment Index per QRH | Agreed-Spec | P1 | IN PROGRESS | 55 | DP-08 | Options/PCR frozen; news rule-based | Real PCR; AI news later | scores/engine.py | engine.py:374 |  |  |  |  | 2026-09-24
134 | 2 | Quant Research (data, factors, backtesting) | DP-10 | Data Platform | FII/DII history | FII/DII time series | Agreed-Spec | P2 | COMPLETED | 80 |  | Session flows; only 7 sessions history | Historical backfill source | data/bhavcopy.py | 969f570 |  |  |  |  | 2026-09-24
135 | 2 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | Pre-open GIFT Nifty | Agreed-Spec | P2 | IN PROGRESS | 60 |  | In index feed; shown on dashboard | Verify pre-market capture; store history | data/dhan.py | dhan.py:486 |  |  |  |  | 2026-09-24
136 | 2 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | Dashboard section | Agreed-Spec | P2 | IN PROGRESS | 60 | DP-11 | In index strip | Dedicated pre-open view | dashboard/server.py | — |  |  |  |  | 2026-09-24
137 | 2 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | Indices; FX; commodities; yields | Agreed-Spec | P2 | IN PROGRESS | 70 |  | 13 yfinance tickers | Bond yields; history depth | data/markets.py | markets.py:22-26 |  |  |  |  | 2026-09-24
138 | 2 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | Sector classification + sector indices | Agreed-Spec | P2 | IN PROGRESS | 60 |  | Industry via constituents | Sector index history; sector breadth | data/index_constituents.py | — |  |  |  |  | 2026-09-24
139 | 2 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | MF; promoter; insider; bulk/block | Agreed-Spec | P1 | IN PROGRESS | 25 |  | Bulk/block only | Promoter/SAST/PIT/MF feeds | data/bhavcopy.py | bhavcopy.py:67-124 |  |  |  |  | 2026-09-24
140 | 2 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | INS formula | Agreed-Spec | P1 | IN PROGRESS | 40 | DP-16 | FII + bulk only | Add MF/promoter/insider | scores/engine.py | engine.py:188 |  |  |  |  | 2026-09-24
141 | 2 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | Deal-flow signal | Agreed-Spec | P2 | IN PROGRESS | 40 | DP-16 | Feeds INS | Validate with IC | data/bhavcopy.py | bhavcopy.py:113 |  |  |  |  | 2026-09-24
142 | 3 | Strategy Engine | SG-04 | Signal Engine | Rich decision states | STRONG BUY..NO TRADE with reasons | Quant-Research | P0 | IN PROGRESS | 20 | BT-02 | WAIT as de-facto no-trade | Extended states + stored reasons | scores/engine.py | engine.py:499 |  |  |  |  | 2026-09-24
143 | 3 | Strategy Engine | SG-01 | Signal Engine | SELL calibration | BUY/SELL/HOLD/WAIT all reachable | Agreed-Spec | P0 | COMPLETED | 70 | BT-02 | SELL never fired | Backtest-based SELL thresholds | scores/engine.py | determine_signal |  |  |  |  | 2026-09-24
144 | 3 | Strategy Engine | SE-01 | Strategy Engine | Strategy library | Multiple strategies (FR-SB-004) | Agreed-Spec | P0 | IN PROGRESS | 20 | BT-16 | One strategy + order rules | Strategy interface + registry | strategy/ | — |  |  |  |  | 2026-09-24
145 | 3 | Strategy Engine | SE-02 | Strategy Engine | Strategy parameters | Parameter management | Agreed-Spec | P0 | IN PROGRESS | 35 | SE-01 | Aggressive params; order_rules | Param store per strategy with versions | strategy/; orders/rules.py | — |  |  |  |  | 2026-09-24
146 | 3 | Strategy Engine | SE-03 | Strategy Engine | Rule-based strategies | Rule engine | Agreed-Spec | P1 | IN PROGRESS | 50 | SE-01 | orders/rules.py rule engine | Generic rule definition format | orders/rules.py | — |  |  |  |  | 2026-09-24
147 | 3 | Strategy Engine | SE-06 | Strategy Engine | Multi-factor strategy | Composite-score entries | Agreed-Spec | P1 | IN PROGRESS | 40 | SE-01; QR-01 | BUY from ATIP composite | IC-weighted multi-factor strategy | scores/engine.py | engine.py:435 |  |  |  |  | 2026-09-24
148 | 3 | Strategy Engine | SE-04 | Strategy Engine | Quant strategies | Factor/stat strategies | Quant-Research | P1 | YET TO START | 5 | SE-01; QR-01 | None | Implement first quant strategies | — | — |  |  |  |  | 2026-09-24
149 | 3 | Strategy Engine | SE-09 | Strategy Engine | Strategy lifecycle | Idea -> research -> paper -> live -> retired | Quant-Research | P1 | YET TO START | 5 | SE-01 | None | State machine + gates | — | strategy_event 3 rows |  |  |  |  | 2026-09-24
150 | 3 | Strategy Engine | SE-11 | Strategy Engine | Strategy health | Rolling Sharpe/DD per strategy | Quant-Research | P1 | YET TO START | 0 | SE-09; BT-16 | None | Health scoring + alerts | — | — |  |  |  |  | 2026-09-24
151 | 3 | Strategy Engine | SE-07 | Strategy Engine | Strategy combination/ranking/selection | Allocator across strategies | Quant-Research | P1 | YET TO START | 5 | SE-11 | None | Allocator | — | — |  |  |  |  | 2026-09-24
152 | 3 | Strategy Engine | SE-08 | Strategy Engine | Regime-aware selection | Regime switches strategies | Quant-Research | P2 | IN PROGRESS | 15 | SE-07; ML-05 | Regime gates only | Regime-conditional allocation | scores/engine.py | — |  |  |  |  | 2026-09-24
153 | 3 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | Midday/pre-close scans on real data | Code-Derived | P2 | IN PROGRESS | 60 | DP-03 | Scheduled 12:30 and 14:45 | Use stored intraday bars | pipeline/scheduler.py | scheduler.py:1048 |  |  |  |  | 2026-09-24
154 | 3 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | Daily top-25 lists per concept document | Agreed-Spec | P1 | IN PROGRESS | 40 |  | CRI per-stock column only | Dedicated lists | dashboard/server.py | — |  |  |  |  | 2026-09-24
155 | 3 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | Dashboard section | Agreed-Spec | P1 | YET TO START | 10 | SE-11 | None | Panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
156 | 4 | AI/ML | ML-13 | AI/ML | Labels/targets | Outcome labels for training | Agreed-Spec | P0 | IN PROGRESS | 40 | AF-03 | predictions + accuracy_tracker | Label store with horizons | scores/ | — |  |  |  |  | 2026-09-24
157 | 4 | AI/ML | ML-07 | AI/ML | Feature selection | Automated selection | Quant-Research | P1 | YET TO START | 0 | ML-13; QR-01 | None | Implement | — | — |  |  |  |  | 2026-09-24
158 | 4 | AI/ML | ML-08 | AI/ML | Model validation | Purged CV; AUC; calibration | Agreed-Spec | P0 | YET TO START | 0 | ML-13; BT-02 | None | Validation framework | — | — |  |  |  |  | 2026-09-24
159 | 4 | AI/ML | ML-01 | AI/ML | Supervised ML | Classification/regression models | Agreed-Spec | P0 | YET TO START | 0 | ML-08 | None; no ML library | First model (e.g. gradient boosting) | — | grep sklearn = 0 |  |  |  |  | 2026-09-24
160 | 4 | AI/ML | ML-12 | AI/ML | Model registry/versioning | FR-ML-002 | Agreed-Spec | P0 | IN PROGRESS | 15 | ML-01; DBS-07 | Signal provenance only | Registry | scores/signal_log.py | — |  |  |  |  | 2026-09-24
161 | 4 | AI/ML | ML-11 | AI/ML | Ensemble models | Ensembles | Quant-Research | P1 | YET TO START | 0 | ML-01 | None | Implement | — | — |  |  |  |  | 2026-09-24
162 | 4 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | Drift alerts (FR-ML-001) | Agreed-Spec | P1 | YET TO START | 0 | ML-12 | None | Implement | — | — |  |  |  |  | 2026-09-24
163 | 4 | AI/ML | ML-10 | AI/ML | Explainability | FR-AI-003 | Agreed-Spec | P1 | IN PROGRESS | 40 | ML-01 | top_factor_1..3 | Model attribution | scores/engine.py | — |  |  |  |  | 2026-09-24
164 | 4 | AI/ML | ML-05 | AI/ML | Regime detection | Model-based regime + probability | Agreed-Spec | P0 | IN PROGRESS | 30 | SC-09 | 5-way threshold on MH | HMM/GMM; regime-conditional weights | scores/engine.py | compute_mh |  |  |  |  | 2026-09-24
165 | 4 | AI/ML | ML-03 | AI/ML | Unsupervised learning | Clustering | Agreed-Spec | P2 | YET TO START | 0 | AF-03 | None | Implement | — | — |  |  |  |  | 2026-09-24
166 | 4 | AI/ML | ML-06 | AI/ML | Anomaly detection | Data/market anomalies | Agreed-Spec | P2 | YET TO START | 0 | DP-19 | None | Implement | — | — |  |  |  |  | 2026-09-24
167 | 4 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | FR-SB-003 | Agreed-Spec | P1 | YET TO START | 0 | ML-01; SE-01 | None | ML-signal strategy through lifecycle | — | — |  |  |  |  | 2026-09-24
168 | 4 | AI/ML | NS-02 | News/Sentiment | News classification | Earnings/Orders/M&A/RBI/Govt/Global/Geopolitics | Agreed-Spec | P0 | IN PROGRESS | 30 |  | Claude classifier coded; key unset | Set key; taxonomy; cost cap | data/news.py | news.py:118-129 |  |  |  |  | 2026-09-24
169 | 4 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | Positive/neutral/negative + confidence | Agreed-Spec | P0 | IN PROGRESS | 40 | NS-02 | Rule-based; confidence frozen 50 | Model-based scoring | data/news.py | — |  |  |  |  | 2026-09-24
170 | 4 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | Decayed weighted sentiment | Quant-Research | P1 | YET TO START | 5 | NS-03 | None | Implement | data/news.py | — |  |  |  |  | 2026-09-24
171 | 4 | AI/ML | NS-04 | News/Sentiment | AI news summary | Summary for dashboard | Agreed-Spec | P1 | IN PROGRESS | 50 | NS-02 | Headline list | LLM summary | dashboard/server.py | /api/news |  |  |  |  | 2026-09-24
172 | 4 | AI/ML | DB-06 | Dashboard | AI News Summary panel | Dashboard section | Agreed-Spec | P1 | IN PROGRESS | 50 | NS-04 | News panel (rule-based) | Show AI summary | dashboard/server.py | — |  |  |  |  | 2026-09-24
173 | 4 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | Transcript sentiment | Agreed-Spec | P2 | YET TO START | 0 | NS-02 | None | Implement | — | — |  |  |  |  | 2026-09-24
174 | 4 | AI/ML | ML-02 | AI/ML | Deep learning | Neural models | Agreed-Spec | P2 | YET TO START | 0 | ML-08 | None | Only if validated benefit | — | — |  |  |  |  | 2026-09-24
175 | 4 | AI/ML | ML-04 | AI/ML | Reinforcement learning | RL where appropriate | Agreed-Spec | P2 | YET TO START | 0 | ML-08 | None | Low priority | — | — |  |  |  |  | 2026-09-24
176 | 4 | AI/ML | DB-18 | Dashboard | Quant/model panel | Factor IC; model health | Quant-Research | P2 | YET TO START | 0 | ML-12 | None | Panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
177 | 5 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | Allocation view | Agreed-Spec | P1 | IN PROGRESS | 30 | PF-02 | Partial via PHS | Sector exposure table | scores/portfolio_health.py | — |  |  |  |  | 2026-09-24
178 | 5 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | HHI; weight caps | Agreed-Spec | P1 | IN PROGRESS | 40 | PF-03 | Diversification term in PHS | Position-weight metrics | scores/portfolio_health.py | portfolio_health.py:127 |  |  |  |  | 2026-09-24
179 | 5 | Risk & Portfolio | PF-09 | Portfolio | Correlation | Holdings correlation | Agreed-Spec | P1 | YET TO START | 0 | QR-04 | None | Implement | — | — |  |  |  |  | 2026-09-24
180 | 5 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | Cluster limits | Quant-Research | P1 | YET TO START | 0 | PF-09 | None | Implement | orders/risk.py | — |  |  |  |  | 2026-09-24
181 | 5 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | Portfolio risk | Quant-Research | P1 | YET TO START | 0 | QR-04 | None | Implement | — | — |  |  |  |  | 2026-09-24
182 | 5 | Risk & Portfolio | RK-06 | Risk Management | Sector limits | Sector cap | Quant-Research | P1 | YET TO START | 0 | PF-03 | None | Pre-trade sector check | orders/risk.py | — |  |  |  |  | 2026-09-24
183 | 5 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | Vol-scaled exposure | Quant-Research | P1 | YET TO START | 0 | TA-12 | None | Implement | orders/risk.py | — |  |  |  |  | 2026-09-24
184 | 5 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | ADV participation cap | Quant-Research | P1 | YET TO START | 5 | DP-02 | None in order path | Pre-trade ADV check | orders/risk.py | — |  |  |  |  | 2026-09-24
185 | 5 | Risk & Portfolio | RK-18 | Risk Management | Strategy risk budget | Per-strategy limits | Quant-Research | P2 | YET TO START | 0 | SE-09 | None | Implement | orders/risk.py | — |  |  |  |  | 2026-09-24
186 | 5 | Risk & Portfolio | RK-01 | Risk Management | Kill switch scopes + auto-trigger | Global/strategy/symbol; auto on breach | Quant-Research | P0 | COMPLETED | 80 | RK-07; RK-08 | Global flag file + config | Per-strategy/symbol; auto-trigger | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
187 | 5 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | Flatten all positions | Quant-Research | P0 | YET TO START | 5 | RK-01 | None | One-command flatten with confirm | orders/ | — |  |  |  |  | 2026-09-24
188 | 5 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | Vol target; risk parity; MV with costs; BL | Quant-Research | P1 | YET TO START | 0 | RK-12 | None | Covariance + optimiser | — | — |  |  |  |  | 2026-09-24
189 | 5 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | Rebalance proposals | Agreed-Spec | P1 | YET TO START | 0 | PF-10 | None | Implement | — | — |  |  |  |  | 2026-09-24
190 | 5 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | Risk contribution | Quant-Research | P2 | YET TO START | 0 | PF-10 | None | Implement | — | — |  |  |  |  | 2026-09-24
191 | 5 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | Return attribution | Quant-Research | P2 | YET TO START | 0 | PF-13 | None | Implement | — | — |  |  |  |  | 2026-09-24
192 | 5 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | FR-PO-004 | Agreed-Spec | P2 | YET TO START | 5 | PF-13 | None | Implement | — | — |  |  |  |  | 2026-09-24
193 | 5 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | Risk panel | Quant-Research | P1 | YET TO START | 5 | RK-12 | None | Panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
194 | 6 | Execution | EX-02 | Execution | Order types | Market/limit/SL/SL-M/GTT/bracket | Agreed-Spec | P0 | IN PROGRESS | 50 |  | Market + limit | Add SL/SL-M/GTT | orders/broker.py | — |  |  |  |  | 2026-09-24
195 | 6 | Execution | EX-08 | Execution | Order modify/cancel | FR-LT-002/003 | Agreed-Spec | P0 | UNCLEAR | 0 |  | Not verified | Confirm; implement | orders/broker.py | — |  |  |  |  | 2026-09-24
196 | 6 | Execution | BR-05 | Broker Integration | Execution reconciliation | Orders vs broker fills/positions | Agreed-Spec | P0 | IN PROGRESS | 30 |  | Partial reconcile code | EOD reconciliation job + alert | orders/ | — |  |  |  |  | 2026-09-24
197 | 6 | Execution | BR-06 | Broker Integration | Connection health | FR-BI-003 | Agreed-Spec | P1 | IN PROGRESS | 40 | MON-03 | broker-status route; WS stall detection | Health checks + alerts | dashboard/server.py | b303d7a |  |  |  |  | 2026-09-24
198 | 6 | Execution | RK-17 | Risk Management | Broker/operational risk | Token expiry; connection loss | Quant-Research | P1 | IN PROGRESS | 30 | BR-06 | broker-status route | Automated checks | dashboard/server.py | — |  |  |  |  | 2026-09-24
199 | 6 | Execution | BR-08 | Broker Integration | Sandbox | Broker sandbox environment | Code-Derived | P2 | IN PROGRESS | 30 |  | SANDBOX env defined | Verify sandbox path end-to-end | orders/environment.py | — |  |  |  |  | 2026-09-24
200 | 6 | Execution | EX-09 | Execution | Measured slippage | Slippage vs decision price | Quant-Research | P1 | YET TO START | 5 | PF-13 | Assumption only | Measure per fill | orders/ | — |  |  |  |  | 2026-09-24
201 | 6 | Execution | EX-10 | Execution | Execution analytics | Implementation shortfall; fill/reject rate | Quant-Research | P1 | IN PROGRESS | 10 | EX-09 | order_log raw data only | Analytics + panel | orders/ | — |  |  |  |  | 2026-09-24
202 | 6 | Execution | BR-02 | Broker Integration | Zerodha/Kite | Portfolio (+orders optional) | Agreed-Spec | P2 | IN PROGRESS | 50 |  | Holdings sync only | Token refresh; orders if wanted | portfolio/zerodha.py | — |  |  |  |  | 2026-09-24
203 | 6 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | Live P&L view | Agreed-Spec | P1 | IN PROGRESS | 25 | PF-13 | Dashboard partial | Live P&L panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
204 | 6 | Execution | SEC-03 | Security | Audit logging | Immutable audit (FR-AT-001) | Agreed-Spec | P1 | IN PROGRESS | 50 |  | order_log; signal_log; pipeline_log | Tamper-evident unified audit | — | — |  |  |  |  | 2026-09-24
205 | 7 | Advanced Quant | DP-04 | Data Platform | Tick data | Tick capture store | Quant-Research | P2 | YET TO START | 5 | DBS-04 | live_ticks exists; 0 rows | Tick ingestion + storage | data/dhan.py | — |  |  |  |  | 2026-09-24
206 | 7 | Advanced Quant | DP-05 | Data Platform | Order book / depth | L2 depth; bid/ask | Quant-Research | P2 | YET TO START | 5 | DP-04 | FULL feed type defined (CLI only) | Depth capture + schema | data/dhan.py | dhan.py FULL=21 |  |  |  |  | 2026-09-24
207 | 7 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | OBI; spread; microprice | Quant-Research | P2 | YET TO START | 0 | DP-05 | None | Implement | — | — |  |  |  |  | 2026-09-24
208 | 7 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors | OI buildup; IV; PCR; skew | Quant-Research | P2 | YET TO START | 0 | DP-08 | None | Implement | — | — |  |  |  |  | 2026-09-24
209 | 7 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | IV/RV; vol breakout | Quant-Research | P2 | YET TO START | 0 | DP-08 | None | Implement | — | — |  |  |  |  | 2026-09-24
210 | 7 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | Pairs research | Quant-Research | P2 | YET TO START | 0 | QR-04 | None | Implement | — | — |  |  |  |  | 2026-09-24
211 | 7 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | Long-short research | Quant-Research | P2 | YET TO START | 0 | DP-08 | None (long-only cash) | Needs shorting via F&O | — | — |  |  |  |  | 2026-09-24
212 | 7 | Advanced Quant | QR-09 | Quant Research | Event-driven research | Earnings/CA event studies | Quant-Research | P2 | YET TO START | 5 | DP-06 | CA data exists; no event study | Abnormal-return engine | — | — |  |  |  |  | 2026-09-24
213 | 7 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | Piotroski; Altman; value z-composite | Quant-Research | P2 | YET TO START | 0 | DP-15 | None | Implement | — | — |  |  |  |  | 2026-09-24
214 | 7 | Advanced Quant | EX-11 | Execution | Execution algos | TWAP/VWAP/POV | Quant-Research | P2 | YET TO START | 0 | DP-03 | None | Implement | — | — |  |  |  |  | 2026-09-24
215 | 7 | Advanced Quant | EX-12 | Execution | Market impact model | Impact estimate | Quant-Research | P2 | YET TO START | 0 | DP-05 | None | Implement | — | — |  |  |  |  | 2026-09-24
216 | 7 | Advanced Quant | EX-15 | Execution | Latency telemetry | p50/p95/p99 | Quant-Research | P2 | YET TO START | 0 |  | None | Instrument data and order paths | — | — |  |  |  |  | 2026-09-24
217 | 7 | Advanced Quant | EX-16 | Execution | Event-driven OMS | Event bus signal->risk->order->fill | Quant-Research | P2 | YET TO START | 10 | EX-15 | Synchronous calls | Implement | — | — |  |  |  |  | 2026-09-24
218 | 7 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | Event engine shared with live | Quant-Research | P2 | YET TO START | 0 | EX-16 | Bar loops only | Implement | — | — |  |  |  |  | 2026-09-24
219 | 7 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | RBI rates; CPI; IIP; yields | Quant-Research | P2 | YET TO START | 0 |  | None | Macro connectors + calendar | — | — |  |  |  |  | 2026-09-24
220 | 7 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | Source abstraction | Quant-Research | P2 | YET TO START | 0 |  | None | DataSource interface | — | — |  |  |  |  | 2026-09-24
221 | 7 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | Web/social/search/etc. | Quant-Research | P2 | YET TO START | 0 | AD-01 | None | Add sources | — | — |  |  |  |  | 2026-09-24
222 | 7 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | Columnar PIT research store | Quant-Research | P2 | YET TO START | 5 |  | SQLite only | Parquet/DuckDB store | — | — |  |  |  |  | 2026-09-24
223 | 7 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | Commodities; FX; bonds; MF | Agreed-Spec | P2 | YET TO START | 0 |  | Global display tickers only | MCX/CDS/bond/MF feeds | — | — |  |  |  |  | 2026-09-24
224 | 8 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | Decay alerts | Quant-Research | P1 | YET TO START | 0 | QR-02; ML-09 | None | Implement | — | — |  |  |  |  | 2026-09-24
225 | 8 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | DR plan | Agreed-Spec | P1 | YET TO START | 5 | DBS-03 | None | Restore drills | — | — |  |  |  |  | 2026-09-24
226 | 8 | Production Hardening | SEC-04 | Security | Encryption | TLS 1.3; AES-256 at rest (SRS) | Agreed-Spec | P1 | YET TO START | 5 |  | None locally | Encrypt secrets and DB at rest | — | — |  |  |  |  | 2026-09-24
227 | 8 | Production Hardening | API-05 | APIs | API contracts/docs | Documented contracts | Agreed-Spec | P2 | IN PROGRESS | 30 |  | FastAPI defaults only | Written contracts | — | — |  |  |  |  | 2026-09-24
228 | 8 | Production Hardening | API-06 | APIs | Widget JSON schemas | QRH deliverable | Agreed-Spec | P2 | YET TO START | 5 |  | None | Define schemas | — | — |  |  |  |  | 2026-09-24
229 | 8 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | BRD..OPS documents with real content | Agreed-Spec | P1 | IN PROGRESS | 15 |  | Mostly 60-word templates | Author docs from as-built system | docs/ | OLd_Archives_ATIP/ATIP_Docs |  |  |  |  | 2026-09-24
230 | 9 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | Per-user data isolation; tenant model | Enterprise-SaaS | P0 | YET TO START | 0 | OPS-05 | Single-user local design | Architecture decision record; tenant-scoped schema | — | BRD-003; SRS 2 |  |  |  |  | 2026-09-24
231 | 9 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | PostgreSQL/time-series (SRS) | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-01 | SQLite | Migrate to Postgres | — | SRS 2 |  |  |  |  | 2026-09-24
232 | 9 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure | TLS; WAF; rate limits; zero trust | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-01 | Local-only by design (never exposed) | Security architecture before any exposure | — | SRS 5 |  |  |  |  | 2026-09-24
233 | 9 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | FR-AU-001/002; RBAC | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-07 | Single-user; none | Identity provider; roles; MFA | — | SRS Part III |  |  |  |  | 2026-09-24
234 | 9 | Enterprise SaaS (final objective) | ENT-05 | Security | Session management | Timeout; refresh tokens; revocation (FR-AU-003) | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | Single static token | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
235 | 9 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | Email; mobile; OAuth; Google; Apple (FR-UM-001) | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | None | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
236 | 9 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | FR-UM-002 | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-02 | None | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
237 | 9 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | Broker OAuth; encrypted per-user tokens | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | One owner's config.json | Vault + broker OAuth | — | — |  |  |  |  | 2026-09-24
238 | 9 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | SEBI retail algo framework (broker/exchange algo approval); RA/IA registration if advice is offered | Enterprise-SaaS | P0 | YET TO START | 0 |  | None | Legal review before offering to other users | — | BRD-006 |  |  |  |  | 2026-09-24
239 | 9 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | FR-AT-002 | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-14 | None | Implement controls from ENT-14 | — | SRS Part III |  |  |  |  | 2026-09-24
240 | 9 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | DPDP Act; consent; retention | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-14 | None | Privacy policy + controls | — | BRD-004 |  |  |  |  | 2026-09-24
241 | 9 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | Web UI for all users | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | Single-user dashboard + read-only snapshot | Build web app | — | SRS 2 |  |  |  |  | 2026-09-24
242 | 9 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | Free/Premium/Enterprise (FR-UM-003) | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-02 | None | Plans + payment gateway | — | SRS Part III |  |  |  |  | 2026-09-24
243 | 9 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | FR-UM-004 | Enterprise-SaaS | P2 | YET TO START | 0 | ENT-05 | None | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
244 | 9 | Enterprise SaaS (final objective) | ENT-19 | Channels | Watchlists | BR-006 | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-08 | None | Implement | — | BRD-004 |  |  |  |  | 2026-09-24
245 | 9 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | FR-AL-001/002 | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-19 | Owner-only Telegram | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
246 | 9 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | Push; SMS; email; WhatsApp; in-app (FR-AL-003) | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-11 | Telegram only | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
247 | 9 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | Android + iOS | Enterprise-SaaS | P1 | YET TO START | 0 | API-03 | None | Build apps | — | SRS 2 |  |  |  |  | 2026-09-24
248 | 9 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | FR-API-001/003 | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | None | /v1 API with auth and rate limits | — | SRS Part III |  |  |  |  | 2026-09-24
249 | 9 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | FR-API-002 | Enterprise-SaaS | P2 | YET TO START | 0 | API-03 | None | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
250 | 9 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | Angel/Groww/Upstox/CSV (FR-PO-002) | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-06 | None | Importers | — | SRS Part III |  |  |  |  | 2026-09-24
251 | 9 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | Angel/Upstox/Groww trading | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-06; BR-03 | None | Adapters behind BR-03 interface | — | SRS Part III |  |  |  |  | 2026-09-24
252 | 9 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | MF; bonds; commodities; currency (FR-PO-003) | Enterprise-SaaS | P2 | YET TO START | 0 | DP-21; BR-07 | Equity cash only | Asset-specific execution/risk adapters | — | BRD-001 |  |  |  |  | 2026-09-24
253 | 9 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | Portfolio; tax; AI performance (FR-RP) | Enterprise-SaaS | P1 | YET TO START | 0 | PF-13 | None | Report generation + export | — | SRS Part III |  |  |  |  | 2026-09-24
254 | 9 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | User admin; system config (FR-AD) | Enterprise-SaaS | P1 | YET TO START | 0 | SEC-02 | config.json edited by hand | Admin console | — | SRS Part III |  |  |  |  | 2026-09-24
255 | 9 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | FR-SB-001/002 | Enterprise-SaaS | P2 | YET TO START | 0 | SE-01; ENT-08 | None | Visual builder on SE-01 interface | — | SRS Part III |  |  |  |  | 2026-09-24
256 | 9 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | NL assistant (SRS) | Enterprise-SaaS | P2 | YET TO START | 0 | ENT-08 | None | Implement | — | SRS 3 |  |  |  |  | 2026-09-24
257 | 9 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | Docker/Kubernetes on cloud (SRS) | Enterprise-SaaS | P0 | YET TO START | 0 | DBS-05; ENT-07 | Local Windows only | Containerise; IaC; environments | — | SRS 2 |  |  |  |  | 2026-09-24
258 | 9 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | 99.9%+ availability; horizontal scale; metrics/tracing | Enterprise-SaaS | P1 | YET TO START | 0 | OPS-04 | Single process | HA design + SLOs | — | SRS 4 |  |  |  |  | 2026-09-24
259 | 12 | UX redesign (2026-10-26) | UXR-01 | Dashboard | Command Center (/command) | One screen: halt/feed/broker/market state, risk budget, pending confirmations, top EOD signals with live gap, 10 sessions, recent activity | Owner prompt: UI/UX redesign | P1 | IMPLEMENTED BUT NOT VERIFIED | 85 |  | dashboard/command_page.py + command_routes.py; GET /api/command/summary; light/dark; phone layout; linked from the main top bar | Owner UAT on the Mac with live data | dashboard/command_page.py; dashboard/command_routes.py | tests/test_ux_command_center.py; tests/test_ux_command_browser.py | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: COMPLETED
260 | 12 | UX redesign (2026-10-26) | UXR-02 | Execution | Kill switch in the UI + API | Halt/resume from any screen, reason logged | Owner prompt: UI/UX redesign | P1 | IMPLEMENTED BUT NOT VERIFIED | 90 |  | POST /api/risk/halt (orders.risk.halt + pauses running sessions), POST /api/risk/resume {confirm:RESUME}; token-guarded; button + dialog on /command | Add the same halt button to / and /trading headers | dashboard/command_routes.py; orders/risk.py | tests/test_ux_command_center.py | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: COMPLETED
261 | 12 | UX redesign (2026-10-26) | UXR-03 | Execution | Trading sessions registry (10) | Per-session mode Manual/Confirm/Auto, status, limits, rule links, audit log | Owner prompt: UI/UX redesign | P1 | IMPLEMENTED BUT NOT VERIFIED | 70 |  | orders/sessions.py: trading_sessions, session_rules, session_events; AUTO needs ack, refused while halted, LIVE AUTO needs sebi_algo_id; /api/sessions* | Engine enforcement is UXR-04 | orders/sessions.py | tests/test_ux_command_center.py | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: COMPLETED
262 | 12 | UX redesign (2026-10-26) | UXR-04 | Execution | Trigger engine honours sessions | Paused sessions do not fire; per-session trade/loss/capital caps; AUTO sends without confirmation | Owner prompt: UI/UX redesign | P1 | BLOCKED | 0 |  | Not wired: orders/rules.py check_triggers/execute_rule do not read sessions | Owner decision: changes when real orders go out ¦ BLOCKER: Owner go-ahead to let AUTO bypass the confirmation gate | orders/rules.py; orders/sessions.py |  | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: YET TO START
263 | 12 | UX redesign (2026-10-26) | UXR-05 | Dashboard | UX redesign + clickable prototype | Design thinking artefacts, IA, 8 screens + mobile, design system | Owner prompt: UI/UX redesign | P1 | COMPLETED | 100 |  | Design canvas 'ATIP Trading Console Redesign'; docs/UX_REDESIGN_2026-10.md | Owner review | docs/UX_REDESIGN_2026-10.md |  | Claude (development) |  | 46321 | 46321 | 2026-10-26 | Testing: N/A
264 | 12 | UX redesign (2026-10-26) | UXR-06 | Dashboard | Signal Explorer with explainability | Ranked signals, factor bars, plain-language reason, signal vs live gap | Owner prompt: UI/UX redesign | P1 | YET TO START | 0 |  | Prototype only | Build after owner review of prototype |  |  | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: YET TO START
265 | 12 | UX redesign (2026-10-26) | UXR-07 | Execution | Trade Setup with ₹ risk preview | Steppers, R:R, charges, remaining loss budget, pre-trade checklist | Owner prompt: UI/UX redesign | P1 | YET TO START | 0 |  | Prototype only; pretrade_check exists | Wrap orders.risk.pretrade_check dry run in a preview endpoint |  |  | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: YET TO START
266 | 12 | UX redesign (2026-10-26) | UXR-08 | Execution | Live Monitor | Positions with stop/target distance, rules watching, order log with rule causes | Owner prompt: UI/UX redesign | P1 | YET TO START | 0 |  | Prototype only; /trading has parts |  |  |  | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: YET TO START
267 | 12 | UX redesign (2026-10-26) | UXR-09 | Analytics | Journal per session + 2027 range | Per-session trades, successes, win rate, P&L, straight-line range to Dec 2027 | Owner prompt: UI/UX redesign | P1 | YET TO START | 0 |  | Prototype only | Needs UXR-03 rule links populated |  |  | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: YET TO START
268 | 12 | UX redesign (2026-10-26) | UXR-10 | Mobile | Android + iOS apps with push | New screens on phone; push for fills, SL hits, halt | Owner prompt: UI/UX redesign | P1 | IN PROGRESS | 60 |  | Native shells written (mobile/android, mobile/ios) with the status banner and Global & Asia; not built — no Android SDK/Xcode on the Mac (MOB-01/02) | Decide: native (React Native/Flutter) vs extend the PWA; needs a reachable server (VPS/Oracle Cloud) ¦ BLOCKER: No native app project or store accounts; ATIP runs on the Mac only | dashboard/w38_page.py |  | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: YET TO START
269 | 12 | UX redesign (2026-10-26) | UXR-11 | Deployment/Ops | Test + Prod server testing | Run the suite and UAT on Test and Prod | Owner prompt: UI/UX redesign | P1 | BLOCKED | 70 |  | Tested on local Test + Prod-profile instances (QA-01); hosted servers still do not exist | Repeat on Oracle Cloud dev/test once ATIP is deployed there ¦ BLOCKER: ATIP not yet deployed to a Test or Prod server |  | docs/UX_TEST_REPORT_2026-10-26.md | Claude (development) |  | 46321 |  | 2026-10-26 | Testing: IN PROGRESS
270 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-01 | Dashboard | Merge pending UI/UX changes (UXR-01..03) | Review + merge Command Center, kill-switch UI/API, sessions registry; no regressions | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | Uncommitted UXR delta reviewed and merged into master; halt-route date.today() replaced with an IST clock; 4 other dashboard branches reviewed and NOT merged (hosting/stale) | Owner decision on central-auth owner gate + /ATIP base path (hosting) | dashboard/command_page.py; dashboard/command_routes.py; orders/sessions.py | tests/test_ux_merge_regression.py (23); test_ux_command_center.py; HTTP smoke 17/17 Test + Prod | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
271 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-02 | Pipeline | Operating schedule STOPPED 21:00-06:00 IST | All jobs, feeds, polling, trigger monitoring paused; no order placed or triggered | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | pipeline/operating_schedule.py gates the schedule loop + run_job; orders.risk.halted() closes every order path; feed window + order monitor check is_stopped() | Watch the first real 21:00 stop on the Mac (atip.log + /api/status) | pipeline/operating_schedule.py; pipeline/scheduler.py; orders/risk.py; data/dhan_ws.py; dashboard/server.py | tests/test_operating_schedule.py (39) | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
272 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-03 | Dashboard | Read-only dashboard + STOPPED banner | Banner 'ATIP stopped — resumes 06:00 IST' + last-updated; writes refused | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | Banner on /, /command, /m, /global-asia (polls /api/status 60s); writes -> HTTP 423 except override, halt, sign-in |  | dashboard/global_asia.py; pipeline/operating_schedule.py | tests/test_operating_schedule.py; HTTP smoke Test + Prod; browser 375px + desktop | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
273 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-04 | Pipeline | scheduler_status table + /api/status | Status STOPPED/RUNNING/RESUMING and every transition recorded and served | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | scheduler_status, scheduler_override, resume_runs, deferred_jobs; GET /api/status |  | pipeline/operating_schedule.py; dashboard/global_asia.py | tests/test_operating_schedule.py | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
274 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-05 | Pipeline | 06:00 resume sequence (6 steps, logged) | Backfill -> collect -> sentiment -> indexes -> report before 08:30 -> live feeds | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 95 |  | Steps logged as resume_1..6 in pipeline_log + resume_runs.steps_json; real end-to-end run on the Prod-profile snapshot | Confirm on the Mac at a real 06:00 with Dhan + Anthropic keys present | pipeline/operating_schedule.py; pipeline/premarket_report.py | tests/test_operating_schedule.py; real run log (testing report) | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
275 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-06 | Pipeline | Missed-resume catch-up + run lock | Machine off at 06:00 -> resume on startup/wake, never twice | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | tick() at start-up, every 15 s and on wake; resume_runs per IST date + job_lock; crashed run re-run after 2 h |  | pipeline/operating_schedule.py; pipeline/scheduler.py | tests/test_operating_schedule.py (catch-up, lock, duplicate, crash) | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
276 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-07 | Pipeline | Weekends / NSE holidays | 06:00 collection + analysis still run; no intraday live feeds | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | Step 6 SKIPPED on non-trading days; status live_feeds false |  | pipeline/operating_schedule.py | tests/test_operating_schedule.py (weekend, holiday) | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
277 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-08 | Dashboard | Manual start/stop override (logged) | Override from the dashboard, logged | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | POST /api/status/override stop¦start¦auto (token, owner-only); CLI too; scheduler_status + alert_log | Add buttons on /command (API + banner done) | dashboard/global_asia.py; enterprise/authz.py | tests/test_operating_schedule.py | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
278 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-09 | AI/News | Loud alert on keyword-classifier fallback | Claude sentiment; fallback alerts loudly | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | Resume step 3 DEGRADED + critical alert 'NEWS SENTIMENT FALLBACK' |  | pipeline/operating_schedule.py | tests/test_operating_schedule.py | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
279 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-10 | Technical | Null-EMA gap for small/mid-caps | EMA-50/SMA-200 null for short-history symbols | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | IMPLEMENTED BUT NOT VERIFIED | 85 |  | data/ema_gap.py fills missing sessions from the NSE Bhavcopy archive (insert-only), recomputes indicators; resume step 4 | Reaches SMA-200 after ~1 week of 06:00 runs; verify on live DB | data/ema_gap.py | tests/test_ema_gap.py (3); real run on snapshot (testing report) | Claude (development) |  | 2026-10-26 |  | 2026-10-26 | Testing: COMPLETED
280 | 13 | Ops schedule + Asia signals (2026-10-26) | OPS-11 | Docs | Scheduler mechanism decision documented | APScheduler or Windows Task Scheduler — pick one, document why | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | Kept ONE mechanism (in-process schedule loop) — deviation from the two named options, reasons in scheduler.py header + docs | Owner to confirm the decision | pipeline/scheduler.py; docs/OPERATING_SCHEDULE_AND_ASIA_2026-10.md |  | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: N/A
281 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-01 | Data | Asia markets data module (6 indices, primary + fallback) | KOSPI, KOSDAQ, TAIEX, Nikkei 225, TOPIX, KSE-100; verify every source | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 95 |  | data/asia_markets.py; 14 sources probed: 11 OK, 3 FLAGGED (TOPIX Yahoo, KSE-100 PSX DPS HTTP 462, KSE-100 Yahoo); Stooq rejected (JS wall) | TOPIX and KSE-100 have one working source from this network ¦ BLOCKER: TOPIX / KSE-100 fallback sources fail from India | data/asia_markets.py; data/asia_exchanges.json | tests/test_asia_markets.py (46); live verify + run | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
282 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-02 | Data | global_indices_daily + 600-day retention | Daily OHLC + session status, retention policy | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | global_indices_daily, asia_signals, asia_sentiment in LONG (600 d) purge; data-inventory classified |  | data/asia_markets.py; db/purge.py; enterprise/privacy.py | tests/test_asia_markets.py | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
283 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-03 | Data | Exchange hours + holidays from config; 3 Asia runs | No hardcoded hours; 06:00 + mid-morning + post-close | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | IMPLEMENTED BUT NOT VERIFIED | 85 |  | data/asia_exchanges.json (JPX/KRX/TWSE/PSX) + config override; runs 06:00, 10:45, 17:15 IST; calendar self-check | 2026 holiday lists unverified (lunar dates for PSX); confirm against exchange notices | data/asia_exchanges.json | tests/test_asia_markets.py | Claude (development) |  | 2026-10-26 |  | 2026-10-26 | Testing: COMPLETED
284 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-04 | Signals | Per-market BULLISH/NEUTRAL/BEARISH + confidence | Trend, momentum, volatility, gap | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | compute_signal; defect fixed in testing: no dead band made sideways tapes BULLISH | Back-test the thresholds on 1y of history | data/asia_markets.py | tests/test_asia_markets.py | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
285 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-05 | Signals | Asia Sentiment Score -> Market Health + pre-market report | Configurable weights | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | weights in asia_exchanges.json; MH weight_config ('MH','Asia') 0.05; pre-market report + 08:30 brief line | Owner to confirm the 0.05 MH weight | data/asia_markets.py; scores/engine.py; pipeline/premarket_report.py; alerts/telegram.py | tests/test_asia_markets.py | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
286 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-06 | Signals | Pakistan geopolitical / risk-event flag | Separate factor driven by news sentiment | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | pakistan_risk(): NONE/ELEVATED/HIGH from classified news + Google News Pakistan feed; PK_GEO_RISK weight 0.10 |  | data/asia_markets.py; data/news.py | tests/test_asia_markets.py (5 cases) | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
287 | 13 | Ops schedule + Asia signals (2026-10-26) | ASIA-07 | Dashboard | Global & Asia tab | Last value, % change, signal, session status | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | COMPLETED | 100 |  | Tab on /, page /global-asia, screen on /m; informational only |  | dashboard/global_asia.py; dashboard/server.py; dashboard/w38_page.py | tests/test_asia_markets.py; browser desktop + 375px | Claude (development) |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | Testing: COMPLETED
288 | 13 | Ops schedule + Asia signals (2026-10-26) | MOB-01 | Mobile | Android app: merged UI, status banner, Global & Asia | Update Android app | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | IN PROGRESS | 60 |  | New Kotlin shell (mobile/android): tabs Today/Command/Global & Asia + native /api/status banner | Build + install: no Android SDK/Java on the Mac; needs Android Studio ¦ BLOCKER: No Android SDK / JDK installed | mobile/android | not built (no toolchain) | Claude (development) |  | 2026-10-26 |  | 2026-10-26 | Testing: IN PROGRESS
289 | 13 | Ops schedule + Asia signals (2026-10-26) | MOB-02 | Mobile | iOS app: merged UI, status banner, Global & Asia | Update iOS app | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | IN PROGRESS | 60 |  | New SwiftUI shell (mobile/ios, XcodeGen spec): same tabs + native banner; swiftc -parse OK | Build: needs Xcode (only Command Line Tools installed); App Store needs a developer account ¦ BLOCKER: Xcode not installed | mobile/ios | swiftc -parse only | Claude (development) |  | 2026-10-26 |  | 2026-10-26 | Testing: IN PROGRESS
290 | 13 | Ops schedule + Asia signals (2026-10-26) | QA-01 | Testing | Test + Prod server testing + report | Suite + UAT on Test and Prod | Owner prompt 2026-10-26: UI/UX merge, operating schedule, Asia signals | P1 | IN PROGRESS | 80 |  | Run on local Test (ATIP_ENV=test, seeded DB, :8765) and Prod-profile (ATIP_ENV=production, live-DB snapshot, :8766) instances; full suite | Repeat on real hosted servers once they exist (GAP-2610-16) ¦ BLOCKER: No hosted Test/Prod servers exist | docs/TEST_REPORT_2026-10-26_OPS_ASIA.md | full suite + HTTP smoke + browser | Claude (development) |  | 2026-10-26 |  | 2026-10-26 | Testing: IN PROGRESS
291 | 14 | News impact estimate (2026-10-27) | NI-01 | Data Platform | News impact module: fetch + analyse | Module pulls Indian + world feeds itself and analyses them | Owner request 2026-10-27: estimate news impact on the Indian market from Indian + world news | P1 | COMPLETED | 100 | NS-02, GLOBAL_FEEDS | data/news_impact.run(): RSS_FEEDS + GLOBAL_FEEDS through run_news_pipeline (dedup, classify, store), then assess, combine, track | Maintain | data/news_impact.py; data/news.py | tests/test_news_impact.py (43); live run on live-DB copy: 115 headlines fetched (29 India, 86 world) | Claude (development) |  | 2026-10-27 | 2026-10-27 | 2026-10-27 | Additive; informational only
292 | 14 | News impact estimate (2026-10-27) | NI-02 | AI/News | Per-headline impact assessment | Direction, size, horizon, channel, sectors, confidence per headline | Owner request 2026-10-27: estimate news impact on the Indian market from Indian + world news | P1 | IN PROGRESS | 90 | NI-01, NS-03 | Claude (news model + daily cap, purpose news_impact) with JSON schema; keyword-rule fallback reads crude/yield/dollar moves for India, keeps company news off the Nifty; recaps skipped | Owner adds ANTHROPIC_API_KEY; then verify a live Claude run (only stubbed so far) ¦ BLOCKER: ANTHROPIC_API_KEY (owner) | data/news_impact.py | tests/test_news_impact.py (43); live run on live-DB copy: 115 headlines fetched (29 India, 86 world) | Claude (development) |  | 2026-10-27 |  | 2026-10-27 | Additive; informational only
293 | 14 | News impact estimate (2026-10-27) | NI-03 | AI/News | Session estimate: score, bias, sectors, drivers, brief | Combine headlines into one call for the coming NSE session | Owner request 2026-10-27: estimate news impact on the Indian market from Indian + world news | P1 | COMPLETED | 100 | NI-02 | 0-100 score, POSITIVE/NEUTRAL/NEGATIVE + strength, per-sector scores for 11 NSE indices, top 8 drivers, Claude brief (rules fallback); informational only | Maintain | data/news_impact.py | tests/test_news_impact.py (43); live run on live-DB copy: 115 headlines fetched (29 India, 86 world) | Claude (development) |  | 2026-10-27 | 2026-10-27 | 2026-10-27 | Additive; informational only
294 | 14 | News impact estimate (2026-10-27) | NI-04 | AI/News | Tracking check vs Nifty close | Score every call against what the market did; compare with naive baselines | Owner request 2026-10-27: estimate news impact on the Indian market from Indian + world news | P1 | COMPLETED | 100 | NI-03 | news_impact_eval vs index_levels 15:30; pre-open call per session; baselines (commonest outcome, yesterday again); per-sector and per-headline hits; scheduled 07:40/12:20/15:50/20:15 + 06:00 resume, scored 16:20 | Read the track record after 20+ sessions before relying on it | data/news_impact.py; pipeline/scheduler.py; pipeline/operating_schedule.py | tests/test_news_impact.py (43); live run on live-DB copy: 115 headlines fetched (29 India, 86 world) | Claude (development) |  | 2026-10-27 | 2026-10-27 | 2026-10-27 | Additive; informational only
295 | 14 | News impact estimate (2026-10-27) | NI-05 | Dashboard | News impact panel + API | Show the estimate on desktop, phone and apps; pre-market report + morning brief | Owner request 2026-10-27: estimate news impact on the Indian market from Indian + world news | P1 | COMPLETED | 100 | NI-03 | /api/news-impact, /accuracy, /refresh (owner token); panel on / News + Global & Asia tabs, /global-asia, /m (Android/iOS apps load it); pre-market report section; Telegram brief line | Maintain | dashboard/news_impact_view.py; dashboard/global_asia.py; dashboard/server.py; dashboard/w38_page.py; pipeline/premarket_report.py; alerts/telegram.py | tests/test_news_impact.py (43); live run on live-DB copy: 115 headlines fetched (29 India, 86 world) | Claude (development) |  | 2026-10-27 | 2026-10-27 | 2026-10-27 | Additive; informational only