## Summary
ATIP feature tracker -- reconciled 2026-10-07 (W39)
Source | docs/ATIP_MASTER_TRACKER.csv (canonical), the owner's uploaded workbook and CSV, the code and a full automated test run with coverage
Features | 333
Development status | Count
IMPLEMENTED BUT NOT VERIFIED | 197
COMPLETED | 126
BLOCKED | 9
IN PROGRESS | 1
Testing status (automated) | Count
COMPLETED | 215
IN PROGRESS | 105
BLOCKED | 9
N/A | 3
YET TO START | 1
Deployment wave | Features | Developed | Blocked | Testing COMPLETED
1 | 36 | 36 | 0 | 18
2 | 27 | 27 | 0 | 11
3 | 12 | 12 | 0 | 12
4 | 49 | 49 | 0 | 36
5 | 19 | 18 | 1 | 11
6 | 32 | 32 | 0 | 22
7 | 49 | 47 | 2 | 26
8 | 36 | 36 | 0 | 25
9+ (Enterprise SaaS) | 23 | 18 | 5 | 5
11 | 1 | 1 | 0 | 1
12 | 1 | 1 | 0 | 1
13 | 1 | 1 | 0 | 1
14 | 1 | 1 | 0 | 1
15 | 1 | 1 | 0 | 1
15.5 | 15 | 15 | 0 | 15
16 | 1 | 1 | 0 | 1
17 | 1 | 1 | 0 | 1
18 | 1 | 0 | 0 | 1
19 | 1 | 0 | 1 | 0
20 | 1 | 1 | 0 | 1
W39 (PR #4) | 19 | 19 | 0 | 19
W39b (PR #5) | 4 | 4 | 0 | 4
W40 (PR #9) | 2 | 2 | 0 | 2
Phase | Features | Developed | Blocked
0 Delivered baseline (maintain) | 58 | 58 | 0
1 Foundation | 31 | 31 | 0
2 Quant Research (data, factors, backtesting) | 52 | 52 | 0
3 Strategy Engine | 14 | 14 | 0
4 AI/ML | 21 | 20 | 1
5 Risk & Portfolio | 17 | 17 | 0
6 Execution | 11 | 10 | 1
7 Advanced Quant | 19 | 19 | 0
8 Production Hardening | 6 | 6 | 0
8 Production hardening | 8 | 8 | 0
9 Enterprise SaaS (final objective) | 29 | 24 | 5
10 Wealth track (Waves 11-20) | 11 | 9 | 1
11 W39 reconciliation (owner tracker 2026-10-07) | 56 | 55 | 1

## All Features
Seq | Phase | Phase Name | ID | Module | Feature | Target Requirement | Scope Source | Priority | Status | Testing Status | Completion % | Depends On | Current Implementation | Next Action / Missing Work | Key Files | Evidence | Owner | Target Date | Started On | Completed On | Last Updated | Notes | Deployment Wave | Test Evidence | Blocker / Input Required
1 | 0 | Delivered baseline (maintain) | DP-02 | Data Platform | Daily OHLCV history | Clean daily bars for universe | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 90 |  | NSE Bhavcopy + Dhan; coverage/freshness/duplicate guards | Maintain | data/bhavcopy.py; data/dhan.py | prices_daily ~234k rows / 426 sessions |  |  |  |  | 2026-09-24 |  | 2 | 49% of 1091 lines in 2 key file(s) run by: test_corporate_actions, test_fii_dii_and_delivery_factor, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions (+3 more)
2 | 0 | Delivered baseline (maintain) | DP-07 | Data Platform | Delivery data | Delivery qty and % | Code-Derived | P1 | COMPLETED | COMPLETED | 90 |  | Full Bhavcopy nightly + backfill | Maintain | data/bhavcopy.py | 223,854 rows |  |  |  |  | 2026-09-24 |  | 2 | 60% of 346 lines in 1 key file(s) run by: test_corporate_actions, test_fii_dii_and_delivery_factor, test_regressions, test_signal_pipeline
3 | 0 | Delivered baseline (maintain) | DP-20 | Data Platform | Trading calendar | NSE holidays/special sessions | Code-Derived | P0 | COMPLETED | COMPLETED | 90 |  | 2025-26 holidays + budget sessions | Add next year's holidays each December | utils/trading_calendar.py | 7132017 |  |  |  |  | 2026-09-24 |  | 2 | 95% of 41 lines in 1 key file(s) run by: test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_regressions, test_risk_controls (+28 more)
4 | 0 | Delivered baseline (maintain) | TA-01 | Technical Analysis | Core indicators | RSI; MACD; EMA; SMA; ATR; ADX; Bollinger | Agreed-Spec | P0 | COMPLETED | COMPLETED | 90 |  | Computed and stored; MACD fixed and normalised | Maintain | data/technical.py | a7d92a7; bbd0540 |  |  |  |  | 2026-09-24 |  | 3 | 80% of 357 lines in 1 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w40_stock_chart
5 | 0 | Delivered baseline (maintain) | TA-02 | Technical Analysis | Extended oscillators | Stoch; Williams %R; CCI; OBV; relative volume | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | Computed and stored | Maintain | data/technical.py | technical.py:47-54 |  |  |  |  | 2026-09-24 |  | 3 | 80% of 357 lines in 1 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w40_stock_chart
6 | 0 | Delivered baseline (maintain) | TA-05 | Technical Analysis | Fibonacci | Retracement levels | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | 52-week 23.6/38.2/50/61.8 levels; W39: swing-anchored Fibonacci (last two 5-bar pivots in 120 sessions, 38.2 / 50 / 61.8 levels, nearest level and distance) in technical_ext, shown in the stock panel | Independent QA | data/technical.py; data/technical_ext.py | tests/test_w39_technical_rs_fib.py |  |  |  |  | 2026-10-07 |  | 3 | tests/test_w39_technical_rs_fib.py ¦ 86% of 728 lines in 2 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules, test_w40_stock_chart
7 | 0 | Delivered baseline (maintain) | TA-07 | Technical Analysis | Trend features | Crosses; 200DMA; gap % | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | Computed and stored | Maintain | data/technical.py | technical.py:291 |  |  |  |  | 2026-09-24 |  | 3 | 80% of 357 lines in 1 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w40_stock_chart
8 | 0 | Delivered baseline (maintain) | TA-08 | Technical Analysis | Relative strength | RS vs NIFTY | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | 20-day RS with date-matched benchmark; W39 (TA-08b): 63 / 126-session RS vs the stock's sector index (NSE industry -> NIFTYIT / PHARMA / AUTO / FMCG / METAL / REALTY / ENERGY / BANK / PSUBANK, NIFTY50 fallback flagged) and percentile within the industry; display only | Independent QA; IC research before any score use | scores/engine.py; data/technical_ext.py | tests/test_w39_technical_rs_fib.py |  |  |  |  | 2026-10-07 |  | 3 | tests/test_w39_technical_rs_fib.py ¦ 88% of 961 lines in 2 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules
9 | 0 | Delivered baseline (maintain) | SC-03 | Alpha/Factor Engine | RRI | Recovery & Rebound Index per QRH | Agreed-Spec | P0 | COMPLETED | COMPLETED | 75 |  | Implemented | Institutional input improves with SC-14 | scores/engine.py | engine.py:260 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
10 | 0 | Delivered baseline (maintain) | SC-04 | Alpha/Factor Engine | MRI | Momentum Reversal Index per QRH | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Implemented; MACD corrected | Maintain | scores/engine.py | engine.py:241 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
11 | 0 | Delivered baseline (maintain) | SC-07 | Alpha/Factor Engine | ZPI | Zone Probability Index per QRH | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 |  | Implemented + delivery component | Maintain | scores/engine.py | 969f570 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
12 | 0 | Delivered baseline (maintain) | SC-10 | Alpha/Factor Engine | Portfolio Health score | PHS formula | Agreed-Spec | P1 | COMPLETED | IN PROGRESS | 75 |  | Implemented | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py | portfolio_health.py |  |  |  |  | 2026-09-24 |  | 4 | 26% of 130 lines in 1 key file(s) run by: test_risk_controls, test_w39_exec_data_tests, test_w39_notify_transactions, test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke, test_wealth_api_security, test_wealth_dna_holdings (+1 more)
13 | 0 | Delivered baseline (maintain) | PF-05 | Portfolio | Portfolio health | Portfolio Health score + panel | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 75 |  | Implemented + dashboard | Maintain | scores/portfolio_health.py | portfolio_health.py |  |  |  |  | 2026-09-24 |  | 8 | 26% of 130 lines in 1 key file(s) run by: test_risk_controls, test_w39_exec_data_tests, test_w39_notify_transactions, test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke, test_wealth_api_security, test_wealth_dna_holdings (+1 more)
14 | 0 | Delivered baseline (maintain) | SC-11 | Alpha/Factor Engine | Trade of the Day | TOD formula | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | Implemented; one TOD per session | Maintain | scores/engine.py | d74e595 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
15 | 0 | Delivered baseline (maintain) | SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | Master ranking | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 |  | Implemented; rank stored | Maintain | scores/engine.py | engine.py:508 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
16 | 0 | Delivered baseline (maintain) | SC-17 | Alpha/Factor Engine | Configurable weights | Weights in configuration | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | weight_config table | Regime-specific rows used by ML-05 | db/schema.py | seed_weights |  |  |  |  | 2026-09-24 |  | 4 | 86% of 346 lines in 1 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
17 | 0 | Delivered baseline (maintain) | SG-02 | Signal Engine | Signal validation | Data gates before signals | Code-Derived | P0 | COMPLETED | IN PROGRESS | 75 |  | EOD coverage guard; FII/DII hold | Maintain | pipeline/scheduler.py | a4a508b; 969f570 |  |  |  |  | 2026-09-24 |  | 5 | 35% of 1229 lines in 1 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_notify_transactions, test_w39_qa_suite, test_w39_ui_smoke (+2 more)
18 | 0 | Delivered baseline (maintain) | SG-03 | Signal Engine | Signal ranking | Top-25 lists | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Implemented | Maintain | scores/engine.py | dashboard lists |  |  |  |  | 2026-09-24 |  | 5 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
19 | 0 | Delivered baseline (maintain) | SG-05 | Signal Engine | Trade plan | Entry/stop/targets/R:R/horizon | Agreed-Spec | P0 | COMPLETED | COMPLETED | 75 |  | Implemented | Maintain | scores/predictions.py | predictions.py |  |  |  |  | 2026-09-24 |  | 5 | 67% of 95 lines in 1 key file(s) run by: test_w39_qa_suite, test_w39_untested_modules
20 | 0 | Delivered baseline (maintain) | SG-06 | Signal Engine | Outcome tracking | Hit rate and P&L per signal | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 |  | Implemented; corrected denominator | Maintain | scores/signal_log.py | cc8ce46 |  |  |  |  | 2026-09-24 |  | 5 | 64% of 301 lines in 1 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_w39_exec_data_tests, test_w39_notify_transactions, test_w39_perf_budget, test_w39_performance_detail (+6 more)
21 | 0 | Delivered baseline (maintain) | SG-07 | Signal Engine | Signal provenance log | Immutable signal log | Code-Derived | P1 | COMPLETED | COMPLETED | 80 |  | Append-only signal_log | Maintain | scores/signal_log.py | signal_log.py |  |  |  |  | 2026-09-24 |  | 5 | 64% of 301 lines in 1 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_w39_exec_data_tests, test_w39_notify_transactions, test_w39_perf_budget, test_w39_performance_detail (+6 more)
22 | 0 | Delivered baseline (maintain) | BT-01 | Backtesting | Historical backtest | Bar-level backtest | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 80 |  | 3 bar engines | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py | — |  |  |  |  | 2026-09-24 |  | 6 | 15% of 192 lines in 1 key file(s) run by: test_regressions
23 | 0 | Delivered baseline (maintain) | BT-10 | Backtesting | Win rate / profit factor / expectancy | Trade metrics | Agreed-Spec | P0 | COMPLETED | COMPLETED | 90 |  | Implemented | Maintain | strategy/backtest_aggressive.py | metrics() |  |  |  |  | 2026-09-24 |  | 6 | 87% of 162 lines in 1 key file(s) run by: test_aggressive_backtest
24 | 0 | Delivered baseline (maintain) | RK-02 | Risk Management | Max order value | Pre-trade limit | Quant-Research | P0 | COMPLETED | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24 |  | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
25 | 0 | Delivered baseline (maintain) | RK-03 | Risk Management | Max orders per day | Pre-trade limit | Quant-Research | P0 | COMPLETED | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24 |  | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
26 | 0 | Delivered baseline (maintain) | RK-04 | Risk Management | Max open positions | Position limit | Quant-Research | P0 | COMPLETED | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24 |  | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
27 | 0 | Delivered baseline (maintain) | RK-05 | Risk Management | Symbol exposure limit | Concentration limit | Quant-Research | P0 | COMPLETED | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24 |  | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
28 | 0 | Delivered baseline (maintain) | RK-14 | Risk Management | Crash-risk gating | CRI gate | Agreed-Spec | P0 | COMPLETED | COMPLETED | 75 |  | SELL_CRI_DANGER + strategy use | Maintain | scores/engine.py | — |  |  |  |  | 2026-09-24 |  | 7 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
29 | 0 | Delivered baseline (maintain) | EX-03 | Execution | Position management | Persistent idempotent positions | Code-Derived | P0 | COMPLETED | COMPLETED | 75 |  | reserve -> place -> apply | Maintain | strategy/positions.py | — |  |  |  |  | 2026-09-24 |  | 7 | 93% of 193 lines in 1 key file(s) run by: test_aggressive_lifecycle, test_strategy_live
30 | 0 | Delivered baseline (maintain) | EX-04 | Execution | Entry/exit | Automated entry and exit | Agreed-Spec | P0 | COMPLETED | COMPLETED | 70 |  | strategy/live.py | Maintain | strategy/live.py | — |  |  |  |  | 2026-09-24 |  | 7 | 70% of 195 lines in 1 key file(s) run by: test_strategy_live
31 | 0 | Delivered baseline (maintain) | EX-05 | Execution | Stop loss | Hard/ATR stops | Agreed-Spec | P0 | COMPLETED | COMPLETED | 75 |  | Implemented | Maintain | strategy/aggressive.py | — |  |  |  |  | 2026-09-24 |  | 7 | 92% of 156 lines in 1 key file(s) run by: test_aggressive_backtest, test_aggressive_decisions, test_aggressive_lifecycle, test_strategy_live
32 | 0 | Delivered baseline (maintain) | EX-06 | Execution | Trailing stop | ATR trailing stop | Quant-Research | P0 | COMPLETED | COMPLETED | 80 |  | Implemented (4.0x ATR) | Maintain | strategy/aggressive.py | aggressive.py:57-66 |  |  |  |  | 2026-09-24 |  | 7 | 92% of 156 lines in 1 key file(s) run by: test_aggressive_backtest, test_aggressive_decisions, test_aggressive_lifecycle, test_strategy_live
33 | 0 | Delivered baseline (maintain) | EX-07 | Execution | Profit booking / partial exit | Checkpoints and partial exits | Agreed-Spec | P1 | COMPLETED | COMPLETED | 70 |  | Implemented in aggressive strategy | Maintain | strategy/aggressive.py | — |  |  |  |  | 2026-09-24 |  | 7 | 92% of 156 lines in 1 key file(s) run by: test_aggressive_backtest, test_aggressive_decisions, test_aggressive_lifecycle, test_strategy_live
34 | 0 | Delivered baseline (maintain) | EX-13 | Execution | Paper trading | Virtual trading (FR-PT) | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Paper broker with slippage | Maintain | orders/paper.py | tests/test_paper_broker.py |  |  |  |  | 2026-09-24 |  | 7 | tests/test_paper_broker.py ¦ 55% of 321 lines in 1 key file(s) run by: test_paper_broker, test_risk_controls, test_strategy_live, test_w37_brokers_multi_asset, test_w39_exec_data_tests, test_w39_performance_detail, test_w39_qa_suite, test_w40_futures_backtest (+4 more)
35 | 0 | Delivered baseline (maintain) | EX-14 | Execution | Live gating | PAPER default; explicit confirm | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 85 |  | Implemented | Maintain | orders/environment.py | environment.py:37-57 |  |  |  |  | 2026-09-24 |  | 7 | 53% of 64 lines in 1 key file(s) run by: test_paper_broker, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget, test_w39_qa_suite (+3 more)
36 | 0 | Delivered baseline (maintain) | BR-01 | Broker Integration | Dhan | Data + orders | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 80 |  | dhanhq integration | Maintain | data/dhan.py; orders/broker.py | — |  |  |  |  | 2026-09-24 |  | 7 | 48% of 909 lines in 2 key file(s) run by: test_auto_recover, test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions (+4 more)
37 | 0 | Delivered baseline (maintain) | BR-03 | Broker Integration | Broker abstraction | Routed execution clients | Quant-Research | P0 | COMPLETED | IN PROGRESS | 75 |  | PAPER/SANDBOX/LIVE routing | Becomes multi-broker interface in ENT-15 | orders/environment.py | — |  |  |  |  | 2026-09-24 |  | 7 | 53% of 64 lines in 1 key file(s) run by: test_paper_broker, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget, test_w39_qa_suite (+3 more)
38 | 0 | Delivered baseline (maintain) | DB-01 | Dashboard | Market Health panel | Dashboard section | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
39 | 0 | Delivered baseline (maintain) | DB-02 | Dashboard | Global Markets panel | Dashboard section | Agreed-Spec | P1 | COMPLETED | COMPLETED | 75 |  | Rendered; snapshot bug fixed | Maintain | dashboard/server.py | db7f506 |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
40 | 0 | Delivered baseline (maintain) | DB-03 | Dashboard | FII/DII panel | Dashboard section | Agreed-Spec | P1 | COMPLETED | COMPLETED | 75 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
41 | 0 | Delivered baseline (maintain) | DB-05 | Dashboard | Sector Rotation | Dashboard section | Agreed-Spec | P1 | COMPLETED | COMPLETED | 70 |  | Heatmap rendered | Maintain | dashboard/server.py | server.py:489 |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
42 | 0 | Delivered baseline (maintain) | DB-07 | Dashboard | Top 25 VPI | Dashboard section | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | /api/scores |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
43 | 0 | Delivered baseline (maintain) | DB-08 | Dashboard | Buy Zone (ZPI) | Dashboard section | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
44 | 0 | Delivered baseline (maintain) | DB-09 | Dashboard | Recovery (RRI) | Dashboard section | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
45 | 0 | Delivered baseline (maintain) | DB-10 | Dashboard | Momentum Reversal (MRI) | Dashboard section | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
46 | 0 | Delivered baseline (maintain) | DB-12 | Dashboard | Portfolio Health panel | Dashboard section | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | /api/portfolio |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
47 | 0 | Delivered baseline (maintain) | DB-13 | Dashboard | Trade of the Day | Dashboard section | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | /api/tod |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
48 | 0 | Delivered baseline (maintain) | DB-15 | Dashboard | Orders/signals panel | Orders tab | Code-Derived | P1 | COMPLETED | COMPLETED | 70 |  | Rendered with PAPER status | Maintain | dashboard/server.py | /api/orders |  |  |  |  | 2026-09-24 |  | 8 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
49 | 0 | Delivered baseline (maintain) | DB-19 | Dashboard | Hosted read-only snapshot | bkesari viewer | Code-Derived | P1 | COMPLETED | COMPLETED | 80 |  | publish_snapshot.py | Superseded by ENT-08 web app | publish_snapshot.py | — |  |  |  |  | 2026-09-24 |  | 8 | 96% of 51 lines in 1 key file(s) run by: test_w39_exec_data_tests
50 | 0 | Delivered baseline (maintain) | API-01 | APIs | Internal REST | Dashboard API | Agreed-Spec | P1 | COMPLETED | COMPLETED | 70 |  | 15 FastAPI routes | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24 |  | 1 | 64% of 812 lines in 1 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+36 more)
51 | 0 | Delivered baseline (maintain) | API-02 | APIs | Local API authentication | Auth on mutating routes | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 |  | 127.0.0.1 bind + X-ATIP-Token | Replaced by per-user auth in SEC-02 | dashboard/security.py | 7191c71 |  |  |  |  | 2026-09-24 |  | 1 | 93% of 43 lines in 1 key file(s) run by: test_auto_recover, test_risk_controls, test_w38_platform_compliance, test_w39_backtest, test_w39_depth20, test_w39_event_calendar, test_w39_exec_data_tests, test_w39_global_sync (+30 more)
52 | 0 | Delivered baseline (maintain) | DBS-01 | Database | Schema | Operational schema | Agreed-Spec | P1 | COMPLETED | COMPLETED | 75 |  | 19 SQLite tables | Migrations via DBS-04 | db/schema.py | — |  |  |  |  | 2026-09-24 |  | 1 | 86% of 346 lines in 1 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
53 | 0 | Delivered baseline (maintain) | DBS-02 | Database | Retention/purge | Data retention | Code-Derived | P2 | COMPLETED | COMPLETED | 70 |  | db/purge.py | Maintain | db/purge.py | — |  |  |  |  | 2026-09-24 |  | 1 | 71% of 79 lines in 1 key file(s) run by: test_w39_history, test_w39_ops_tests
54 | 0 | Delivered baseline (maintain) | SEC-01 | Security | Credential handling | Secrets outside code | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 85 |  | Secrets abstraction (env > .env > atip_data/secrets > legacy config), presence/format validation, name-only access log, rotation dates, masking in logs | Move legacy plaintext keys out of config.json (owner action) | ops/secrets.py; ops/logs.py | — | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 36% of 202 lines in 2 key file(s) run by: test_regressions, test_risk_controls, test_w37_brokers_multi_asset, test_w38_platform_compliance, test_w39_exec_data_tests, test_w39_ops_tests, test_w39_perf_budget, test_w39_ui_smoke (+1 more)
55 | 0 | Delivered baseline (maintain) | MON-07 | Monitoring | Feed health | WebSocket stall detection | Code-Derived | P1 | COMPLETED | COMPLETED | 70 |  | Implemented | Maintain | data/dhan_ws.py | b303d7a |  |  |  |  | 2026-09-24 |  | 1 | 76% of 234 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_index_feed, test_regressions, test_w39_notify_transactions
56 | 0 | Delivered baseline (maintain) | MON-08 | Monitoring | Diagnostics | Diagnostic tool | Code-Derived | P2 | COMPLETED | COMPLETED | 80 |  | /health, /health/live¦ready¦database¦broker¦data¦scheduler¦ml (LIVE/READY/DEGRADED/FAILED); python -m ops status | Validate | ops/health.py; dashboard/ops_routes.py | — | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 68% of 360 lines in 2 key file(s) run by: test_auto_recover, test_w39_ops_tests, test_w39_perf_budget, test_w39b_razorpay
57 | 0 | Delivered baseline (maintain) | OPS-01 | Deployment/Ops | Autostart/scheduling | Windows autostart | Code-Derived | P1 | COMPLETED | N/A | 75 |  | Task Scheduler + VBS | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml | — |  |  |  |  | 2026-09-24 |  | 1 | no code file listed
58 | 0 | Delivered baseline (maintain) | OPS-07 | Deployment/Ops | Snapshot publishing | Hosted read-only view | Code-Derived | P2 | COMPLETED | COMPLETED | 80 |  | Implemented | Maintain | publish_snapshot.py | — |  |  |  |  | 2026-09-24 |  | 1 | 96% of 51 lines in 1 key file(s) run by: test_w39_exec_data_tests
59 | 1 | Foundation | DP-09 | Data Platform | India VIX | Real VIX series as MH/MSI/CRI input | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 95 |  | Daily INDIAVIX series in prices_daily (421 sessions 2025-01-13..; Dhan history + NSE close nightly); get_vix() = session feed then daily series; no 15.0 default | None for DP-09; VIX term structure/percentile features belong to later factor work | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py | get_vix() returns a value for 411/411 sessions; 17/17 scored sessions unchanged; 4 new tests; 376 tests pass |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | Also fixed: history sync stored every index_key as NIFTY50. Backup atip.db.bak-before-vix-series-20260924-0828 | 2 | 46% of 3170 lines in 5 key file(s) run by: test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_job_monitoring, test_market_health, test_regressions, test_risk_controls, test_signal_pipeline (+9 more)
60 | 1 | Foundation | DP-17 | Data Platform | Market breadth | Advance/decline; new highs/lows | Agreed-Spec | P0 | COMPLETED | COMPLETED | 90 | DP-02 | breadth_series(): advances/declines; % advancing; A/D ratio; % above 200-DMA; 52-week new highs/lows over tracked universe; 80% coverage gate; stored in market_health | Survivorship-free universe (BT-15); sector-level breadth (DP-13) | scores/engine.py; db/schema.py | % above 200-DMA from 2025-11-17; highs/lows from 2026-01-16; 2025-04-07 crash reads 14 adv / 461 dec |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | Replaced adv_decline (NULL in every row) that scored Breadth and AdvanceDecline as a constant 25.93 | 2 | 85% of 936 lines in 2 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
61 | 1 | Foundation | SC-09 | Alpha/Factor Engine | Market Health score | MH formula + regime label | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 90 | DP-09; DP-17 | Every MH input is real or left out (index_levels then daily index series; session-own FII/DII; global <=4 days; VIX; breadth); coverage + inputs stored; no score below 50% coverage; upsert keeps portfolio_health; 393 past sessions backfilled | FII/DII and global history only from 2026-07 (backfilled coverage avg 0.65); determine_signal still defaults a missing MH to 50; model-based regime is ML-05 | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py | market_health 411 sessions (394 backfilled); 17 live rows untouched; re-score would move 2 of 17 regimes NEUTRAL->BULL |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | New daily series NIFTYBANK/NIFTYMIDCAP150/NIFTYSMLCAP250 (421 sessions each; match feed on 17/17). Backup atip.db.bak-before-breadth-mh-20260924-0852 | 4 | 46% of 3170 lines in 5 key file(s) run by: test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_job_monitoring, test_market_health, test_regressions, test_risk_controls, test_signal_pipeline (+9 more)
62 | 1 | Foundation | SC-08 | Alpha/Factor Engine | ACS | AI Confidence Score | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | SC-09 | HistoricalAccuracy = 90-day 5-session hit rate from outcomes known by the scored day (min 5); NewsConfidence only from AI-classified news with no look-ahead; missing inputs left out (no 50/60 stand-ins) | NewsConfidence stays absent until NS-02 (Anthropic key) classifies news | scores/engine.py; data/news.py; db/schema.py | 09-23 re-score on a copy: signals unchanged; ACS mean 56.36->57.50; ACS>=60 169->191 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | news_articles.classifier added; 1,249 existing rows marked rule | 4 | 72% of 1105 lines in 3 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
63 | 1 | Foundation | MON-01 | Monitoring | Job logging | Accurate pipeline_log | Code-Derived | P0 | COMPLETED | IN PROGRESS | 90 |  | run_job records every run (start/end/duration/rows/status/error); returned FAILED is a failure; EMPTY status | Record failures, end time, row counts | pipeline/scheduler.py; db/schema.py | Phase status Tier 2 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 1 | 46% of 1575 lines in 2 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
64 | 1 | Foundation | MON-02 | Monitoring | Stalled-job detection | Heartbeat per job | Code-Derived | P0 | COMPLETED | IN PROGRESS | 85 | MON-01 | pipeline/health.py expectations: MISSED/STALLED/FAILING/EMPTY; every 30 min | Expected-run table + missed-run check | pipeline/health.py; pipeline/scheduler.py | news job silent 11 days |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 1 | 39% of 1345 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_risk_controls, test_signal_pipeline, test_w38_platform_compliance, test_w39_api_contract, test_w39_exec_data_tests (+8 more)
65 | 1 | Foundation | MON-03 | Monitoring | Failure alerting | Alerts on failure | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | MON-02 | alert_log + dashboard panel + Telegram when configured; daily de-dup; token scrubbed | Configure Telegram; alert on failure/stall | alerts/telegram.py; dashboard/server.py | run_job |  |  | 2026-09-24 | 2026-09-24 | 2026-10-07 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) ¦ W39 audit of every notify path: an alert sent while the caller held an uncommitted write stalled 60 s and was lost -- fixed in SIP run_due, the wealth investor cycle, the Dhan live-quote refresh and portfolio sync; log_job and the Dhan tick / index flushes now close on failure (tests/test_w39_notify_transactions.py) | 1 | 63% of 1074 lines in 2 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_signal_pipeline, test_w39_api_contract, test_w39_backtest (+38 more)
66 | 1 | Foundation | DB-14 | Dashboard | Alerts / morning brief | Telegram + 08:30 digest | Agreed-Spec | P1 | COMPLETED | IN PROGRESS | 80 | MON-03 | Brief recorded for the dashboard + Telegram; pipeline-health section (outside W1, same tree) | Deliver digest; verify daily | alerts/telegram.py | scheduler.py:1032 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 8 | 59% of 262 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_signal_pipeline, test_w39_exec_data_tests, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget (+3 more)
67 | 1 | Foundation | RK-15 | Risk Management | Risk alerts | Alerts on risk events | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 | MON-03 | Alerts on halt/resume and on halted or limit-refused orders (outside W1, same tree) | Alert on halt, limit breach, CRI spike | orders/risk.py; orders/broker.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 7 | 66% of 502 lines in 2 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
68 | 1 | Foundation | MON-06 | Monitoring | Log rotation | Rotating logs | Code-Derived | P1 | COMPLETED | IN PROGRESS | 90 |  | SafeRotatingFileHandler 20 MB x 10, survives refused rename (outside W1, same tree) | RotatingFileHandler | main.py | Phase status Tier 2 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 1 | 6% of 260 lines in 1 key file(s) run by: test_w39_qa_suite
69 | 1 | Foundation | DBS-06 | Database | Timestamp consistency | One timezone convention | Code-Derived | P1 | COMPLETED | IN PROGRESS | 85 |  | Convention documented (IST; created_at UTC); news UTC->IST; status query fixed; repair tool | Normalise; fix news recency | db/schema.py; data/news.py; tools/repair_news_timezone.py | Phase status Tier 2 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 1 | 57% of 515 lines in 3 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
70 | 1 | Foundation | NS-01 | News/Sentiment | News ingestion | Reliable daily news feed | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 80 | MON-02 | News first + morning catch-up; de-dup; per-feed status; 4 more RSS feeds | Fix job; add second source; health check | data/news.py; pipeline/scheduler.py | Phase status Tier 2 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 2 | 31% of 1398 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_notify_transactions, test_w39_qa_suite, test_w39_ui_smoke (+2 more)
71 | 1 | Foundation | OPS-03 | Deployment/Ops | Install/setup | Reproducible install | Code-Derived | P1 | COMPLETED | YET TO START | 85 |  | ta not pandas-ta everywhere; requirements-dev.txt; CI httpx; config template; docs/DEV_SETUP.md | Fix requirements/setup; pin versions | setup.py; install.bat; requirements-dev.txt; docs/DEV_SETUP.md | Phase status Tier 3 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 1 | 0% of 2 lines in 1 key file(s) run by: no test
72 | 1 | Foundation | EX-01 | Execution | Order management tests | Tested order rule engine | Agreed-Spec | P0 | COMPLETED | COMPLETED | 70 |  | orders/rules.py (944 lines) without tests | Independent QA | orders/rules.py | tests/test_w39_qa_suite.py |  |  |  |  | 2026-10-07 | W39: tests/test_w39_qa_suite.py -- validation, triggers, OCO / bracket lifecycle, trailing stops through the paper broker; fix: bracket legs now anchor on the real fill price | 7 | tests/test_w39_qa_suite.py ¦ 73% of 469 lines in 1 key file(s) run by: test_auto_recover, test_risk_controls, test_w39_exec_data_tests, test_w39_perf_budget, test_w39_performance_detail, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke
73 | 1 | Foundation | OPS-02 | Deployment/Ops | CI + end-to-end test | Data->score->signal->order->P&L test | Code-Derived | P0 | COMPLETED | COMPLETED | 70 | EX-01 | GitHub Actions; ~270 test functions; no E2E | Independent QA; network download steps are exercised only live | pipeline/scheduler.py; .github/workflows/tests.yml | test_postmarket_scores_a_seeded_session_end_to_end; test_postmarket_refuses_a_session_that_is_a_copy_of_the_previous_one |  |  |  |  | 2026-10-07 | W39: end-to-end test of run_postmarket on 260 seeded sessions (offline steps run for real) in tests/test_w39_qa_suite.py | 1 | test_postmarket_scores_a_seeded_session_end_to_end; test_postmarket_refuses_a_session_that_is_a_copy_of_the_previous_one ¦ 35% of 1229 lines in 1 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_notify_transactions, test_w39_qa_suite, test_w39_ui_smoke (+2 more)
74 | 1 | Foundation | DP-15 | Data Platform | Fundamentals | ROE; ROCE; EPS; PEG; FCF; D/E | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W27: NSE integrated-filing XBRL (owner decision: NSE, not Screener) -> fundamental_filing (per-filing facts, point in time) -> fundamental_data per quarter: revenue/profit/EPS, YoY/QoQ, margins, TTM EPS, ROE/ROCE/ROA, D/E, current ratio, coverage, FY FCF, book value, shares; bank taxonomy handled; incremental; weekly over the tracked universe | First full backfill (python -m data.nse_filings, ~1 h); --history for pre-2025 quarters; QA | data/nse_filings.py; data/nse_api.py; data/fundamentals.py; pipeline/scheduler.py | Scratch-DB run: INFY FY27Q1 rev 48,211 Cr, EPS TTM 74.13, ROE 32.6%; HDFCBANK/SBIN bank path ROE 13.6%/14.0% | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 2 | 30% of 1683 lines in 4 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_fundamentals_screener, test_job_monitoring, test_signal_pipeline, test_w38_platform_compliance, test_w39_history, test_w39_notify_transactions (+4 more)
75 | 1 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | FS formula per concept document | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-15 | W27 scores/fundamental.compute_fs: Valuation(P/E inv), P/B inv, operating margin, profit QoQ, interest coverage, current ratio; valued at the session close; None below 3 inputs (no 50.0 default); FS weight set seeded | Enable fundamentals.score_enabled after QA; IC study once history exists | scores/fundamental.py; scores/engine.py | Scratch rescore 2026-10-01 with flag on: INFY FS 70.6, TCS 70.0 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 78% of 692 lines in 2 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_mcp, test_w39_qa_suite, test_w39_research
76 | 1 | Foundation | SC-02 | Alpha/Factor Engine | SPI | Stability Profit Index per QRH | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | SC-13 | W27 SPI (Stability Profit Index) on the seeded SPI weights: ROE, ROCE, EPS YoY, revenue YoY, FCF conversion, D/E inv, PEG inv, Quality (profitable-quarter share + margin stability); separate from FS -- double weighting removed | Enable after QA; measure SPI/FS correlation (QR-03) | scores/fundamental.py; scores/engine.py | Scratch rescore: INFY SPI 84.0, TCS 73.4, TATASTEEL 53.0 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 78% of 692 lines in 2 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_mcp, test_w39_qa_suite, test_w39_research
77 | 1 | Foundation | SC-05 | Alpha/Factor Engine | CRI debt input | CRI per QRH incl. Debt | Agreed-Spec | P1 | COMPLETED | COMPLETED | 75 | DP-15 | Implemented; Debt input missing | Feed Debt/Equity | scores/engine.py | engine.py:276 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
78 | 1 | Foundation | SC-01 | Alpha/Factor Engine | VPI inputs | VPI per QRH | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 | DP-15 | Implemented; FG/IS inputs weak | Real Fundamental Growth input | scores/engine.py | engine.py:222 |  |  |  |  | 2026-09-24 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
79 | 1 | Foundation | PF-01 | Portfolio | Portfolio ingestion | Zerodha/Dhan holdings sync | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 80 |  | portfolio_sync records each attempt and reason (DH-901 named); qty/avg update; sold removed | Scheduled reliable sync + token handling | data/dhan.py; portfolio/zerodha.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 8 | 40% of 881 lines in 2 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions, test_w39_risk_gateway (+2 more)
80 | 1 | Foundation | BR-04 | Broker Integration | Portfolio sync schedule | Real-time/daily sync (FR-BI-002) | Agreed-Spec | P0 | COMPLETED | IN PROGRESS | 80 | PF-01 | Morning catch-up re-sync; Zerodha SKIPPED when not connected; health expects SUCCESS | Scheduled sync with alert on failure | pipeline/scheduler.py; pipeline/health.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 7 | 39% of 1345 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_risk_controls, test_signal_pipeline, test_w38_platform_compliance, test_w39_api_contract, test_w39_exec_data_tests (+8 more)
81 | 1 | Foundation | PF-02 | Portfolio | Holdings & P&L | Holdings and P&L | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 | PF-01 | portfolio/pnl.py PAPER + LIVE books marked to market; /api/pnl | Realised + unrealised P&L | portfolio/pnl.py; dashboard/server.py | zerodha.py:64 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 8 | 62% of 946 lines in 2 key file(s) run by: test_auto_recover, test_index_feed, test_job_monitoring, test_regressions, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20 (+40 more)
82 | 1 | Foundation | PF-13 | Portfolio | Daily P&L series | Stored daily P&L (paper + live) | Code-Derived | P0 | COMPLETED | COMPLETED | 85 | PF-02 | pnl_daily equity/day P&L/peak/drawdown per env; post-market daily_pnl job | Daily P&L table; EOD job | portfolio/pnl.py; db/schema.py | orders/risk.py docstring |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 8 | 76% of 480 lines in 2 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
83 | 1 | Foundation | RK-13 | Risk Management | Risk-based sizing wired to orders | FR-RM-001 position size | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | size_position() pure + size_for_account(); quantity_type RISK in order rules | Use size in order path | orders/risk.py; orders/rules.py | predictions.py:84 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 7 | 70% of 807 lines in 2 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_exec_data_tests (+13 more)
84 | 1 | Foundation | RK-07 | Risk Management | Daily loss limit | Circuit breaker | Quant-Research | P0 | COMPLETED | COMPLETED | 85 | PF-13 | max_daily_loss_value blocks BUYs; unmeasurable blocks | Limit on PF-13; auto-halt | orders/risk.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
85 | 1 | Foundation | RK-08 | Risk Management | Drawdown limit | Drawdown halt | Quant-Research | P0 | COMPLETED | COMPLETED | 85 | PF-13 | max_drawdown_pct blocks BUYs; unmeasurable blocks | Peak-to-trough on PF-13; auto-halt | orders/risk.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
86 | 1 | Foundation | DBS-03 | Database | Backups | Automated backups | Agreed-Spec | P1 | COMPLETED | COMPLETED | 85 |  | ops/backup.py: daily online SQLite backup (19:15) VERIFIED by integrity_check + key-table counts + sha256 (ops_backup); 7 daily + 4 weekly retention of its own files only; restore to a NEW file; python -m ops backup/restore/verify | Off-machine copy of backups; restore drill | ops/backup.py; docs/BACKUP_RESTORE.md | atip_data/*.bak | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 92% of 306 lines in 1 key file(s) run by: test_w39_ops_tests, test_w39_qa_suite
87 | 1 | Foundation | DP-06 | Data Platform | Corporate actions open items | Split/bonus/demerger adjustment | Code-Derived | P2 | COMPLETED | COMPLETED | 85 |  | NSE CA calendar; reconciliation; volume re-base | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py | 4416ac7 |  |  |  |  | 2026-09-24 |  | 2 | 70% of 229 lines in 1 key file(s) run by: test_corporate_actions, test_w39_history, test_w39_performance_detail, test_w39_research, test_w39b_merge, test_wealth_performance
88 | 1 | Foundation | TA-06 | Technical Analysis | Support/Resistance | S/R levels (ZPI/RRI inputs) | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W21: fractal pivots over 120 sessions, mean-anchored clusters, nearest confirmed support/resistance with touches and distance | QA; optionally feed the Technical Score SR component | data/technical_ext.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 92% of 371 lines in 1 key file(s) run by: test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules
89 | 1 | Foundation | DP-19 | Data Platform | Data quality layer | Validation + DataQualityScore | Quant-Research | P1 | COMPLETED | IN PROGRESS | 85 | MON-01 | data/quality.py 12 checks + DQS per session; data_quality table; post-market; alert | DQS table; outlier and timestamp checks | data/quality.py; pipeline/scheduler.py | ba31981; 8526a9b |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W1 developed 2026-09-24 — not yet independently validated (docs/W1_FOUNDATION_HANDOFF.md) | 2 | 40% of 1352 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_notify_transactions, test_w39_qa_suite, test_w39_ui_smoke (+2 more)
90 | 2 | Quant Research (data, factors, backtesting) | DBS-04 | Database | Schema migrations | Versioned migrations | Code-Derived | P0 | COMPLETED | COMPLETED | 80 |  | schema_migrations (version, checksum, applied_at, duration, status, rollback note); 0001 baseline, 0002 W8 tables, 0003 indexes, 0004 append-only audit triggers; drift detection; additive layer now runs once per process (W7-R8) | Down-migration scripts beyond rollback notes (policy: restore pre-release backup) | ops/migrations.py; db/schema.py | — | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 83% of 459 lines in 2 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
91 | 2 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | Live quotes + index feed (FR-MD-001) | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 |  | W27 data/stock_feed.py: supervised Dhan Quote WebSocket for up to 100 symbols (holdings, positions, order rules, top-25), REST failover when parked/dead/silent, live_feed_status; off by default (live_feed.stocks_enabled) | Enable and observe one live session (cannot be exercised outside market hours) | data/stock_feed.py; main.py | Compiles; not run against a live session | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 2 | 27% of 526 lines in 2 key file(s) run by: test_w39_qa_suite, test_w39_untested_modules
92 | 2 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | Stored 1/5/15-min bars | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | DBS-04 | W21: intraday_bars stores the 30-min job's 15-min bars (was discarded); 90-day retention | QA; consider 5-min bars for session VWAP | data/dhan.py; db/schema.py; db/purge.py | branch w21-data-technical; docs/W21_DATA_TECHNICAL_HANDOFF.md |  |  | 2026-09-27 |  | 2026-09-27 |  | 2 | 58% of 1170 lines in 3 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
93 | 2 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | VWAP (TS weight 0.08) | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-03 | W21: vwap_20d, vwap_session (intraday bars), vwap_dev_pct in technical_ext; strategy feature vwap_dev_pct | Owner: technical.vwap_in_score (changes scores); QA | data/technical_ext.py; data/technical.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 86% of 728 lines in 2 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules, test_w40_stock_chart
94 | 2 | Quant Research (data, factors, backtesting) | SC-12 | Alpha/Factor Engine | Technical Score VWAP input | TS formula complete | Agreed-Spec | P1 | COMPLETED | COMPLETED | 75 | TA-03 | Implemented; VWAP weight dead | Include VWAP | data/technical.py | technical.py:307 |  |  |  |  | 2026-09-24 |  | 4 | 80% of 357 lines in 1 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w40_stock_chart
95 | 2 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | Volume by price; POC | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-03 | W21: volume profile POC/VAH/VAL over 20 sessions (intraday or daily basis) | QA | data/technical_ext.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 92% of 371 lines in 1 key file(s) run by: test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules
96 | 2 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | Daily/weekly/intraday confluence | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-03 | W21: weekly RSI/trend, monthly trend, mtf_alignment -3..+3 | QA | data/technical_ext.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 92% of 371 lines in 1 key file(s) run by: test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules
97 | 2 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | Indicators for every history date | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 70 |  | W21: python -m data.technical --backfill N (tracked universe, resumable) | Run the backfill (owner timing; copy first) | data/technical.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 80% of 357 lines in 1 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w40_stock_chart
98 | 2 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | (date, symbol, factor, value) | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | TA-12 | W22: score_components stores every ATIP index's sub-components per symbol/date (weighted_score label capture; scores unchanged) | QA | scores/engine.py; scores/formulas.py | branch w22-factor-research; docs/W22_FACTOR_RESEARCH_HANDOFF.md |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 83% of 641 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
99 | 2 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | Momentum; MR; trend; vol; volume; liquidity | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | AF-03 | W22: 11 standalone factors: mean reversion, trend, volume, recovery, risk (BRI) | QA; research on full history | quant/factors.py | branch w22-factor-research |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 68% of 269 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_quant_portfolio, test_w40_risk_model
100 | 2 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | z-score; robust; winsorise; percentile | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | AF-03 | W6 quant/normalize.py per-factor spec (winsorize/zscore/percentile/rank/minmax/sector/neutralize) -- tracker was stale | QA | quant/normalize.py | W6 79dd809 |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 75% of 114 lines in 1 key file(s) run by: test_w39_quant_portfolio
101 | 2 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | ID; formula; lookback; version | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | AF-03 | W6 registry quant_factor + factor sets + content-hash versioning (tracker was stale); W22 adds 11 factors | QA | quant/factors.py | W6 79dd809; W22 |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 68% of 269 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_quant_portfolio, test_w40_risk_model
102 | 2 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | Versioned score formulas | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | AF-01 | W22: formula_registry resolves each signal_log weights_hash to the full weight set + code version | QA | scores/formulas.py | branch w22-factor-research |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 61% of 51 lines in 1 key file(s) run by: test_auto_recover, test_w39_qa_suite
103 | 2 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | Factor/model/experiment tables | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | DBS-04 | W22: research_study + research_link registry, frozen on conclusion | QA | quant/studies.py | branch w22-factor-research |  |  | 2026-09-27 |  | 2026-09-27 |  | 1 | 19% of 78 lines in 1 key file(s) run by: test_auto_recover
104 | 2 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | Rank IC; ICIR; hit-rate of IC | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | AF-03 | W22: backfill_scores + research_report run IC for every factor | Run full-history backfill + report | quant/research.py | branch w22-factor-research | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 18% of 120 lines in 1 key file(s) run by: test_auto_recover, test_w39_exec_data_tests
105 | 2 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | Decay by horizon | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | QR-01 | W22: IC decay 1/5/10/20 for every factor in research_report | Run on full history | quant/research.py | branch w22-factor-research | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 18% of 120 lines in 1 key file(s) run by: test_auto_recover, test_w39_exec_data_tests
106 | 2 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | Correlation matrix | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | AF-03 | W22: redundancy report (pairs ¦rho¦>=0.7) in research_report | Run on full history | quant/research.py | branch w22-factor-research | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 18% of 120 lines in 1 key file(s) run by: test_auto_recover, test_w39_exec_data_tests
107 | 2 | Quant Research (data, factors, backtesting) | QR-04 | Quant Research | Statistical toolkit | Correlation; covariance; regression | Quant-Research | P1 | COMPLETED | COMPLETED | 75 | AF-03 | statarb (OLS, ADF, Engle-Granger, half-life, z) + normalize + volatility estimators | Validate | quant/statarb.py; quant/normalize.py; quant/volatility.py | technical.py:99 | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 70% of 242 lines in 3 key file(s) run by: test_auto_recover, test_w39_quant_portfolio, test_w40_futures_backtest
108 | 2 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | Validation before production | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | QR-01; QR-03 | W22: evidence-based approval gate, decision history, lifecycle enforcement behind quant.require_approved_factors | Owner: enable after review | quant/approval.py; strategy_engine/lifecycle.py | branch w22-factor-research |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 45% of 167 lines in 2 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_backtest_partial, test_w39_exec_data_tests, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
109 | 2 | Quant Research (data, factors, backtesting) | BT-16 | Backtesting | Dated equity curve / run records | Run registry with dated equity | Quant-Research | P0 | COMPLETED | COMPLETED | 85 |  | backtest_run snapshot+hash, code version, data fingerprint; trades/equity/drawdowns tables | Dated trades + equity curve + run table | backtest/store.py; db/schema.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 87% of 423 lines in 2 key file(s) run by: test_aggressive_lifecycle, test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_job_monitoring, test_market_health, test_mysql_backend (+65 more)
110 | 2 | Quant Research (data, factors, backtesting) | BT-08 | Backtesting | Portfolio-level backtest | Shared capital; sizing | Quant-Research | P0 | COMPLETED | COMPLETED | 85 | BT-16 | Portfolio engine: cash, positions, sizing (W1 size_position), exposure, dated equity | Portfolio simulator | backtest/engine.py | backtest_history.py:139 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 93% of 409 lines in 1 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips (+1 more)
111 | 2 | Quant Research (data, factors, backtesting) | BT-09 | Backtesting | Drawdown analysis | Max DD on dated equity | Agreed-Spec | P0 | COMPLETED | COMPLETED | 90 | BT-16 | Drawdown series, max DD, episodes with duration/recovery on dated equity | Compute on equity curve | backtest/metrics.py | backtest_aggressive.py:206 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 96% of 121 lines in 1 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39_mcp, test_w39_performance_detail, test_w39_qa_suite, test_w39_untested_modules, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+6 more)
112 | 2 | Quant Research (data, factors, backtesting) | BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | Risk-adjusted metrics | Agreed-Spec | P0 | COMPLETED | COMPLETED | 90 | BT-16 | Return, CAGR, vol, Sharpe, Sortino, Calmar, trade stats; conventions documented | Implement | backtest/metrics.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 96% of 121 lines in 1 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39_mcp, test_w39_performance_detail, test_w39_qa_suite, test_w39_untested_modules, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+6 more)
113 | 2 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | Tail metrics | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | BT-16 | W23: historical VaR/CVaR 95/99, parametric VaR, skew, kurtosis in every backtest's metrics | QA | backtest/metrics.py | branch w23-research-backtest |  |  | 2026-09-27 |  | 2026-09-27 |  | 6 | 96% of 121 lines in 1 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39_mcp, test_w39_performance_detail, test_w39_qa_suite, test_w39_untested_modules, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+6 more)
114 | 2 | Quant Research (data, factors, backtesting) | BT-05 | Backtesting | Itemised costs | Brokerage; STT; GST; stamp; SEBI fee; exchange fee | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 |  | Itemised NSE cost model (delivery/intraday/flat/zero), central config | Indian cost model shared by backtest and paper | backtest/costs.py; backtest/config.py | backtest_history.py:39 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 91% of 131 lines in 2 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_contract_note_fees, test_w39_performance_detail, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+7 more)
115 | 2 | Quant Research (data, factors, backtesting) | BT-06 | Backtesting | Slippage in backtest | Slippage model | Agreed-Spec | P1 | COMPLETED | COMPLETED | 90 | BT-05 | none / fixed / pct slippage, default = paper broker 5 bps | Shared slippage model | backtest/slippage.py | paper.py:199 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 69% of 29 lines in 1 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips (+1 more)
116 | 2 | Quant Research (data, factors, backtesting) | BT-07 | Backtesting | Liquidity constraints | ADV/turnover floor + participation cap | Agreed-Spec | P1 | COMPLETED | IN PROGRESS | 85 |  | Volume participation cap/reject + prior-bar turnover floor | All engines | backtest/liquidity.py | backtest.py:61 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 56% of 36 lines in 1 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips (+1 more)
117 | 2 | Quant Research (data, factors, backtesting) | DP-18 | Data Platform | Survivorship-free universe | Point-in-time constituents | Agreed-Spec | P1 | COMPLETED | COMPLETED | 80 |  | Current NIFTY 500 download | Store constituent history | data/index_constituents.py | — |  |  |  |  | 2026-09-24 |  | 2 | 84% of 105 lines in 1 key file(s) run by: test_index_feed, test_w39_index_constituents, test_w39_perf_budget, test_w39_performance_detail, test_w39_qa_suite, test_w39_ui_smoke, test_w39b_tf75, test_w40_total_return (+4 more)
118 | 2 | Quant Research (data, factors, backtesting) | BT-15 | Backtesting | Bias controls | Look-ahead; survivorship | Quant-Research | P1 | COMPLETED | COMPLETED | 80 | DP-18 | Point-in-time view + LookAheadError, next-open fills, data/timestamp validation, survivorship flag | Systematic checks | backtest/data.py; backtest/engine.py | backtest.py:163-174 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 92% of 545 lines in 2 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39_quant_portfolio, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo (+3 more)
119 | 2 | Quant Research (data, factors, backtesting) | BT-03 | Backtesting | In/out-of-sample | Split testing | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | BT-16 | Ordered non-overlapping research/validation/test; test needs allow_test; re-test flagged | Formal splits | backtest/periods.py; backtest/service.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 81% of 181 lines in 2 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips (+2 more)
120 | 2 | Quant Research (data, factors, backtesting) | BT-02 | Backtesting | Walk-forward | Rolling train/test (purged) | Agreed-Spec | P0 | COMPLETED | COMPLETED | 80 | BT-03 | Rolling windows, candidate selection on validation, stitched OOS; no optimiser | Implement | backtest/walkforward.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 83% of 126 lines in 1 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips, test_w40_futures_backtest
121 | 2 | Quant Research (data, factors, backtesting) | BT-13 | Backtesting | Monte Carlo | Trade shuffle/bootstrap | Agreed-Spec | P1 | COMPLETED | COMPLETED | 85 | BT-16 | Seeded trade shuffle + return bootstrap; percentiles, P(loss), disclaimer | Implement | backtest/montecarlo.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W2 developed 2026-09-24 — not yet independently validated (docs/W2_BACKTESTING_HANDOFF.md) | 6 | 94% of 53 lines in 1 key file(s) run by: test_w39_backtest_partial, test_w39_untested_modules, test_w40_futures_backtest
122 | 2 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | Optimiser | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 | BT-02 | W23: grid / random / adaptive optimiser with trial runs, test-window refusal, Deflated Sharpe + overfit warning. W40: method="bayes" -- a Tree-structured Parzen Estimator (Bergstra et al. 2011) in numpy after a seeded random start, same trial storage and deflated-Sharpe accounting | Independent QA | backtest/optimize.py | tests/test_w39b_bayes_optimize.py |  |  | 2026-09-27 |  | 2026-10-07 |  | 6 | tests/test_w39b_bayes_optimize.py ¦ 88% of 352 lines in 1 key file(s) run by: test_w39_backtest, test_w39_qa_suite, test_w39_untested_modules, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo
123 | 2 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | Sensitivity analysis | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | BT-04 | W23: one-at-a-time sensitivity curves, stability, knife-edge flags, 2-D heat map. W39b: a +-1 step neighbour with fewer than min_trades trades (or a failed run) is listed in thin_neighbours / thin_edges (study summary and CLI too) instead of vanishing; knife_edge and robust_share still compare only neighbours that have a metric | Independent QA | backtest/sensitivity.py | test_a_neighbour_that_stops_trading_is_a_thin_edge_not_a_knife_edge; test_stability_and_knife_edge_by_hand (tests/test_w39_qa_suite.py) |  |  | 2026-09-27 |  | 2026-10-07 | W39 QA finding (owner methodology call): a neighbouring parameter value with too few trades is ignored, so 'stops trading one step away' is not flagged as a knife edge (backtest/sensitivity.py) ¦ W39 QA finding (methodology call): 'stops trading one step away' was not flagged. W39b decision: report it as a separate thin-edge fragility flag rather than a knife edge, so robust_share keeps its meaning | 6 | test_a_neighbour_that_stops_trading_is_a_thin_edge_not_a_knife_edge; test_stability_and_knife_edge_by_hand (tests/test_w39_qa_suite.py) ¦ 100% of 71 lines in 1 key file(s) run by: test_w39_qa_suite
124 | 2 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | Deflated Sharpe; PBO; regime testing | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 | BT-02 | W23: robustness battery (costs x2, slippage x3, universe halves, period halves, regimes, Monte Carlo) with verdict. W39b: backtest/cpcv.py -- combinatorial purged cross-validation (N groups, k test groups, purge + embargo per AFML 7.4, C(N-1,k-1) out-of-sample paths with their distribution) and PBO by CSCV (Bailey et al.: logits, degradation regression, probability of loss; from a matrix or an optimisation's trials); python -m backtest cpcv ¦ pbo; POST /api/backtests/cpcv and /api/backtests/{id}/pbo | Independent QA. W40: first / second-order stochastic dominance of the selected trial's out-of-sample results over a random selection (in pbo() and CPCV); CPCV on the event-driven engine (engine="event_driven") | backtest/robustness.py; backtest/cpcv.py | tests/test_w39b_cpcv_pbo.py; tests/test_w39b_cpcv_dominance.py |  |  | 2026-09-27 |  | 2026-10-07 |  | 6 | tests/test_w39b_cpcv_pbo.py; tests/test_w39b_cpcv_dominance.py ¦ 83% of 678 lines in 2 key file(s) run by: test_w39_backtest, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo
125 | 2 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | Seeded runs; experiment log | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | DBS-07 | W6 experiments + W22 studies linking experiments/backtests/research | QA | quant/experiments.py; quant/studies.py | branch w22-factor-research | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 18% of 139 lines in 2 key file(s) run by: test_auto_recover
126 | 2 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | Trend strategy research | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 | BT-02 | W23: momentum breakout strategy + end-to-end study (optimise/validate/sensitivity/robustness/test) | Run full-universe study; review | backtest/strategies.py; backtest/study.py | branch w23-research-backtest |  |  | 2026-09-27 |  | 2026-09-27 |  | 6 | 43% of 259 lines in 2 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips (+2 more)
127 | 2 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | MR strategy research | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 | BT-02 | W23: RSI(2) mean-reversion strategy + study; 12-stock smoke: REJECTED out of sample | Run full-universe study; review | backtest/strategies.py; backtest/study.py | branch w23-research-backtest |  |  | 2026-09-27 |  | 2026-09-27 |  | 6 | 43% of 259 lines in 2 key file(s) run by: test_auto_recover, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips (+2 more)
128 | 2 | Quant Research (data, factors, backtesting) | QR-13 | Quant Research | Signal outcome research by regime | Hit rate by regime/ACS decile | Code-Derived | P1 | COMPLETED | COMPLETED | 70 | ML-05 | success_report keyed on signal/threshold | Add regime/ACS buckets | scores/signal_log.py | signal_log.py:522 |  |  |  |  | 2026-09-24 |  | 6 | 64% of 301 lines in 1 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_w39_exec_data_tests, test_w39_notify_transactions, test_w39_perf_budget, test_w39_performance_detail (+6 more)
129 | 2 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | 1y; 3y; rolling-60 beta (QRH) | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 70 | TA-12 | W21: beta_60, beta_downside, beta_long (>=500 sessions) | Owner: prices_daily retention >= 1,100 days for a 3-year beta | data/technical_ext.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 92% of 371 lines in 1 key file(s) run by: test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules
130 | 2 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | Optional BRI (QRH) | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 75 | TA-09 | W21: Beta Risk Index 0-100 (level, downside, instability); strategy feature bri | QA; decide if it joins a composite | data/technical_ext.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 92% of 371 lines in 1 key file(s) run by: test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules
131 | 2 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | Ichimoku; Donchian; Keltner; SAR; MFI; CMF; HV | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | TA-12 | W21: Supertrend, Ichimoku, Keltner, Donchian, MFI, CMF, ROC, Aroon, PSAR; stoch/Williams %R/CCI now computed | QA | data/technical_ext.py; data/technical.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 3 | 86% of 728 lines in 2 key file(s) run by: test_regressions, test_w39_qa_suite, test_w39_technical_rs_fib, test_w39_untested_modules, test_w40_stock_chart
132 | 2 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | Futures; options; OI; IV; PCR | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | DBS-04 | W35: data/derivatives_store.py -- every F&O contract to lake "fo_bhavcopy"; fo_contract_daily (futures + nearest 2 option expiries, all strikes, contract IV); NSE option-chain intraday snapshots (derivatives.option_chain_enabled, off) + lake "option_chain" | QA; verify NSE option-chain fields live | data/derivatives_store.py; data/derivatives.py | 219 underlyings for 2026-09-30 | Claude (dev) |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 31% of 347 lines in 2 key file(s) run by: test_regressions, test_w37_brokers_multi_asset, test_w39_qa_suite, test_w40_option_intents
133 | 2 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | Market Sentiment Index per QRH | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 75 | DP-08 | W27: MSI Options uses the session's real NIFTY PCR (OI) from the NSE F&O bhavcopy; component dropped when missing (was a constant 1.0) | AI news input to MSI (W28, NS-*) | scores/engine.py; data/derivatives.py | NIFTY PCR 0.788 on 2026-09-30 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 71% of 743 lines in 2 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
134 | 2 | Quant Research (data, factors, backtesting) | DP-10 | Data Platform | FII/DII history | FII/DII time series | Agreed-Spec | P2 | COMPLETED | COMPLETED | 80 |  | Session flows; only 7 sessions history | Historical backfill source | data/bhavcopy.py | 969f570 |  |  |  |  | 2026-09-24 |  | 2 | 60% of 346 lines in 1 key file(s) run by: test_corporate_actions, test_fii_dii_and_delivery_factor, test_regressions, test_signal_pipeline
135 | 2 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | Pre-open GIFT Nifty | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 |  | W21: daily GIFTNIFTY close from index_levels into prices_daily | Pre-open panel (DB-04) | data/market_series.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 2 | 15% of 89 lines in 1 key file(s) run by: test_signal_pipeline
136 | 2 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | Dashboard section | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | DP-11 | W27 /market page pre-open view: GIFT Nifty, implied gap vs Nifty close, GIFT daily series, overnight global + US yields, NIFTY/BANKNIFTY PCR + max pain, FII/DII | QA | dashboard/market_routes.py; dashboard/market_page.py | TestClient: /api/market/preopen 200 (implied gap +1.04%) | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 8 | 23% of 159 lines in 2 key file(s) run by: test_auto_recover, test_w39_perf_budget
137 | 2 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | Indices; FX; commodities; yields | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W27: US 3M/5Y/30Y yields added (10Y existed); global_market_history (daily closes of every series, appended each run, backfill 1y-max); /api/market/global-history | India 10Y G-sec: no reliable free source via yfinance (left out, not approximated) | data/markets.py | Backfill 1y: 4,281 rows, 17 series | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 2 | 21% of 141 lines in 1 key file(s) run by: test_regressions
138 | 2 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | Sector classification + sector indices | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 |  | W21: 8 sector index series in the daily Dhan sync + sector_breadth table | Run --backfill-sectors; QA | data/market_series.py; data/dhan.py | branch w21-data-technical |  |  | 2026-09-27 |  | 2026-09-27 |  | 2 | 40% of 834 lines in 2 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions, test_w39_risk_gateway (+2 more)
139 | 2 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | MF; promoter; insider; bulk/block | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W27 data/institutional.py: NSE shareholding pattern (+ SHP XBRL MF/FPI/insurance/DII/retail %, pledge), PIT insider trades, SAST Reg 29; point-in-time features(); weekly | Daily per-stock MF flow has no free source (quarterly SHP change used); QA | data/institutional.py | INFY promoter 13.82, MF 23.0, FPI 27.09, QoQ deltas | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 2 | 78% of 148 lines in 1 key file(s) run by: test_w39_exec_data_tests
140 | 2 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | INS formula | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-16 | W27 INS adds MutualFund (SHP MF change), Insider (90d net PIT value), promoter trend + pledge; behind institutional.score_enabled (off) | Enable after QA; IC study | scores/engine.py | Scratch rescore: INS INFY 36.7, TCS 50.7 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
141 | 2 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | Deal-flow signal | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 75 | DP-16 | W27 quant/deal_signal.py event study: abnormal (vs NIFTY50) forward returns by side, t-stats, pooled IC; verdict with direction; weekly; /market panel | Owner decision: first study CONTRADICTS INS BulkDeals direction (net SELL deals -> +4.5% 5d abnormal, t=4.1, n=139) on 4 weeks of data -- do not up-weight; re-check as history grows | quant/deal_signal.py | 494 events 2026-09-07..10-01 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 2 | 89% of 74 lines in 1 key file(s) run by: test_w39_exec_data_tests
142 | 3 | Strategy Engine | SG-04 | Signal Engine | Rich decision states | STRONG BUY..NO TRADE with reasons | Quant-Research | P0 | COMPLETED | COMPLETED | 80 | BT-02 | Decision states BUY/ADD/HOLD/REDUCE/EXIT/SELL/NO_ACTION/BLOCKED_BY_RISK with reasons; PositionIntent | Extended states + stored reasons | strategy_engine/decisions.py | engine.py:499 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — not yet independently validated (docs/W3_STRATEGY_ENGINE_HANDOFF.md) | 5 | 88% of 132 lines in 1 key file(s) run by: test_auto_recover, test_w39_backtest_partial, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
143 | 3 | Strategy Engine | SG-01 | Signal Engine | SELL calibration | BUY/SELL/HOLD/WAIT all reachable | Agreed-Spec | P0 | COMPLETED | COMPLETED | 70 | BT-02 | SELL never fired | Backtest-based SELL thresholds | scores/engine.py | determine_signal |  |  |  |  | 2026-09-24 |  | 5 | 85% of 590 lines in 1 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_w39_qa_suite
144 | 3 | Strategy Engine | SE-01 | Strategy Engine | Strategy library | Multiple strategies (FR-SB-004) | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | BT-16 | Versioned JSON definitions + DB registry (id, name, description, category, version, status, owner, created/updated, priority, weight); VERSION/LIFECYCLE events; 9 library strategies | Strategy interface + registry | strategy_engine/definition.py; registry.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-10-07 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md ¦ W39: KNOWN_DEFECTS W3-L4 resolved -- ADD / REDUCE decisions are simulated in backtests | 5 | 79% of 204 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_backtest_partial, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
145 | 3 | Strategy Engine | SE-02 | Strategy Engine | Strategy parameters | Parameter management | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | SE-01 | ParamSpec name/type/default/min/max/allowed/required/description; validated on resolve; stored per version in strategy_parameter | Param store per strategy with versions | strategy_engine/params.py; registry.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 68% of 98 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_backtest_partial, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
146 | 3 | Strategy Engine | SE-03 | Strategy Engine | Rule-based strategies | Rule engine | Agreed-Spec | P1 | COMPLETED | IN PROGRESS | 85 | SE-01 | Rule language all/any/not/min-of, 11 operators incl. crosses; rule kind | Generic rule definition format | strategy_engine/rules.py; kinds.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 58% of 119 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w40_option_intents
147 | 3 | Strategy Engine | SE-06 | Strategy Engine | Multi-factor strategy | Composite-score entries | Agreed-Spec | P1 | COMPLETED | COMPLETED | 85 | SE-01; QR-01 | multi_factor kind: weights, scaling, thresholds, confirmations, coverage, ranking | IC-weighted multi-factor strategy | strategy_engine/kinds.py | engine.py:435 |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 66% of 502 lines in 1 key file(s) run by: test_signal_pipeline, test_w39_backtest_partial, test_w39_qa_suite, test_w39_quant_portfolio, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
148 | 3 | Strategy Engine | SE-04 | Strategy Engine | Quant strategies | Factor/stat strategies | Quant-Research | P1 | COMPLETED | COMPLETED | 75 | SE-01; QR-01 | quant_rank kind + point-in-time feature catalogue (framework only) | Implement first quant strategies | strategy_engine/kinds.py; features.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 66% of 502 lines in 1 key file(s) run by: test_signal_pipeline, test_w39_backtest_partial, test_w39_qa_suite, test_w39_quant_portfolio, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
149 | 3 | Strategy Engine | SE-09 | Strategy Engine | Strategy lifecycle | Idea -> research -> paper -> live -> retired | Quant-Research | P1 | COMPLETED | COMPLETED | 85 | SE-01 | 12 states incl. DRAFT/ACTIVE/PAUSED/DISABLED/RETIRED/ARCHIVED; allowed transitions; backtest evidence for ACTIVE/VALIDATION/APPROVED; strategy_engine_event audit | State machine + gates | strategy_engine/lifecycle.py | strategy_event 3 rows |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 88% of 64 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_backtest_partial, test_w39_exec_data_tests, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
150 | 3 | Strategy Engine | SE-11 | Strategy Engine | Strategy health | Rolling Sharpe/DD per strategy | Quant-Research | P1 | COMPLETED | IN PROGRESS | 75 | SE-09; BT-16 | HEALTHY/WARNING/ERROR/STALE/DISABLED; last execution, last signal, signal frequency, error count, performance reference, data availability, parameter validity | Health scoring + alerts | strategy_engine/health.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 17% of 103 lines in 1 key file(s) run by: test_auto_recover
151 | 3 | Strategy Engine | SE-07 | Strategy Engine | Strategy combination/ranking/selection | Allocator across strategies | Quant-Research | P1 | COMPLETED | IN PROGRESS | 75 | SE-11 | composite kind (vote/weighted/priority/regime_select) + cross-strategy combine(): priority, weighting, vote, conflict -> WAIT, NO_TRADE veto; enable/disable via lifecycle and mapping | Allocator | strategy_engine/selection.py; kinds.py | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 44% of 124 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract
152 | 3 | Strategy Engine | SE-08 | Strategy Engine | Regime-aware selection | Regime switches strategies | Quant-Research | P2 | COMPLETED | IN PROGRESS | 75 | SE-07; ML-05 | Configurable regime mapping STRONG_BULL/BULL/NEUTRAL/BEAR/HIGH_RISK (+DEFAULT) -> strategies or NO_TRADE; Market Health regime provider; default mapping seeded | Regime-conditional allocation | strategy_engine/selection.py; regime.py; library/regime_mapping.json | — |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | W3 developed 2026-09-24 — independent functional validation PENDING (ChatGPT); see docs/W3_STRATEGY_ENGINE_HANDOFF.md | 5 | 44% of 124 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract
153 | 3 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | Midday/pre-close scans on real data | Code-Derived | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | DP-03 | W28 strategy/intraday_scan.py: zpi_pullback, breakout, vwap_reclaim, momentum, breakdown_risk on live quotes + today's CLOSED 15-min bars vs the previous session's scores/levels (no lookahead); 10:30/12:30/14:45; intraday_scan_hit; Telegram digest. Replaces the 12:30 ZPI alert that read today's not-yet-computed scores | QA; tune thresholds after a few sessions | strategy/intraday_scan.py; pipeline/scheduler.py | Scratch 2026-10-01 12:30: 8 hits, last bar used 12:15 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 5 | 33% of 1365 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_intraday, test_w39_notify_transactions, test_w39_qa_suite (+3 more)
154 | 3 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | Daily top-25 lists per concept document | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W28 dashboard 'Lists & scans' tab: Crash-risk 25 (CRI, 5-session change, main CRI driver, held flag), Top SPI 25 (ai_scores or NSE-fundamentals SPI, source shown), MSI series + components (stored under __MARKET__ from W28) | QA | scores/lists.py; dashboard/w28_assets.py; scores/engine.py | TestClient /api/lists/* 200 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 8 | 81% of 622 lines in 3 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_risk_controls, test_w39_qa_suite
155 | 3 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | Dashboard section | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | SE-11 | W28 /strategies Performance panel: health + issues, current-version backtest (return, Sharpe, DD, win rate), decisions by action and blocked, PAPER/LIVE book P&L from W4 fills (average cost, realised/unrealised) | No strategy has run (all DRAFT, no fills) -- panel populates once strategies run in PAPER | strategy_engine/performance.py; dashboard/strategy_page.py | TestClient /api/strategy-performance 200 (15 strategies) | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 8 | 89% of 75 lines in 2 key file(s) run by: test_w39_exec_data_tests, test_w39_perf_budget, test_w40_option_intents
156 | 4 | AI/ML | ML-13 | AI/ML | Labels/targets | Outcome labels for training | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | AF-03 | ml/labels.py: direction, binary_return, forward_return, return_rank, volatility_regime, market_regime, signal_outcome; ml_label definitions; computed only from bars after t | Validate | ml/labels.py | — | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 76% of 106 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_qa_suite, test_w40_meta_label
157 | 4 | AI/ML | ML-07 | AI/ML | Feature selection | Automated selection | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | ML-13; QR-01 | W24: importance-stability selection -> new feature-set version | QA | ml/selection.py | branch w24-ml | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 11% of 27 lines in 1 key file(s) run by: test_auto_recover
158 | 4 | AI/ML | ML-08 | AI/ML | Model validation | Purged CV; AUC; calibration | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | ML-13; BT-02 | W24: purged expanding walk-forward reports vs baselines, IC, calibration, verdict | QA | ml/validation.py | branch w24-ml | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 87% of 198 lines in 1 key file(s) run by: test_auto_recover, test_w39_qa_suite, test_w40_meta_label
159 | 4 | AI/ML | ML-01 | AI/ML | Supervised ML | Classification/regression models | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | ML-08 | W24: native numpy GBM + random forest; bootstrap trains + validates first models (TRAINED, not ACTIVE); real-data smoke: NO_EDGE on 5-day direction | Richer features / labels; full-universe validation | ml/trees.py; ml/presets.py | branch w24-ml; docs/W24_ML_HANDOFF.md | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 71% of 385 lines in 2 key file(s) run by: test_auto_recover, test_w39_qa_suite, test_w40_meta_label
160 | 4 | AI/ML | ML-12 | AI/ML | Model registry/versioning | FR-ML-002 | Agreed-Spec | P0 | COMPLETED | COMPLETED | 85 | ML-01; DBS-07 | ml_model / ml_model_version with feature-set, dataset, config and artifact hashes; immutable artifacts; lifecycle | Validate | ml/registry.py; ml/artifacts.py | — | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 88% of 184 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_ml_regime_lineage_surface, test_w39_qa_suite, test_w40_meta_label
161 | 4 | AI/ML | ML-11 | AI/ML | Ensemble models | Ensembles | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | ML-01 | W24: ensemble model type blended by held-out loss | QA | ml/trees.py | branch w24-ml | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 67% of 322 lines in 1 key file(s) run by: test_auto_recover, test_w39_qa_suite, test_w40_meta_label
162 | 4 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | Drift alerts (FR-ML-001) | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | ML-12 | W24: drift (PSI share) + realised decay alerts, ml_health_check, monitor rule | QA | ml/decay.py; ops/monitor.py | branch w24-ml | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 63% of 213 lines in 2 key file(s) run by: test_auto_recover, test_w39_ops_tests
163 | 4 | AI/ML | ML-10 | AI/ML | Explainability | FR-AI-003 | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | ML-01 | W24: exact path contributions for trees, gain importances, out-of-sample permutation importance | QA | ml/trees.py; ml/validation.py | branch w24-ml | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 75% of 520 lines in 2 key file(s) run by: test_auto_recover, test_w39_qa_suite, test_w40_meta_label
164 | 4 | AI/ML | ML-05 | AI/ML | Regime detection | Model-based regime + probability | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 75 | SC-09 | W24: market_regime model preset validated + trained (NO_EDGE on smoke) | Owner decides regime provider after evidence | ml/presets.py | branch w24-ml | Claude (development) |  | 2026-09-25 |  | 2026-09-27 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 4 | 90% of 63 lines in 1 key file(s) run by: test_w39_qa_suite
165 | 4 | AI/ML | ML-03 | AI/ML | Unsupervised learning | Clustering | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | AF-03 | W24: k-means++ factor clusters with profiles; return PCA | QA | ml/unsupervised.py | branch w24-ml |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 19% of 131 lines in 1 key file(s) run by: test_auto_recover, test_w39_ml_regime_lineage_surface
166 | 4 | AI/ML | ML-06 | AI/ML | Anomaly detection | Data/market anomalies | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | DP-19 | W24: robust-z + multivariate anomaly scan, CA-explained, post-market (flag off) | Owner: ml.anomalies_enabled | ml/unsupervised.py | branch w24-ml |  |  | 2026-09-27 |  | 2026-09-27 |  | 4 | 19% of 131 lines in 1 key file(s) run by: test_auto_recover, test_w39_ml_regime_lineage_surface
167 | 4 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | FR-SB-003 | Agreed-Spec | P1 | BLOCKED | BLOCKED | 75 | ML-01; SE-01 | W28 ml/ai_strategy.py: 8-gate readiness chain per ML strategy (ml.enabled, default_model, model, ACTIVE version, validation not NO_EDGE, fresh predictions, backtest, W4 risk gate) + guarded activation (PAPER first, ACTIVE only from PAPER) via lifecycle.transition; /ml panel | Blocked on a model with edge: no ML model registered in production; W24 validation showed NO_EDGE | ml/ai_strategy.py; dashboard/ml_page.py | ml_direction / atip_ml_blend blocked at ml_enabled | Owner (model) / Claude (dev) |  | 2026-09-25 |  | 2026-10-07 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 5 |  | Evidence, not a decision: no ML model version has passed validation (W24: NO_EDGE). Re-train when more history exists (DP-23 backfill) and activate only an ADOPTABLE model
168 | 4 | AI/ML | NS-02 | News/Sentiment | News classification | Earnings/Orders/M&A/RBI/Govt/Global/Geopolitics | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 |  | W28 data/news_ai.py: batched Claude Haiku 4.5 classification (20 headlines/request, JSON-schema structured output: sentiment, confidence, importance, 17-category taxonomy, NSE symbols, rationale); daily cost cap with ai_usage_log; off by default | Working ANTHROPIC_API_KEY (current key 401, KD-001), then news.ai_enabled=true | data/news_ai.py; data/news.py | 401 handled -> rule fallback, failed request logged | Owner (key) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 16% of 367 lines in 2 key file(s) run by: test_w36_ml_strategy_tooling, test_w39_screener_nl, test_w39_ui_smoke
169 | 4 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | Positive/neutral/negative + confidence | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | NS-02 | W28: model sentiment + model confidence (classifier='claude', read by ACS); rule fallback rebuilt: weighted lexicon with negation, category keywords, MEASURED confidence from evidence (no longer constant 0.5; still excluded from ACS) | Enable the AI path; compare AI vs rule sentiment on a labelled sample | data/news_ai.py | Rule: 'Infosys Q2 profit beats...' +0.73 conf 0.59 EARNINGS HIGH | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 29% of 198 lines in 1 key file(s) run by: test_w36_ml_strategy_tooling, test_w39_screener_nl, test_w39_ui_smoke
170 | 4 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | Decayed weighted sentiment | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | NS-03 | W28b: data/news_weighting.py -- novelty (shingle Jaccard vs 72h, dup_of), half-life by W28 category, measured source weights (duplicate share, next-session reaction hit rate), per-stock decayed weighted score in news_symbol_score (shrunk toward 50); scores/engine.get_ns reads it; News tab card | Independent QA; review effect on VPI/MRI/RRI/CRI/ZPI | data/news_weighting.py; data/news.py; scores/engine.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W28b developed 2026-10-01 on branch w28b-news-weighting (on w33-wealth-qa) — independent validation PENDING (ChatGPT); see docs/W28B_NEWS_WEIGHTING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 4 | 58% of 926 lines in 3 key file(s) run by: test_fii_dii_and_delivery_factor, test_market_health, test_regressions, test_signal_pipeline, test_w39_qa_suite
171 | 4 | AI/ML | NS-04 | News/Sentiment | AI news summary | Summary for dashboard | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | NS-02 | W28 market_summary(): one Claude request over the window's headlines -> headline, tone, bullets with headline refs, key risks, stocks in focus; rule-based summary (labelled) as fallback; news_summary table; after pre-market and midday news | Enable AI path | data/news_ai.py; pipeline/scheduler.py | Rule summary over 60 headlines stored | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 4 | 34% of 1427 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w36_ml_strategy_tooling, test_w39_history, test_w39_notify_transactions, test_w39_qa_suite (+4 more)
172 | 4 | AI/ML | DB-06 | Dashboard | AI News Summary panel | Dashboard section | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | NS-04 | W28 market brief card at the top of the dashboard News tab (AI or rule, labelled; tone; bullets; risks; stocks in focus clickable; AI spend vs cap) | QA | dashboard/w28_assets.py | Rendered by TestClient; JS node --check OK | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 8 | 100% of 1 lines in 1 key file(s) run by: test_risk_controls
173 | 4 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | Transcript sentiment | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | NS-02 | W28b: data/announcements.py -- NSE corporate announcements classified (subject rules + W28 lexicon); transcripts / results / presentations of tracked stocks read from the PDF by the W28 news model under the daily cap (tone, guidance, key points, risks); material ones -> market_event ANNOUNCEMENT (QR-09); News tab card | Independent QA; verify NSE field names live; owner: news.ai_enabled for document NLP | data/announcements.py; dashboard/w28b_routes.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W28b developed 2026-10-01 on branch w28b-news-weighting (on w33-wealth-qa) — independent validation PENDING (ChatGPT); see docs/W28B_NEWS_WEIGHTING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 4 | 20% of 213 lines in 2 key file(s) run by: test_auto_recover, test_w39_ui_smoke
174 | 4 | AI/ML | ML-02 | AI/ML | Deep learning | Neural models | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | ML-08 | W36: ml/deep.py native NumPy MLP (model_type neural_network, Adam, dropout, time-ordered early stopping, gradient importances) replacing the W5 placeholder; benefit_check() walk-forward vs logistic/linear + native_gbm; registry refuses APPROVED/ACTIVE without an ADOPTABLE check | Run benefit_check on a real dataset; adopt only if ADOPTABLE | ml/deep.py; ml/models.py; ml/registry.py | — |  |  | 2026-10-02 |  | 2026-10-02 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_STRATEGY_TOOLING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 4 | 72% of 614 lines in 3 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_ml_regime_lineage_surface, test_w39_qa_suite, test_w40_meta_label
175 | 4 | AI/ML | ML-04 | AI/ML | Reinforcement learning | RL where appropriate | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 75 | ML-08 | W36: ml/rl.py tabular Q-learning long/flat agent (36 states: momentum, trend, volatility, position) with costs; out-of-sample vs buy-and-hold and trend baselines; research only, cannot be activated | Run on the universe; expect NO_ADVANTAGE unless proven otherwise | ml/rl.py | — |  |  | 2026-10-02 |  | 2026-10-02 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_STRATEGY_TOOLING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 4 | 88% of 120 lines in 1 key file(s) run by: test_w36_ml_strategy_tooling
176 | 4 | AI/ML | DB-18 | Dashboard | Quant/model panel | Factor IC; model health | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | ML-12 | W28 /ml Model monitoring: max/mean feature PSI and features-shifted series, realised metric series, health-check history (/api/ml/monitoring-series) | Shows data once a model runs with ml.enabled (none in production) | dashboard/w28_routes.py; dashboard/ml_page.py | TestClient 200 with 'no model monitoring yet' | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOFF.md | 8 | 47% of 103 lines in 2 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_ui_smoke
177 | 5 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | Allocation view | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 90 | PF-02 | W25: portfolio/risk.py book_snapshot for PAPER and LIVE books (weights, % equity, sector exposure); /api/risk/portfolio; /trading Portfolio risk panel | Independent QA | portfolio/risk.py; dashboard/portfolio_risk_routes.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-25 |  | 2026-09-28 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 8 | 39% of 507 lines in 2 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model
178 | 5 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | HHI; weight caps | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 90 | PF-03 | W25: concentration() max/top-5 weight, HHI, effective N, sector HHI; in /api/risk/portfolio and snapshots | Independent QA | portfolio/risk.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 8 | 29% of 365 lines in 1 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model
179 | 5 | Risk & Portfolio | PF-09 | Portfolio | Correlation | Holdings correlation | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 90 | QR-04 | W25: portfolio correlation matrix, weighted avg pairwise correlation, high pairs, diversification ratio; heatmap on /trading | Independent QA | portfolio/risk.py; dashboard/execution_page.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md | Claude (development) |  | 2026-09-25 |  | 2026-09-28 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 8 | 30% of 369 lines in 2 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model
180 | 5 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | Cluster limits | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | PF-09 | W25: W4 limit max_avg_correlation (value-weighted correlation of the new symbol with the held book; fail closed); analytics in /api/risk/portfolio | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; portfolio/limits.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 7 | 46% of 600 lines in 2 key file(s) run by: test_auto_recover, test_w39_risk_gateway, test_w40_option_intents
181 | 5 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | Portfolio risk | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | QR-04 | W25: historical / parametric / Monte Carlo VaR and ES, 95/99%, 1 and 10 days; W4 limit max_portfolio_var_pct (post-trade); snapshot job + VaR alert (off by default) | Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | portfolio/risk.py; portfolio/limits.py; execution/risk_engine.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 7 | 40% of 965 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_risk_gateway, test_w39_ui_smoke, test_w40_option_intents, test_w40_risk_model
182 | 5 | Risk & Portfolio | RK-06 | Risk Management | Sector limits | Sector cap | Quant-Research | P1 | COMPLETED | IN PROGRESS | 80 | PF-03 | max_sector_exposure_pct in the W4 risk engine (NSE industry from cached Nifty 500 list; fails closed when unavailable) | Validate | execution/risk_engine.py; execution/positions.py | — |  |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 52% of 609 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_perf_budget, test_w39_qa_suite, test_w39_risk_gateway, test_w39_ui_smoke, test_w40_option_intents, test_w40_risk_model
183 | 5 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | Vol-scaled exposure | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | TA-12 | W25: W4 limit max_symbol_volatility_pct (annualised 60-session vol; fail closed) | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; execution/config.py; portfolio/limits.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 7 | 47% of 697 lines in 3 key file(s) run by: test_auto_recover, test_w38_platform_compliance, test_w39_exec_data_tests, test_w39_ops_tests, test_w39_perf_budget, test_w39_qa_suite, test_w39_risk_gateway, test_w39_ui_smoke (+1 more)
184 | 5 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | ADV participation cap | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | DP-02 | W25: W4 cap max_adv_participation_pct (qty <= % of 20-session ADV) and W1 risk_limits.max_adv_participation_pct (BUY and SELL, unmeasurable -> refused) | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; orders/risk.py; portfolio/limits.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 7 | 53% of 938 lines in 3 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
185 | 5 | Risk & Portfolio | RK-18 | Risk Management | Strategy risk budget | Per-strategy limits | Quant-Research | P2 | COMPLETED | IN PROGRESS | 75 | SE-09 | max_strategy_exposure_pct + strategy_drawdown_limit_pct from per-strategy fill attribution | Per-strategy capital budgets | execution/risk_engine.py; execution/positions.py | — |  |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 52% of 609 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_perf_budget, test_w39_qa_suite, test_w39_risk_gateway, test_w39_ui_smoke, test_w40_option_intents, test_w40_risk_model
186 | 5 | Risk & Portfolio | RK-01 | Risk Management | Kill switch scopes + auto-trigger | Global/strategy/symbol; auto on breach | Quant-Research | P0 | COMPLETED | COMPLETED | 80 | RK-07; RK-08 | Global flag file + config | Per-strategy/symbol; auto-trigger | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24 |  | 7 | 66% of 338 lines in 1 key file(s) run by: test_auto_recover, test_job_monitoring, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_backtest, test_w39_backtest_partial, test_w39_notify_transactions (+10 more)
187 | 5 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | Flatten all positions | Quant-Research | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | RK-01 | W25: portfolio/emergency.py plan + confirm code (10 min) -> kill switch ON, cancel open W4 orders, sell PAPER book; LIVE = sell list only, never an order; /api/risk/emergency-exit (risk:approve); dashboard button | Independent QA | portfolio/emergency.py; dashboard/portfolio_risk_routes.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 7 | 51% of 239 lines in 2 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke
188 | 5 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | Vol target; risk parity; MV with costs; BL | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | RK-12 | W25: portfolio/optimize.py min_variance / mean_variance / max_sharpe / risk_parity; long-only, max/min weight, sector caps (FISTA + exact Dykstra projection); shrunk covariance; frontier; stored runs | Independent QA; expected-return model review | portfolio/optimize.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md ¦ W39 fix: the sector-cap projection (Dykstra, stopped early) could return weights over the sector cap (29 of 294 random cases, up to 48 points); replaced by the exact KKT projection (test_projection_never_breaks_a_sector_cap_and_is_the_nearest_feasible_point) | 8 | 65% of 417 lines in 1 key file(s) run by: test_w39_quant_portfolio
189 | 5 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | Rebalance proposals | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 | PF-10 | W25: rebalance_plan (NEW/ADD/REDUCE/EXIT/HOLD, band, min trade, costs, turnover); portfolio kind reweight_band_pct emits ADD/REDUCE with exact quantity. W39: the W2 backtest simulates ADD / REDUCE (partial rows, averaged entries, max_position_pct cap, P&L conserved; BUY/SELL-only runs byte-identical); reweight_band_pct accepted by definition validation (was refused); saved runs, walk-forward and Monte Carlo count positions | Independent QA. W39b: the event-driven engine (BT-17) now trades ADD / REDUCE too, through its own order model | portfolio/optimize.py; strategy_engine/kinds.py; backtest/engine.py; backtest/event_driven.py; strategy_engine/adapter.py | tests/test_w39_backtest_partial.py | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 8 | tests/test_w39_backtest_partial.py ¦ 79% of 1894 lines in 5 key file(s) run by: test_auto_recover, test_signal_pipeline, test_w39_backtest, test_w39_backtest_partial, test_w39_qa_suite, test_w39_quant_portfolio, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+4 more)
190 | 5 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | Risk contribution | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | PF-10 | W25: risk_attribution per position / sector variance share, component VaR, beta, systematic vs idiosyncratic | Independent QA | portfolio/risk.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-09-28 |  | 8 | 29% of 365 lines in 1 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model
191 | 5 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | Return attribution | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | PF-13 | W25: holdings-based contribution by position / sector, beta-alpha split vs NIFTY50, Brinson allocation/selection vs equal-weighted universe | Independent QA. Trade-based attribution of the LIVE book now exists in the wealth performance report (PERF-001-07 / -09 / -10 on portfolio LIVE: broker_sync + PF-12 imports) | portfolio/risk.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-10-07 |  | 8 | 29% of 365 lines in 1 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model
192 | 5 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | FR-PO-004 | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 | PF-13 | W25: CAGR from pnl_daily equity; PAPER book + per-position XIRR from paper fills (wealth ledger XIRR in W15.5) | Independent QA. LIVE XIRR now comes from the wealth performance ledger (PERF-001-04, portfolio LIVE: Dhan broker_sync + PF-12 broker imports) | portfolio/risk.py; wealth/perf/metrics.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-28 |  | 2026-10-07 |  | 8 | 43% of 461 lines in 2 key file(s) run by: test_auto_recover, test_w39_mcp, test_w39_perf_budget, test_w39_performance_detail, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w39b_mf_analytics (+4 more)
193 | 5 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | Risk panel | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | RK-12 | W25: /trading Portfolio risk panels: KPIs, VaR/ES table, concentration, risk contribution, correlation heatmap, performance attribution, emergency exit | Independent QA | dashboard/execution_page.py | docs/W25_PORTFOLIO_RISK_HANDOFF.md |  |  | 2026-09-25 |  | 2026-09-28 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 8 | 100% of 4 lines in 1 key file(s) run by: test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke, test_w40_risk_model
194 | 6 | Execution | EX-02 | Execution | Order types | Market/limit/SL/SL-M/GTT/bracket | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W29: SL (stop-limit) and SL-M (stop-market) in the paper broker and OMS (per-order order_type / limit / trigger, validated); paper matching loop fills resting LIMIT / SL / SL-M (fixes W4-R4); protective child SL-M/SL after an entry fill (execution.protective_stops, off); LIMIT fills capped at the limit (slippage defect fixed) | QA; LIVE order types only with live execution (not built) | orders/paper.py; execution/order_manager.py; execution/paper_matching.py; execution/models.py | Scratch: SL-M trig 950 filled 948.53 at ltp 949; LIMIT 3000 filled 3000.00; protective stop rests ACKNOWLEDGED | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 56% of 695 lines in 4 key file(s) run by: test_auto_recover, test_paper_broker, test_risk_controls, test_strategy_live, test_w37_brokers_multi_asset, test_w39_exec_data_tests, test_w39_performance_detail, test_w39_qa_suite (+6 more)
195 | 6 | Execution | EX-08 | Execution | Order modify/cancel | FR-LT-002/003 | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W29 modify_order: quantity (down only -- up needs a new risk decision), limit, trigger, type for CREATED/VALIDATED (in place) and ACKNOWLEDGED (via adapter); append-only event rows old->new; paper broker modify_order; Dhan adapter refuses | QA | execution/order_manager.py; execution/adapters.py; dashboard/w29_routes.py | Scratch: qty 4->8 refused; 4->3 @1690 modified then filled | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 52% of 542 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke, test_w40_option_intents
196 | 6 | Execution | BR-05 | Broker Integration | Execution reconciliation | Orders vs broker fills/positions | Agreed-Spec | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W29 EOD reconciliation: PAPER positions (OMS fills vs paper_position, non-OMS orders explained), orders (status / filled qty vs paper_order), fill rows; LIVE holdings info; reconciliation_run + alert on breaks; post-market after the execution cycle | QA | execution/reconcile.py | Scratch: detected orders whose paper book had been reset (BREAKS) and explained a non-OMS TCS position | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 7 | 20% of 86 lines in 1 key file(s) run by: test_signal_pipeline, test_w39_qa_suite, test_w39_ui_smoke
197 | 6 | Execution | BR-06 | Broker Integration | Connection health | FR-BI-003 | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | MON-03 | W29 broker health: Dhan market data (latency), Dhan token (fund-limits), index feed, stock feed, quote freshness, Zerodha token, paper book; broker_health_check every 5 min in session + 08:45; alert on transition to/from DOWN/STALE; /trading panel | Observe in a live session | execution/broker_health.py | Scratch (network off): OK | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 7 | 73% of 135 lines in 1 key file(s) run by: test_w39_exec_data_tests, test_w39_qa_suite, test_w39_risk_gateway, test_w39_ui_smoke, test_w40_option_intents
198 | 6 | Execution | RK-17 | Risk Management | Broker/operational risk | Token expiry; connection loss | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | BR-06 | W29 risk check broker_health: BUY REJECTED while the latest check (<= 30 min) is DOWN or STALE; SKIP without a recent check; exits never blocked (execution.block_on_broker_health) | QA | execution/risk_engine.py; execution/broker_health.py | gate() PASS on OK | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 55% of 674 lines in 2 key file(s) run by: test_auto_recover, test_w39_exec_data_tests, test_w39_qa_suite, test_w39_risk_gateway, test_w39_ui_smoke, test_w40_option_intents
199 | 6 | Execution | BR-08 | Broker Integration | Sandbox | Broker sandbox environment | Code-Derived | P2 | BLOCKED | BLOCKED | 70 |  | W29: SANDBOX now uses its own credentials (dhan_sandbox_client_id / token; the old path reused the production token, which the sandbox rejects); verified redirect; python -m orders.sandbox_check (credentials, redirect, reachability, auth, optional place/status/cancel round trip); /api/execution/sandbox-check | Needs a Dhan-issued sandbox token (owner) -- then run the check with --place-test-order | orders/environment.py; orders/sandbox_check.py | Check reports NOT_CONFIGURED (no sandbox token) | Owner (Dhan sandbox token) |  | 2026-10-01 |  | 2026-10-07 |  | 7 |  | Owner: a Dhan-issued sandbox token, then run python -m orders.sandbox_check --place-test-order
200 | 6 | Execution | EX-09 | Execution | Measured slippage | Slippage vs decision price | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | PF-13 | W29 measured slippage per fill: bps vs decision reference (vs trigger for stops), positive = adverse, rupee cost; /api/execution/slippage | Meaningful once PAPER strategies execute | execution/analytics.py | Scratch fills measured | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 100% of 74 lines in 1 key file(s) run by: test_w39_exec_data_tests, test_w39_qa_suite, test_w39_ui_smoke
201 | 6 | Execution | EX-10 | Execution | Execution analytics | Implementation shortfall; fill/reject rate | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | EX-09 | W29 execution analytics: fill rate (qty / orders), rejection rate + reasons, cancels, failures, time to fill p50/p90, slippage mean/median/p90/worst, cost, fees; by strategy / order type / mode / day; /trading panel | QA | execution/analytics.py; dashboard/execution_page.py | TestClient /api/execution/analytics 200 | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W4 developed 2026-09-25 — independent functional validation PENDING (ChatGPT); see docs/W4_RISK_EXECUTION_HANDOFF.md | 7 | 100% of 78 lines in 2 key file(s) run by: test_w39_exec_data_tests, test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke, test_w40_risk_model
202 | 6 | Execution | BR-02 | Broker Integration | Zerodha/Kite | Portfolio (+orders optional) | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 |  | W29 Kite session lifecycle: token_status (VALID / EXPIRED at 06:00 IST / MISSING), login URL + /zerodha/callback request_token exchange (owner logs in at Zerodha; ATIP never handles the password), pre-market expiry alert; holdings sync skips an expired session | Register http://127.0.0.1:8000/zerodha/callback in the Kite developer console; Kite ORDERS not built (owner decision) | portfolio/zerodha.py; dashboard/w29_routes.py | Status MISSING (not configured here) | Owner / Claude (dev) |  | 2026-10-01 |  | 2026-10-01 |  | 7 | 37% of 244 lines in 2 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke
203 | 6 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | Live P&L view | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | PF-13 | W29 live P&L: LIVE holdings + PAPER book + per-strategy open positions at the newest live quote (price source and age shown, stale flagged): day P&L, unrealised, realised, cash; 15-min snapshots and an intraday chart on /trading (refresh 60 s) | QA in a live session | portfolio/live_pnl.py; dashboard/execution_page.py | Scratch: LIVE 8 holdings day P&L -1,191.85 | Claude (dev) / ChatGPT (QA) |  | 2026-10-01 |  | 2026-10-01 |  | 1 | 82% of 89 lines in 2 key file(s) run by: test_w39_exec_data_tests, test_w39_perf_budget, test_w39_qa_suite, test_w39_ui_smoke, test_w40_risk_model
204 | 6 | Execution | SEC-03 | Security | Audit logging | Immutable audit (FR-AT-001) | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 95 |  | W29 audit export: incremental gzip JSONL segments of enterprise_audit (chain verified, broken chain alerted) and oms_order_event with sha256 sidecars, off-box copy to audit.offbox_dir (hash re-checked), audit_export registry, daily 19:30; retention policy documented (append-only, operator-only pruning after off-box copy) | Set audit.offbox_dir (owner: a second drive / NAS / synced folder) | enterprise/audit_export.py | Scratch: 10 rows exported, sidecar verified | Owner (offbox dir) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 87% of 90 lines in 1 key file(s) run by: test_w39_ops_tests
205 | 7 | Advanced Quant | DP-04 | Data Platform | Tick data | Tick capture store | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | DBS-04 | W35: data/ticks.py -- every Dhan Quote packet of the stock feed captured (live_feed.capture_ticks, off) to lake "ticks", tick_capture_status, EOD 1-minute bars into intraday_bars | Owner: enable stock feed + capture_ticks; QA | data/ticks.py; data/stock_feed.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 56% of 366 lines in 2 key file(s) run by: test_w39_untested_modules
206 | 7 | Advanced Quant | DP-05 | Data Platform | Order book / depth | L2 depth; bid/ask | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | DP-04 | W35: data/depth.py -- 5-level depth from Dhan quote_data polled for a small set (depth.enabled, off): order_book_snapshot (spread bps, imbalance, top-5 qty) + lake "depth"; daily features for AF-07 | Owner: depth.enabled; verify Dhan depth payload live; QA | data/depth.py | dhan.py FULL=21 |  |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 43% of 101 lines in 1 key file(s) run by: test_w39_market_pulse, test_w39_untested_modules
207 | 7 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | OBI; spread; microprice | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 | DP-05 | W30: bar-based microstructure from stored 15-min bars per symbol/day: bar RV, Roll and Corwin-Schultz spread ESTIMATES, VWAP deviation, close location, last-hour volume share, order imbalance from stock-feed Quote packets (buy/sell qty now stored); ms_* strategy features incl. ms_spread_20; post-market job independent of quant.enabled | Quoted spread / depth / tick features need DP-04 / DP-05 feeds | quant/microstructure.py; quant/w30.py; data/stock_feed.py | Scratch 2026-10-01: 502 symbols | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 4 | 38% of 398 lines in 3 key file(s) run by: test_auto_recover, test_signal_pipeline, test_w39_untested_modules, test_w40_option_intents
208 | 7 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors | OI buildup; IV; PCR; skew | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-08 | W36: 8 derivatives factors in quant/factors.py from fo_underlying_daily (basis, OI build-up, PCR, PCR change, ATM IV, IV rank, IV skew, max-pain gap), point in time, F&O symbols only; engine loads derivatives inputs | Run factor IC research once F&O history accumulates | quant/factors.py; quant/engine.py | — | Claude (development) |  | 2026-09-25 |  | 2026-10-02 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_STRATEGY_TOOLING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 4 | 65% of 422 lines in 2 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_quant_portfolio, test_w40_risk_model
209 | 7 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | IV/RV; vol breakout | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | DP-08 | W30: implied volatility from F&O bhavcopy option closes (Black-Scholes; ATM call/put IV, 95/105 skew, expiry >= 4 days) per underlying per day; dv_* features: iv_atm, iv_rank / pct (252), VRP (IV - RV20), skew, PCR, annualised basis, futures OI change, F&O flag; 2 DRAFT library strategies (vol_compression_breakout, vrp_trend_filter) | Backfill IV history (python -m data.derivatives --backfill 250 --recompute) so iv_rank has a year; backtest the two strategies; options strategies (selling vol) not executable in cash | data/derivatives.py; quant/derivatives_features.py; strategy_engine/library/70_*,71_* | 2026-10-01 ATM IV: NIFTY 12.4, BANKNIFTY 15.7, RELIANCE 24.2, INFY 37.2 | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 32% of 208 lines in 2 key file(s) run by: test_regressions, test_w39_qa_suite, test_w40_option_intents
210 | 7 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | Pairs research | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 | QR-04 | W30 shortable instrument: paper stock-futures book (near-month, whole lots, margin_pct of notional, EOD futures close + slippage, expiry settlement); SHORT / COVER actions; pairs kind with short_via_futures emits SHORT + long leg; risk engine lot sizing / margin / health gate; OMS FUT routing; LIVE refused; futures.enabled off by default | Independent QA. W40: the W2 backtest simulates SHORT / COVER as near-month stock futures (lots, margin, daily variation margin, NSE F&O costs, a roll N sessions before expiry; refused, never priced off spot, without futures history); the paper book can auto-roll (futures.auto_roll, off by default). Not modelled: physical settlement, SPAN margin | execution/futures_paper.py; backtest/futures.py; backtest/engine.py | tests/test_w40_futures_backtest.py | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-07 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | tests/test_w40_futures_backtest.py ¦ 90% of 1065 lines in 3 key file(s) run by: test_auto_recover, test_risk_controls, test_w39_backtest, test_w39_backtest_partial, test_w39_exec_data_tests, test_w39_perf_budget, test_w39_qa_suite, test_w39_risk_gateway (+7 more)
211 | 7 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | Long-short research | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-08 | W30: portfolio kind with short_via_futures: negative weights on F&O names become SHORT intents (target = ¦weight¦), held shorts dropped from the target are COVERed; neutral books no longer held back when shorts are executable | Independent QA. W40: long/short portfolios backtest with their futures legs (see QR-05); lot granularity still makes small books non-neutral -- check exposure after sizing | strategy_engine/kinds.py | tests/test_w40_futures_backtest.py | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-07 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | tests/test_w40_futures_backtest.py ¦ 66% of 502 lines in 1 key file(s) run by: test_signal_pipeline, test_w39_backtest_partial, test_w39_qa_suite, test_w39_quant_portfolio, test_w39b_event_driven_skips, test_w40_futures_backtest, test_w40_option_intents
212 | 7 | Advanced Quant | QR-09 | Quant Research | Event-driven research | Earnings/CA event studies | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | DP-06 | W30 event sources: EARNINGS (NSE filings, known next day for evening filings, value = profit YoY), DIVIDEND (NSE corporate actions), INSIDER_BUY/SELL (PIT, promoters/directors/KMP), SAST; ev_days_since_earnings/dividend/insider_buy, ev_earnings_growth, ev_insider_net_90d; generic event study (CAR vs NIFTY50 by horizon and direction, pre-event drift, winsorized t-stats, day-0 and data-gap guards); weekly studies | MACRO / INDEX_CHANGE calendars (no free source); earnings history needs the full fundamentals backfill | quant/event_sources.py; quant/event_study.py; quant/events.py; quant/w30.py | Scratch: 1,805 dividends, 36 earnings, 54 SAST; dividend 5d winsorized +0.60% but median -0.07% (skewed, not robust) | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 6 | 11% of 258 lines in 4 key file(s) run by: test_auto_recover, test_signal_pipeline, test_w40_option_intents
213 | 7 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | Piotroski; Altman; value z-composite | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | DP-15 | W30: value / size factors v2 from NSE fundamentals at the factor date's close: earnings_yield (TTM EPS / close, negative for losses), book_to_market, fcf_yield, price_to_sales (TTM revenue), rel_earnings_yield, market_cap, size_log, turnover (filed shares); fundamentals_as_of uses the filing broadcast time; vqm / vqmg composites now have inputs | Full fundamentals backfill (W27-1) then a factor IC study | quant/factors.py | Scratch 2026-10-01: SBIN EY 9.78, BTM 69.8; RELIANCE mcap 15.8 lakh cr | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md | 4 | 68% of 269 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_quant_portfolio, test_w40_risk_model
214 | 7 | Advanced Quant | EX-11 | Execution | Execution algos | TWAP/VWAP/POV | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | DP-03 | W34: execution/algos.py -- TWAP / VWAP (20-session slot volume profile) / POV / ICEBERG parents worked in child oms_orders (algo_parent_id), selected by size vs ADV or value (execution.algo, off), PAPER only; pause on failed child, cancel/resume, execution-quality report vs arrival and interval VWAP; /execution-lab | Independent QA; owner: execution.algo.enabled | execution/algos.py; execution/pipeline.py; dashboard/w34_routes.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 7 | 29% of 466 lines in 3 key file(s) run by: test_auto_recover, test_w40_option_intents
215 | 7 | Advanced Quant | EX-12 | Execution | Market impact model | Impact estimate | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | DP-05 | W34: execution/impact.py -- square-root impact (sigma, median ADV, Corwin-Schultz spread), Y calibrated weekly from LIVE fills only (default 0.7 until 30 fills), pre-trade API; used by algo selection and BT-17 | Independent QA; calibration needs live fills | execution/impact.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 7 | 71% of 101 lines in 1 key file(s) run by: test_w39_backtest_partial, test_w39_performance_detail, test_w39_untested_modules, test_w40_futures_backtest
216 | 7 | Advanced Quant | EX-15 | Execution | Latency telemetry | p50/p95/p99 | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 |  | W34: ops/latency.py -- in-memory samples + metrics histogram, per-minute rollups (p50/p95/p99/max) for data.live_quotes, feed.tick_to_flush, risk.evaluate, order.decision_to_submit, order.submit_adapter, order.submit_to_fill, algo.tick, events.dispatch; /execution-lab chart | Independent QA | ops/latency.py; execution/order_manager.py; data/dhan.py; data/dhan_ws.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 7 | 50% of 1327 lines in 4 key file(s) run by: test_auto_recover, test_corporate_actions, test_fii_dii_and_delivery_factor, test_index_feed, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live (+6 more)
217 | 7 | Advanced Quant | EX-16 | Execution | Event-driven OMS | Event bus signal->risk->order->fill | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | EX-15 | W34: execution/events.py -- transactional outbox (order.state, order.fill, algo.parent published in the same transaction as the change), at-least-once dispatcher with per-handler idempotent delivery, dead letters, replay; handlers for algo progress, submit-to-fill latency, audit line | Independent QA | execution/events.py; execution/event_handlers.py; execution/order_manager.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 7 | 36% of 418 lines in 3 key file(s) run by: test_auto_recover, test_w40_option_intents
218 | 7 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | Event engine shared with live | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | EX-16 | W34: backtest/event_driven.py -- event queue over daily or intraday bars; latency, partial fills vs bar volume, MARKET/LIMIT/STOP, impact-priced fills, TWAP slices, intrabar protective exits; same Strategy interface; stored as kind event_driven. W39b: ADD / REDUCE through the order model (matches the W2 engine leg for leg on a hand-computed case; BUY / SELL-only runs byte-identical); fix: a SELL with nothing left to sell (a max-hold exit queued on the bar a stop fired) was charged costs and a fill, an over-sized SELL was charged on its full size, and a slow max-hold exit was queued again every session | Independent QA. W40: reports the adapter's skipped decisions like W2; fix: the end-of-window close-out is now in the last day's return (chained returns overstated final equity by the close-out costs). It still does not trade SHORT (W2 does, as futures) | backtest/event_driven.py; dashboard/w34_routes.py | tests/test_w39_backtest_partial.py (test_event_driven_*); tests/test_w39b_event_driven_skips.py |  |  | 2026-10-01 |  | 2026-10-07 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 6 | tests/test_w39_backtest_partial.py (test_event_driven_*); tests/test_w39b_event_driven_skips.py ¦ 81% of 568 lines in 2 key file(s) run by: test_auto_recover, test_w39_backtest_partial, test_w39b_cpcv_dominance, test_w39b_event_driven_skips, test_w40_futures_backtest
219 | 7 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | RBI rates; CPI; IIP; yields | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W35: data/macro.py -- 11 series from FRED / World Bank (India CPI, IIP, call rate, 10Y, GDP, inflation; USDINR, US 10Y, Fed funds, US CPI, Brent) with point-in-time available_from (release lags), revisions flagged, vintages in lake; macro_calendar (owner + rule-derived expected CPI dates); MACRO events to market_event | QA; owner: add RBI MPC dates to the calendar | data/macro.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 87% of 137 lines in 1 key file(s) run by: test_w39_exec_data_tests
220 | 7 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | Source abstraction | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W35: altdata/framework.py -- DataSource interface, registry, point-in-time alt_observation (available_from required), health (coverage, staleness), lake copy, panel() for research | QA | altdata/framework.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 82% of 132 lines in 1 key file(s) run by: test_w39_exec_data_tests
221 | 7 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | Web/social/search/etc. | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 | AD-01 | W35: altdata/sources.py -- news_attention and announcement_intensity (internal, on) and wiki_pageviews (Wikimedia, off); research inputs only, not score inputs | QA; IC research before any use | altdata/sources.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 54% of 126 lines in 1 key file(s) run by: test_w39_exec_data_tests
222 | 7 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | Columnar PIT research store | Quant-Research | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 |  | W35: data/lake.py -- partitioned lake (Parquet with pyarrow, else csv.gz), manifest lake_partition with version + knowledge time + sha256; point-in-time read(as_of), archive_table, verify, DuckDB query when installed | Owner: pip install pyarrow duckdb for Parquet + SQL; QA | data/lake.py | — |  |  | 2026-10-01 |  | 2026-10-01 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 2 | 58% of 177 lines in 1 key file(s) run by: test_w39_exec_data_tests, test_w39_ui_smoke, test_w39_untested_modules
223 | 7 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | Commodities; FX; bonds; MF | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 |  | W35: data/multi_asset.py -- AMFI daily NAVs of all MF schemes (mf_nav) + on-demand scheme history; commodities / FX / rates via yfinance (asset_price_daily). MCX / NSE-CDS exchange bhavcopies NOT wired (no verified free endpoint) | QA; MCX/CDS exchange feeds if a source is chosen | data/multi_asset.py | — |  |  | 2026-10-01 |  | 2026-10-07 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check: AMFI mutual-fund NAV ingestion (owner note 'amfi for MF data') is this row -- mf_nav daily at 23:30; MF remains outside the wealth-track mitigation scope (owner Scope Exclusions) | 2 | 27% of 154 lines in 1 key file(s) run by: test_w39_untested_modules
224 | 8 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | Decay alerts | Quant-Research | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | QR-02; ML-09 | W24: model + factor IC decay monitoring with alerts | Needs factor history (W22 backfill) | ml/decay.py | branch w24-ml |  |  | 2026-09-27 |  | 2026-09-27 |  | 1 | 12% of 81 lines in 1 key file(s) run by: test_auto_recover
225 | 8 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | DR plan | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 90 | DBS-03 | W31: encrypted off-site copy of each VERIFIED backup (AES-256-GCM, 4 MiB authenticated chunks, sha256 sidecar, re-hashed at destination, retention 14; never plaintext off-site without an explicit flag); weekly restore drill (newest backup, from the off-site encrypted copy when present: decrypt, integrity, row counts vs backup time, timed, recorded, alert on failure); decrypt-backup CLI | Owner: set ops.backup_offsite_dir (second drive / NAS / synced folder) and keep the data key outside it | ops/backup.py; ops/__main__.py; docs/DISASTER_RECOVERY.md | Scratch: 100 MB backup encrypted + copied; drill PASSED from the encrypted copy in 3.2 s; 1-byte tamper -> InvalidTag | Owner (offsite dir) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 59% of 483 lines in 2 key file(s) run by: test_w39_ops_tests, test_w39_qa_suite
226 | 8 | Production Hardening | SEC-04 | Security | Encryption | TLS 1.3; AES-256 at rest (SRS) | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W31: encrypted credential vault (atip_data/secrets/vault.json, AES-GCM with per-name context) consulted by ops/secrets before legacy config; vault-migrate (dry run / apply with verified copy and config backup) blanks config.json secrets; legacy readers (Dhan, Kite, Telegram) fall back to the vault; key rotation re-encrypts MFA secrets + vault under a new key, old key kept as .previous (still readable, incl. old encrypted backups); refuses when the key comes from env/.env | Owner: python -m ops keygen + vault-migrate --apply; TLS only with ENT-07 (exposure blocked) | ops/vault.py; ops/crypto.py; ops/secrets.py; data/dhan.py; portfolio/zerodha.py; alerts/telegram.py | Scratch: migrate -> config blanked -> load_dhan_config from vault; rotate 73b87072 -> 1d5a5573, vault + old backup still decrypt | Owner / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 47% of 1469 lines in 6 key file(s) run by: test_auto_recover, test_corporate_actions, test_job_monitoring, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w37_brokers_multi_asset (+12 more)
227 | 8 | Production Hardening | API-05 | APIs | API contracts/docs | Documented contracts | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 100 |  | W31: python -m ops api-docs (openapi.json + API_REFERENCE.md, 362 routes with permissions). W39: every public v1 resource has a typed response schema (openapi-v1.json) checked against the real handlers by a contract test; error bodies (incl. 422) use the envelope | Independent QA. Per-route schemas for the internal dashboard routes are not planned: /api/v1 is the published contract | ops/api_docs.py; docs/API_REFERENCE.md; docs/openapi.json | tests/test_w39_api_contract.py | Claude (dev) |  | 2026-09-25 |  | 2026-10-07 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 9+ (Enterprise SaaS) | tests/test_w39_api_contract.py ¦ 91% of 99 lines in 1 key file(s) run by: test_w39_ops_tests
228 | 8 | Production Hardening | API-06 | APIs | Widget JSON schemas | QRH deliverable | Agreed-Spec | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W36: dashboard/widget_schemas.py + dashboard/schemas/*.json -- 16 widget JSON Schemas, dependency-free validator, /api/schemas catalogue + live check-all | QA; extend as widgets change | dashboard/widget_schemas.py; dashboard/schemas/ | — |  |  | 2026-10-02 |  | 2026-10-02 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_STRATEGY_TOOLING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 9+ (Enterprise SaaS) | 59% of 79 lines in 1 key file(s) run by: test_w36_ml_strategy_tooling
229 | 8 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | BRD..OPS documents with real content | Agreed-Spec | P1 | IMPLEMENTED BUT NOT VERIFIED | N/A | 90 |  | W31: docs/USER_GUIDE.md (start/stop, the trading-day schedule, every page, every W27-W31 switch, routine tasks, troubleshooting, what ATIP will not do); generated API reference; DR + rollback docs updated (off-site, drills, the PS scripts' kill-all-main.py caveat) | Refresh after W32/W33 | docs/USER_GUIDE.md; docs/API_REFERENCE.md; docs/DISASTER_RECOVERY.md; docs/ROLLBACK_PROCEDURE.md | Docs written | Claude (dev) |  | 2026-09-25 |  | 2026-10-01 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | no code file listed
230 | 9 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | Per-user data isolation; tenant model | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | OPS-05 | W9 merged in W32: per-tenant paper books + TenantPaperAdapter routing, tenant risk on own book, 186/186 tables classified (W10-W31 tables added), single-resource 404 + list filtering | QA isolation scenarios (W32 handoff); Postgres (DBS-05) | enterprise/scoping.py; execution/tenant_books.py; execution/adapters.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) | 51% of 403 lines in 3 key file(s) run by: test_auto_recover, test_w37_brokers_multi_asset, test_w39_api_contract, test_w39_depth20, test_w39_risk_gateway, test_w40_option_intents
231 | 9 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | PostgreSQL/time-series (SRS) | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 70 | ENT-01 | W38: db/postgres.py translator (placeholders, OR IGNORE/REPLACE on the covered unique key, qualified upserts, date(), GROUP_CONCAT, GREATEST/LEAST, ILIKE, SUM(bool), rowid->ctid tie-breaks, sqlite_master/PRAGMA via information_schema) + PgConnection; AST dialect scan 99.7% of 1,327 statements; tools/sqlite_to_postgres.py upgrades the copy, migrates schema/triggers/data, resets identities, verifies. Proven on PostgreSQL 16 with a live-DB copy: 213 tables / 497,317 rows identical, 198 GET routes 0 server errors. Opt-in runtime switch (ATIP_DATABASE_URL + database.backend + allow_experimental) | Run the scheduler's write jobs for a few days on a PostgreSQL copy; connection pool; then decide the switch | db/postgres.py; db/dialect_scan.py; db/backend.py; tools/sqlite_to_postgres.py; docs/POSTGRESQL_MIGRATION.md | SRS 2 |  |  | 2026-10-02 |  | 2026-10-02 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMPLIANCE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 1 | 69% of 531 lines in 4 key file(s) run by: test_mysql_backend, test_postgres_backend, test_w36_ml_strategy_tooling, test_w38_platform_compliance, test_w39_perf_budget, test_w39b_razorpay
232 | 9 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure | TLS; WAF; rate limits; zero trust | Enterprise-SaaS | P0 | BLOCKED | BLOCKED | 5 | ENT-01 | Not implemented by design: W7 keeps the 127.0.0.1 bind; exposure needs TLS, MFA, rate limiting, security review | Owner decision + security architecture | dashboard/security.py | SRS 5 | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) |  | Owner decision: how ATIP is exposed to the internet (Cloudflare Tunnel / Tailscale / VPS reverse proxy), the domain and TLS
233 | 9 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | FR-AU-001/002; RBAC | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 90 | ENT-07 | Users/RBAC/TOTP MFA + W32 one-time recovery codes (sha256 digests, login fallback, TOTP needed to generate) | WebAuthn after ENT-07 (HTTPS origin) | enterprise/w32.py; enterprise/mfa.py; enterprise/users.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 26% of 520 lines in 3 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_exec_data_tests, test_w39_perf_budget, test_w39_risk_gateway, test_w39b_mf_analytics, test_w39b_razorpay
234 | 9 | Enterprise SaaS (final objective) | ENT-05 | Security | Session management | Timeout; refresh tokens; revocation (FR-AU-003) | Enterprise-SaaS | P0 | COMPLETED | IN PROGRESS | 90 | SEC-02 | Sessions (digest-only, expiry, revoke) + W8 refresh tokens: rotation on every use, reuse detection revokes the family and all sessions, HttpOnly cookie scoped to /api/auth/refresh | Validate | enterprise/users.py; dashboard/enterprise_routes.py | SRS Part III | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 9+ (Enterprise SaaS) | 32% of 673 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_exec_data_tests, test_w39b_mf_analytics, test_w39b_razorpay
235 | 9 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | Email; mobile; OAuth; Google; Apple (FR-UM-001) | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | SEC-02 | Self-registration, activation, consent, e-mail verification (generic SMTP, sandbox outbox when unset), onboarding checklist + tenant paper account | OAuth / Google / Apple / mobile OTP (need ENT-07) | enterprise/onboarding.py; enterprise/email_flows.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) | 22% of 87 lines in 2 key file(s) run by: test_auto_recover
236 | 9 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | FR-UM-002 | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | ENT-02 | Profiles + W32 per-user/tenant capital accounting: risk check profile_max_capital caps BUYs by remaining max_capital (open positions of the tenant's / user's strategies); strategies owned by the creating user | QA | enterprise/w32.py; execution/risk_engine.py; enterprise/profiles.py | W32 smoke: capped at 48 sh by Rs 50,000 | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) | 47% of 762 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_risk_gateway, test_w39b_razorpay, test_w40_option_intents
237 | 9 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | Broker OAuth; encrypted per-user tokens | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | SEC-02 | W9 vault foundation completed (W37): expiry per broker (daily tokens), credentials_for() as the single audited way connectors obtain a credential (owner falls back to existing Dhan / Zerodha config), read-only verify(), expiring() + daily reminder, key rotation now re-encrypts per-user broker credentials | QA; owner stores real credentials on /account and runs verify | enterprise/vault.py; ops/crypto.py; dashboard/w37_routes.py | — | Claude (development) |  | 2026-10-02 |  | 2026-10-02 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKERS_MULTI_ASSET_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 9+ (Enterprise SaaS) | 49% of 380 lines in 3 key file(s) run by: test_auto_recover, test_w37_brokers_multi_asset, test_w38_platform_compliance, test_w39_ops_tests
238 | 9 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | SEBI retail algo framework (broker/exchange algo approval); RA/IA registration if advice is offered | Enterprise-SaaS | P0 | BLOCKED | BLOCKED | 30 |  | W38: regulatory sign-off register (10 items: SEBI RA/IA, retail algo framework, broker API terms, NSE data redistribution, DPDP, CERT-In, terms, payments/GST, live-risk sign-off, annual review) gated pre_multi_user / pre_live / ongoing; sign-off needs reviewer + reference, audited; compliance check fails if a gate is crossed with open items; docs/ENT14_REGULATORY_PACK.md | LEGAL WORK: a qualified professional must review and sign off each item | ops/regulatory.py; docs/ENT14_REGULATORY_PACK.md | BRD-006 |  |  | 2026-10-02 |  | 2026-10-07 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMPLIANCE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 9+ (Enterprise SaaS) |  | Legal: a qualified professional must review and sign off each register item (SEBI RA / IA applicability)
239 | 9 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | FR-AT-002 | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | ENT-14 | W38: ops/compliance.py -- 14 daily checks (audit chain, live gate, algo order controls, exposure, admin MFA, plaintext secrets, encryption key, rotation, backup recency, restore drill, retention purge, DSR SLA, data inventory, regulatory gates) stored per run with evidence, alert when a check worsens, /compliance page, 07:50 job | Owner: act on the first run's findings (risk_limits unset, 7 plaintext secrets, no encryption key, no restore drill); QA | ops/compliance.py; dashboard/w38_routes.py; dashboard/w38_page.py | SRS Part III |  |  | 2026-10-02 |  | 2026-10-02 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMPLIANCE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 1 | 77% of 359 lines in 3 key file(s) run by: test_auto_recover, test_w38_platform_compliance, test_w39_perf_budget, test_w39_ui_smoke
240 | 9 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | DPDP Act; consent; retention | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | ENT-14 | W38: whole database classified (explicit + rules, gaps flagged), DSR response SLA (due date, overdue, daily reminders), privacy notice generated from the inventory at /privacy (DRAFT until saas.privacy_policy_approved), inventory + DSR tabs on /compliance; W9 consent / export / delete unchanged | Legal review of the notice (ENT-14 DPDP item); fill saas.company_name / privacy_contact / grievance_officer | enterprise/privacy.py; dashboard/w38_page.py | BRD-004 |  |  | 2026-10-02 |  | 2026-10-02 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMPLIANCE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 9+ (Enterprise SaaS) | 48% of 231 lines in 2 key file(s) run by: test_auto_recover, test_w38_platform_compliance, test_w39_depth20, test_w39_event_calendar, test_w39_global_sync, test_w39_intraday, test_w39_market_pulse, test_w39_perf_budget (+10 more)
241 | 9 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | Web UI for all users | Enterprise-SaaS | P0 | BLOCKED | BLOCKED | 65 | SEC-02 | /app user web app + /admin/console (W32), local-only | Blocked on ENT-07 for any exposure | dashboard/saas_page.py; dashboard/saas_routes.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) |  | Depends on ENT-07 (no exposure decided)
242 | 9 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | Free/Premium/Enterprise (FR-UM-003) | Enterprise-SaaS | P1 | BLOCKED | BLOCKED | 90 | ENT-02 | Plans, subscriptions, invoices DRAFT/OPEN/PAID, provider interface (sandbox/noop), dunning + grace, payment webhook consumer. W39b (gateway decision delegated: Razorpay -- UPI / cards / netbanking, native Subscriptions): enterprise/razorpay.py on the existing payments interface -- REST v1 invoices with idempotent receipts, customers, plans, autopay subscriptions, cancel; signed webhook mapping onto invoices, payments, refunds, dunning and grace (out-of-order safe, money once per Razorpay id); reconcile() polling so payments settle without a public webhook; keys only from the vault; live keys refused without billing.razorpay.allow_live and the production environment | Owner: run the flows in Razorpay test mode (docs/BILLING_RAZORPAY.md); GST tax lines are not built (ENT-14 PAYMENTS-TAX) | enterprise/payments.py; enterprise/razorpay.py; enterprise/billing.py; enterprise/w32.py; db/schema_billing.py | tests/test_w39b_razorpay.py (26 tests on recorded Razorpay v1 response shapes) | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) |  | Owner: a KYC-activated Razorpay business account with Invoices and Subscriptions enabled; store RAZORPAY_KEY_ID / RAZORPAY_KEY_SECRET / WEBHOOK_SECRET_RAZORPAY with python -m ops vault-set; registering the webhook URL needs ENT-07 (public HTTPS)
243 | 9 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | FR-UM-004 | Enterprise-SaaS | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | ENT-05 | Concurrent sessions with IP/user agent; list + revoke one / all (API + /app) | QA | enterprise/users.py; dashboard/saas_routes.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) | 40% of 612 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_exec_data_tests, test_w39b_mf_analytics, test_w39b_razorpay
244 | 9 | Enterprise SaaS (final objective) | ENT-19 | Channels | Watchlists | BR-006 | Enterprise-SaaS | P1 | COMPLETED | IN PROGRESS | 75 | ENT-08 | Per-user / shared watchlists | Validate | enterprise/workspace.py | BRD-004 | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-10-07 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md ¦ W39 check: watchlists exist (Zerodha / Dhan parity); live quotes beside them are not shown | 9+ (Enterprise SaaS) | 58% of 108 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_perf_budget
245 | 9 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | FR-AL-001/002 | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | ENT-19 | Post-market evaluation on any feature + W32 intraday evaluation on live quotes (close/ltp/change_pct/volume, <=20 min old, once a day) every 15 min | QA | enterprise/w32.py; enterprise/workspace.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md ¦ W39 check: ad-hoc intraday price alerts (Zerodha / Dhan parity) are covered here (W32 evaluate_alerts_intraday every 15 min) | 9+ (Enterprise SaaS) | 47% of 278 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_perf_budget, test_w39_risk_gateway, test_w39b_razorpay
246 | 9 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | Push; SMS; email; WhatsApp; in-app (FR-AL-003) | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | ENT-11 | In-app, e-mail (SMTP), Telegram, webhook channels; preferences, quiet hours, digest, unsubscribe; scheduled delivery jobs | SMS / push / WhatsApp (providers: owner) | enterprise/channels.py; pipeline/scheduler.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) | 33% of 1437 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_notify_transactions, test_w39_qa_suite, test_w39_ui_smoke (+2 more)
247 | 9 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | Android + iOS | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 45 | API-03 | W38: installable mobile web app (PWA) at /m -- read-only phone summary (market health, Nifty/VIX, global, buy/sell, trade of the day, P&L, pipeline, alerts), manifest + service worker (shell cached, no API data cached), offline last-good view; no token in the page | Native Android/iOS apps not built; reaching /m from a phone needs a private tunnel or the ENT-07 exposure | dashboard/w38_page.py; dashboard/w38_routes.py | SRS 2 |  |  | 2026-10-02 |  | 2026-10-07 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMPLIANCE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 9+ (Enterprise SaaS) | 77% of 138 lines in 2 key file(s) run by: test_auto_recover, test_w38_platform_compliance, test_w39_perf_budget, test_w39_ui_smoke | Native apps: Apple / Google developer accounts and an exposure decision (ENT-07); the PWA (/m) works today on a private network
248 | 9 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | FR-API-001/003 | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 | SEC-02 | API keys with scopes + per-key limits; /api/v1 alias; v1 OpenAPI contract written by python -m ops api-docs; W39: deprecation policy (docs/API_VERSIONING_POLICY.md) enforced by a registry -- Deprecation / Sunset / Link headers, deprecated in OpenAPI, 410 GONE after sunset, >= 180 days notice validated | Independent QA | enterprise/public_api.py; ops/http.py; ops/__main__.py; docs/API_VERSIONING_POLICY.md | test_a_deprecated_v1_resource_warns_then_answers_410_after_sunset | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 9+ (Enterprise SaaS) | test_a_deprecated_v1_resource_warns_then_answers_410_after_sunset ¦ 59% of 657 lines in 3 key file(s) run by: test_auto_recover, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20, test_w39_event_calendar, test_w39_exec_data_tests, test_w39_global_sync (+34 more)
249 | 9 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | FR-API-002 | Enterprise-SaaS | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | API-03 | Signed inbound/outbound webhooks + W32 business consumers (payments, broker order.update), event status PROCESSED/IGNORED/FAILED. W39b: the Razorpay provider payloads are mapped (POST /api/webhooks/razorpay: X-Razorpay-Signature HMAC-SHA256 of the raw body, event-id and body-digest dedupe, 72 h replay bound, REJECTED rows for bad signatures) | Independent QA; verify against real Razorpay test-mode deliveries once ENT-07 gives ATIP a public URL; a broker postback mapping when a broker offers one | enterprise/w32.py; enterprise/razorpay.py; ops/webhooks.py; dashboard/ops_routes.py | tests/test_w39b_razorpay.py | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 9+ (Enterprise SaaS) | tests/test_w39b_razorpay.py ¦ 70% of 1134 lines in 4 key file(s) run by: test_auto_recover, test_w39_ops_tests, test_w39_perf_budget, test_w39_risk_gateway, test_w39b_razorpay
250 | 9 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | Angel/Groww/Upstox/CSV (FR-PO-002) | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | ENT-06 | W37: portfolio/imports.py -- CSV tradebook / holdings import from Zerodha, Upstox, Groww, ICICI Direct, Angel or any CSV (column aliases, ISIN / name -> symbol via the NSE bhavcopy), idempotent into the wealth ledger (import:<broker>), holdings open once, Dhan double-count guard, API import via BR-07; /brokers Import tab | QA with the owner's real broker exports | portfolio/imports.py; dashboard/w37_page.py | SRS Part III |  |  | 2026-10-02 |  | 2026-10-07 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKERS_MULTI_ASSET_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master ¦ W39 (PERF-001-06): contract-note charge columns stored per trade as fee_breakdown; a charges-only file becomes FEE rows (tests/test_w39_contract_note_fees.py) | 8 | 80% of 220 lines in 2 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees
251 | 9 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | Angel/Upstox/Groww trading | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 75 | ENT-06; BR-03 | W37: brokers/ package -- read-only connectors for Dhan (dhanhq), Zerodha (kiteconnect), Upstox (REST v2), Angel One (SmartAPI REST + TOTP) normalised to Holding / Position / Trade; LIVE order adapters map the OMS order to each broker's payload and REFUSE to send (LIVE not built); consolidated holdings | QA against real accounts (read-only); live orders need owner + ENT-14 decision | brokers/base.py; brokers/connectors.py; brokers/registry.py | SRS Part III |  |  | 2026-10-02 |  | 2026-10-02 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKERS_MULTI_ASSET_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 7 | 55% of 278 lines in 3 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees
252 | 9 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | MF; bonds; commodities; currency (FR-PO-003) | Enterprise-SaaS | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 | DP-21; BR-07 | W37: execution/options_paper.py paper options book (long premium only, whole lots, premium caps, expiry rules, chain or EOD pricing, intrinsic settlement) + execution/assets.py asset-class registry (EQUITY / ETF / FUTURE / OPTION tradable on paper; COMMODITY / CURRENCY / BOND explicitly research-only) | Owner: options.enabled; QA. W40: option-overlay strategies (strategy_engine/option_overlay.py) emit multi-leg OPTION intents -- covered call, protective put, spreads, iron condor and more, strikes by delta or % OTM, monthly expiry -- sized by the risk engine (max loss, margin approximation, naked short calls refused unless allowed), filled all-or-nothing in the paper options book, marked daily, exited by rule, settled at expiry; PAPER only, LIVE refused; a replay on stored daily option prices | execution/options_paper.py; execution/option_intents.py; strategy_engine/option_overlay.py | tests/test_w40_option_intents.py; docs/W40_OPTION_INTENTS_HANDOFF.md |  |  | 2026-10-02 |  | 2026-10-07 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKERS_MULTI_ASSET_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 9+ (Enterprise SaaS) | tests/test_w40_option_intents.py; docs/W40_OPTION_INTENTS_HANDOFF.md ¦ 84% of 1203 lines in 3 key file(s) run by: test_signal_pipeline, test_w37_brokers_multi_asset, test_w39_exec_data_tests, test_w40_option_intents
253 | 9 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | Portfolio; tax; AI performance (FR-RP) | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 70 | PF-13 | Report rendering/export (HTML, CSV), schedules, stored outputs, daily run | Independent QA. Tax report content is NOT built: Tax is excluded by the owner (deployment tracker, Scope Exclusions sheet); revisit only if the owner re-scopes it | enterprise/reports.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md ¦ W39 check: the remaining gap (tax report) is owner-excluded scope, not open work; W39 adds the printable performance report (PERF-001-13) | 9+ (Enterprise SaaS) | 40% of 135 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract
254 | 9 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | User admin; system config (FR-AD) | Enterprise-SaaS | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 80 | SEC-02 | /admin + /admin/console: tenants, onboarding, payments, dunning/billing runs, privacy decisions, API-key limits, isolation report | QA | dashboard/saas_routes.py; dashboard/saas_page.py | W32 smoke (scratch) | Claude (development) |  | 2026-09-25 |  | 2026-10-01 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md | 9+ (Enterprise SaaS) | 49% of 356 lines in 2 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39b_razorpay
255 | 9 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | FR-SB-001/002 | Enterprise-SaaS | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | SE-01; ENT-08 | W36: strategy_engine/builder.py + /strategy-builder -- form -> validated W3 rule definition (thresholds become bounded parameters), today's-match preview, save as DRAFT through the normal lifecycle | QA; backtest builder strategies before promotion | strategy_engine/builder.py; dashboard/strategy_builder_page.py | SRS Part III |  |  | 2026-10-02 |  | 2026-10-02 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_STRATEGY_TOOLING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 5 | 56% of 138 lines in 2 key file(s) run by: test_w36_ml_strategy_tooling
256 | 9 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | NL assistant (SRS) | Enterprise-SaaS | P2 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 | ENT-08 | W36: ml/chat.py + /assistant page -- Claude tool-use loop over 7 read-only tools (market, stock, lists, portfolio, news, score history, symbol search), own daily cost cap, ai_usage_log, server-side refusal fallback, conversations stored; rule-based fallback when off | Owner: assistant.enabled + working ANTHROPIC_API_KEY; QA | ml/chat.py; dashboard/assistant_page.py; dashboard/w36_routes.py | SRS 3 |  |  | 2026-10-02 |  | 2026-10-02 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_STRATEGY_TOOLING_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 4 | 37% of 318 lines in 3 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling
257 | 9 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | Docker/Kubernetes on cloud (SRS) | Enterprise-SaaS | P0 | IMPLEMENTED BUT NOT VERIFIED | N/A | 75 | DBS-05; ENT-07 | W38: Dockerfile (IST, non-root, volume, healthcheck), docker-compose (127.0.0.1-only ports, optional postgres profile), deploy/atip.env.example, cloud-init VM. W39b: the image is BUILT and smoke-tested (dev container + .github/workflows/docker.yml on every PR): --init on an empty volume, /health/live and /health/ready 200, uid 10001, IST, no state / .git / .claude in the image, live_gate() closed; BASE_IMAGE build arg for registry mirrors; .dockerignore fix (local agent worktrees had added 75 MB) | Owner: choose a host (ENT-16) and exposure (ENT-07); Kubernetes manifests and a registry push only after that | Dockerfile; docker-compose.yml; .dockerignore; .github/workflows/docker.yml; docs/CONTAINER_DEPLOYMENT.md | .github/workflows/docker.yml; docs/CONTAINER_DEPLOYMENT.md (Status) |  |  | 2026-10-02 |  | 2026-10-07 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMPLIANCE_HANDOFF.md ¦ W39 check 2026-10-07: commit is an ancestor of master | 1 | no code file listed
258 | 9 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | 99.9%+ availability; horizontal scale; metrics/tracing | Enterprise-SaaS | P1 | BLOCKED | BLOCKED | 50 | OPS-04 | Observability (W8) + shared state, job leader lease, DB backend abstraction, sqlite->postgres tool (W9 merge) | DBS-05 (PostgreSQL path) and OPS-04 (container packaging) are done (W38); multi-instance HA needs the runtime moved to PostgreSQL and a host | ops/shared_state.py; ops/jobs.py; db/backend.py | W32 merge | Claude (development) |  | 2026-09-25 |  | 2026-10-07 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 9+ (Enterprise SaaS) |  | Owner decision: switch the production runtime to PostgreSQL and choose a cloud host (OPS-04 packaging is ready)
259 | 8 | Production hardening | SEC-06 | Security | API security hardening | Rate limit, size limits, JSON validation, security headers, CORS policy | W8 brief | P1 | COMPLETED | COMPLETED | 80 |  | OpsMiddleware: 2 MB limit (413), JSON content-type/parse checks (415/400), optional token-bucket rate limit (429), nosniff/DENY/no-referrer/COOP/Permissions-Policy, no-store on auth/account/admin, HSTS only with TLS, CORS only when origins configured | Enable rate limiting in production config | ops/http.py |  | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 71% of 254 lines in 1 key file(s) run by: test_auto_recover, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20, test_w39_event_calendar, test_w39_exec_data_tests, test_w39_global_sync (+34 more)
260 | 8 | Production hardening | OPS-08 | Deployment/Ops | Configuration management | Environments, validation, overrides, versioning | W8 brief | P1 | COMPLETED | IN PROGRESS | 80 |  | ATIP_ENV / environment (development/test/staging/production), config.<env>.json overlay, ATIP__SECTION__KEY overrides, validation (production refuses to start on errors), fingerprint + ops_config_version + audit of changed keys, feature flags | Validate | ops/config.py; ops/startup.py |  | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 53% of 232 lines in 2 key file(s) run by: test_auto_recover, test_regressions, test_risk_controls, test_w38_platform_compliance, test_w39_api_contract, test_w39_backtest, test_w39_delivery, test_w39_depth20 (+37 more)
261 | 8 | Production hardening | OPS-09 | Deployment/Ops | Scheduler hardening | Locks, heartbeat, duplicate-job prevention | W8 brief | P1 | COMPLETED | IN PROGRESS | 80 |  | ops_job_lock per job name (stale-owner takeover), scheduler heartbeat every 60 s, SKIPPED run when another runner holds the job, job metrics | Validate | ops/jobs.py; pipeline/scheduler.py |  | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 35% of 1357 lines in 2 key file(s) run by: test_auto_recover, test_fii_dii_and_delivery_factor, test_job_monitoring, test_signal_pipeline, test_w39_history, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget (+4 more)
262 | 8 | Production hardening | OPS-10 | Deployment/Ops | Resilience + idempotency | Timeouts, retry/backoff, circuit breakers, idempotent orders/webhooks | W8 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 85 |  | W31: circuit breakers on every Dhan market-data call (dhan_data, 6 failures / 120 s), NSE client (nse, 8 / 180 s, fails fast to None), yfinance (retry x3 + breaker), each news feed (breaker per feed); breaker states already in /health/broker and metrics; orders never retried | Observe breaker behaviour in a real outage | data/dhan.py; data/nse_api.py; data/markets.py; data/news.py | Compile; NSE / F&O fetches still work through the breaker in scratch runs | Claude (dev) / ChatGPT (QA) |  | 2026-09-25 |  | 2026-10-01 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 31% of 1132 lines in 4 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions, test_w39_risk_gateway (+2 more)
263 | 8 | Production hardening | MON-09 | Monitoring | Operational alerting | Rules for db, data, scheduler, jobs, errors, auth, orders, disk, backup, live gate | W8 brief | P1 | COMPLETED | COMPLETED | 75 |  | ops_monitor every 15 min, 12 rules, FIRING/RESOLVED state with 6 h re-notify, delivered via the W1 alert channel (alert_log + Telegram when configured) | Tune thresholds after observation | ops/monitor.py |  | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 1 | 94% of 132 lines in 1 key file(s) run by: test_w39_ops_tests
264 | 8 | Production hardening | RK-19 | Risk | Stale-data trade protection | No BUY on stale market data; live session validation | W8 brief | P1 | COMPLETED | IN PROGRESS | 80 |  | Risk check market_data_fresh (BUY rejected when last bar > 2 sessions behind); LIVE orders validated against the NSE session; live gate additionally requires environment production | Validate | execution/risk_engine.py; execution/order_manager.py; execution/config.py |  | Claude (development) |  | 2026-09-25 | 2026-09-25 | 2026-09-25 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md | 7 | 51% of 896 lines in 3 key file(s) run by: test_auto_recover, test_w38_platform_compliance, test_w39_exec_data_tests, test_w39_ops_tests, test_w39_perf_budget, test_w39_qa_suite, test_w39_risk_gateway, test_w39_ui_smoke (+1 more)
265 | 8 | Production hardening | OPS-11 | Deployment/Ops | Release management & deployment | Release candidate, preflight, manifest, deploy/rollback procedure, health verification | W9 brief | P0 | IMPLEMENTED BUT NOT VERIFIED | IN PROGRESS | 90 |  | W31: executed rollback drill (python -m ops rollback-drill) on a scratch clone: verified-backup DB, dashboard-only on 8078, postcheck, timed rollback (stop own PID, git reset to tag, DB re-restore, start, postcheck), recorded; ATIP_INSTANCE_NAME for drill isolation; documented that the PS deploy/rollback scripts stop every main.py on the machine | Owner-authorized production deployment of W25-W33 (not done by development) | ops/rollback_drill.py; main.py; docs/ROLLBACK_PROCEDURE.md | Drill PASSED HEAD (W30) -> ATIP-W24-RC1, RTO 47.6 s; production PID 115268 untouched | Owner (deployment) / Claude (dev) |  | 2026-09-26 |  | 2026-10-01 | W9 (final release) developed 2026-09-26 -- release engineering only; NOT DEPLOYED (owner authorization required); independent testing PENDING; see docs/W9_FINAL_RELEASE.md | 1 | 18% of 387 lines in 2 key file(s) run by: test_w39_qa_suite
266 | 8 | Production hardening | RK-20 | Risk | Unified live-trading master switch | LIVE_TRADING_ENABLED enforced on every order path | W9 brief | P0 | COMPLETED | COMPLETED | 90 |  | W1 real orders (order rules, aggressive strategy) also require execution.live_trading_enabled + environment production (BLOCKED_LIVE_DISABLED otherwise); W4 gate + Dhan adapter refusal unchanged | Validate | orders/broker.py; ops/trading_safety.py |  | Claude (development) |  | 2026-09-26 | 2026-09-26 | 2026-09-26 | W9 (final release) developed 2026-09-26 -- release engineering only; NOT DEPLOYED (owner authorization required); independent testing PENDING; see docs/W9_FINAL_RELEASE.md | 7 | 65% of 221 lines in 2 key file(s) run by: test_auto_recover, test_risk_controls, test_strategy_live, test_w38_platform_compliance, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget, test_w39_qa_suite (+1 more)
267 | 10 | Wealth track (Waves 11-20) | INV-001 | Wealth | Investor DNA | Risk capacity / tolerance / requirement, horizon, behaviour, personality | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W11: Risk capacity / tolerance / requirement, horizon, behaviour, personality | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/dna.py | commit 1da609f; docs/W11* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 11 | 75% of 207 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_perf_budget, test_w39_ui_smoke, test_wealth_api_security, test_wealth_dna_holdings, test_wealth_planning
268 | 10 | Wealth track (Waves 11-20) | WLT-001 | Wealth | Multi-asset wealth dashboard | Unified holdings, net worth, allocation, concentration, overlay | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | INV-001 | W12: Unified holdings, net worth, allocation, concentration, overlay | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/holdings.py; wealth/assets.py | commit 45f0b4b; docs/W12* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 12 | 77% of 373 lines in 2 key file(s) run by: test_w39_notify_transactions, test_w39_perf_budget, test_w39_performance_detail, test_w39_ui_smoke, test_wealth_api_security, test_wealth_dna_holdings, test_wealth_performance, test_wealth_planning
269 | 10 | Wealth track (Waves 11-20) | GOL-001 | Wealth | Goal planning engine | Corpus, contributions, CAGR, shortfall, Monte Carlo, scenarios | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | INV-001; WLT-001 | W13: Corpus, contributions, CAGR, shortfall, Monte Carlo, scenarios | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/goals.py | commit 9680ee6; docs/W13* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 13 | 77% of 324 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_perf_budget, test_w39_ui_smoke, test_wealth_api_security, test_wealth_dna_holdings, test_wealth_math, test_wealth_planning
270 | 10 | Wealth track (Waves 11-20) | AAL-001 | Wealth | Dynamic asset allocation | Strategic + tactical from DNA, goals, regime, ATIP signals | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | INV-001; GOL-001 | W14: Strategic + tactical from DNA, goals, regime, ATIP signals | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/allocation.py | commit c790b95; docs/W14* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 14 | 83% of 347 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_perf_budget, test_w39_ui_smoke, test_wealth_api_security, test_wealth_math, test_wealth_planning
271 | 10 | Wealth track (Waves 11-20) | RBL-001 | Wealth | Portfolio rebalancing | Drift, triggers, cost-aware plans (tax-neutral) | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | WLT-001; AAL-001 | W15: Drift, triggers, cost-aware plans (tax-neutral) | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/rebalance.py | commit 643ad57; docs/W15* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 15 | 87% of 239 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_perf_budget, test_w39_ui_smoke, test_wealth_api_security, test_wealth_planning
272 | 10 | Wealth track (Waves 11-20) | PERF-001 | Wealth | Investor performance attribution | Model / executable / actual / benchmark; attribution; audit; export | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 | RBL-001 | W15.5 + W39 (PERF-001-01..14 detail gaps closed: see the PERF-001-xx rows) | Independent QA + owner UAT | wealth/perf/ | commit 8210de6; docs/W15.5* handoff |  |  | 2026-09-26 |  | 2026-10-07 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 15.5 | 90% of 1207 lines in 6 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_mcp, test_w39_notify_transactions, test_w39_performance_detail, test_w39b_mf_analytics, test_w40_total_return, test_wealth_api_security (+3 more)
273 | 10 | Wealth track (Waves 11-20) | AIA-001 | Wealth | AI investment advisor | Evidence-backed, suitability-checked; optional Claude narration | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | PERF-001 | W16: Evidence-backed, suitability-checked; optional Claude narration | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/advisor.py | commit 4340cc8; docs/W16* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 16 | 68% of 313 lines in 1 key file(s) run by: test_w39_perf_budget, test_w39_ui_smoke, test_wealth_api_security, test_wealth_planning
274 | 10 | Wealth track (Waves 11-20) | INT-001 | Wealth | Integrated intelligence | Investor cycle, overview, modes, signal suitability | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | AIA-001 | W17: Investor cycle, overview, modes, signal suitability | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/integrated.py | commit 8346d8d; docs/W17* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 17 | 81% of 245 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_perf_budget, test_w39_ui_smoke, test_wealth_api_security, test_wealth_planning
275 | 10 | Wealth track (Waves 11-20) | QA-001 | Wealth | Wealth QA / security / performance | 70-test suite, security review (S1/S2 fixed), performance | ATIP Waves 11-20 brief | P1 | IN PROGRESS | COMPLETED | 85 | INT-001 | W18: 70-test wealth suite, security review, performance. W33: static security review. W39: load / latency tool (tools/load_test.py, in-process or against a running dashboard, targets from W18 / W33), Playwright browser smoke tests of every page and tab, QA suite for untested modules; measured p95 145-184 ms over HTTP at 4-8 threads, 0 errors (docs/W39_QA_PERFORMANCE.md) | Independent testing (ChatGPT) per W33 handoff; the development suite now runs 820+ tests green (W39); run tools/load_test.py against the production machine | docs/W33_QA_UAT_HANDOFF.md; tests/test_wealth_*.py; enterprise/authz.py; dashboard/enterprise_page.py | W33 handoff; branch w33-wealth-qa |  |  | 2026-09-26 |  | 2026-10-07 | RC line = w33-wealth-qa (W11-W32); merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 18 | 75% of 204 lines in 2 key file(s) run by: test_auto_recover, test_risk_controls, test_w39_api_contract, test_w39_backtest, test_w39_depth20, test_w39_event_calendar, test_w39_exec_data_tests, test_w39_global_sync (+34 more)
276 | 10 | Wealth track (Waves 11-20) | UAT-001 | Wealth | Beta / UAT | Personas, persona view, feedback, UAT plan | ATIP Waves 11-20 brief | P1 | BLOCKED | BLOCKED | 70 | QA-001 | W19 personas, persona view, feedback, UAT plan + W33 SaaS personas (platform admin, tenant admin, tenant trader, MFA user) with journeys and acceptance criteria | Owner UAT; exit criteria W33 section 5 | docs/W33_QA_UAT_HANDOFF.md; docs/W19_UAT_PLAN.md; wealth/uat.py | W33 handoff |  |  | 2026-09-26 |  | 2026-10-07 | RC line = w33-wealth-qa; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 19 |  | Owner: execute the UAT journeys (docs/W19_UAT_PLAN.md, W33 section 5) and record acceptance
277 | 10 | Wealth track (Waves 11-20) | REL-001 | Wealth | Wealth production hardening | Migration 0005, /health/wealth, monitor, backup, docs, RC | ATIP Waves 11-20 brief | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 | UAT-001 | W20: Migration 0005, /health/wealth, monitor, backup, docs, RC | Independent testing (ChatGPT) + UAT; merge after authorization | ops/migrations.py; wealth/health.py | commit w20-release; docs/W20* handoff |  |  | 2026-09-26 |  | 2026-09-26 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master | 20 | 83% of 174 lines in 2 key file(s) run by: test_w39_ops_tests, test_w39_perf_budget, test_w39_performance_detail
278 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-01 | Wealth / Performance | Performance data model | Signals, orders, fills, positions, cash, costs, benchmarks, timestamps; immutable history | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | perf_ledger append-only (migration 0005 triggers; UPDATE/DELETE refused); source refs per import; W39: order_ref, signal_ref, fee_breakdown, entry_seq (portable entry order, migration 0006), DEPOSIT / WITHDRAWAL cash rows, paper PARTIALLY_FILLED orders imported (were lost) | Positions are derived from the ledger by design (no second source of truth); independent QA | wealth/perf/ledger.py; db/schema_w39.py; ops/migrations.py | test_paper_partial_fills_reach_the_ledger; test_entry_order_is_portable_and_numbered; test_migration_0006_numbers_old_rows_and_the_ledger_stays_append_only; test_cash_rows_and_fee_breakdown_are_validated; test_voided_transactions_are_ignored_but_kept | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_paper_partial_fills_reach_the_ledger; test_entry_order_is_portable_and_numbered; test_migration_0006_numbers_old_rows_and_the_ledger_stays_append_only; test_cash_rows_and_fee_breakdown_are_validated; test_voided_transactions_are_ignored_but_kept ¦ 77% of 317 lines in 3 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget, test_w39_performance_detail, test_w40_total_return, test_wealth_api_security (+2 more)
279 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-02 | Wealth / Performance | Model Return | Model signal execution at model price/rules; reproducible from signal log | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | model.build: BUY signals (duplicate_of IS NULL) at the signal close, exit at horizon / SELL signal, equal weight, gross; pure function of signal_log + prices_daily | Independent QA | wealth/perf/model.py | test_model_return_is_reproducible_and_matches_a_hand_calculation; test_model_and_executable_are_reported_separately | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_model_return_is_reproducible_and_matches_a_hand_calculation; test_model_and_executable_are_reported_separately ¦ 88% of 230 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
280 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-03 | Wealth / Performance | Executable Return | Realistic execution incl. slippage and liquidity | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | next-session open x (1 + slippage bps), NSE cost model both sides, ADV cap (NOT_EXECUTABLE); W39: liquidity UNKNOWN flag when volume is missing, exit liquidity check, optional square-root market-impact slippage (slippage_model=impact: half spread + Y x sigma x sqrt(Q/ADV), inputs up to the signal date) | Parity with the OMS paper fill model is not automated (different fill rule by design) | wealth/perf/model.py; execution/impact.py | test_executable_applies_slippage_costs_and_the_liquidity_cap; test_impact_slippage_uses_the_square_root_estimate_known_at_the_signal | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_executable_applies_slippage_costs_and_the_liquidity_cap; test_impact_slippage_uses_the_square_root_estimate_known_at_the_signal ¦ 83% of 331 lines in 2 key file(s) run by: test_w39_backtest_partial, test_w39_contract_note_fees, test_w39_performance_detail, test_w39_untested_modules, test_w40_futures_backtest, test_w40_total_return, test_wealth_performance
281 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-04 | Wealth / Performance | Actual Investor Return | Actual quantities, prices, cash flows, exits; ledger-derived P&L / XIRR | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | engine.run_actual: average cost, TWR, XIRR, PME; W39: realized P&L / fees / dividends for the period and lifetime-to-end, labelled; whole-account return with cash | Independent QA | wealth/perf/engine.py | test_period_scope_is_separate_from_lifetime; test_xirr_and_pme_match_hand_computed_flows; test_average_cost_realized_pnl_and_fees | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_period_scope_is_separate_from_lifetime; test_xirr_and_pme_match_hand_computed_flows; test_average_cost_realized_pnl_and_fees ¦ 94% of 371 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
282 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-05 | Wealth / Performance | Benchmark Return | NIFTY / index / sector benchmark; period and methodology displayed | Owner deployment tracker: PERF-001 Detail | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | any prices_daily symbol (NIFTY50, NIFTYBANK, midcap, smallcap, sector indices); price return over the same sessions + PME of the investor's flows; W39: days invested shown and exported. W40: benchmark "nifty50tr" -- the Nifty 50 with dividends reinvested (data/total_return.py: NSE's TRI method, the price index exact, its dividend points estimated from the top 50 stored stocks by cap, picked monthly and weighted daily; nightly 21:10; GET /api/data/total-return), part of the report's audited inputs | Independent QA; the dividend part is an estimate (no free-float or constituent data) -- compare once with NSE's published TRI | wealth/perf/data.py; wealth/perf/report.py; data/total_return.py | test_benchmark_return_is_the_price_return_over_the_sessions; tests/test_w40_total_return.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_benchmark_return_is_the_price_return_over_the_sessions; tests/test_w40_total_return.py ¦ 91% of 502 lines in 3 key file(s) run by: test_w39_mcp, test_w39_performance_detail, test_w39b_mf_analytics, test_w40_total_return, test_wealth_api_security, test_wealth_performance
283 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-06 | Wealth / Performance | Cost Attribution | Brokerage, exchange, slippage, other costs; reconcile exactly to the ledger | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | W39: fees per kind for the period (dividend TDS and capped-sell fees counted), independent SUM over perf_ledger reconciliation, recorded components (fee_breakdown), itemised NSE statutory estimate for trades without a breakdown, slippage vs reference price; broker imports carry the contract-note split (brokerage / STT / exchange / SEBI / stamp / GST / DP) per trade, and a contract-note charges file becomes FEE rows (no double count) | Independent QA with real broker contract notes | wealth/perf/engine.py; portfolio/imports.py | test_costs_reconcile_with_dividend_tax_fee_rows_and_a_capped_sell; test_statutory_estimate_itemises_paper_brokerage_only_trades; tests/test_w39_contract_note_fees.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_costs_reconcile_with_dividend_tax_fee_rows_and_a_capped_sell; test_statutory_estimate_itemises_paper_brokerage_only_trades; tests/test_w39_contract_note_fees.py ¦ 89% of 587 lines in 2 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
284 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-07 | Wealth / Performance | Position Attribution | Entry / exit timing, sizing, averaging; variance from model decomposed | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | entry timing + averaging + exit timing + costs = actual - model P&L on the same quantity; W39: + sizing effect = actual - model P&L on the model notional | Independent QA | wealth/perf/model.py | test_sizing_effect_completes_the_decomposition_and_exact_links_win; test_position_attribution_identity | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_sizing_effect_completes_the_decomposition_and_exact_links_win; test_position_attribution_identity ¦ 88% of 230 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
285 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-08 | Wealth / Performance | Return Metrics | CAGR, XIRR, Alpha, Sharpe, Sortino, drawdown, win rate, profit factor; validated independently | Owner deployment tracker: PERF-001 Detail | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | metrics.py + backtest/metrics.py; W39 tests recompute Sharpe, Sortino, max drawdown, beta, alpha, volatility, CAGR with the statistics module | Independent QA | wealth/perf/metrics.py; backtest/metrics.py | test_risk_metrics_match_independent_formulas; test_cagr_annualises_a_full_year; test_xirr_one_year_ten_percent; test_trade_stats | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_risk_metrics_match_independent_formulas; test_cagr_annualises_a_full_year; test_xirr_one_year_ten_percent; test_trade_stats ¦ 96% of 217 lines in 2 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39_mcp, test_w39_performance_detail, test_w39_qa_suite, test_w39_untested_modules, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+7 more)
286 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-09 | Wealth / Performance | Signal Attribution | Each signal to entry, add-on, exit, outcome | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | link_signals: EXACT (the buy carries signal_ref, W39) or WINDOW (first buy within 5 sessions); add-ons, exits, open quantity, momentum outcomes; signal-driven vs discretionary P&L on the period gain (W39) | Independent QA | wealth/perf/model.py; wealth/perf/report.py | test_sizing_effect_completes_the_decomposition_and_exact_links_win | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_sizing_effect_completes_the_decomposition_and_exact_links_win ¦ 92% of 461 lines in 2 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_api_security, test_wealth_performance
287 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-10 | Wealth / Performance | Portfolio Attribution | Asset / sector / stock contribution to return and risk; reconciles | Owner deployment tracker: PERF-001 Detail | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | gain by symbol / sector / asset class on average capital (sums to total); W39: Euler risk contribution (shares sum to 100%, volatility contributions to portfolio volatility), cash account | Independent QA | wealth/perf/engine.py | test_risk_contribution_reconciles_and_groups_sum_to_the_total; test_contributions_reconcile_to_the_total | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_risk_contribution_reconciles_and_groups_sum_to_the_total; test_contributions_reconcile_to_the_total ¦ 94% of 371 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
288 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-11 | Wealth / Performance | Performance Dashboard | Model / executable / actual / benchmark side by side; no single ambiguous figure | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | /wealth Performance tab: four returns with definitions and days invested, gaps, actual, costs, contribution, risk contribution, cash account, signal attribution, trades, audit + verify, ledger; overview card shows all four (W39 added EXECUTABLE) | Owner UAT | dashboard/wealth_ui/performance_tab.py; dashboard/wealth_ui/overview_tab.py | test_routes_export_a_preview_and_verify_a_saved_report; test_happy_path_through_the_api | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_routes_export_a_preview_and_verify_a_saved_report; test_happy_path_through_the_api ¦ 100% of 6 lines in 2 key file(s) run by: test_w39_perf_budget
289 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-12 | Wealth / Performance | Audit & Explainability | Methodology, assumptions, calculation version, source data; every number traceable | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | audit block: methodology + CALCULATION_VERSION (+git), assumptions, ledger / signal / price content sha256, last price date per series, basis fallbacks; W39 verify() rebuilds a saved report and diffs it (GET .../reports/{id}/verify) | Independent QA | wealth/perf/report.py | test_verify_reproduces_and_detects_changed_inputs | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_verify_reproduces_and_detects_changed_inputs ¦ 96% of 231 lines in 1 key file(s) run by: test_w39_performance_detail, test_w40_total_return, test_wealth_api_security, test_wealth_performance
290 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-13 | Wealth / Performance | Report Export | Downloadable report for period / portfolio / strategy; matches dashboard | Owner deployment tracker: PERF-001 Detail | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | CSV (every section, copied not recomputed) and JSON of a saved report; W39: preview export route, strategy filter (ACTUAL limited to one strategy's trades), printable HTML report (A4, Print / Save as PDF) rendered from the same sections as the CSV | Owner UAT of the printed layout | wealth/perf/report.py; dashboard/wealth_routes.py; dashboard/wealth_ui/performance_tab.py | test_export_carries_every_section_with_the_reports_numbers; test_strategy_filter_limits_the_actual_portfolio; test_printable_html_has_the_csv_sections_and_numbers_and_escapes_text | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_export_carries_every_section_with_the_reports_numbers; test_strategy_filter_limits_the_actual_portfolio; test_printable_html_has_the_csv_sections_and_numbers_and_escapes_text ¦ 87% of 594 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_performance_detail, test_w39_ui_smoke, test_w40_total_return, test_wealth_api_security, test_wealth_performance
291 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-14 | Wealth / Performance | Regression & Edge Cases | Corporate actions, partial fills, averaging, cash flows, missing data, holidays | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | edge-case suite: split, bonus, partial fill, averaging, intraday round trip, OPENING, cash, holiday, missing bars, oversell, future date, void | Independent QA | wealth/perf/ | test_a_trade_on_a_market_holiday_counts_on_the_next_session; test_missing_bars_are_reported_not_hidden; test_a_bonus_issue_keeps_value_and_cost; test_an_opening_position_is_measured_from_that_days_close; test_split_between_buy_and_today_moves_neither_value_nor_return | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_a_trade_on_a_market_holiday_counts_on_the_next_session; test_missing_bars_are_reported_not_hidden; test_a_bonus_issue_keeps_value_and_cost; test_an_opening_position_is_measured_from_that_days_close; test_split_between_buy_and_today_moves_neither_value_nor_return ¦ 90% of 1207 lines in 6 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_mcp, test_w39_notify_transactions, test_w39_performance_detail, test_w39b_mf_analytics, test_w40_total_return, test_wealth_api_security (+3 more)
292 | 11 | W39 reconciliation (owner tracker 2026-10-07) | OPS-12 | Deployment/Ops | Dhan token auto-renewal (TOTP) | dhan_totp_secret: the 24-hour token renewed without manual login | Owner notes (ATIP-.txt / FEatures-.txt) | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | tools/dhan_token_refresh.py (RenewToken with the documented dhanClientId header, else TOTP + PIN generateAccessToken; writes config or vault), run daily at 06:30 and at login by the macOS LaunchAgent com.atip.dhan-token-refresh (W39, PR #4) and at 08:00 by the Windows task. W39b's own scheduler job was dropped on merging #4 (two renewals a day) | Owner: add dhan_pin + dhan_totp_secret (or vault them) once; run deploy/launchd/install.sh token | tools/dhan_token_refresh.py; deploy/launchd/com.atip.dhan-token-refresh.plist | tests/test_dhan_token_refresh.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | Delivered by W39 (PR #4, merged to master 2026-10-08); independent validation PENDING | 1 | tests/test_dhan_token_refresh.py ¦ 71% of 105 lines in 1 key file(s) run by: test_dhan_token_refresh, test_w38_platform_compliance
293 | 11 | W39 reconciliation (owner tracker 2026-10-07) | DP-23 | Data Platform | Long price history (7 years) | Last 7 years of daily data pulled and stored | Owner notes (ATIP-.txt / FEatures-.txt) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | W39 (PR #4, its DP-11): data/history_backfill.py walks each tracked symbol back to 7 years in 365-day windows, resumable (prices_daily_backfill), listing-aware, nightly 22:20 (40 symbols); db/purge.py HISTORY tier keeps prices_daily / ai_scores / predictions 7 years. W39b fix on merge: old windows are stored with today's corporate-action basis. W39b's own backfill was dropped | Owner: Dhan Data API subscription; the Nifty 500 completes in ~2 weeks of nightly runs | data/history_backfill.py; db/purge.py; data/dhan.py | tests/test_w39_history.py; tests/test_w39b_merge.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | Delivered by W39 (PR #4, merged to master 2026-10-08); independent validation PENDING | 2 | tests/test_w39_history.py; tests/test_w39b_merge.py ¦ 50% of 1001 lines in 3 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions, test_w39_ops_tests (+3 more)
294 | 11 | W39 reconciliation (owner tracker 2026-10-07) | DB-20 | Dashboard | Stock history like a trading platform | History of a stock shown like any trading software | Owner notes (ATIP-.txt / FEatures-.txt) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | W26 stock panel + W39: 3Y / 5Y / All, daily / weekly / monthly bars, SMA 20/50/200, EMA 21, Bollinger, log scale, multi-year returns; checked in headless Chromium. W39b: signal / pattern marks. W40: RSI 14 and MACD 12-26-9 panels (the server's definitions), an intraday chart (1D / 5D on 15-minute bars, session VWAP, previous close, intraday scan marks; GET /api/stock/{symbol}/intraday) and the on-demand 75-minute rating | Owner UAT | dashboard/stock_view.py | test_stock_history_reports_multi_year_returns; tests/test_w40_stock_chart.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | test_stock_history_reports_multi_year_returns; tests/test_w40_stock_chart.py ¦ 88% of 248 lines in 1 key file(s) run by: test_auto_recover, test_w39_mcp, test_w39_owner_notes, test_w39_perf_budget, test_w39b_patterns_more, test_w39b_tf75_signals, test_w40_stock_chart
295 | 11 | W39 reconciliation (owner tracker 2026-10-07) | RK-21 | Risk Management | Pre-trade price band + gross leverage | Position, notional, leverage, price-band, liquidity constraints (central risk gateway) | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: price band vs LTP / last close in the W4 risk engine and the manual / rule path; NSE circuit limits (Dhan quote upper / lower circuit stored in live_quotes) refuse a price outside today's circuit; paper futures notional in gross exposure; gross-exposure limit on the manual path | Independent QA; circuit fields confirmed against a live Dhan quote | execution/risk_engine.py; orders/risk.py; data/dhan.py | tests/test_w39_risk_gateway.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 7 | tests/test_w39_risk_gateway.py ¦ 51% of 1622 lines in 3 key file(s) run by: test_auto_recover, test_corporate_actions, test_job_monitoring, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w38_platform_compliance (+15 more)
296 | 11 | W39 reconciliation (owner tracker 2026-10-07) | AF-09 | Alpha/Factor Engine | Time-series momentum + vol-adjusted 12-1 | sign(return_n) x vol scaling; rank(12-1M) volatility-adjusted | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: tsmom_12m and mom_12_1_vol_adj registered point-in-time factors | Factor IC research before any score use | quant/factors.py | tests/test_w39_quant_portfolio.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_quant_portfolio.py ¦ 68% of 269 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_quant_portfolio, test_w40_risk_model
297 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PF-14 | Portfolio | Mean-variance with turnover penalty | max mu'w - lambda w'Sw - kappa turnover | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: turnover_penalty + current_weights in portfolio/optimize (exact proximal step inside the budget / sector-cap shifts); kappa = 0 reproduces the old solver; route falls back to the book's weights | Independent QA | portfolio/optimize.py | tests/test_w39_quant_portfolio.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | tests/test_w39_quant_portfolio.py ¦ 65% of 417 lines in 1 key file(s) run by: test_w39_quant_portfolio
298 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PF-15 | Portfolio | Factor neutrality | Minimise unwanted factor exposure subject to alpha | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: normalize.apply neutralize spec (OLS residual, sector dummies); optimiser neutral_to equality constraints | Independent QA | quant/normalize.py; portfolio/optimize.py | tests/test_w39_quant_portfolio.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | tests/test_w39_quant_portfolio.py ¦ 67% of 531 lines in 2 key file(s) run by: test_w39_quant_portfolio
299 | 11 | W39 reconciliation (owner tracker 2026-10-07) | AF-10 | Alpha/Factor Engine | Volatility surface + term structure | IV by strike / maturity, skew, term structure, Greeks | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: quant.derivatives.vol_surface from fo_contract_daily (moneyness x expiry grid, ATM term structure, skew, per-strike Greeks); GET /api/data/fo/surface | Needs F&O contract history (DP-08 store, daily) | quant/derivatives.py | tests/test_w39_ml_regime_lineage_surface.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_ml_regime_lineage_surface.py ¦ 86% of 140 lines in 1 key file(s) run by: test_w36_ml_strategy_tooling, test_w39_ml_regime_lineage_surface, test_w39_options, test_w40_option_intents
300 | 11 | W39 reconciliation (owner tracker 2026-10-07) | ML-17 | AI/ML | Unsupervised market regime (HMM) | HMM / clustering / volatility-breadth state model | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: numpy Gaussian HMM on market features, point-in-time, as regime provider mode 'hmm' (opt-in) | Owner: choose the regime provider; research validation | ml/hmm.py; ml/regime.py | tests/test_w39_ml_regime_lineage_surface.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_ml_regime_lineage_surface.py ¦ 87% of 341 lines in 2 key file(s) run by: test_w39_ml_regime_lineage_surface, test_w40_option_intents
301 | 11 | W39 reconciliation (owner tracker 2026-10-07) | ML-18 | AI/ML | Research-to-production lineage | Version data + features + model + params + code hash | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: ml_model_version.code_version + lineage_json; lineage() manifest + route | Independent QA | ml/registry.py | tests/test_w39_ml_regime_lineage_surface.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_ml_regime_lineage_surface.py ¦ 88% of 154 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_ml_regime_lineage_surface, test_w39_qa_suite, test_w40_meta_label
302 | 11 | W39 reconciliation (owner tracker 2026-10-07) | BT-18 | Backtesting | Purged walk-forward for strategies | Train / test with purge + embargo | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: purge_sessions / embargo_sessions in backtest/walkforward (default 0 = old behaviour) | Independent QA | backtest/walkforward.py | tests/test_w39_backtest.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 6 | tests/test_w39_backtest.py ¦ 83% of 126 lines in 1 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips, test_w40_futures_backtest
303 | 11 | W39 reconciliation (owner tracker 2026-10-07) | BT-19 | Backtesting | Transaction-cost stress sweep | Net = gross - commissions - slippage - impact - taxes; multiplier sweep + break-even | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: cost_sweep over cost / slippage multipliers with interpolated break-even multiplier | Independent QA | backtest/robustness.py | tests/test_w39_backtest.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 6 | tests/test_w39_backtest.py ¦ 45% of 175 lines in 1 key file(s) run by: test_w39_backtest
304 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-17 | Execution | Aggressive exit: enable flag + CRI-spike / momentum-decay exit | Aggressive exit default-disabled until validated (owner workbook Wave 9) | Owner deployment tracker: Wave 9 | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | strategy/aggressive.py: ATR trail, T1 partial, T2 checkpoint. W39b (decision taken under the owner's 'take the decisions' instruction): aggressive_enabled=false refuses NEW entries in strategy.live, while open positions keep being managed (stops / targets / trails), so switching it off never strands a position; new cri_exit_threshold (default off) closes the remaining quantity with MARKET_RISK_EXIT when the stock's crash-risk index reaches it, on the existing broker path (pretrade checks incl. price band and circuit limits unchanged); threshold validated to (0, 100] | Independent QA; the owner picks a CRI threshold (e.g. 80) after reviewing CRI history before turning it on; the aggressive strategy stays unscheduled and PAPER | strategy/aggressive.py; strategy/live.py | tests/test_strategy_live.py (test_disabled_flag_refuses_new_entries_but_keeps_managing_open_positions, test_cri_spike_exits_the_whole_position_only_when_configured, test_cri_below_threshold_or_unknown_does_not_exit, test_cri_threshold_is_validated); tests/test_aggressive_*.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); was BLOCKED on an owner decision, decided as described (reversible: one config key each); independent validation PENDING | 7 | tests/test_strategy_live.py (test_disabled_flag_refuses_new_entries_but_keeps_managing_open_positions, test_cri_spike_exits_the_whole_position_only_when_configured, test_cri_below_threshold_or_unknown_does_not_exit, test_cri_threshold_is_validated); tests/test_aggressive_*.py ¦ 80% of 351 lines in 2 key file(s) run by: test_aggressive_backtest, test_aggressive_decisions, test_aggressive_lifecycle, test_strategy_live
305 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-18 | Execution | Basket orders (paper) | Zerodha / Dhan parity: place a list of orders together | Owner notes (ATIP-.txt / FEatures-.txt) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: orders/basket.py -- named baskets, margin / risk pre-check of the whole basket, all-or-nothing PAPER placement through the existing order path | LIVE placement stays behind the live-trading master switch | orders/basket.py | tests/test_w39_retail.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 7 | tests/test_w39_retail.py ¦ 89% of 132 lines in 1 key file(s) run by: test_w39_retail, test_w39_ui_smoke
306 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-19 | Execution | Broker-side GTT / forever orders | Zerodha GTT / Dhan forever orders | Owner notes (ATIP-.txt / FEatures-.txt) | P2 | BLOCKED | BLOCKED | 20 |  | ATIP-side trigger rules (orders/rules.py) fire while ATIP runs; nothing is placed at the broker | Place / modify / cancel broker GTT (Dhan forever-order API, Kite GTT) for LIVE positions | orders/rules.py |  | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 7 |  | Owner authorization for LIVE broker order placement (live trading is off by design) and the Dhan forever-order API enabled on the account
307 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-20 | Execution | Stock SIP (recurring buys, paper) | Zerodha / Dhan parity: systematic stock SIP | Owner notes (ATIP-.txt / FEatures-.txt) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: orders/sip.py -- monthly / weekly plans by amount or quantity, executed in PAPER by the scheduler, skipped on holidays, history kept | LIVE SIP stays behind the live-trading master switch | orders/sip.py | tests/test_w39_retail.py; tests/test_w39_notify_transactions.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 (PR #5); fix: with two or more plans due, the second order waited on the first plan's uncommitted rows and failed -- the loop now commits before each placement | 7 | tests/test_w39_retail.py; tests/test_w39_notify_transactions.py ¦ 89% of 150 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_retail, test_w39_ui_smoke
308 | 11 | W39 reconciliation (owner tracker 2026-10-07) | UX-01 | Dashboard | Investor / Trader mode + progressive disclosure | Consumer UX gap (owner Gap Analysis: 50% -> 90%) | Owner deployment tracker: Gap Analysis | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | Investor / Trader mode preference (W17 INT-001); W39: Simple / Detailed view on /wealth -- Simple hides the audit, ledger and trade-level tables | Owner UAT of which panels belong in Simple | dashboard/wealth_page.py | tests/test_w39_retail.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | tests/test_w39_retail.py ¦ 100% of 20 lines in 1 key file(s) run by: test_w39_perf_budget, test_w39_retail, test_w39_ui_smoke, test_wealth_api_security
309 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-RS | Research | Equity research reports (RS-01..10) | Institutional-style valuation, targets, ratings, reports with disclosures and tracked calls | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/valuation.py (DCF + scenarios + sensitivity, justified P/B, peer / own-history multiples); research/report.py (12-month targets, ratings, SEBI-style disclosures, calls and hit rate); nightly 20:40 | No consensus estimates feed; XBRL key lines only (no 3-statement model); hit rates start from the first report and need PaRRVA review before being shown to others | research/valuation.py; research/report.py | tests/test_w39_research.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_research.py ¦ 90% of 554 lines in 2 key file(s) run by: test_w39_mcp, test_w39_research, test_w39_scorecard, test_w39_screener, test_w39_technicals, test_w39b_dvm, test_w39b_earnings_surprise, test_w39b_tf75
310 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-SCREENER | Research | Stock screener: fundamental + technical (SC-20) | Query screener with presets, saved screens and alerts | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/screener.py: query language (precedence, NOT, IN, aliases), presets, saved screens with new-match alerts, CSV; /screener | Independent QA | research/screener.py | tests/test_w39_screener.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_screener.py ¦ 88% of 446 lines in 1 key file(s) run by: test_w39_delivery, test_w39_mcp, test_w39_patterns, test_w39_rs_line, test_w39_scorecard, test_w39_screener, test_w39_screener_nl, test_w39_technicals (+5 more)
311 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-OPTIONS | Derivatives | Options strategy builder (OP-01..05) | Payoff, breakevens, POP and Greeks for multi-leg strategies | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | quant/options_strategy.py: templates, payoff and breakevens, POP, Greeks, implied IV, chain pricing; POST /api/options/(build¦analyse) | Analysis only: one-click execution needs the live OMS and the owner's explicit go-ahead | quant/options_strategy.py | tests/test_w39_options.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_options.py ¦ 88% of 209 lines in 1 key file(s) run by: test_signal_pipeline, test_w39_options, test_w40_option_intents
312 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-TECH | Technical Analysis | Technical scans, ratings and signals (TA-01..04) | 30 scans, 19 candle patterns, technical / RS ratings, signals with ATR levels and confluence | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py + research/tech_signals.py: scans, patterns, ratings, signals with entry / stop / target, confluence, outcomes (TARGET / STOPPED / EXPIRED); nightly 20:30 | Trust a scan only after ~30 closed signals (records start on the first run) | research/technicals.py; research/tech_signals.py | tests/test_w39_technicals.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_technicals.py ¦ 89% of 885 lines in 2 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+12 more)
313 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-PULSE | Market Intelligence | Market pulse (MP-01..05) | Global-cue model, GIFT gap, FII flow pressure, participant OI, OI walls | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/market_pulse.py + data/participant_oi.py: global-cue model, basis-free GIFT gap, FII streak / absorption, NSE participant OI positioning, OI walls; /market-pulse | Needs Nifty + global history loaded, Dhan index quotes for GIFT, NSE reachable for participant OI | research/market_pulse.py; data/participant_oi.py | tests/test_w39_market_pulse.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_market_pulse.py ¦ 70% of 529 lines in 2 key file(s) run by: test_w39_event_calendar, test_w39_global_sync, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate
314 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-REGIME | Market Intelligence | Market regime gate (RG-01..04) | Distribution / follow-through days, 200-DMA, signals tagged with or against the market | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/regime_gate.py: OPEN / CAUTION / CLOSED gate, signals tagged and never alerted against it, 'does the gate help' record | Thresholds are ATIP's choices (IBD tradition); evidence needs 30+ closed signals per side | research/regime_gate.py | tests/test_w39_regime_gate.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_regime_gate.py ¦ 83% of 248 lines in 1 key file(s) run by: test_w39_delivery, test_w39_event_calendar, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate, test_w39_rs_line, test_w39_scorecard, test_w39_technicals (+6 more)
315 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-TRACK | Research | Signal track record by regime and horizon (TR-01..03) | 5/20/60-session returns vs the Nifty per signal, by scan x gate and confluence | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/tech_signals.py forward returns and stats, shown next to today's signals | Useful after a few months of signals | research/tech_signals.py | tests/test_w39_track_record.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_track_record.py ¦ 85% of 587 lines in 1 key file(s) run by: test_w39_delivery, test_w39_mcp, test_w39_patterns, test_w39_regime_gate, test_w39_rs_line, test_w39_scorecard, test_w39_screener, test_w39_technicals (+9 more)
316 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-WEEKLY | Technical Analysis | Weekly technical rating (WK-01..02) | Weekly rating on completed weeks; daily / weekly agreement | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py weekly bars, rating, agreement as screener field and signal attribute | Independent QA | research/technicals.py | tests/test_w39_weekly.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_weekly.py ¦ 95% of 298 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
317 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-PATTERNS | Technical Analysis | Chart patterns from swing pivots (CP-01..04) and marks on the stock chart | Darvas box, VCP, double bottom, ascending triangle, head and shoulders; W39b: inverse H&S, descending triangle, channels, wedges, chart marks | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/patterns.py: patterns as scans with levels, screener setups, alerts held until a positive 30-signal record. W39b (CP-04): inverse head and shoulders, descending triangle, rising / falling channels (breakout and breakdown each), rising / falling wedges -- 14 pattern scans, each calibrated at 0.02-0.1 % of stock-days on random walks; the stock chart (/api/stock/{symbol}/history chart_marks) marks signals, pattern breakouts, candle patterns and the lines of the patterns in place, on daily / weekly / monthly bars, with a toggle | Rule-based approximations; independent QA; each new scan needs 30 closed signals before its alerts start | research/patterns.py; dashboard/stock_view.py | tests/test_w39_patterns.py; tests/test_w39b_patterns_more.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_patterns.py; tests/test_w39b_patterns_more.py ¦ 93% of 626 lines in 2 key file(s) run by: test_auto_recover, test_w39_delivery, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
318 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-RSLINE | Technical Analysis | RS-line new highs and size-group RS ranks (RL-01..02) | RS line new highs (also before price); RS ranks within AMFI size groups | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py RS line; AMFI size groups from shares x price | Independent QA | research/technicals.py | tests/test_w39_rs_line.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_rs_line.py ¦ 95% of 298 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
319 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-DELIVERY | Technical Analysis | Delivery-% spike scan (DL-01) | NSE delivery percentage spike as a scan and screener field | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py delivery spike scan, snapshot fields, preset | Independent QA | research/technicals.py | tests/test_w39_delivery.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_delivery.py ¦ 95% of 298 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
320 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-SCORECARD | Research | Explainable fundamental scorecard (FS-01..03) | 5 axes x 6 pass / fail checks with their numbers, stored nightly with a record vs the Nifty | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/scorecard.py: value, earnings, growth, dividend, balance-sheet checks; screener fields and presets; nightly 20:50 | Reported (not forecast) growth; banks / NBFCs miss six checks by design; record needs months | research/scorecard.py | tests/test_w39_scorecard.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_scorecard.py ¦ 89% of 420 lines in 1 key file(s) run by: test_w39_mcp, test_w39_scorecard, test_w39_screener, test_w39_technicals, test_w39b_dvm, test_w39b_earnings_surprise, test_w39b_tf75
321 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-EVENTS | Market Intelligence | Macro event calendar (EV-01..03) | FOMC, US CPI, payrolls, RBI dates; the NSE session each hits; gap band widening | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/event_calendar.py: seeded dates, config / API additions, band widened after US releases | Seeded dates reach end-2026 (RBI Feb-2027): add next year's dates each December | research/event_calendar.py | tests/test_w39_event_calendar.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_event_calendar.py ¦ 85% of 159 lines in 1 key file(s) run by: test_w39_event_calendar, test_w39_global_sync, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate
322 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-INTRADAY | Technical Analysis | Intraday scans on 15-minute bars (IN-01..03) | Opening-range breakout, open = low / high, intraday squeeze with a record to the close | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/intraday_signals.py; every 15 minutes 09:45-15:50 | Needs the Dhan Data API (15-minute bars) and 3 sessions of stored bars | research/intraday_signals.py | tests/test_w39_intraday.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_intraday.py ¦ 88% of 225 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_regime_gate, test_w39_rs_line, test_w39_technicals, test_w39_weekly, test_w39b_tf75 (+2 more)
323 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-DEPTH20 | Data Platform | 20-level depth, depth-weighted imbalance and order-flow imbalance (DP-01..03, OF-01..03) | Dhan 20-level depth WebSocket, DWI, OFI from quote changes (best level and multi-level), persistent flags, validation | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | data/depth20.py: depth feed (off by default), DWI, OFI summed over every book update, logistic validation vs the next 1 / 5 minutes and OFI vs its own interval | Owner: depth20.enabled and the Dhan Data API | data/depth20.py | tests/test_w39_depth20.py; tests/test_w39b_ofi.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_depth20.py; tests/test_w39b_ofi.py ¦ 82% of 379 lines in 1 key file(s) run by: test_w39_depth20, test_w39b_ofi
324 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-GLOBALSYNC | Market Intelligence | Synchronised global-cue model (GS-01..03) | 15:30 / 08:45 snapshots of global futures, Asia and FX; the opening gap modelled on them | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/global_sync.py: snapshots, walk-forward record vs GIFT | Needs 40 mornings of snapshots (~2 months) | research/global_sync.py | tests/test_w39_global_sync.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_global_sync.py ¦ 84% of 128 lines in 1 key file(s) run by: test_w39_event_calendar, test_w39_global_sync, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate
325 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-NLSCREEN | Research | English to screener query (NL-01..03) | Plain-English screener queries, validated and never run unseen | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/screener_nl.py: Claude path when enabled, rule translator otherwise; POST /api/screener/ask | Claude path needs a working Anthropic key (KD-001) | research/screener_nl.py | tests/test_w39_screener_nl.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_screener_nl.py ¦ 95% of 199 lines in 1 key file(s) run by: test_w39_screener_nl
326 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-MCP | APIs | Read-only ATIP MCP server (MC-01..03) | 12 read-only tools over stdio on a query-only database connection | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | tools/atip_mcp.py; W40: 20 tools -- adds dvm, earnings_surprise, mf_search / mf_analytics / mf_sip / mf_compare, backtest_validation (stored CPCV / PBO) and chart_marks, each checked under query_only | Local stdio only (no hosted transport) | tools/atip_mcp.py | tests/test_w39_mcp.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_mcp.py ¦ 91% of 331 lines in 1 key file(s) run by: test_w39_mcp
327 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-ORDERBOOK | Market Intelligence | Order-book pressure and open orders (OB-01..03) | Market-wide pending buy / sell pressure; a read-only view of your open orders | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | data/order_pressure.py (every 15 minutes, market hours); portfolio/open_orders.py | Needs the Dhan Data API; context, not a signal | data/order_pressure.py; portfolio/open_orders.py | tests/test_w39_market_pulse.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_market_pulse.py ¦ 56% of 190 lines in 2 key file(s) run by: test_w39_event_calendar, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate, test_w39_scorecard, test_w39_screener, test_w39_technicals, test_w39b_dvm (+2 more)
328 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-TF75 | Technical Analysis | 75-minute technical rating and its agreement with the daily one | Trendlyne / TradingView-style intraday timeframe rating | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py bars_75 / rating_75: the daily rating's votes on 75-minute bars built only from stored 15-minute bars (09:15 / 10:30 / 11:45 / 13:00 / 14:15), completed bars only, 35 bars (7 sessions) needed, never a stale session; stored in technical_snapshot (tech_rating_75*, rsi_14_75, supertrend_dir_75, bar_75_end, mtf_alignment_75) by the 20:30 run; screener fields and a preset | Independent QA. W40: a 75m column on /signals and GET /api/stock/{symbol}/rating-75 (on demand from the stored 15-minute bars, completed bars only); the /signals column is still the 20:30 snapshot | research/technicals.py; research/tech_signals.py; research/screener.py | tests/test_w39b_tf75.py; tests/test_w39b_tf75_signals.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_tf75.py; tests/test_w39b_tf75_signals.py ¦ 89% of 1331 lines in 3 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+13 more)
329 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-DVM | Research | DVM view: durability, valuation, momentum 0-100 and zones | Trendlyne-style DVM scores with explanations | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/dvm.py: durability from the scorecard's 12 health / past-performance checks, valuation from the research fair value (60 %) and P/E (P/B for financials) vs the industry median (40 %), momentum from the technical and RS ratings; every score explains itself with its numbers; seven zones; stored nightly on fundamental_scorecard (dvm_*); GET /api/research/dvm/{symbol}; DVM card on /research; 3 screener presets | Independent QA; weights are ATIP's definitions, not backtested -- record whether the zones pay before using them | research/dvm.py; research/scorecard.py; dashboard/w39_routes.py | tests/test_w39b_dvm.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_dvm.py ¦ 86% of 1044 lines in 3 key file(s) run by: test_auto_recover, test_w39_depth20, test_w39_event_calendar, test_w39_global_sync, test_w39_intraday, test_w39_market_pulse, test_w39_mcp, test_w39_options (+14 more)
330 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-PEAD | Research | Earnings surprise (SUE), EPS-trend proxy and a post-earnings-drift scan | Earnings surprise and PEAD (gap analysis 4.7) | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/earnings_surprise.py: SUE and revenue SUE vs the same quarter a year earlier (8-quarter standard deviation, 4 needed), point in time from the NSE broadcast date; EPS-trend revisions proxy; pead_bull / pead_bear scans (¦SUE¦ >= 2, first session after the filing, 60-session horizon) stored and tracked like every scan, alerts held until 30 closed signals with positive expectancy; 20:35 job; screener fields and a preset; GET /api/research/earnings-surprise/{symbol} | Independent QA; needs 9+ quarters of NSE XBRL history (run the history backfill); no consensus estimates (ATIP's own history only); filings arrive with the Saturday fundamentals job | research/earnings_surprise.py; research/tech_signals.py | tests/test_w39b_earnings_surprise.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_earnings_surprise.py ¦ 86% of 970 lines in 2 key file(s) run by: test_w39_delivery, test_w39_mcp, test_w39_patterns, test_w39_regime_gate, test_w39_rs_line, test_w39_scorecard, test_w39_screener, test_w39_technicals (+9 more) | For a consensus-based surprise: a consensus estimates feed (not available today)
331 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-MFA | Wealth / Mutual funds | Mutual fund analytics on stored AMFI NAVs (read-only) | Value Research / Kuvera-style scheme analytics (gap analysis 4.3) | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | data/mf_analytics.py: point-to-point and CAGR returns, 1Y / 3Y rolling returns with hurdle stats, volatility / Sharpe / Sortino, drawdown with dates, beta / alpha / tracking error vs a price index, SIP and lump-sum XIRR, category rank among stored schemes, side-by-side compare; 3 read-only GET routes; scheme detail card on /data-platform. W40: step-up SIP, stamp duty (0.005 %) and units rounded down to 3 decimals by default, optional flat exit load per instalment; volatility annualised by the NAVs actually observed a year (not a fixed 252) | Independent QA. Holding MFs in the wealth ledger stays out of scope (owner Scope Exclusions); benchmark is a price index (the W40 Nifty 50 TR is not wired here yet); peers limited to stored schemes; tiered exit loads not modelled | data/mf_analytics.py; dashboard/w35_routes.py; dashboard/w35_page.py | tests/test_w39b_mf_analytics.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_mf_analytics.py ¦ 87% of 688 lines in 3 key file(s) run by: test_auto_recover, test_w39_mcp, test_w39_ml_regime_lineage_surface, test_w39_perf_budget, test_w39_ui_smoke, test_w39b_mf_analytics
332 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W40-RISKMODEL | Risk & Portfolio | Fundamental factor risk model (Barra-style) | Factor exposures, factor returns, covariance, specific risk and portfolio risk decomposition | W40 (PR #9): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4 items 5 and 9; tracker next actions | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | quant/risk_model.py: 8 styles (size, beta, momentum, residual volatility, book-to-price, earnings yield, ROE, liquidity) point in time, winsorised and cap-standardised, NSE industries (small ones pooled); daily sqrt(cap)-weighted regression with the industry constraint and robust t statistics; EWMA / Newey-West factor covariance; shrunk EWMA specific risk; decomposition of the PAPER / LIVE book (factor vs specific, per factor, marginal per stock, beta, active risk vs a cap-weighted Nifty 50 proxy); bias statistic on standard portfolios; nightly 21:45, incremental; /trading and /quant cards | Independent QA on the real database; needs filed share counts for 30+ stocks; universe and industries are today's (survivorship); no free-float data | quant/risk_model.py; portfolio/risk.py; dashboard/risk_model_routes.py | tests/test_w40_risk_model.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W40 developed 2026-10-09 on branch claude/wizardly-curie-fbjeoa (PR #9); independent validation PENDING | W40 (PR #9) | tests/test_w40_risk_model.py ¦ 76% of 1466 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model, test_w40_total_return
333 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W40-META | AI/ML | Meta-labelling of the technical signals (AFML ch. 3-4, 7, 10) | A second model deciding which primary signals to take, with bet sizes | W40 (PR #9): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4 items 5 and 9; tracker next actions | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | ml/meta_label.py: triple-barrier labels from the signal engine's own outcome rule; 37 features known at the signal's close; sample weights by average uniqueness; purged k-fold with embargo; GBM / logistic / RF; out-of-fold precision / recall / AUC and the kept signals' expectancy vs all; AFML bet sizing (reported only); ADOPTABLE only with 200+ signals and t >= 2, and the registry refuses activating anything else; Saturday retrain and 20:45 scoring, both off unless meta_label.enabled; /signals column when adopted | Owner: switch on after a few hundred closed signals exist and a version is ADOPTABLE; independent QA | ml/meta_label.py; ml/validation.py; dashboard/w40_routes.py | tests/test_w40_meta_label.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W40 developed 2026-10-09 on branch claude/wizardly-curie-fbjeoa (PR #9); independent validation PENDING | W40 (PR #9) | tests/test_w40_meta_label.py ¦ 90% of 861 lines in 3 key file(s) run by: test_auto_recover, test_w39_qa_suite, test_w39_regime_gate, test_w39_technicals, test_w40_meta_label

## New Items (W39)
Seq | Phase | Phase Name | ID | Module | Feature | Target Requirement | Scope Source | Priority | Status | Testing Status | Completion % | Depends On | Current Implementation | Next Action / Missing Work | Key Files | Evidence | Owner | Target Date | Started On | Completed On | Last Updated | Notes | Deployment Wave | Test Evidence | Blocker / Input Required
278 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-01 | Wealth / Performance | Performance data model | Signals, orders, fills, positions, cash, costs, benchmarks, timestamps; immutable history | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | perf_ledger append-only (migration 0005 triggers; UPDATE/DELETE refused); source refs per import; W39: order_ref, signal_ref, fee_breakdown, entry_seq (portable entry order, migration 0006), DEPOSIT / WITHDRAWAL cash rows, paper PARTIALLY_FILLED orders imported (were lost) | Positions are derived from the ledger by design (no second source of truth); independent QA | wealth/perf/ledger.py; db/schema_w39.py; ops/migrations.py | test_paper_partial_fills_reach_the_ledger; test_entry_order_is_portable_and_numbered; test_migration_0006_numbers_old_rows_and_the_ledger_stays_append_only; test_cash_rows_and_fee_breakdown_are_validated; test_voided_transactions_are_ignored_but_kept | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_paper_partial_fills_reach_the_ledger; test_entry_order_is_portable_and_numbered; test_migration_0006_numbers_old_rows_and_the_ledger_stays_append_only; test_cash_rows_and_fee_breakdown_are_validated; test_voided_transactions_are_ignored_but_kept ¦ 77% of 317 lines in 3 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_notify_transactions, test_w39_ops_tests, test_w39_perf_budget, test_w39_performance_detail, test_w40_total_return, test_wealth_api_security (+2 more)
279 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-02 | Wealth / Performance | Model Return | Model signal execution at model price/rules; reproducible from signal log | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | model.build: BUY signals (duplicate_of IS NULL) at the signal close, exit at horizon / SELL signal, equal weight, gross; pure function of signal_log + prices_daily | Independent QA | wealth/perf/model.py | test_model_return_is_reproducible_and_matches_a_hand_calculation; test_model_and_executable_are_reported_separately | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_model_return_is_reproducible_and_matches_a_hand_calculation; test_model_and_executable_are_reported_separately ¦ 88% of 230 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
280 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-03 | Wealth / Performance | Executable Return | Realistic execution incl. slippage and liquidity | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | next-session open x (1 + slippage bps), NSE cost model both sides, ADV cap (NOT_EXECUTABLE); W39: liquidity UNKNOWN flag when volume is missing, exit liquidity check, optional square-root market-impact slippage (slippage_model=impact: half spread + Y x sigma x sqrt(Q/ADV), inputs up to the signal date) | Parity with the OMS paper fill model is not automated (different fill rule by design) | wealth/perf/model.py; execution/impact.py | test_executable_applies_slippage_costs_and_the_liquidity_cap; test_impact_slippage_uses_the_square_root_estimate_known_at_the_signal | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_executable_applies_slippage_costs_and_the_liquidity_cap; test_impact_slippage_uses_the_square_root_estimate_known_at_the_signal ¦ 83% of 331 lines in 2 key file(s) run by: test_w39_backtest_partial, test_w39_contract_note_fees, test_w39_performance_detail, test_w39_untested_modules, test_w40_futures_backtest, test_w40_total_return, test_wealth_performance
281 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-04 | Wealth / Performance | Actual Investor Return | Actual quantities, prices, cash flows, exits; ledger-derived P&L / XIRR | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | engine.run_actual: average cost, TWR, XIRR, PME; W39: realized P&L / fees / dividends for the period and lifetime-to-end, labelled; whole-account return with cash | Independent QA | wealth/perf/engine.py | test_period_scope_is_separate_from_lifetime; test_xirr_and_pme_match_hand_computed_flows; test_average_cost_realized_pnl_and_fees | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_period_scope_is_separate_from_lifetime; test_xirr_and_pme_match_hand_computed_flows; test_average_cost_realized_pnl_and_fees ¦ 94% of 371 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
282 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-05 | Wealth / Performance | Benchmark Return | NIFTY / index / sector benchmark; period and methodology displayed | Owner deployment tracker: PERF-001 Detail | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | any prices_daily symbol (NIFTY50, NIFTYBANK, midcap, smallcap, sector indices); price return over the same sessions + PME of the investor's flows; W39: days invested shown and exported. W40: benchmark "nifty50tr" -- the Nifty 50 with dividends reinvested (data/total_return.py: NSE's TRI method, the price index exact, its dividend points estimated from the top 50 stored stocks by cap, picked monthly and weighted daily; nightly 21:10; GET /api/data/total-return), part of the report's audited inputs | Independent QA; the dividend part is an estimate (no free-float or constituent data) -- compare once with NSE's published TRI | wealth/perf/data.py; wealth/perf/report.py; data/total_return.py | test_benchmark_return_is_the_price_return_over_the_sessions; tests/test_w40_total_return.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_benchmark_return_is_the_price_return_over_the_sessions; tests/test_w40_total_return.py ¦ 91% of 502 lines in 3 key file(s) run by: test_w39_mcp, test_w39_performance_detail, test_w39b_mf_analytics, test_w40_total_return, test_wealth_api_security, test_wealth_performance
283 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-06 | Wealth / Performance | Cost Attribution | Brokerage, exchange, slippage, other costs; reconcile exactly to the ledger | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | W39: fees per kind for the period (dividend TDS and capped-sell fees counted), independent SUM over perf_ledger reconciliation, recorded components (fee_breakdown), itemised NSE statutory estimate for trades without a breakdown, slippage vs reference price; broker imports carry the contract-note split (brokerage / STT / exchange / SEBI / stamp / GST / DP) per trade, and a contract-note charges file becomes FEE rows (no double count) | Independent QA with real broker contract notes | wealth/perf/engine.py; portfolio/imports.py | test_costs_reconcile_with_dividend_tax_fee_rows_and_a_capped_sell; test_statutory_estimate_itemises_paper_brokerage_only_trades; tests/test_w39_contract_note_fees.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_costs_reconcile_with_dividend_tax_fee_rows_and_a_capped_sell; test_statutory_estimate_itemises_paper_brokerage_only_trades; tests/test_w39_contract_note_fees.py ¦ 89% of 587 lines in 2 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
284 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-07 | Wealth / Performance | Position Attribution | Entry / exit timing, sizing, averaging; variance from model decomposed | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | entry timing + averaging + exit timing + costs = actual - model P&L on the same quantity; W39: + sizing effect = actual - model P&L on the model notional | Independent QA | wealth/perf/model.py | test_sizing_effect_completes_the_decomposition_and_exact_links_win; test_position_attribution_identity | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_sizing_effect_completes_the_decomposition_and_exact_links_win; test_position_attribution_identity ¦ 88% of 230 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
285 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-08 | Wealth / Performance | Return Metrics | CAGR, XIRR, Alpha, Sharpe, Sortino, drawdown, win rate, profit factor; validated independently | Owner deployment tracker: PERF-001 Detail | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | metrics.py + backtest/metrics.py; W39 tests recompute Sharpe, Sortino, max drawdown, beta, alpha, volatility, CAGR with the statistics module | Independent QA | wealth/perf/metrics.py; backtest/metrics.py | test_risk_metrics_match_independent_formulas; test_cagr_annualises_a_full_year; test_xirr_one_year_ten_percent; test_trade_stats | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_risk_metrics_match_independent_formulas; test_cagr_annualises_a_full_year; test_xirr_one_year_ten_percent; test_trade_stats ¦ 96% of 217 lines in 2 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39_mcp, test_w39_performance_detail, test_w39_qa_suite, test_w39_untested_modules, test_w39b_bayes_optimize, test_w39b_cpcv_dominance (+7 more)
286 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-09 | Wealth / Performance | Signal Attribution | Each signal to entry, add-on, exit, outcome | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | link_signals: EXACT (the buy carries signal_ref, W39) or WINDOW (first buy within 5 sessions); add-ons, exits, open quantity, momentum outcomes; signal-driven vs discretionary P&L on the period gain (W39) | Independent QA | wealth/perf/model.py; wealth/perf/report.py | test_sizing_effect_completes_the_decomposition_and_exact_links_win | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_sizing_effect_completes_the_decomposition_and_exact_links_win ¦ 92% of 461 lines in 2 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_api_security, test_wealth_performance
287 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-10 | Wealth / Performance | Portfolio Attribution | Asset / sector / stock contribution to return and risk; reconciles | Owner deployment tracker: PERF-001 Detail | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | gain by symbol / sector / asset class on average capital (sums to total); W39: Euler risk contribution (shares sum to 100%, volatility contributions to portfolio volatility), cash account | Independent QA | wealth/perf/engine.py | test_risk_contribution_reconciles_and_groups_sum_to_the_total; test_contributions_reconcile_to_the_total | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_risk_contribution_reconciles_and_groups_sum_to_the_total; test_contributions_reconcile_to_the_total ¦ 94% of 371 lines in 1 key file(s) run by: test_w39_contract_note_fees, test_w39_performance_detail, test_w40_total_return, test_wealth_performance
288 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-11 | Wealth / Performance | Performance Dashboard | Model / executable / actual / benchmark side by side; no single ambiguous figure | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | /wealth Performance tab: four returns with definitions and days invested, gaps, actual, costs, contribution, risk contribution, cash account, signal attribution, trades, audit + verify, ledger; overview card shows all four (W39 added EXECUTABLE) | Owner UAT | dashboard/wealth_ui/performance_tab.py; dashboard/wealth_ui/overview_tab.py | test_routes_export_a_preview_and_verify_a_saved_report; test_happy_path_through_the_api | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_routes_export_a_preview_and_verify_a_saved_report; test_happy_path_through_the_api ¦ 100% of 6 lines in 2 key file(s) run by: test_w39_perf_budget
289 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-12 | Wealth / Performance | Audit & Explainability | Methodology, assumptions, calculation version, source data; every number traceable | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | audit block: methodology + CALCULATION_VERSION (+git), assumptions, ledger / signal / price content sha256, last price date per series, basis fallbacks; W39 verify() rebuilds a saved report and diffs it (GET .../reports/{id}/verify) | Independent QA | wealth/perf/report.py | test_verify_reproduces_and_detects_changed_inputs | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_verify_reproduces_and_detects_changed_inputs ¦ 96% of 231 lines in 1 key file(s) run by: test_w39_performance_detail, test_w40_total_return, test_wealth_api_security, test_wealth_performance
290 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-13 | Wealth / Performance | Report Export | Downloadable report for period / portfolio / strategy; matches dashboard | Owner deployment tracker: PERF-001 Detail | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | CSV (every section, copied not recomputed) and JSON of a saved report; W39: preview export route, strategy filter (ACTUAL limited to one strategy's trades), printable HTML report (A4, Print / Save as PDF) rendered from the same sections as the CSV | Owner UAT of the printed layout | wealth/perf/report.py; dashboard/wealth_routes.py; dashboard/wealth_ui/performance_tab.py | test_export_carries_every_section_with_the_reports_numbers; test_strategy_filter_limits_the_actual_portfolio; test_printable_html_has_the_csv_sections_and_numbers_and_escapes_text | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_export_carries_every_section_with_the_reports_numbers; test_strategy_filter_limits_the_actual_portfolio; test_printable_html_has_the_csv_sections_and_numbers_and_escapes_text ¦ 87% of 594 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_performance_detail, test_w39_ui_smoke, test_w40_total_return, test_wealth_api_security, test_wealth_performance
291 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PERF-001-14 | Wealth / Performance | Regression & Edge Cases | Corporate actions, partial fills, averaging, cash flows, missing data, holidays | Owner deployment tracker: PERF-001 Detail | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | edge-case suite: split, bonus, partial fill, averaging, intraday round trip, OPENING, cash, holiday, missing bars, oversell, future date, void | Independent QA | wealth/perf/ | test_a_trade_on_a_market_holiday_counts_on_the_next_session; test_missing_bars_are_reported_not_hidden; test_a_bonus_issue_keeps_value_and_cost; test_an_opening_position_is_measured_from_that_days_close; test_split_between_buy_and_today_moves_neither_value_nor_return | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 15.5 | test_a_trade_on_a_market_holiday_counts_on_the_next_session; test_missing_bars_are_reported_not_hidden; test_a_bonus_issue_keeps_value_and_cost; test_an_opening_position_is_measured_from_that_days_close; test_split_between_buy_and_today_moves_neither_value_nor_return ¦ 90% of 1207 lines in 6 key file(s) run by: test_w37_brokers_multi_asset, test_w39_contract_note_fees, test_w39_mcp, test_w39_notify_transactions, test_w39_performance_detail, test_w39b_mf_analytics, test_w40_total_return, test_wealth_api_security (+3 more)
292 | 11 | W39 reconciliation (owner tracker 2026-10-07) | OPS-12 | Deployment/Ops | Dhan token auto-renewal (TOTP) | dhan_totp_secret: the 24-hour token renewed without manual login | Owner notes (ATIP-.txt / FEatures-.txt) | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | tools/dhan_token_refresh.py (RenewToken with the documented dhanClientId header, else TOTP + PIN generateAccessToken; writes config or vault), run daily at 06:30 and at login by the macOS LaunchAgent com.atip.dhan-token-refresh (W39, PR #4) and at 08:00 by the Windows task. W39b's own scheduler job was dropped on merging #4 (two renewals a day) | Owner: add dhan_pin + dhan_totp_secret (or vault them) once; run deploy/launchd/install.sh token | tools/dhan_token_refresh.py; deploy/launchd/com.atip.dhan-token-refresh.plist | tests/test_dhan_token_refresh.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | Delivered by W39 (PR #4, merged to master 2026-10-08); independent validation PENDING | 1 | tests/test_dhan_token_refresh.py ¦ 71% of 105 lines in 1 key file(s) run by: test_dhan_token_refresh, test_w38_platform_compliance
293 | 11 | W39 reconciliation (owner tracker 2026-10-07) | DP-23 | Data Platform | Long price history (7 years) | Last 7 years of daily data pulled and stored | Owner notes (ATIP-.txt / FEatures-.txt) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | W39 (PR #4, its DP-11): data/history_backfill.py walks each tracked symbol back to 7 years in 365-day windows, resumable (prices_daily_backfill), listing-aware, nightly 22:20 (40 symbols); db/purge.py HISTORY tier keeps prices_daily / ai_scores / predictions 7 years. W39b fix on merge: old windows are stored with today's corporate-action basis. W39b's own backfill was dropped | Owner: Dhan Data API subscription; the Nifty 500 completes in ~2 weeks of nightly runs | data/history_backfill.py; db/purge.py; data/dhan.py | tests/test_w39_history.py; tests/test_w39b_merge.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | Delivered by W39 (PR #4, merged to master 2026-10-08); independent validation PENDING | 2 | tests/test_w39_history.py; tests/test_w39b_merge.py ¦ 50% of 1001 lines in 3 key file(s) run by: test_corporate_actions, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w39_history, test_w39_notify_transactions, test_w39_ops_tests (+3 more)
294 | 11 | W39 reconciliation (owner tracker 2026-10-07) | DB-20 | Dashboard | Stock history like a trading platform | History of a stock shown like any trading software | Owner notes (ATIP-.txt / FEatures-.txt) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 90 |  | W26 stock panel + W39: 3Y / 5Y / All, daily / weekly / monthly bars, SMA 20/50/200, EMA 21, Bollinger, log scale, multi-year returns; checked in headless Chromium. W39b: signal / pattern marks. W40: RSI 14 and MACD 12-26-9 panels (the server's definitions), an intraday chart (1D / 5D on 15-minute bars, session VWAP, previous close, intraday scan marks; GET /api/stock/{symbol}/intraday) and the on-demand 75-minute rating | Owner UAT | dashboard/stock_view.py | test_stock_history_reports_multi_year_returns; tests/test_w40_stock_chart.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | test_stock_history_reports_multi_year_returns; tests/test_w40_stock_chart.py ¦ 88% of 248 lines in 1 key file(s) run by: test_auto_recover, test_w39_mcp, test_w39_owner_notes, test_w39_perf_budget, test_w39b_patterns_more, test_w39b_tf75_signals, test_w40_stock_chart
295 | 11 | W39 reconciliation (owner tracker 2026-10-07) | RK-21 | Risk Management | Pre-trade price band + gross leverage | Position, notional, leverage, price-band, liquidity constraints (central risk gateway) | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P0 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: price band vs LTP / last close in the W4 risk engine and the manual / rule path; NSE circuit limits (Dhan quote upper / lower circuit stored in live_quotes) refuse a price outside today's circuit; paper futures notional in gross exposure; gross-exposure limit on the manual path | Independent QA; circuit fields confirmed against a live Dhan quote | execution/risk_engine.py; orders/risk.py; data/dhan.py | tests/test_w39_risk_gateway.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 7 | tests/test_w39_risk_gateway.py ¦ 51% of 1622 lines in 3 key file(s) run by: test_auto_recover, test_corporate_actions, test_job_monitoring, test_regressions, test_risk_controls, test_signal_pipeline, test_strategy_live, test_w38_platform_compliance (+15 more)
296 | 11 | W39 reconciliation (owner tracker 2026-10-07) | AF-09 | Alpha/Factor Engine | Time-series momentum + vol-adjusted 12-1 | sign(return_n) x vol scaling; rank(12-1M) volatility-adjusted | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: tsmom_12m and mom_12_1_vol_adj registered point-in-time factors | Factor IC research before any score use | quant/factors.py | tests/test_w39_quant_portfolio.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_quant_portfolio.py ¦ 68% of 269 lines in 1 key file(s) run by: test_auto_recover, test_w36_ml_strategy_tooling, test_w39_api_contract, test_w39_quant_portfolio, test_w40_risk_model
297 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PF-14 | Portfolio | Mean-variance with turnover penalty | max mu'w - lambda w'Sw - kappa turnover | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: turnover_penalty + current_weights in portfolio/optimize (exact proximal step inside the budget / sector-cap shifts); kappa = 0 reproduces the old solver; route falls back to the book's weights | Independent QA | portfolio/optimize.py | tests/test_w39_quant_portfolio.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | tests/test_w39_quant_portfolio.py ¦ 65% of 417 lines in 1 key file(s) run by: test_w39_quant_portfolio
298 | 11 | W39 reconciliation (owner tracker 2026-10-07) | PF-15 | Portfolio | Factor neutrality | Minimise unwanted factor exposure subject to alpha | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: normalize.apply neutralize spec (OLS residual, sector dummies); optimiser neutral_to equality constraints | Independent QA | quant/normalize.py; portfolio/optimize.py | tests/test_w39_quant_portfolio.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | tests/test_w39_quant_portfolio.py ¦ 67% of 531 lines in 2 key file(s) run by: test_w39_quant_portfolio
299 | 11 | W39 reconciliation (owner tracker 2026-10-07) | AF-10 | Alpha/Factor Engine | Volatility surface + term structure | IV by strike / maturity, skew, term structure, Greeks | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: quant.derivatives.vol_surface from fo_contract_daily (moneyness x expiry grid, ATM term structure, skew, per-strike Greeks); GET /api/data/fo/surface | Needs F&O contract history (DP-08 store, daily) | quant/derivatives.py | tests/test_w39_ml_regime_lineage_surface.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_ml_regime_lineage_surface.py ¦ 86% of 140 lines in 1 key file(s) run by: test_w36_ml_strategy_tooling, test_w39_ml_regime_lineage_surface, test_w39_options, test_w40_option_intents
300 | 11 | W39 reconciliation (owner tracker 2026-10-07) | ML-17 | AI/ML | Unsupervised market regime (HMM) | HMM / clustering / volatility-breadth state model | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: numpy Gaussian HMM on market features, point-in-time, as regime provider mode 'hmm' (opt-in) | Owner: choose the regime provider; research validation | ml/hmm.py; ml/regime.py | tests/test_w39_ml_regime_lineage_surface.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_ml_regime_lineage_surface.py ¦ 87% of 341 lines in 2 key file(s) run by: test_w39_ml_regime_lineage_surface, test_w40_option_intents
301 | 11 | W39 reconciliation (owner tracker 2026-10-07) | ML-18 | AI/ML | Research-to-production lineage | Version data + features + model + params + code hash | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: ml_model_version.code_version + lineage_json; lineage() manifest + route | Independent QA | ml/registry.py | tests/test_w39_ml_regime_lineage_surface.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 4 | tests/test_w39_ml_regime_lineage_surface.py ¦ 88% of 154 lines in 1 key file(s) run by: test_auto_recover, test_w39_api_contract, test_w39_ml_regime_lineage_surface, test_w39_qa_suite, test_w40_meta_label
302 | 11 | W39 reconciliation (owner tracker 2026-10-07) | BT-18 | Backtesting | Purged walk-forward for strategies | Train / test with purge + embargo | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: purge_sessions / embargo_sessions in backtest/walkforward (default 0 = old behaviour) | Independent QA | backtest/walkforward.py | tests/test_w39_backtest.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 6 | tests/test_w39_backtest.py ¦ 83% of 126 lines in 1 key file(s) run by: test_w39_backtest, test_w39_backtest_partial, test_w39b_bayes_optimize, test_w39b_cpcv_dominance, test_w39b_cpcv_pbo, test_w39b_event_driven_skips, test_w40_futures_backtest
303 | 11 | W39 reconciliation (owner tracker 2026-10-07) | BT-19 | Backtesting | Transaction-cost stress sweep | Net = gross - commissions - slippage - impact - taxes; multiplier sweep + break-even | Feature map (ATIP_Global_Algo_Trading_Features_and_Formulas) | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | W39: cost_sweep over cost / slippage multipliers with interpolated break-even multiplier | Independent QA | backtest/robustness.py | tests/test_w39_backtest.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 6 | tests/test_w39_backtest.py ¦ 45% of 175 lines in 1 key file(s) run by: test_w39_backtest
304 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-17 | Execution | Aggressive exit: enable flag + CRI-spike / momentum-decay exit | Aggressive exit default-disabled until validated (owner workbook Wave 9) | Owner deployment tracker: Wave 9 | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | strategy/aggressive.py: ATR trail, T1 partial, T2 checkpoint. W39b (decision taken under the owner's 'take the decisions' instruction): aggressive_enabled=false refuses NEW entries in strategy.live, while open positions keep being managed (stops / targets / trails), so switching it off never strands a position; new cri_exit_threshold (default off) closes the remaining quantity with MARKET_RISK_EXIT when the stock's crash-risk index reaches it, on the existing broker path (pretrade checks incl. price band and circuit limits unchanged); threshold validated to (0, 100] | Independent QA; the owner picks a CRI threshold (e.g. 80) after reviewing CRI history before turning it on; the aggressive strategy stays unscheduled and PAPER | strategy/aggressive.py; strategy/live.py | tests/test_strategy_live.py (test_disabled_flag_refuses_new_entries_but_keeps_managing_open_positions, test_cri_spike_exits_the_whole_position_only_when_configured, test_cri_below_threshold_or_unknown_does_not_exit, test_cri_threshold_is_validated); tests/test_aggressive_*.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); was BLOCKED on an owner decision, decided as described (reversible: one config key each); independent validation PENDING | 7 | tests/test_strategy_live.py (test_disabled_flag_refuses_new_entries_but_keeps_managing_open_positions, test_cri_spike_exits_the_whole_position_only_when_configured, test_cri_below_threshold_or_unknown_does_not_exit, test_cri_threshold_is_validated); tests/test_aggressive_*.py ¦ 80% of 351 lines in 2 key file(s) run by: test_aggressive_backtest, test_aggressive_decisions, test_aggressive_lifecycle, test_strategy_live
305 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-18 | Execution | Basket orders (paper) | Zerodha / Dhan parity: place a list of orders together | Owner notes (ATIP-.txt / FEatures-.txt) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: orders/basket.py -- named baskets, margin / risk pre-check of the whole basket, all-or-nothing PAPER placement through the existing order path | LIVE placement stays behind the live-trading master switch | orders/basket.py | tests/test_w39_retail.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 7 | tests/test_w39_retail.py ¦ 89% of 132 lines in 1 key file(s) run by: test_w39_retail, test_w39_ui_smoke
306 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-19 | Execution | Broker-side GTT / forever orders | Zerodha GTT / Dhan forever orders | Owner notes (ATIP-.txt / FEatures-.txt) | P2 | BLOCKED | BLOCKED | 20 |  | ATIP-side trigger rules (orders/rules.py) fire while ATIP runs; nothing is placed at the broker | Place / modify / cancel broker GTT (Dhan forever-order API, Kite GTT) for LIVE positions | orders/rules.py |  | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 7 |  | Owner authorization for LIVE broker order placement (live trading is off by design) and the Dhan forever-order API enabled on the account
307 | 11 | W39 reconciliation (owner tracker 2026-10-07) | EX-20 | Execution | Stock SIP (recurring buys, paper) | Zerodha / Dhan parity: systematic stock SIP | Owner notes (ATIP-.txt / FEatures-.txt) | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | W39: orders/sip.py -- monthly / weekly plans by amount or quantity, executed in PAPER by the scheduler, skipped on holidays, history kept | LIVE SIP stays behind the live-trading master switch | orders/sip.py | tests/test_w39_retail.py; tests/test_w39_notify_transactions.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 (PR #5); fix: with two or more plans due, the second order waited on the first plan's uncommitted rows and failed -- the loop now commits before each placement | 7 | tests/test_w39_retail.py; tests/test_w39_notify_transactions.py ¦ 89% of 150 lines in 1 key file(s) run by: test_w39_notify_transactions, test_w39_retail, test_w39_ui_smoke
308 | 11 | W39 reconciliation (owner tracker 2026-10-07) | UX-01 | Dashboard | Investor / Trader mode + progressive disclosure | Consumer UX gap (owner Gap Analysis: 50% -> 90%) | Owner deployment tracker: Gap Analysis | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 80 |  | Investor / Trader mode preference (W17 INT-001); W39: Simple / Detailed view on /wealth -- Simple hides the audit, ledger and trade-level tables | Owner UAT of which panels belong in Simple | dashboard/wealth_page.py | tests/test_w39_retail.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39 developed 2026-10-07 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | 8 | tests/test_w39_retail.py ¦ 100% of 20 lines in 1 key file(s) run by: test_w39_perf_budget, test_w39_retail, test_w39_ui_smoke, test_wealth_api_security
309 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-RS | Research | Equity research reports (RS-01..10) | Institutional-style valuation, targets, ratings, reports with disclosures and tracked calls | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/valuation.py (DCF + scenarios + sensitivity, justified P/B, peer / own-history multiples); research/report.py (12-month targets, ratings, SEBI-style disclosures, calls and hit rate); nightly 20:40 | No consensus estimates feed; XBRL key lines only (no 3-statement model); hit rates start from the first report and need PaRRVA review before being shown to others | research/valuation.py; research/report.py | tests/test_w39_research.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_research.py ¦ 90% of 554 lines in 2 key file(s) run by: test_w39_mcp, test_w39_research, test_w39_scorecard, test_w39_screener, test_w39_technicals, test_w39b_dvm, test_w39b_earnings_surprise, test_w39b_tf75
310 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-SCREENER | Research | Stock screener: fundamental + technical (SC-20) | Query screener with presets, saved screens and alerts | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/screener.py: query language (precedence, NOT, IN, aliases), presets, saved screens with new-match alerts, CSV; /screener | Independent QA | research/screener.py | tests/test_w39_screener.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_screener.py ¦ 88% of 446 lines in 1 key file(s) run by: test_w39_delivery, test_w39_mcp, test_w39_patterns, test_w39_rs_line, test_w39_scorecard, test_w39_screener, test_w39_screener_nl, test_w39_technicals (+5 more)
311 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-OPTIONS | Derivatives | Options strategy builder (OP-01..05) | Payoff, breakevens, POP and Greeks for multi-leg strategies | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | quant/options_strategy.py: templates, payoff and breakevens, POP, Greeks, implied IV, chain pricing; POST /api/options/(build¦analyse) | Analysis only: one-click execution needs the live OMS and the owner's explicit go-ahead | quant/options_strategy.py | tests/test_w39_options.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_options.py ¦ 88% of 209 lines in 1 key file(s) run by: test_signal_pipeline, test_w39_options, test_w40_option_intents
312 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-TECH | Technical Analysis | Technical scans, ratings and signals (TA-01..04) | 30 scans, 19 candle patterns, technical / RS ratings, signals with ATR levels and confluence | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py + research/tech_signals.py: scans, patterns, ratings, signals with entry / stop / target, confluence, outcomes (TARGET / STOPPED / EXPIRED); nightly 20:30 | Trust a scan only after ~30 closed signals (records start on the first run) | research/technicals.py; research/tech_signals.py | tests/test_w39_technicals.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_technicals.py ¦ 89% of 885 lines in 2 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+12 more)
313 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-PULSE | Market Intelligence | Market pulse (MP-01..05) | Global-cue model, GIFT gap, FII flow pressure, participant OI, OI walls | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/market_pulse.py + data/participant_oi.py: global-cue model, basis-free GIFT gap, FII streak / absorption, NSE participant OI positioning, OI walls; /market-pulse | Needs Nifty + global history loaded, Dhan index quotes for GIFT, NSE reachable for participant OI | research/market_pulse.py; data/participant_oi.py | tests/test_w39_market_pulse.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_market_pulse.py ¦ 70% of 529 lines in 2 key file(s) run by: test_w39_event_calendar, test_w39_global_sync, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate
314 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-REGIME | Market Intelligence | Market regime gate (RG-01..04) | Distribution / follow-through days, 200-DMA, signals tagged with or against the market | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/regime_gate.py: OPEN / CAUTION / CLOSED gate, signals tagged and never alerted against it, 'does the gate help' record | Thresholds are ATIP's choices (IBD tradition); evidence needs 30+ closed signals per side | research/regime_gate.py | tests/test_w39_regime_gate.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_regime_gate.py ¦ 83% of 248 lines in 1 key file(s) run by: test_w39_delivery, test_w39_event_calendar, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate, test_w39_rs_line, test_w39_scorecard, test_w39_technicals (+6 more)
315 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-TRACK | Research | Signal track record by regime and horizon (TR-01..03) | 5/20/60-session returns vs the Nifty per signal, by scan x gate and confluence | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/tech_signals.py forward returns and stats, shown next to today's signals | Useful after a few months of signals | research/tech_signals.py | tests/test_w39_track_record.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_track_record.py ¦ 85% of 587 lines in 1 key file(s) run by: test_w39_delivery, test_w39_mcp, test_w39_patterns, test_w39_regime_gate, test_w39_rs_line, test_w39_scorecard, test_w39_screener, test_w39_technicals (+9 more)
316 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-WEEKLY | Technical Analysis | Weekly technical rating (WK-01..02) | Weekly rating on completed weeks; daily / weekly agreement | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py weekly bars, rating, agreement as screener field and signal attribute | Independent QA | research/technicals.py | tests/test_w39_weekly.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_weekly.py ¦ 95% of 298 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
317 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-PATTERNS | Technical Analysis | Chart patterns from swing pivots (CP-01..04) and marks on the stock chart | Darvas box, VCP, double bottom, ascending triangle, head and shoulders; W39b: inverse H&S, descending triangle, channels, wedges, chart marks | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/patterns.py: patterns as scans with levels, screener setups, alerts held until a positive 30-signal record. W39b (CP-04): inverse head and shoulders, descending triangle, rising / falling channels (breakout and breakdown each), rising / falling wedges -- 14 pattern scans, each calibrated at 0.02-0.1 % of stock-days on random walks; the stock chart (/api/stock/{symbol}/history chart_marks) marks signals, pattern breakouts, candle patterns and the lines of the patterns in place, on daily / weekly / monthly bars, with a toggle | Rule-based approximations; independent QA; each new scan needs 30 closed signals before its alerts start | research/patterns.py; dashboard/stock_view.py | tests/test_w39_patterns.py; tests/test_w39b_patterns_more.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_patterns.py; tests/test_w39b_patterns_more.py ¦ 93% of 626 lines in 2 key file(s) run by: test_auto_recover, test_w39_delivery, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
318 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-RSLINE | Technical Analysis | RS-line new highs and size-group RS ranks (RL-01..02) | RS line new highs (also before price); RS ranks within AMFI size groups | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py RS line; AMFI size groups from shares x price | Independent QA | research/technicals.py | tests/test_w39_rs_line.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_rs_line.py ¦ 95% of 298 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
319 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-DELIVERY | Technical Analysis | Delivery-% spike scan (DL-01) | NSE delivery percentage spike as a scan and screener field | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py delivery spike scan, snapshot fields, preset | Independent QA | research/technicals.py | tests/test_w39_delivery.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_delivery.py ¦ 95% of 298 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+7 more)
320 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-SCORECARD | Research | Explainable fundamental scorecard (FS-01..03) | 5 axes x 6 pass / fail checks with their numbers, stored nightly with a record vs the Nifty | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/scorecard.py: value, earnings, growth, dividend, balance-sheet checks; screener fields and presets; nightly 20:50 | Reported (not forecast) growth; banks / NBFCs miss six checks by design; record needs months | research/scorecard.py | tests/test_w39_scorecard.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_scorecard.py ¦ 89% of 420 lines in 1 key file(s) run by: test_w39_mcp, test_w39_scorecard, test_w39_screener, test_w39_technicals, test_w39b_dvm, test_w39b_earnings_surprise, test_w39b_tf75
321 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-EVENTS | Market Intelligence | Macro event calendar (EV-01..03) | FOMC, US CPI, payrolls, RBI dates; the NSE session each hits; gap band widening | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/event_calendar.py: seeded dates, config / API additions, band widened after US releases | Seeded dates reach end-2026 (RBI Feb-2027): add next year's dates each December | research/event_calendar.py | tests/test_w39_event_calendar.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_event_calendar.py ¦ 85% of 159 lines in 1 key file(s) run by: test_w39_event_calendar, test_w39_global_sync, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate
322 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-INTRADAY | Technical Analysis | Intraday scans on 15-minute bars (IN-01..03) | Opening-range breakout, open = low / high, intraday squeeze with a record to the close | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/intraday_signals.py; every 15 minutes 09:45-15:50 | Needs the Dhan Data API (15-minute bars) and 3 sessions of stored bars | research/intraday_signals.py | tests/test_w39_intraday.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_intraday.py ¦ 88% of 225 lines in 1 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_regime_gate, test_w39_rs_line, test_w39_technicals, test_w39_weekly, test_w39b_tf75 (+2 more)
323 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-DEPTH20 | Data Platform | 20-level depth, depth-weighted imbalance and order-flow imbalance (DP-01..03, OF-01..03) | Dhan 20-level depth WebSocket, DWI, OFI from quote changes (best level and multi-level), persistent flags, validation | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | data/depth20.py: depth feed (off by default), DWI, OFI summed over every book update, logistic validation vs the next 1 / 5 minutes and OFI vs its own interval | Owner: depth20.enabled and the Dhan Data API | data/depth20.py | tests/test_w39_depth20.py; tests/test_w39b_ofi.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_depth20.py; tests/test_w39b_ofi.py ¦ 82% of 379 lines in 1 key file(s) run by: test_w39_depth20, test_w39b_ofi
324 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-GLOBALSYNC | Market Intelligence | Synchronised global-cue model (GS-01..03) | 15:30 / 08:45 snapshots of global futures, Asia and FX; the opening gap modelled on them | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/global_sync.py: snapshots, walk-forward record vs GIFT | Needs 40 mornings of snapshots (~2 months) | research/global_sync.py | tests/test_w39_global_sync.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_global_sync.py ¦ 84% of 128 lines in 1 key file(s) run by: test_w39_event_calendar, test_w39_global_sync, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate
325 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-NLSCREEN | Research | English to screener query (NL-01..03) | Plain-English screener queries, validated and never run unseen | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/screener_nl.py: Claude path when enabled, rule translator otherwise; POST /api/screener/ask | Claude path needs a working Anthropic key (KD-001) | research/screener_nl.py | tests/test_w39_screener_nl.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_screener_nl.py ¦ 95% of 199 lines in 1 key file(s) run by: test_w39_screener_nl
326 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-MCP | APIs | Read-only ATIP MCP server (MC-01..03) | 12 read-only tools over stdio on a query-only database connection | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | tools/atip_mcp.py; W40: 20 tools -- adds dvm, earnings_surprise, mf_search / mf_analytics / mf_sip / mf_compare, backtest_validation (stored CPCV / PBO) and chart_marks, each checked under query_only | Local stdio only (no hosted transport) | tools/atip_mcp.py | tests/test_w39_mcp.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_mcp.py ¦ 91% of 331 lines in 1 key file(s) run by: test_w39_mcp
327 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39-ORDERBOOK | Market Intelligence | Order-book pressure and open orders (OB-01..03) | Market-wide pending buy / sell pressure; a read-only view of your open orders | W39 (PR #4): docs/W39_RESEARCH_HISTORY_OPTIONS_HANDOFF.md | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | data/order_pressure.py (every 15 minutes, market hours); portfolio/open_orders.py | Needs the Dhan Data API; context, not a signal | data/order_pressure.py; portfolio/open_orders.py | tests/test_w39_market_pulse.py | Claude (development), PR #4 |  | 2026-10-07 |  | 2026-10-07 | W39 developed on branch ccr-643d84fc-yig8ts (PR #4), merged to master 2026-10-08; NOT DEPLOYED; independent validation PENDING | W39 (PR #4) | tests/test_w39_market_pulse.py ¦ 56% of 190 lines in 2 key file(s) run by: test_w39_event_calendar, test_w39_market_pulse, test_w39_mcp, test_w39_regime_gate, test_w39_scorecard, test_w39_screener, test_w39_technicals, test_w39b_dvm (+2 more)
328 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-TF75 | Technical Analysis | 75-minute technical rating and its agreement with the daily one | Trendlyne / TradingView-style intraday timeframe rating | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/technicals.py bars_75 / rating_75: the daily rating's votes on 75-minute bars built only from stored 15-minute bars (09:15 / 10:30 / 11:45 / 13:00 / 14:15), completed bars only, 35 bars (7 sessions) needed, never a stale session; stored in technical_snapshot (tech_rating_75*, rsi_14_75, supertrend_dir_75, bar_75_end, mtf_alignment_75) by the 20:30 run; screener fields and a preset | Independent QA. W40: a 75m column on /signals and GET /api/stock/{symbol}/rating-75 (on demand from the stored 15-minute bars, completed bars only); the /signals column is still the 20:30 snapshot | research/technicals.py; research/tech_signals.py; research/screener.py | tests/test_w39b_tf75.py; tests/test_w39b_tf75_signals.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_tf75.py; tests/test_w39b_tf75_signals.py ¦ 89% of 1331 lines in 3 key file(s) run by: test_w39_delivery, test_w39_intraday, test_w39_mcp, test_w39_owner_notes, test_w39_patterns, test_w39_perf_budget, test_w39_regime_gate, test_w39_rs_line (+13 more)
329 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-DVM | Research | DVM view: durability, valuation, momentum 0-100 and zones | Trendlyne-style DVM scores with explanations | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/dvm.py: durability from the scorecard's 12 health / past-performance checks, valuation from the research fair value (60 %) and P/E (P/B for financials) vs the industry median (40 %), momentum from the technical and RS ratings; every score explains itself with its numbers; seven zones; stored nightly on fundamental_scorecard (dvm_*); GET /api/research/dvm/{symbol}; DVM card on /research; 3 screener presets | Independent QA; weights are ATIP's definitions, not backtested -- record whether the zones pay before using them | research/dvm.py; research/scorecard.py; dashboard/w39_routes.py | tests/test_w39b_dvm.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_dvm.py ¦ 86% of 1044 lines in 3 key file(s) run by: test_auto_recover, test_w39_depth20, test_w39_event_calendar, test_w39_global_sync, test_w39_intraday, test_w39_market_pulse, test_w39_mcp, test_w39_options (+14 more)
330 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-PEAD | Research | Earnings surprise (SUE), EPS-trend proxy and a post-earnings-drift scan | Earnings surprise and PEAD (gap analysis 4.7) | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | research/earnings_surprise.py: SUE and revenue SUE vs the same quarter a year earlier (8-quarter standard deviation, 4 needed), point in time from the NSE broadcast date; EPS-trend revisions proxy; pead_bull / pead_bear scans (¦SUE¦ >= 2, first session after the filing, 60-session horizon) stored and tracked like every scan, alerts held until 30 closed signals with positive expectancy; 20:35 job; screener fields and a preset; GET /api/research/earnings-surprise/{symbol} | Independent QA; needs 9+ quarters of NSE XBRL history (run the history backfill); no consensus estimates (ATIP's own history only); filings arrive with the Saturday fundamentals job | research/earnings_surprise.py; research/tech_signals.py | tests/test_w39b_earnings_surprise.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_earnings_surprise.py ¦ 86% of 970 lines in 2 key file(s) run by: test_w39_delivery, test_w39_mcp, test_w39_patterns, test_w39_regime_gate, test_w39_rs_line, test_w39_scorecard, test_w39_screener, test_w39_technicals (+9 more) | For a consensus-based surprise: a consensus estimates feed (not available today)
331 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W39B-MFA | Wealth / Mutual funds | Mutual fund analytics on stored AMFI NAVs (read-only) | Value Research / Kuvera-style scheme analytics (gap analysis 4.3) | W39b (PR #5): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4; docs/ANALYSIS_TOOLS_AND_SIGNALS_PLAN_2026-10.md | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | data/mf_analytics.py: point-to-point and CAGR returns, 1Y / 3Y rolling returns with hurdle stats, volatility / Sharpe / Sortino, drawdown with dates, beta / alpha / tracking error vs a price index, SIP and lump-sum XIRR, category rank among stored schemes, side-by-side compare; 3 read-only GET routes; scheme detail card on /data-platform. W40: step-up SIP, stamp duty (0.005 %) and units rounded down to 3 decimals by default, optional flat exit load per instalment; volatility annualised by the NAVs actually observed a year (not a fixed 252) | Independent QA. Holding MFs in the wealth ledger stays out of scope (owner Scope Exclusions); benchmark is a price index (the W40 Nifty 50 TR is not wired here yet); peers limited to stored schemes; tiered exit loads not modelled | data/mf_analytics.py; dashboard/w35_routes.py; dashboard/w35_page.py | tests/test_w39b_mf_analytics.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W39b developed 2026-10-08 on branch claude/wizardly-curie-fbjeoa (PR #5); independent validation PENDING | W39b (PR #5) | tests/test_w39b_mf_analytics.py ¦ 87% of 688 lines in 3 key file(s) run by: test_auto_recover, test_w39_mcp, test_w39_ml_regime_lineage_surface, test_w39_perf_budget, test_w39_ui_smoke, test_w39b_mf_analytics
332 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W40-RISKMODEL | Risk & Portfolio | Fundamental factor risk model (Barra-style) | Factor exposures, factor returns, covariance, specific risk and portfolio risk decomposition | W40 (PR #9): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4 items 5 and 9; tracker next actions | P1 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | quant/risk_model.py: 8 styles (size, beta, momentum, residual volatility, book-to-price, earnings yield, ROE, liquidity) point in time, winsorised and cap-standardised, NSE industries (small ones pooled); daily sqrt(cap)-weighted regression with the industry constraint and robust t statistics; EWMA / Newey-West factor covariance; shrunk EWMA specific risk; decomposition of the PAPER / LIVE book (factor vs specific, per factor, marginal per stock, beta, active risk vs a cap-weighted Nifty 50 proxy); bias statistic on standard portfolios; nightly 21:45, incremental; /trading and /quant cards | Independent QA on the real database; needs filed share counts for 30+ stocks; universe and industries are today's (survivorship); no free-float data | quant/risk_model.py; portfolio/risk.py; dashboard/risk_model_routes.py | tests/test_w40_risk_model.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W40 developed 2026-10-09 on branch claude/wizardly-curie-fbjeoa (PR #9); independent validation PENDING | W40 (PR #9) | tests/test_w40_risk_model.py ¦ 76% of 1466 lines in 3 key file(s) run by: test_auto_recover, test_w39_perf_budget, test_w39_qa_suite, test_w39_quant_portfolio, test_w39_ui_smoke, test_w40_risk_model, test_w40_total_return
333 | 11 | W39 reconciliation (owner tracker 2026-10-07) | W40-META | AI/ML | Meta-labelling of the technical signals (AFML ch. 3-4, 7, 10) | A second model deciding which primary signals to take, with bet sizes | W40 (PR #9): docs/ATIP_GAP_ANALYSIS_2026-10.md section 4 items 5 and 9; tracker next actions | P2 | IMPLEMENTED BUT NOT VERIFIED | COMPLETED | 85 |  | ml/meta_label.py: triple-barrier labels from the signal engine's own outcome rule; 37 features known at the signal's close; sample weights by average uniqueness; purged k-fold with embargo; GBM / logistic / RF; out-of-fold precision / recall / AUC and the kept signals' expectancy vs all; AFML bet sizing (reported only); ADOPTABLE only with 200+ signals and t >= 2, and the registry refuses activating anything else; Saturday retrain and 20:45 scoring, both off unless meta_label.enabled; /signals column when adopted | Owner: switch on after a few hundred closed signals exist and a version is ADOPTABLE; independent QA | ml/meta_label.py; ml/validation.py; dashboard/w40_routes.py | tests/test_w40_meta_label.py | Claude (development) |  | 2026-10-07 |  | 2026-10-07 | W40 developed 2026-10-09 on branch claude/wizardly-curie-fbjeoa (PR #9); independent validation PENDING | W40 (PR #9) | tests/test_w40_meta_label.py ¦ 90% of 861 lines in 3 key file(s) run by: test_auto_recover, test_w39_qa_suite, test_w39_regime_gate, test_w39_technicals, test_w40_meta_label

## Blockers
ID | Feature | Status | Completion % | Blocker / Input Required | Current Implementation | Next Action / Missing Work
SE-05 | AI-driven strategies | BLOCKED | 75 | Evidence, not a decision: no ML model version has passed validation (W24: NO_EDGE). Re-train when more history exists (DP-23 backfill) and activate only an ADOPTABLE model | W28 ml/ai_strategy.py: 8-gate readiness chain per ML strategy (ml.enabled, default_model, model, ACTIVE version, validation not NO_EDGE, fresh predictions, backtest, W4 risk gate) + guarded activation (PAPER first, ACTIVE only from PAPER) via lifecycle.transition; /ml panel | Blocked on a model with edge: no ML model registered in production; W24 validation showed NO_EDGE
BR-08 | Sandbox | BLOCKED | 70 | Owner: a Dhan-issued sandbox token, then run python -m orders.sandbox_check --place-test-order | W29: SANDBOX now uses its own credentials (dhan_sandbox_client_id / token; the old path reused the production token, which the sandbox rejects); verified redirect; python -m orders.sandbox_check (credentials, redirect, reachability, auth, optional place/status/cancel round trip); /api/execution/sandbox-check | Needs a Dhan-issued sandbox token (owner) -- then run the check with --place-test-order
ENT-07 | Secure internet exposure | BLOCKED | 5 | Owner decision: how ATIP is exposed to the internet (Cloudflare Tunnel / Tailscale / VPS reverse proxy), the domain and TLS | Not implemented by design: W7 keeps the 127.0.0.1 bind; exposure needs TLS, MFA, rate limiting, security review | Owner decision + security architecture
ENT-14 | Regulatory approvals | BLOCKED | 30 | Legal: a qualified professional must review and sign off each register item (SEBI RA / IA applicability) | W38: regulatory sign-off register (10 items: SEBI RA/IA, retail algo framework, broker API terms, NSE data redistribution, DPDP, CERT-In, terms, payments/GST, live-risk sign-off, annual review) gated pre_multi_user / pre_live / ongoing; sign-off needs reviewer + reference, audited; compliance check fails if a gate is crossed with open items; docs/ENT14_REGULATORY_PACK.md | LEGAL WORK: a qualified professional must review and sign off each item
ENT-08 | Multi-user web app | BLOCKED | 65 | Depends on ENT-07 (no exposure decided) | /app user web app + /admin/console (W32), local-only | Blocked on ENT-07 for any exposure
ENT-04 | Subscriptions & billing | BLOCKED | 90 | Owner: a KYC-activated Razorpay business account with Invoices and Subscriptions enabled; store RAZORPAY_KEY_ID / RAZORPAY_KEY_SECRET / WEBHOOK_SECRET_RAZORPAY with python -m ops vault-set; registering the webhook URL needs ENT-07 (public HTTPS) | Plans, subscriptions, invoices DRAFT/OPEN/PAID, provider interface (sandbox/noop), dunning + grace, payment webhook consumer. W39b (gateway decision delegated: Razorpay -- UPI / cards / netbanking, native Subscriptions): enterprise/razorpay.py on the existing payments interface -- REST v1 invoices with idempotent receipts, customers, plans, autopay subscriptions, cancel; signed webhook mapping onto invoices, payments, refunds, dunning and grace (out-of-order safe, money once per Razorpay id); reconcile() polling so payments settle without a public webhook; keys only from the vault; live keys refused without billing.razorpay.allow_live and the production environment | Owner: run the flows in Razorpay test mode (docs/BILLING_RAZORPAY.md); GST tax lines are not built (ENT-14 PAYMENTS-TAX)
ENT-09 | Mobile apps | IMPLEMENTED BUT NOT VERIFIED | 45 | Native apps: Apple / Google developer accounts and an exposure decision (ENT-07); the PWA (/m) works today on a private network | W38: installable mobile web app (PWA) at /m -- read-only phone summary (market health, Nifty/VIX, global, buy/sell, trade of the day, P&L, pipeline, alerts), manifest + service worker (shell cached, no API data cached), offline last-good view; no token in the page | Native Android/iOS apps not built; reaching /m from a phone needs a private tunnel or the ENT-07 exposure
ENT-16 | Scalability, HA & observability | BLOCKED | 50 | Owner decision: switch the production runtime to PostgreSQL and choose a cloud host (OPS-04 packaging is ready) | Observability (W8) + shared state, job leader lease, DB backend abstraction, sqlite->postgres tool (W9 merge) | DBS-05 (PostgreSQL path) and OPS-04 (container packaging) are done (W38); multi-instance HA needs the runtime moved to PostgreSQL and a host
UAT-001 | Beta / UAT | BLOCKED | 70 | Owner: execute the UAT journeys (docs/W19_UAT_PLAN.md, W33 section 5) and record acceptance | W19 personas, persona view, feedback, UAT plan + W33 SaaS personas (platform admin, tenant admin, tenant trader, MFA user) with journeys and acceptance criteria | Owner UAT; exit criteria W33 section 5
EX-19 | Broker-side GTT / forever orders | BLOCKED | 20 | Owner authorization for LIVE broker order placement (live trading is off by design) and the Dhan forever-order API enabled on the account | ATIP-side trigger rules (orders/rules.py) fire while ATIP runs; nothing is placed at the broker | Place / modify / cancel broker GTT (Dhan forever-order API, Kite GTT) for LIVE positions
W39B-PEAD | Earnings surprise (SUE), EPS-trend proxy and a post-earnings-drift scan | IMPLEMENTED BUT NOT VERIFIED | 85 | For a consensus-based surprise: a consensus estimates feed (not available today) | research/earnings_surprise.py: SUE and revenue SUE vs the same quarter a year earlier (8-quarter standard deviation, 4 needed), point in time from the NSE broadcast date; EPS-trend revisions proxy; pead_bull / pead_bear scans (¦SUE¦ >= 2, first session after the filing, 60-session horizon) stored and tracked like every scan, alerts held until 30 closed signals with positive expectancy; 20:35 job; screener fields and a preset; GET /api/research/earnings-surprise/{symbol} | Independent QA; needs 9+ quarters of NSE XBRL history (run the history backfill); no consensus estimates (ATIP's own history only); filings arrive with the Saturday fundamentals job

## Master Tracker
Wave | Module / Workstream | Scope / Deliverables | Track | Development Status | Testing Status | Current Status / Rationale | Next Action / Dependency
1 | Foundation & Architecture | Core architecture, project setup, database, authentication, base services | Existing ATIP baseline | Completed | In Progress | [2026-10-07] 36/36 features developed (22 COMPLETED, 14 awaiting independent QA); automated tests: 18 covered, 14 partly, 1 none | Independent QA (QA-001) + owner UAT (UAT-001)
2 | Market Data Integration | Dhan live quotes, historical data, index data, market feeds | Existing ATIP baseline | Completed | In Progress | [2026-10-07] 27/27 features developed (10 COMPLETED, 17 awaiting independent QA); automated tests: 11 covered, 16 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
3 | Technical Analysis | Technical indicators, calculations, chart/indicator services | Existing ATIP baseline | Completed | Completed (automated) | [2026-10-07] 12/12 features developed (5 COMPLETED, 7 awaiting independent QA); automated tests: 12 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
4 | AI Scoring Engine | VPI, SPI, RRI, MRI, CRI, ZPI and related scoring | Existing ATIP baseline | Completed | In Progress | [2026-10-07] 49/49 features developed (14 COMPLETED, 35 awaiting independent QA); automated tests: 36 covered, 13 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
5 | Signal & Strategy Engine | Signal generation, entry/exit logic, signal log, strategy rules | Existing ATIP baseline | Completed (blocked items) | In Progress | [2026-10-07] 18/19 features developed (16 COMPLETED, 2 awaiting independent QA); automated tests: 11 covered, 7 partly, 0 none; BLOCKED: SE-05 | Evidence, not a decision: no ML model version has passed validation (W24: NO_EDGE). Re-train when more history exists (DP-23 backfill) and activate only an ADOPTABLE model
6 | Backtesting | Historical strategy testing, performance metrics, strategy comparison | Existing ATIP baseline | Completed | In Progress | [2026-10-07] 32/32 features developed (15 COMPLETED, 17 awaiting independent QA); automated tests: 22 covered, 10 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
7 | Paper Trading & Order Rules | Paper broker, order rules engine, simulated execution | Existing ATIP baseline | Completed (blocked items) | In Progress | [2026-10-07] 47/49 features developed (25 COMPLETED, 22 awaiting independent QA); automated tests: 26 covered, 21 partly, 0 none; BLOCKED: BR-08, EX-19 | Owner authorization for LIVE broker order placement (live trading is off by design) and the Dhan forever-order API enabled on the account ¦ Owner: a Dhan-issued sandbox token, then run python -m orders.sandbox_check --place-test-order
8 | Portfolio & Dashboard | Portfolio health, dashboard tabs, market/portfolio views | Existing ATIP baseline | Completed | In Progress | [2026-10-07] 36/36 features developed (17 COMPLETED, 19 awaiting independent QA); automated tests: 25 covered, 11 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
9 | Integration / Stabilization | Cross-module integration, aggressive exit strategy, end-to-end stabilization | Current deployment through Wave 9 | Completed (blocked items) | In Progress | [2026-10-07] 18/23 features developed (2 COMPLETED, 16 awaiting independent QA); automated tests: 5 covered, 13 partly, 0 none; BLOCKED: ENT-07, ENT-14, ENT-08, ENT-04, ENT-16 | Depends on ENT-07 (no exposure decided) ¦ Legal: a qualified professional must review and sign off each register item (SEBI RA / IA applicability) ¦ Native apps: Apple / Google developer accounts and an exposure decision (ENT-07); the PWA (/m) works today on a private network ¦ Owner decision: how ATIP is exposed to the internet (Cloudflare Tunnel / Tailscale / VPS reverse proxy), the domain and TLS
11 | ATIP-INV-001 — Investor DNA | Investor profile, risk capacity/tolerance/requirement, investment horizon, behavioural profile, trading personality | New wealth track | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
12 | ATIP-WLT-001 — Multi-Asset Wealth Dashboard | Unified wealth view for stocks, ETFs, gold, bonds, international assets, cash and supported holdings | New wealth track | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
13 | ATIP-GOL-001 — Goal Planning Engine | Financial goals, target corpus, target date, contributions, CAGR, shortfall/surplus and scenarios | New wealth track | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
14 | ATIP-AAL-001 — Dynamic Asset Allocation Engine | Strategic + tactical allocation using Investor DNA, goals, market regime and ATIP intelligence | New wealth track | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
15 | ATIP-RBL-001 — Portfolio Rebalancing Engine | Target allocation, drift, risk reduction, transaction-cost awareness and rebalance recommendations | New wealth track | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
15.5 | ATIP-PERF-001 — Investor Performance Attribution | Full performance-trust layer: Model Return, Executable Return, Actual Investor Return, Benchmark Return; trade-level attribution; average cost; weighted position sizing; slippage; brokerage/transaction costs; realized/unrealized P&L; XIRR; CAGR; Alpha; Sharpe; Sortino; maximum drawdown; win rate; profit factor; holding period; signal-to-execution attribution; portfolio-vs-model variance; performance audit trail; performance dashboards and downloadable reports. | Cross-cutting trust layer | Completed | Completed (automated) | [2026-10-07] 15/15 features developed (0 COMPLETED, 15 awaiting independent QA); automated tests: 15 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
16 | ATIP-AIA-001 — AI Investment Advisor | Explainable AI advisor using investor profile, goals, portfolio, market data, models, risk and scenarios | New wealth track | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
17 | ATIP-INT-001 — Integrated Intelligence | End-to-end integration of investor, goals, allocation, portfolio, rebalancing, market intelligence and AI advisor | Integration | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
18 | ATIP-QA-001 — Full QA / Security / Performance | Functional, regression, API, data, security, performance, resilience and model validation | Quality gate | In Progress | Completed (automated) | [2026-10-07] 0/1 features developed (0 COMPLETED, 0 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none; open: QA-001 | Independent QA (QA-001) + owner UAT (UAT-001)
19 | ATIP-UAT-001 — Beta / User Acceptance | Realistic investor/trader journeys, usability, acceptance, defect triage and business validation | Release validation | Blocked | Yet to Start | [2026-10-07] 0/1 features developed (0 COMPLETED, 0 awaiting independent QA); automated tests: 0 covered, 0 partly, 0 none; BLOCKED: UAT-001 | Owner: execute the UAT journeys (docs/W19_UAT_PLAN.md, W33 section 5) and record acceptance
20 | ATIP-REL-001 — Production Hardening | Release readiness, monitoring, logging, backup/recovery, deployment, documentation and production controls | Production | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA (QA-001) + owner UAT (UAT-001)
W21 | Data & technical analysis (VWAP, S/R, betas, multi-timeframe, sector breadth) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 11/11 features developed (0 COMPLETED, 11 awaiting independent QA); automated tests: 8 covered, 3 partly, 0 none | Independent QA
W22 | Factor research platform (formulas, factors, approval gate, studies) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 10/10 features developed (0 COMPLETED, 10 awaiting independent QA); automated tests: 4 covered, 6 partly, 0 none | Independent QA
W23 | Research & backtesting depth (optimisation, sensitivity, robustness) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 6/6 features developed (0 COMPLETED, 6 awaiting independent QA); automated tests: 4 covered, 2 partly, 0 none | Independent QA
W24 | Machine learning (GBM / RF / ensemble, walk-forward validation, anomalies, decay) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 10/10 features developed (0 COMPLETED, 10 awaiting independent QA); automated tests: 6 covered, 4 partly, 0 none | Independent QA
W25 | Portfolio risk (exposure, concentration, correlation, VaR / ES, optimiser, emergency exit) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 14/14 features developed (0 COMPLETED, 14 awaiting independent QA); automated tests: 3 covered, 11 partly, 0 none | Independent QA
W26 | Dashboard signals table + stock history panel | repository wave (platform extension) | Platform extension | Completed | Completed (automated) | [2026-10-07] 1/1 features developed (0 COMPLETED, 1 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none | Independent QA
W27 | Data & scores (NSE fundamentals, ownership, F&O summary, live feed, pre-open) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 10/10 features developed (0 COMPLETED, 10 awaiting independent QA); automated tests: 6 covered, 4 partly, 0 none | Independent QA
W28 | Strategy & AI (intraday scans, lists, strategy performance, news AI) | repository wave (platform extension) | Platform extension | Completed (blocked items) | In Progress | [2026-10-07] 10/11 features developed (0 COMPLETED, 10 awaiting independent QA); automated tests: 3 covered, 7 partly, 0 none; BLOCKED: SE-05 | Independent QA
W28b | News weighting + announcement NLP | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 2/2 features developed (0 COMPLETED, 2 awaiting independent QA); automated tests: 0 covered, 2 partly, 0 none | Independent QA
W29 | Execution (stop orders, modify, reconciliation, broker health, slippage, live P&L) | repository wave (platform extension) | Platform extension | Completed (blocked items) | In Progress | [2026-10-07] 10/11 features developed (0 COMPLETED, 10 awaiting independent QA); automated tests: 5 covered, 5 partly, 0 none; BLOCKED: BR-08 | Independent QA
W30 | Advanced quant (value / size, IV, pairs short leg, events, microstructure) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 6/6 features developed (0 COMPLETED, 6 awaiting independent QA); automated tests: 3 covered, 3 partly, 0 none | Independent QA
W31 | Production hardening (off-site backups, vault, API reference, breakers, rollback drill) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 6/6 features developed (0 COMPLETED, 6 awaiting independent QA); automated tests: 1 covered, 4 partly, 0 none | Independent QA
W32 | Enterprise SaaS layer (tenants, onboarding, billing foundation, alerts, webhooks) | repository wave (platform extension) | Platform extension | Completed (blocked items) | In Progress | [2026-10-07] 5/6 features developed (0 COMPLETED, 5 awaiting independent QA); automated tests: 1 covered, 4 partly, 0 none; BLOCKED: ENT-08 | Independent QA
W33 | QA / UAT preparation | repository wave (platform extension) | Platform extension | In Progress | Completed (automated) | [2026-10-07] 0/2 features developed (0 COMPLETED, 0 awaiting independent QA); automated tests: 1 covered, 0 partly, 0 none; BLOCKED: UAT-001; open: QA-001 | see Blockers
W34 | Execution microstructure (algos, impact, latency, event-driven OMS / backtester) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 5/5 features developed (0 COMPLETED, 5 awaiting independent QA); automated tests: 2 covered, 3 partly, 0 none | Independent QA
W35 | Data platform (lake, ticks, depth, F&O chains, macro, MF / multi-asset, alt data) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 8/8 features developed (0 COMPLETED, 8 awaiting independent QA); automated tests: 2 covered, 6 partly, 0 none | Independent QA
W36 | ML & strategy tooling (neural net, RL, AI assistant, strategy builder, derivatives factors) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 6/6 features developed (0 COMPLETED, 6 awaiting independent QA); automated tests: 3 covered, 3 partly, 0 none | Independent QA
W37 | Brokers & multi-asset (vault, connectors, multi-broker import, paper options) | repository wave (platform extension) | Platform extension | Completed | In Progress | [2026-10-07] 4/4 features developed (0 COMPLETED, 4 awaiting independent QA); automated tests: 2 covered, 2 partly, 0 none | Independent QA
W38 | Platform & compliance (PostgreSQL path, containers, compliance, privacy, PWA) | repository wave (platform extension) | Platform extension | Completed (blocked items) | In Progress | [2026-10-07] 5/6 features developed (0 COMPLETED, 5 awaiting independent QA); automated tests: 3 covered, 1 partly, 0 none; BLOCKED: ENT-14 | Independent QA
W39 | Tracker reconciliation: PERF-001 detail, owner notes, feature-map gaps, retail parity | repository wave (platform extension) | Platform extension | In Progress | Completed (automated) | [2026-10-07] 59/61 features developed (1 COMPLETED, 58 awaiting independent QA); automated tests: 60 covered, 0 partly, 0 none; BLOCKED: EX-19; open: QA-001 | see Blockers

## Gap Analysis
Area | Current Estimated % | Target % | Gap % | Mitigation | Tracker-derived % (2026-10-07) | Features counted | Blocked in area
Market intelligence | 85 | 100 | 15 | Maintain and strengthen data quality, regime intelligence and cross-asset inputs | 81.9 | 36 | -
Technical analysis | 90 | 100 | 10 | Validate all indicators and edge cases | 79.2 | 12 | -
Quant signals | 80 | 100 | 20 | Improve model validation, signal lifecycle and performance attribution | 79.8 | 41 | -
Backtesting | 80 | 100 | 20 | Add realistic costs, slippage, benchmark and reproducibility controls | 85.5 | 19 | -
Paper trading | 80 | 100 | 20 | Validate complete simulated order lifecycle | 82.2 | 9 | -
Active trading | 65 | 100 | 35 | Strengthen execution, risk controls and broker integration | 80.2 | 49 | BR-08, EX-19
Portfolio intelligence | 70 | 100 | 30 | Integrate portfolio health, concentration, risk and goals | 82.8 | 18 | -
Investor profiling | 25 | 100 | 75 | Wave 11 — Investor DNA | 80 | 1 | -
Goal planning | 20 | 100 | 80 | Wave 13 — Goal Planning Engine | 80 | 1 | -
Asset allocation | 35 | 100 | 65 | Wave 14 — Dynamic Asset Allocation | 83.8 | 4 | -
Portfolio rebalancing | 30 | 100 | 70 | Wave 15 — Portfolio Rebalancing | 85 | 2 | -
Wealth aggregation | 25 | 95 | 70 | Wave 12 — Multi-Asset Wealth Dashboard | 78.3 | 3 | -
Consumer UX | 50 | 90 | 40 | Investor Mode + Trader Mode + progressive disclosure | 78.9 | 23 | -
AI Investment Advisor | 25 | 100 | 75 | Wave 16 — Explainable AI Advisor | 82.5 | 2 | -

## Scope Exclusions
Scope | Area | Reason | Status in code (2026-10-07)
Excluded from this mitigation plan | NPS | Explicitly excluded by user | Not built (excluded).
Excluded from this mitigation plan | FDs | Explicitly excluded by user | Not built (excluded).
Excluded from this mitigation plan | Tax | Explicitly excluded by user | Not built: rebalancing is tax-neutral by design (wealth/rebalance.py); costs include STT / stamp / GST only as transaction charges.
Excluded from this mitigation plan | Insurance | Explicitly excluded by user | Not built (excluded).
Excluded from this mitigation plan | Mutual Funds | Excluded from the requested mitigation scope | Data only: AMFI daily NAVs are ingested (DP-21, the owner's note 'amfi for MF data'); no MF planning / advice features.

## Roadmap
Milestone | Wave | Deliverable | Priority | Status (2026-10-07)
Baseline | Waves 1–9 | Existing deployment baseline | Completed / stabilization | Completed (blocked items)
Investor foundation | Wave 11 | Investor DNA | Critical | Completed
Wealth foundation | Wave 12 | Multi-Asset Wealth Dashboard | Critical | Completed
Planning | Wave 13 | Goal Planning Engine | Critical | Completed
Allocation | Wave 14 | Dynamic Asset Allocation | Critical | Completed
Risk control | Wave 15 | Rebalancing + Performance Attribution | Critical | Completed
AI layer | Wave 16 | AI Investment Advisor | Critical | Completed
Integration | Wave 17 | End-to-end integration | Critical | Completed
Quality gate | Wave 18 | QA/Security/Performance | Critical | In Progress
Validation | Wave 19 | Beta/UAT | Critical | Blocked
Release | Wave 20 | Production hardening | Critical | Completed

## PERF-001 Detail
ID | Requirement | Description | Priority | Dependency | Development Status | Testing Status | Acceptance Criteria | Implementation (2026-10-07) | Automated tests | Remaining
PERF-001-01 | Performance data model | Store signals, orders, fills, positions, cash, costs, benchmarks and timestamps | Critical | Waves 5–8 | Completed | Completed (automated) | Complete auditable schema with immutable transaction history | perf_ledger append-only (migration 0005 triggers; UPDATE/DELETE refused); source refs per import; W39: order_ref, signal_ref, fee_breakdown, entry_seq (portable entry order, migration 0006), DEPOSIT / WITHDRAWAL cash rows, paper PARTIALLY_FILLED orders imported (were lost) | test_paper_partial_fills_reach_the_ledger; test_entry_order_is_portable_and_numbered; test_migration_0006_numbers_old_rows_and_the_ledger_stays_append_only; test_cash_rows_and_fee_breakdown_are_validated; test_voided_transactions_are_ignored_but_kept | Positions are derived from the ledger by design (no second source of truth); independent QA
PERF-001-02 | Model Return | Return assuming model signal execution at defined model price/rules | Critical | Backtesting/Signal Engine | Completed | Completed (automated) | Reproducible from signal log | model.build: BUY signals (duplicate_of IS NULL) at the signal close, exit at horizon / SELL signal, equal weight, gross; pure function of signal_log + prices_daily | test_model_return_is_reproducible_and_matches_a_hand_calculation; test_model_and_executable_are_reported_separately | Independent QA
PERF-001-03 | Executable Return | Return after realistic execution assumptions including slippage and liquidity | Critical | Order Rules/Paper Trading | Completed | Completed (automated) | Matches execution simulation within tolerance | next-session open x (1 + slippage bps), NSE cost model both sides, ADV cap (NOT_EXECUTABLE); W39: liquidity UNKNOWN flag when volume is missing, exit liquidity check, optional square-root market-impact slippage (slippage_model=impact: half spread + Y x sigma x sqrt(Q/ADV), inputs up to the signal date) | test_executable_applies_slippage_costs_and_the_liquidity_cap; test_impact_slippage_uses_the_square_root_estimate_known_at_the_signal | Parity with the OMS paper fill model is not automated (different fill rule by design)
PERF-001-04 | Actual Investor Return | Return based on actual investor quantities, prices, cash flows and exits | Critical | Portfolio/Orders | Completed | Completed (automated) | Matches ledger-derived P&L/XIRR | engine.run_actual: average cost, TWR, XIRR, PME; W39: realized P&L / fees / dividends for the period and lifetime-to-end, labelled; whole-account return with cash | test_period_scope_is_separate_from_lifetime; test_xirr_and_pme_match_hand_computed_flows; test_average_cost_realized_pnl_and_fees | Independent QA
PERF-001-05 | Benchmark Return | Compare strategy/portfolio against NIFTY/index/sector/selected benchmark | High | Market Data | Completed | Completed (automated) | Benchmark period and methodology clearly displayed | any prices_daily symbol (NIFTY50, NIFTYBANK, midcap, smallcap, sector indices); price return over the same sessions + PME of the investor's flows; W39: days invested shown and exported. W40: benchmark "nifty50tr" -- the Nifty 50 with dividends reinvested (data/total_return.py: NSE's TRI method, the price index exact, its dividend points estimated from the top 50 stored stocks by cap, picked monthly and weighted daily; nightly 21:10; GET /api/data/total-return), part of the report's audited inputs | test_benchmark_return_is_the_price_return_over_the_sessions; tests/test_w40_total_return.py | Independent QA; the dividend part is an estimate (no free-float or constituent data) -- compare once with NSE's published TRI
PERF-001-06 | Cost Attribution | Brokerage, exchange charges, slippage and other supported transaction costs | Critical | Order Data | Completed | Completed (automated) | Costs reconcile exactly to transaction ledger | W39: fees per kind for the period (dividend TDS and capped-sell fees counted), independent SUM over perf_ledger reconciliation, recorded components (fee_breakdown), itemised NSE statutory estimate for trades without a breakdown, slippage vs reference price; broker imports carry the contract-note split (brokerage / STT / exchange / SEBI / stamp / GST / DP) per trade, and a contract-note charges file becomes FEE rows (no double count) | test_costs_reconcile_with_dividend_tax_fee_rows_and_a_capped_sell; test_statutory_estimate_itemises_paper_brokerage_only_trades; tests/test_w39_contract_note_fees.py | Independent QA with real broker contract notes
PERF-001-07 | Position Attribution | Entry timing, exit timing, position sizing and averaging impact | Critical | Portfolio Data | Completed | Completed (automated) | Variance from model is decomposed | entry timing + averaging + exit timing + costs = actual - model P&L on the same quantity; W39: + sizing effect = actual - model P&L on the model notional | test_sizing_effect_completes_the_decomposition_and_exact_links_win; test_position_attribution_identity | Independent QA
PERF-001-08 | Return Metrics | CAGR, XIRR, Alpha, Sharpe, Sortino, drawdown, win rate, profit factor | High | Performance Engine | Completed | Completed (automated) | Metrics validated against independent calculations | metrics.py + backtest/metrics.py; W39 tests recompute Sharpe, Sortino, max drawdown, beta, alpha, volatility, CAGR with the statistics module | test_risk_metrics_match_independent_formulas; test_cagr_annualises_a_full_year; test_xirr_one_year_ten_percent; test_trade_stats | Independent QA
PERF-001-09 | Signal Attribution | Connect each signal to entry, add-on, exit and outcome | Critical | Signal Log | Completed | Completed (automated) | Complete signal lifecycle is traceable | link_signals: EXACT (the buy carries signal_ref, W39) or WINDOW (first buy within 5 sessions); add-ons, exits, open quantity, momentum outcomes; signal-driven vs discretionary P&L on the period gain (W39) | test_sizing_effect_completes_the_decomposition_and_exact_links_win | Independent QA
PERF-001-10 | Portfolio Attribution | Asset/sector/stock contribution to portfolio return and risk | High | Wealth Dashboard | Completed | Completed (automated) | Contributions reconcile to total portfolio return | gain by symbol / sector / asset class on average capital (sums to total); W39: Euler risk contribution (shares sum to 100%, volatility contributions to portfolio volatility), cash account | test_risk_contribution_reconciles_and_groups_sum_to_the_total; test_contributions_reconcile_to_the_total | Independent QA
PERF-001-11 | Performance Dashboard | Investor-facing comparison of model/executable/actual/benchmark returns | Critical | All above | Completed | Completed (automated) | No ambiguous single return figure | /wealth Performance tab: four returns with definitions and days invested, gaps, actual, costs, contribution, risk contribution, cash account, signal attribution, trades, audit + verify, ledger; overview card shows all four (W39 added EXECUTABLE) | test_routes_export_a_preview_and_verify_a_saved_report; test_happy_path_through_the_api | Owner UAT
PERF-001-12 | Audit & Explainability | Timestamped methodology, assumptions, calculation version and source data | Critical | All above | Completed | Completed (automated) | Every reported number can be traced to source data | audit block: methodology + CALCULATION_VERSION (+git), assumptions, ledger / signal / price content sha256, last price date per series, basis fallbacks; W39 verify() rebuilds a saved report and diffs it (GET .../reports/{id}/verify) | test_verify_reproduces_and_detects_changed_inputs | Independent QA
PERF-001-13 | Report Export | Downloadable performance report for selected period/portfolio/strategy | Medium | Dashboard | Completed | Completed (automated) | Export matches dashboard figures | CSV (every section, copied not recomputed) and JSON of a saved report; W39: preview export route, strategy filter (ACTUAL limited to one strategy's trades), printable HTML report (A4, Print / Save as PDF) rendered from the same sections as the CSV | test_export_carries_every_section_with_the_reports_numbers; test_strategy_filter_limits_the_actual_portfolio; test_printable_html_has_the_csv_sections_and_numbers_and_escapes_text | Owner UAT of the printed layout
PERF-001-14 | Regression & Edge Cases | Corporate actions, partial fills, averaging, cash flows, missing data, market holidays | Critical | All above | Completed | Completed (automated) | Defined edge-case suite passes | edge-case suite: split, bonus, partial fill, averaging, intraday round trip, OPENING, cash, holiday, missing bars, oversell, future date, void | test_a_trade_on_a_market_holiday_counts_on_the_next_session; test_missing_bars_are_reported_not_hidden; test_a_bonus_issue_keeps_value_and_cost; test_an_opening_position_is_measured_from_that_days_close; test_split_between_buy_and_today_moves_neither_value_nor_return | Independent QA

## Implementation Sequence
Sequence | Wave | Module | Primary Objective | Must Complete Before | Development Gate | Testing Gate | Development Status (2026-10-07) | Testing Status (2026-10-07)
1 | 1 | Foundation & Architecture | Establish stable ATIP baseline | None | Existing baseline verified | Baseline regression | Completed | In Progress
2 | 2 | Market Data Integration | Reliable live/historical market data | 1 | Data contracts stable | Data integrity tests | Completed | In Progress
3 | 3 | Technical Analysis | Validate indicator engine | 2 | Indicator APIs stable | Indicator validation | Completed | Completed (automated)
4 | 4 | AI Scoring Engine | Validate VPI/SPI/RRI/MRI/CRI/ZPI | 3 | Scores reproducible | Historical/model tests | Completed | In Progress
5 | 5 | Signal & Strategy Engine | Complete signal lifecycle | 4 | Signals traceable | Signal tests | Completed (blocked items) | In Progress
6 | 6 | Backtesting | Realistic backtesting | 5 | Strategy engine stable | Backtest reconciliation | Completed | In Progress
7 | 7 | Paper Trading & Order Rules | Execution simulation | 6 | Order lifecycle stable | Execution tests | Completed (blocked items) | In Progress
8 | 8 | Portfolio & Dashboard | Portfolio health and dashboards | 7 | Holdings data stable | UI/API regression | Completed | In Progress
9 | 9 | Integration / Stabilization | Stabilize existing product | 1–8 | Critical defects controlled | End-to-end regression | Completed (blocked items) | In Progress
10 | 11 | ATIP-INV-001 — Investor DNA | Build investor/risk/personality profile | 9 | Investor profile model/API | Profile/risk validation | Completed | Completed (automated)
11 | 12 | ATIP-WLT-001 — Multi-Asset Wealth Dashboard | Unify supported asset/holding views | 9,11 | Normalized wealth model | Reconciliation/UI tests | Completed | Completed (automated)
12 | 13 | ATIP-GOL-001 — Goal Planning Engine | Goal, corpus, contribution and scenario planning | 11,12 | Goal calculations stable | Scenario/financial math tests | Completed | Completed (automated)
13 | 14 | ATIP-AAL-001 — Dynamic Asset Allocation Engine | Strategic+tactical allocation | 11,13,9 | Allocation engine stable | Allocation/model tests | Completed | Completed (automated)
14 | 15 | ATIP-RBL-001 — Portfolio Rebalancing Engine | Drift, risk and rebalance recommendations | 12,14 | Target/current allocation stable | Rebalance simulations | Completed | Completed (automated)
15 | 15.5 | ATIP-PERF-001 — Investor Performance Attribution | Separate model/executable/actual/benchmark returns | 5,6,7,8,15 | Performance ledger and calculations stable | Independent metric reconciliation | Completed | Completed (automated)
16 | 16 | ATIP-AIA-001 — AI Investment Advisor | Explainable advisor using all trusted inputs | 11–15.5 | All core intelligence stable | AI response/evidence tests | Completed | Completed (automated)
17 | 17 | ATIP-INT-001 — Integrated Intelligence | End-to-end Investor + Trader integration | 11–16 | Integrated workflows stable | E2E regression/UAT prep | Completed | Completed (automated)
18 | 18 | ATIP-QA-001 — Full QA / Security / Performance | Full production quality gate | 17 | Critical defects closed | Full test suite | In Progress | Completed (automated)
19 | 19 | ATIP-UAT-001 — Beta / User Acceptance | Real-world user validation | 18 | UAT release candidate | UAT acceptance | Blocked | Yet to Start
20 | 20 | ATIP-REL-001 — Production Hardening | Production deployment readiness | 19 | Release checklist complete | Production smoke tests | Completed | Completed (automated)

## Master Dev Prompt
ATIP SEQUENTIAL DEVELOPMENT MASTER PROMPT Objective: Continue ATIP development from the existing deployment through Wave 9. Implement the remaining wealth, portfolio-intelligence and AI-advisor capabilities sequentially through Wave 20, including ATIP-PERF-001 Investor Performance Attribution. Do not rewrite, remove, or break any existing working ATIP functionality. Scope exclusions: Do NOT implement NPS, FDs, Tax or Insurance as part of this roadmap. Mutual Funds are also outside this mitigation scope unless an existing dependency requires a placeholder/interface only. Authoritative baseline: - Existing ATIP source repository and current local deployment. - Existing Waves 1–9 are the baseline. - Preserve Dhan live data, historical data, technical indicators, AI scoring, signal log, backtesting, paper broker, order rules engine, portfolio/dashboard functionality and existing APIs. - Existing functionality must be inspected before modification. Mandatory implementation sequence: Wave 11 — ATIP-INV-001 Investor DNA Wave 12 — ATIP-WLT-001 Multi-Asset Wealth Dashboard Wave 13 — ATIP-GOL-001 Goal Planning Engine Wave 14 — ATIP-AAL-001 Dynamic Asset Allocation Engine Wave 15 — ATIP-RBL-001 Portfolio Rebalancing Engine Wave 15.5 — ATIP-PERF-001 Investor Performance Attribution Wave 16 — ATIP-AIA-001 AI Investment Advisor Wave 17 — ATIP-INT-001 Integrated Intelligence Wave 18 — ATIP-QA-001 Full QA / Security / Performance Wave 19 — ATIP-UAT-001 Beta / User Acceptance Wave 20 — ATIP-REL-001 Production Hardening For EVERY wave: 1. Inspect the existing code, database, APIs, UI and documentation first. 2. Produce a short implementation assessment identifying reusable components and blockers. 3. Define database/schema/API/UI changes before coding. 4. Implement only the current wave. 5. Do not start the next wave until the current wave's development acceptance criteria pass. 6. Run unit, integration and regression tests appropriate to the wave. 7. Verify that existing Waves 1–9 functionality still works. 8. Record changed files, database migrations, APIs, UI routes/components and tests. 9. Update documentation. 10. Update the ATIP master tracker with Development Status, Testing Status, blockers and evidence. 11. If a blocker requires user input, stop that dependency and clearly report the exact input required; do not invent business rules. 12. Use feature flags/configuration where appropriate so existing production/stable functionality is protected. Detailed requirements: WAVE 11 — Investor DNA Build: - investor profile - risk capacity - risk tolerance - risk requirement - investment horizon - investment experience - liquidity needs - drawdown tolerance - behavioural profile - trading/investment personality - investor classification Output a transparent Investor DNA profile that can be consumed by Goals, Allocation, Rebalancing and AI Advisor. WAVE 12 — Multi-Asset Wealth Dashboard Build a normalized wealth/holdings layer for supported assets: - stocks - ETFs - gold - bonds - international assets - cash - supported broker holdings Provide total wealth, allocation, concentration, diversification, risk, liquidity and portfolio-health views. Do not add NPS, FD, Tax or Insurance. WAVE 13 — Goal Planning Engine Build: - goal creation - target amount - target date - current corpus - contribution plan - required CAGR - expected corpus - surplus/shortfall - inflation assumptions - bull/base/bear scenarios - crash/stress scenario - goal progress Connect goals to Investor DNA and portfolio allocation. WAVE 14 — Dynamic Asset Allocation Engine Build: - strategic asset allocation - tactical allocation - investor-risk constraints - goal constraints - market-regime inputs - ATIP market intelligence inputs - allocation recommendations - allocation drift analysis Reuse existing ATIP intelligence such as VPI/MRI/RRI/CRI/ZPI and market-regime signals where technically appropriate. Do not create duplicate market engines. WAVE 15 — Portfolio Rebalancing Engine Build: - target vs current allocation - drift calculation - concentration limits - risk reduction estimate - expected impact - transaction-cost awareness - rebalance recommendations - "Why rebalance?" explanation Do not perform autonomous live trades unless explicitly supported by the existing execution architecture and separately authorized. WAVE 15.5 — ATIP-PERF-001 Investor Performance Attribution This is mandatory and must be treated as a first-class module. Build: - performance data model - immutable transaction/performance ledger - Model Return - Executable Return - Actual Investor Return - Benchmark Return - realized/unrealized P&L - average cost - weighted position sizing - slippage - brokerage/transaction costs - entry/exit timing attribution - signal-to-trade lifecycle - position-sizing attribution - CAGR - XIRR - Alpha - Sharpe - Sortino - maximum drawdown - win rate - profit factor - holding period - portfolio/sector/stock contribution - performance dashboard - downloadable report - calculation-version and source-data audit trail Never combine Model Return and Actual Investor Return into one ambiguous number. Every reported number must be traceable to source transactions/signals and calculation methodology. WAVE 16 — ATIP-AIA-001 AI Investment Advisor Build an explainable advisor using: - Investor DNA - Goals - Wealth - Portfolio - Asset allocation - Rebalancing - Market intelligence - Technical analysis - Quant signals - Performance Attribution The advisor must answer "why" questions with evidence and show relevant risks, assumptions, scenarios and confidence. Do not make unsupported claims or hide the reasoning inputs. Separate informational analysis from execution; no autonomous investment/trading action without explicit authorization. WAVE 17 — Integrated Intelligence Integrate: Investor → Goals → Risk → Allocation → Portfolio → Market Intelligence → Signals → Rebalancing → Performance → AI Advisor. Provide separate Investor Mode and Trader Mode while sharing a common data/AI layer. WAVE 18 — Full QA / Security / Performance Execute: - functional tests - API tests - database tests - regression tests - integration tests - calculation reconciliation - performance/load tests - security tests - authentication/authorization tests - data-integrity tests - failure/recovery tests - browser/UI tests - model/signal validation - performance attribution reconciliation Critical defects must be closed before proceeding. WAVE 19 — Beta / UAT Run realistic journeys: - new investor onboarding - investor profile creation - goal creation - portfolio import - allocation analysis - rebalance recommendation - performance analysis - AI advisor questions - trader workflows Capture defects, usability issues and requested changes. No production release until acceptance criteria pass. WAVE 20 — Production Hardening Complete: - production configuration - secrets/security review - logging - monitoring - backups - recovery procedures - migrations - deployment scripts - rollback plan - smoke tests - documentation - operational runbook - release checklist Non-negotiable engineering rules: - Preserve all existing working functionality. - Do not replace working implementations simply for style or architecture preference. - Reuse existing services and data wherever possible. - No duplicate sources of truth. - No hard-coded financial calculations where they should be configuration/data driven. - Every financial metric must have a documented formula and test. - Every recommendation must be traceable to data/model inputs. - No silent changes to scoring formulas. - Use versioned models/formulas where required. - Maintain backward compatibility for existing APIs where possible. - Use migrations safely and provide rollback considerations. - Never claim a feature is complete without executable tests/evidence. Definition of Done for each wave: Development = implemented, integrated, documented and code-reviewed. Testing = unit + integration + regression tests appropriate to the wave pass. Evidence = changed files, test results, screenshots/API evidence where applicable. Status must be one of: Completed, In Progress, Blocked, Yet to Start. If blocked, state the exact blocker and exact user input required. Final objective: Deliver ATIP as an integrated Investment Intelligence + Portfolio/Wealth Intelligence + Explainable AI platform while retaining the existing Market/Trading Intelligence capabilities.

## Owner CSV vs repo
ID | Feature | Owner CSV status | Owner CSV % | Repo status (W39) | Repo % | Why
BT-04 | Parameter optimisation | IMPLEMENTED BUT NOT VERIFIED | 80 | IMPLEMENTED BUT NOT VERIFIED | 90 | W23: grid / random / adaptive optimiser with trial runs, test-window refusal, Deflated Sharpe + overfit warning. W40: method="bayes" -- a Tree-structured Parzen
BT-14 | Robustness | IMPLEMENTED BUT NOT VERIFIED | 80 | IMPLEMENTED BUT NOT VERIFIED | 90 | W23: robustness battery (costs x2, slippage x3, universe halves, period halves, regimes, Monte Carlo) with verdict. W39b: backtest/cpcv.py -- combinatorial purg
DP-08 | Derivatives data | IN PROGRESS | 35 | IMPLEMENTED BUT NOT VERIFIED | 85 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
SE-05 | AI-driven strategies | IN PROGRESS | 75 | BLOCKED | 75 | W5 developed 2026-09-25 (incl. completion pass) — framework only, no model trained or validated; independent testing PENDING (ChatGPT); see docs/W5_AI_ML_HANDOF
NS-05 | Novelty/decay/source weighting | YET TO START | 5 | IMPLEMENTED BUT NOT VERIFIED | 85 | W28b developed 2026-10-01 on branch w28b-news-weighting (on w33-wealth-qa) — independent validation PENDING (ChatGPT); see docs/W28B_NEWS_WEIGHTING_HANDOFF.md ¦
NS-06 | Earnings call / announcement NLP | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 75 | W28b developed 2026-10-01 on branch w28b-news-weighting (on w33-wealth-qa) — independent validation PENDING (ChatGPT); see docs/W28B_NEWS_WEIGHTING_HANDOFF.md ¦
ML-02 | Deep learning | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_ST
ML-04 | Reinforcement learning | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 75 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_ST
PF-06 | Rebalancing | IMPLEMENTED BUT NOT VERIFIED | 80 | IMPLEMENTED BUT NOT VERIFIED | 90 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md
DP-04 | Tick data | YET TO START | 5 | IMPLEMENTED BUT NOT VERIFIED | 75 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
DP-05 | Order book / depth | YET TO START | 5 | IMPLEMENTED BUT NOT VERIFIED | 75 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
AF-06 | Derivatives factors | BLOCKED | 20 | IMPLEMENTED BUT NOT VERIFIED | 80 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_ST
QR-05 | Stat-arb / pairs / cointegration | IMPLEMENTED BUT NOT VERIFIED | 85 | IMPLEMENTED BUT NOT VERIFIED | 90 | W6 developed 2026-09-25 — coding only; independent testing PENDING (ChatGPT); see docs/W6_ADVANCED_QUANT_HANDOFF.md
EX-11 | Execution algos | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W
EX-12 | Market impact model | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W
EX-15 | Latency telemetry | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W
EX-16 | Event-driven OMS | YET TO START | 10 | IMPLEMENTED BUT NOT VERIFIED | 80 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W
BT-17 | Event-driven backtester | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W34 developed 2026-10-01 on branch w34-execution-microstructure — independent validation PENDING (ChatGPT); see docs/W34_EXECUTION_MICROSTRUCTURE_HANDOFF.md ¦ W
DP-14 | Macroeconomic data | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
AD-01 | Alt-data framework | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
AD-02 | Alt-data sources | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 70 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
DP-22 | Point-in-time data lake | YET TO START | 5 | IMPLEMENTED BUT NOT VERIFIED | 80 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check 2026-10-07: c
DP-21 | Multi-asset data | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 70 | W35 developed 2026-10-01 on branch w35-data-platform — independent validation PENDING (ChatGPT); see docs/W35_DATA_PLATFORM_HANDOFF.md ¦ W39 check: AMFI mutual-
API-05 | API contracts/docs | IMPLEMENTED BUT NOT VERIFIED | 95 | IMPLEMENTED BUT NOT VERIFIED | 100 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md
API-06 | Widget JSON schemas | YET TO START | 5 | IMPLEMENTED BUT NOT VERIFIED | 85 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_ST
DBS-05 | Scalable database | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 70 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMP
ENT-06 | Per-user broker credential vault | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 85 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKER
ENT-14 | Regulatory approvals | YET TO START | 0 | BLOCKED | 30 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMP
SEC-05 | Compliance monitoring | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 80 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMP
ENT-17 | Data privacy | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 75 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMP
ENT-04 | Subscriptions & billing | IN PROGRESS | 70 | BLOCKED | 90 | W7 developed 2026-09-25 (enterprise layer, off by default) — coding only; independent testing PENDING (ChatGPT); see docs/W7_ENTERPRISE_HANDOFF.md
ENT-09 | Mobile apps | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 45 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMP
API-03 | Versioned public API | IMPLEMENTED BUT NOT VERIFIED | 80 | IMPLEMENTED BUT NOT VERIFIED | 90 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md
PF-12 | Multi-broker import | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 85 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKER
BR-07 | Additional brokers | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 75 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKER
ENT-15 | Multi-asset trading | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 85 | W37 developed 2026-10-02 on branch w37-brokers-multi-asset; 9 new tests + full suite 508/508 pass; independent validation PENDING (ChatGPT); see docs/W37_BROKER
SE-10 | No/low-code strategy builder | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 85 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_ST
ML-16 | AI chat assistant | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 85 | W36 developed 2026-10-02 on branch w36-ml-strategy-tooling; 13 new tests + full suite 499/499 pass; independent validation PENDING (ChatGPT); see docs/W36_ML_ST
OPS-04 | Cloud deployment | YET TO START | 0 | IMPLEMENTED BUT NOT VERIFIED | 75 | W38 developed 2026-10-02 on branch w38-platform-compliance; 15 new tests + full suite pass; independent validation PENDING (ChatGPT); see docs/W38_PLATFORM_COMP
ENT-16 | Scalability, HA & observability | IN PROGRESS | 50 | BLOCKED | 50 | W8 developed 2026-09-25 (production hardening) — coding only; independent testing PENDING (ChatGPT); see docs/W8_PRODUCTION_HARDENING_HANDOFF.md
PERF-001 | Investor performance attribution | IMPLEMENTED BUT NOT VERIFIED | 80 | IMPLEMENTED BUT NOT VERIFIED | 90 | branch w20-release; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master
QA-001 | Wealth QA / security / performance | IN PROGRESS | 75 | IN PROGRESS | 85 | RC line = w33-wealth-qa (W11-W32); merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master
UAT-001 | Beta / UAT | IN PROGRESS | 70 | BLOCKED | 70 | RC line = w33-wealth-qa; merged to master; not deployed ¦ W39 check 2026-10-07: commit is an ancestor of master

## Status Legend
Development status (CSV vocabulary) | Meaning
COMPLETED | In master, with tests / evidence; maintained
IMPLEMENTED BUT NOT VERIFIED | Developed and merged; automated tests where listed; independent QA (ChatGPT) and owner UAT still pending
IN PROGRESS | Partly built
BLOCKED | Cannot proceed without the input in 'Blocker / Input Required'
YET TO START | Not started
Testing status (automated, development side) | Meaning
COMPLETED | >= 60% of the key files' lines run by passing automated tests, or W39 tests written for the feature
IN PROGRESS | 1-59% of the key files' lines run by tests
YET TO START | No automated test reaches the key files
BLOCKED / N/A | Feature blocked / no code (documentation, legal, process)
Owner workbook vocabulary | Completed / In Progress / Blocked / Yet to Start; 'Completed (automated)' = automated tests pass, independent QA pending