## Pivot
Sum of Completion %2 | Column Labels
Row Labels | COMPLETED | IN PROGRESS | UNCLEAR | YET TO START | Grand Total | Completed % | In Progress % | Yet to Start %
Agreed-Spec | 3890 | 2125 | 30 | 45 | 6090 | 63.88% | 34.89% | 0.7389%
Advanced Quant |  |  |  | 0 | 0 | 0% | 0% | 0%
AI/ML |  | 295 |  | 0 | 295 | 0% | 100% | 0%
Delivered baseline (maintain) | 3170 |  |  |  | 3170 | 100% | 0% | 0%
Execution |  | 245 | 0 |  | 245 | 0% | 100% | 0%
Foundation | 415 | 485 | 30 |  | 930 | 44.62% | 52.15% | 0%
Production Hardening |  | 45 |  | 15 | 60 | 0% | 75% | 25%
Quant Research (data, factors, backtesting) | 235 | 800 |  | 15 | 1050 | 22.38% | 76.19% | 1.429%
Risk & Portfolio |  | 70 |  | 5 | 75 | 0% | 93.33% | 6.667%
Strategy Engine | 70 | 185 |  | 10 | 265 | 26.42% | 69.81% | 3.774%
Code-Derived | 1145 | 240 |  | 5 | 1390 | 82.37% | 17.27% | 0.3597%
Delivered baseline (maintain) | 920 |  |  |  | 920 | 100% | 0% | 0%
Execution |  | 30 |  |  | 30 | 0% | 100% | 0%
Foundation | 155 | 130 |  | 5 | 290 | 53.45% | 44.83% | 1.724%
Quant Research (data, factors, backtesting) | 70 | 20 |  |  | 90 | 77.78% | 22.22% | 0%
Strategy Engine |  | 60 |  |  | 60 | 0% | 100% | 0%
Enterprise-SaaS |  |  |  | 0 | 0 | 0% | 0% | 0%
Enterprise SaaS (final objective) |  |  |  | 0 | 0 | 0% | 0% | 0%
Quant-Research | 595 | 265 |  | 105 | 965 | 61.66% | 27.46% | 10.88%
Advanced Quant |  |  |  | 30 | 30 | 0% | 0% | 100%
AI/ML |  |  |  | 5 | 5 | 0% | 0% | 100%
Delivered baseline (maintain) | 515 |  |  |  | 515 | 100% | 0% | 0%
Execution |  | 40 |  | 5 | 45 | 0% | 88.89% | 11.11%
Foundation |  | 35 |  | 0 | 35 | 0% | 100% | 0%
Production Hardening |  |  |  | 0 | 0 | 0% | 0% | 0%
Quant Research (data, factors, backtesting) |  | 155 |  | 35 | 190 | 0% | 81.58% | 18.42%
Risk & Portfolio | 80 |  |  | 15 | 95 | 84.21% | 0% | 15.79%
Strategy Engine |  | 35 |  | 15 | 50 | 0% | 70% | 30%
Grand Total | 5630 | 2630 | 30 | 155 | 8445 | 66.67% | 31.14% | 1.835%

## Executive Summary
ATIP RE-PRIORITIZED DEVELOPMENT PLAN
Purpose | Reorganize the existing ATIP tracker into dependency-based development waves, with multi-role architecture and final cloud/Claude deployment last.
Primary principle | Protect completed baseline functionality; build research/backtesting before advanced AI; implement multi-role after the core engine; deploy last.
Source | ATIP_MASTER_TRACKER.xlsx + development observations from the current review.
Target waves | W1 Foundation → W2 Research/Backtesting → W3 Strategy → W4 Risk/Execution → W5 AI/ML → W6 Advanced Quant → W7 Multi-Role → W8 Production → W9 Deployment
Completed baseline | 58 items identified in the current tracker summary; do not disturb working functionality.
Enterprise SaaS | Treat as a later layer. Define interfaces/role boundaries early, but avoid letting SaaS features delay the core trading engine.
Deployment | Claude/cloud deployment is explicitly the LAST step.

## Development Waves
Wave | Name | Objective | Outcome | Priority | Dependency Principle | Scope Areas
W1 | Foundation Completion | Finish core data, portfolio, jobs, monitoring and foundational risk capabilities. | Core platform | P0 | Must precede advanced strategy work | Foundation; Data; Portfolio; Monitoring; Risk
W2 | Research & Backtesting | Build a trustworthy research and backtesting environment with realistic costs, slippage and robustness analysis. | Research engine | P0 | Required before relying on new strategies | Backtesting; Quant Research
W3 | Strategy Engine | Turn indicators/factors/signals into reusable, configurable and lifecycle-managed strategies. | Strategy platform | P0 | Depends on W1-W2 | Strategy Engine; Signal Engine
W4 | Risk & Execution | Complete risk controls, execution, reconciliation and operational safeguards. | Controlled trading pipeline | P0 | Depends on W1-W3 | Risk; Execution; Broker
W5 | AI/ML | Add validated ML, model registry, feature selection, ensembles, regimes and monitoring. | ML-enhanced ATIP | P1 | Depends on reliable research/backtesting | AI/ML
W6 | Advanced Quant | Add institutional-style quantitative research capabilities such as advanced factors, microstructure, stat-arb and alternative data. | Advanced quant platform | P1 | Depends on W1-W5 and suitable data | Advanced Quant
W7 | Multi-Role / Enterprise | Add RBAC, user profiles, broker credential controls, multi-user APIs and role-specific workflows. | Multi-role platform | P1 | Design early; implement after core engine | Enterprise SaaS; Security
W8 | Production Hardening | Complete security, backups, observability, DR, documentation and operational readiness. | Production-ready system | P0 | Before public/production deployment | Production Hardening; Security; Operations
W9 | Final Deployment | Perform final integration and deploy the stable system to the target cloud/Claude environment. | Deployment | P0 | LAST STEP | Deployment

## Priority Features
Area | ID | Feature | Implementation Objective | Wave | Priority
Foundation | SC-13 | Fundamental Score | Complete foundation scoring component | W1 | P0
Foundation | SC-02 | SPI | Complete SPI implementation | W1 | P0
Portfolio | PF-01 | Portfolio ingestion | Reliable portfolio ingestion | W1 | P0
Portfolio | PF-02 | Portfolio holdings/P&L | Authoritative holdings and P&L state | W1 | P0
Portfolio | PF-13 | Daily P&L | Daily portfolio performance | W1 | P0
Broker | BR-04 | Portfolio sync | Synchronize portfolio with broker | W1 | P0
Risk | RK-13 | Risk-based sizing | Position sizing based on risk | W1 | P0
Risk | RK-07 | Daily loss limit | Enforce daily loss limit | W1 | P0
Risk | RK-08 | Drawdown limit | Enforce drawdown limit | W1 | P0
Data | DP-19 | Data-quality layer | Validate and monitor data quality | W1 | P0
Monitoring | MON-01 | Job logging | Track scheduled/background jobs | W1 | P0
Monitoring | MON-02 | Stalled-job detection | Detect stalled jobs | W1 | P0
Monitoring | MON-03 | Failure alerting | Alert on critical failures | W1 | P0
News | NS-01 | News ingestion | Establish news ingestion foundation | W1 | P1
Database | DBS-06 | Timestamp consistency | Normalize timestamp handling | W1 | P0
Operations | OPS-03 | Installation/setup | Document and automate setup | W1 | P1
Backtesting | BT-16 | Dated equity curve/run records | Persist reproducible backtest runs | W2 | P0
Backtesting | BT-08 | Portfolio-level backtest | Backtest complete portfolios | W2 | P0
Backtesting | BT-09 | Drawdown analysis | Analyze drawdowns | W2 | P0
Backtesting | BT-11 | Performance metrics | Sharpe, Sortino, CAGR, Calmar | W2 | P0
Backtesting | BT-12 | VaR/CVaR | Risk-adjusted tail metrics | W2 | P1
Backtesting | BT-05 | Transaction-cost model | Model brokerage and transaction costs | W2 | P0
Backtesting | BT-06 | Slippage | Model realistic slippage | W2 | P0
Backtesting | BT-07 | Liquidity constraints | Account for liquidity | W2 | P1
Backtesting | BT-03 | In/out-of-sample | Separate training and evaluation periods | W2 | P0
Backtesting | BT-02 | Walk-forward | Walk-forward validation | W2 | P0
Backtesting | BT-13 | Monte Carlo | Robustness simulation | W2 | P1
Backtesting | BT-15 | Bias controls | Control look-ahead/survivorship/data leakage | W2 | P0
Strategy | SE-01 | Strategy interface/registry | Standard reusable strategy framework | W3 | P0
Strategy | SE-02 | Strategy parameters | Central parameter management | W3 | P0
Strategy | SE-03 | Rule-based strategies | Reusable rule strategy layer | W3 | P0
Strategy | SE-06 | Multi-factor strategy | Combine factors into strategies | W3 | P0
Strategy | SE-04 | Quant strategies | Support quantitative strategy types | W3 | P0
Strategy | SE-09 | Strategy lifecycle | Draft/test/approved/deployed/retired states | W3 | P0
Strategy | SE-11 | Strategy health | Monitor strategy health | W3 | P1
Strategy | SE-07 | Strategy combination/selection | Combine/select strategies | W3 | P1
Strategy | SE-08 | Regime-aware selection | Select strategies by market regime | W3 | P1
Signal | SG-04 | Rich decision states | Standardize signal/decision states | W3 | P0
Risk | RK-16 | Emergency exit | One-command flatten with confirmation | W4 | P0
Execution | EX-02 | Order types | Support required order types | W4 | P0
Execution | EX-08 | Order modify/cancel | Modify and cancel orders | W4 | P0
Broker | BR-05 | Execution reconciliation | Reconcile broker execution | W4 | P0
Broker | BR-06 | Broker connection health | Monitor broker connectivity | W4 | P0
Risk | RK-17 | Broker/operational risk | Operational and broker risk controls | W4 | P0
Execution | EX-09 | Measured slippage | Capture actual execution slippage | W4 | P1
Execution | EX-10 | Execution analytics | Analyze execution quality | W4 | P1
Monitoring | MON-04 | Live strategy/P&L monitoring | Monitor live strategy and P&L | W4 | P0
Security | SEC-03 | Audit logging | Immutable/traceable audit trail | W4 | P0
ML | ML-13 | Labels/targets | Define reproducible ML targets | W5 | P0
ML | ML-08 | Model validation | Validate models correctly | W5 | P0
ML | ML-01 | Supervised ML | Add validated supervised ML models | W5 | P1
ML | ML-12 | Model registry/versioning | Version and manage models | W5 | P0
ML | ML-07 | Feature selection | Select robust features | W5 | P1
ML | ML-11 | Ensemble models | Combine model outputs | W5 | P1
ML | ML-09 | Model monitoring/drift | Monitor model degradation | W5 | P0
ML | ML-10 | Explainability | Explain model outputs | W5 | P1
ML | ML-05 | Regime detection | Detect market regimes | W5 | P1
Advanced Quant | AQ-01 | Tick data | Support tick-level research | W6 | P2
Advanced Quant | AQ-02 | Order-book/depth | Support depth/microstructure research | W6 | P2
Advanced Quant | AQ-03 | Microstructure factors | Develop microstructure factors | W6 | P2
Advanced Quant | AQ-04 | Derivatives factors | Develop derivatives-specific factors | W6 | P2
Advanced Quant | AQ-05 | Volatility strategies | Systematic volatility strategies | W6 | P1
Advanced Quant | AQ-06 | Statistical arbitrage | Stat-arb research framework | W6 | P1
Advanced Quant | AQ-07 | Pairs/cointegration | Pairs and cointegration research | W6 | P1
Advanced Quant | AQ-08 | Cross-sectional/market-neutral | Cross-sectional factor strategies | W6 | P1
Advanced Quant | AQ-09 | Event-driven | Event-driven strategy research | W6 | P2
Advanced Quant | AQ-10 | Value/quality factors | Fundamental factor research | W6 | P1
Advanced Quant | AQ-11 | Execution algorithms | Systematic execution algorithms | W6 | P1
Advanced Quant | AQ-12 | Market-impact model | Estimate market impact | W6 | P2
Advanced Quant | AQ-13 | Latency telemetry | Measure execution latency | W6 | P2
Advanced Quant | AQ-14 | Event-driven OMS | Event-driven order management | W6 | P2
Advanced Quant | AQ-15 | Event-driven backtester | Event-driven simulation | W6 | P2
Advanced Quant | AQ-16 | Macro data | Integrate macroeconomic datasets | W6 | P1
Advanced Quant | AQ-17 | Alternative data | Alternative data research | W6 | P2
Advanced Quant | AQ-18 | Point-in-time data lake | Avoid historical data leakage | W6 | P0
Advanced Quant | AQ-19 | Multi-asset data | Extend data model across asset classes | W6 | P2
Enterprise | ENT-01 | Multi-tenant architecture | Tenant isolation and architecture | W7 | P1
Security | SEC-02 | Users/RBAC/MFA | Role-based access and authentication | W7 | P0
Enterprise | ENT-02 | User registration | User onboarding | W7 | P1
Enterprise | ENT-03 | User/risk profile | Profile and risk preferences | W7 | P1
Enterprise | ENT-06 | Broker credential vault | Secure broker credentials | W7 | P0
Enterprise | ENT-14 | Regulatory approvals | Approval workflow where applicable | W7 | P1
Enterprise | ENT-08 | Multi-user web app | Multi-user application | W7 | P1
API | API-03 | Versioned public API | Stable versioned API | W7 | P1
Enterprise | ENT-19 | Watchlists | User watchlists | W7 | P2
Enterprise | ENT-11 | User alerts | User-specific alerts | W7 | P1
Enterprise | ENT-10 | Notification channels | Email/SMS/push or supported channels | W7 | P2
Enterprise | ENT-04 | Subscriptions/billing | Commercial subscription layer | W7 | P2
Enterprise | ENT-13 | Administration console | Admin control plane | W7 | P1
Portfolio | PF-12 | Multi-broker import | Normalize portfolios across brokers | W7 | P1
Broker | BR-07 | Additional brokers | Broker abstraction and additional integrations | W7 | P2
Production | OPS-01 | Encryption | Encryption and secrets management | W8 | P0
Production | OPS-02 | Backup/restore | Backup and recovery | W8 | P0
Production | API-01 | API contracts | Documented stable contracts | W8 | P1
Production | OPS-05 | Observability | Metrics/logging/tracing | W8 | P0
Production | OPS-06 | Disaster recovery | Recovery procedures | W8 | P0
Production | DOC-01 | Operational documentation | Runbooks and operational docs | W8 | P1
Deployment | OPS-04 | Cloud deployment | Final cloud/Claude deployment | W9 | P0

## Multi-Role Plan
Role | Primary Responsibilities | Implementation Window | Architecture Principle
Super Admin | Global configuration, users, security, broker integrations, system controls | W7-W8 | Do not embed admin logic in trading engine
Researcher / Quant | Factors, experiments, datasets, strategy research, backtests, model research | W3-W6 | Core research workflow should remain reusable
Strategy Manager | Strategy lifecycle, parameters, approvals, deployment state | W3-W7 | Separate strategy lifecycle from execution
Risk Manager | Risk limits, exposure, drawdown, VaR, emergency controls | W4-W7 | Risk controls should be independent of UI roles
Trader / Execution Operator | Signals, orders, positions, execution and reconciliation | W4-W7 | No direct bypass of risk controls
Portfolio Manager | Allocation, portfolio analytics, rebalancing and performance | W1-W7 | Portfolio state must be authoritative
Viewer / Investor | Read-only dashboards, reports and portfolio views | W7 | No execution authority

## Key Observations
No | Observation | Action / Rationale | Target Wave
1 | Do not disturb completed baseline | 58 baseline items are already completed; preserve them and build around them. | All
2 | Finish core foundation first | Data quality, portfolio state, monitoring, timestamps and foundational risk are prerequisites. | W1
3 | Backtesting before advanced AI | Reliable cost/slippage/bias/out-of-sample/walk-forward analysis is needed before trusting new strategies. | W2
4 | Build reusable strategy framework | Create registry, parameters, lifecycle, multi-factor and regime-aware strategy capabilities. | W3
5 | Risk before expanded execution | Emergency exit, loss/drawdown limits, reconciliation and execution monitoring should precede broader execution. | W4
6 | AI/ML after research foundation | Use validated labels, model validation, registry, feature selection and monitoring before advanced models. | W5
7 | Advanced quant later | Tick/order-book, stat-arb, alternative data and advanced execution depend on data and research infrastructure. | W6
8 | Design multi-role early; implement later | Define role boundaries and RBAC architecture without embedding user logic in the core trading engine. | W7
9 | Production hardening before deployment | Security, backup, observability, DR and documentation must be complete before public deployment. | W8
10 | Claude/cloud deployment last | Deployment should be the final integration step after functional and operational readiness. | W9

## Target Architecture
Layer | Component | Purpose
1 | Data | Market, broker, news, macro and alternative data
2 | Data Normalization | Quality, timestamps, point-in-time handling and normalization
3 | Feature Engineering | Technical indicators, factors and derived features
4 | Technical Indicators | RSI, MACD, EMA, SMA, ATR, ADX, VWAP, etc.
5 | Quant Factors | Alpha/factor research and scoring
6 | AI/ML | Validated models, ensembles and regime detection
7 | Signal Engine | Standardized signals and decisions
8 | Strategy Engine | Reusable, parameterized and lifecycle-managed strategies
9 | Portfolio Construction | Allocation, diversification and optimization
10 | Risk Engine | Limits, sizing, drawdown, VaR/ES and emergency controls
11 | Execution Engine | Orders, slippage, reconciliation and execution analytics
12 | Broker | Dhan/Zerodha/additional brokers via abstraction
13 | Monitoring | P&L, strategy health, model health, alerts and audit
14 | Role/API Layer | RBAC, user profiles, APIs and role-specific workflows
15 | Deployment | Production/cloud/Claude environment

## Source_Sheet1
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5
Sum of Phase | Column Labels
Row Labels | COMPLETED | IN PROGRESS | UNCLEAR | YET TO START | Grand Total
P0 | 10 | 73 | 6 | 146 | 235
AI/ML |  | 20 |  | 8 | 28
Delivered baseline (maintain) | 0 |  |  |  | 0
Enterprise SaaS (final objective) |  |  |  | 117 | 117
Execution |  | 12 | 6 |  | 18
Broker Integration |  | 6 |  |  | 6
Execution |  | 6 | 6 |  | 12
Foundation | 2 | 14 |  | 4 | 20
Alpha/Factor Engine |  | 4 |  |  | 4
Broker Integration |  | 1 |  |  | 1
Data Platform |  | 3 |  |  | 3
Deployment/Ops | 1 |  |  |  | 1
Execution | 1 |  |  |  | 1
Monitoring |  | 2 |  | 1 | 3
News/Sentiment |  | 1 |  |  | 1
Portfolio |  | 2 |  | 1 | 3
Risk Management |  | 1 |  | 2 | 3
Quant Research (data, factors, backtesting) |  | 18 |  | 12 | 30
Alpha/Factor Engine |  | 6 |  | 2 | 8
Backtesting |  | 6 |  | 8 | 14
Data Platform |  | 2 |  |  | 2
Database |  | 2 |  |  | 2
Quant Research |  |  |  | 2 | 2
Technical Analysis |  | 2 |  |  | 2
Risk & Portfolio | 5 |  |  | 5 | 10
Risk Management | 5 |  |  | 5 | 10
Strategy Engine | 3 | 9 |  |  | 12
Signal Engine | 3 | 3 |  |  | 6
Strategy Engine |  | 6 |  |  | 6
P1 | 8 | 99 | 1 | 234 | 342
AI/ML |  | 12 |  | 20 | 32
Delivered baseline (maintain) | 0 |  |  |  | 0
Enterprise SaaS (final objective) |  |  |  | 99 | 99
Execution |  | 30 |  | 6 | 36
Broker Integration |  | 6 |  |  | 6
Execution |  | 6 |  | 6 | 12
Monitoring |  | 6 |  |  | 6
Risk Management |  | 6 |  |  | 6
Security |  | 6 |  |  | 6
Foundation | 2 | 6 | 1 | 1 | 10
Alpha/Factor Engine | 2 |  |  |  | 2
Dashboard |  | 1 |  |  | 1
Data Platform |  | 1 |  |  | 1
Database |  | 2 |  |  | 2
Deployment/Ops |  | 1 |  |  | 1
Monitoring |  |  |  | 1 | 1
Risk Management |  | 1 |  |  | 1
Technical Analysis |  |  | 1 |  | 1
Production Hardening |  | 8 |  | 24 | 32
Deployment/Ops |  | 8 |  | 8 | 16
Monitoring |  |  |  | 8 | 8
Security |  |  |  | 8 | 8
Quant Research (data, factors, backtesting) | 6 | 24 |  | 24 | 54
Alpha/Factor Engine | 2 | 6 |  | 2 | 10
Backtesting |  | 8 |  | 6 | 14
Data Platform | 2 | 4 |  | 2 | 8
Database |  |  |  | 2 | 2
Quant Research | 2 | 6 |  | 8 | 16
Technical Analysis |  |  |  | 4 | 4
Risk & Portfolio |  | 10 |  | 45 | 55
Dashboard |  |  |  | 5 | 5
Portfolio |  | 10 |  | 15 | 25
Risk Management |  |  |  | 25 | 25
Strategy Engine |  | 9 |  | 15 | 24
Dashboard |  | 3 |  | 3 | 6
Strategy Engine |  | 6 |  | 12 | 18
P2 | 3 | 38 |  | 236 | 277
Advanced Quant |  |  |  | 133 | 133
Alpha/Factor Engine |  |  |  | 21 | 21
Alternative Data |  |  |  | 14 | 14
Backtesting |  |  |  | 7 | 7
Data Platform |  |  |  | 35 | 35
Execution |  |  |  | 28 | 28
Quant Research |  |  |  | 28 | 28
AI/ML |  |  |  | 24 | 24
Delivered baseline (maintain) | 0 |  |  |  | 0
Enterprise SaaS (final objective) |  |  |  | 45 | 45
Execution |  | 12 |  |  | 12
Broker Integration |  | 12 |  |  | 12
Foundation | 1 |  |  |  | 1
Data Platform | 1 |  |  |  | 1
Production Hardening |  | 8 |  | 8 | 16
APIs |  | 8 |  | 8 | 16
Quant Research (data, factors, backtesting) | 2 | 12 |  | 6 | 20
Alpha/Factor Engine |  |  |  | 2 | 2
Alternative Data |  | 2 |  |  | 2
Dashboard |  | 2 |  |  | 2
Data Platform | 2 | 6 |  |  | 8
Technical Analysis |  | 2 |  | 4 | 6
Risk & Portfolio |  |  |  | 20 | 20
Portfolio |  |  |  | 15 | 15
Risk Management |  |  |  | 5 | 5
Strategy Engine |  | 6 |  |  | 6
Signal Engine |  | 3 |  |  | 3
Strategy Engine |  | 3 |  |  | 3
Grand Total | 21 | 210 | 7 | 616 | 854

## Source_ATIP_MASTER_TRACKER
Seq | Phase | Phase Name | ID | Module | Feature | Target Requirement | Scope Source | Priority | Status | Completion % | Depends On | Current Implementation | Next Action / Missing Work | Key Files | Evidence | Owner | Target Date | Started On | Completed On | Last Updated | Notes
1 | 0 | Delivered baseline (maintain) | DP-02 | Data Platform | Daily OHLCV history | Clean daily bars for universe | Agreed-Spec | P0 | COMPLETED | 90 |  | NSE Bhavcopy + Dhan; coverage/freshness/duplicate guards | Maintain | data/bhavcopy.py; data/dhan.py | prices_daily ~234k rows / 426 sessions |  |  |  |  | 2026-09-24
2 | 0 | Delivered baseline (maintain) | DP-07 | Data Platform | Delivery data | Delivery qty and % | Code-Derived | P1 | COMPLETED | 90 |  | Full Bhavcopy nightly + backfill | Maintain | data/bhavcopy.py | 223,854 rows |  |  |  |  | 2026-09-24
3 | 0 | Delivered baseline (maintain) | DP-20 | Data Platform | Trading calendar | NSE holidays/special sessions | Code-Derived | P0 | COMPLETED | 90 |  | 2025-26 holidays + budget sessions | Add next year's holidays each December | utils/trading_calendar.py | 7132017 |  |  |  |  | 2026-09-24
4 | 0 | Delivered baseline (maintain) | TA-01 | Technical Analysis | Core indicators | RSI; MACD; EMA; SMA; ATR; ADX; Bollinger | Agreed-Spec | P0 | COMPLETED | 90 |  | Computed and stored; MACD fixed and normalised | Maintain | data/technical.py | a7d92a7; bbd0540 |  |  |  |  | 2026-09-24
5 | 0 | Delivered baseline (maintain) | TA-02 | Technical Analysis | Extended oscillators | Stoch; Williams %R; CCI; OBV; relative volume | Agreed-Spec | P1 | COMPLETED | 80 |  | Computed and stored | Maintain | data/technical.py | technical.py:47-54 |  |  |  |  | 2026-09-24
6 | 0 | Delivered baseline (maintain) | TA-05 | Technical Analysis | Fibonacci | Retracement levels | Agreed-Spec | P1 | COMPLETED | 80 |  | 52-week 23.6/38.2/50/61.8 levels | Optional: swing-anchored levels | data/technical.py | technical.py:262-268 |  |  |  |  | 2026-09-24
7 | 0 | Delivered baseline (maintain) | TA-07 | Technical Analysis | Trend features | Crosses; 200DMA; gap % | Agreed-Spec | P1 | COMPLETED | 80 |  | Computed and stored | Maintain | data/technical.py | technical.py:291 |  |  |  |  | 2026-09-24
8 | 0 | Delivered baseline (maintain) | TA-08 | Technical Analysis | Relative strength | RS vs NIFTY | Agreed-Spec | P1 | COMPLETED | 80 |  | 20-day RS with date-matched benchmark | Sector-relative RS later (TA-08b in Phase 2 if wanted) | scores/engine.py | 8dd04fb |  |  |  |  | 2026-09-24
9 | 0 | Delivered baseline (maintain) | SC-03 | Alpha/Factor Engine | RRI | Recovery & Rebound Index per QRH | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented | Institutional input improves with SC-14 | scores/engine.py | engine.py:260 |  |  |  |  | 2026-09-24
10 | 0 | Delivered baseline (maintain) | SC-04 | Alpha/Factor Engine | MRI | Momentum Reversal Index per QRH | Agreed-Spec | P0 | COMPLETED | 85 |  | Implemented; MACD corrected | Maintain | scores/engine.py | engine.py:241 |  |  |  |  | 2026-09-24
11 | 0 | Delivered baseline (maintain) | SC-07 | Alpha/Factor Engine | ZPI | Zone Probability Index per QRH | Agreed-Spec | P0 | COMPLETED | 80 |  | Implemented + delivery component | Maintain | scores/engine.py | 969f570 |  |  |  |  | 2026-09-24
12 | 0 | Delivered baseline (maintain) | SC-10 | Alpha/Factor Engine | Portfolio Health score | PHS formula | Agreed-Spec | P1 | COMPLETED | 75 |  | Implemented | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py | portfolio_health.py |  |  |  |  | 2026-09-24
13 | 0 | Delivered baseline (maintain) | PF-05 | Portfolio | Portfolio health | Portfolio Health score + panel | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented + dashboard | Maintain | scores/portfolio_health.py | portfolio_health.py |  |  |  |  | 2026-09-24
14 | 0 | Delivered baseline (maintain) | SC-11 | Alpha/Factor Engine | Trade of the Day | TOD formula | Agreed-Spec | P1 | COMPLETED | 80 |  | Implemented; one TOD per session | Maintain | scores/engine.py | d74e595 |  |  |  |  | 2026-09-24
15 | 0 | Delivered baseline (maintain) | SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | Master ranking | Agreed-Spec | P0 | COMPLETED | 80 |  | Implemented; rank stored | Maintain | scores/engine.py | engine.py:508 |  |  |  |  | 2026-09-24
16 | 0 | Delivered baseline (maintain) | SC-17 | Alpha/Factor Engine | Configurable weights | Weights in configuration | Agreed-Spec | P1 | COMPLETED | 80 |  | weight_config table | Regime-specific rows used by ML-05 | db/schema.py | seed_weights |  |  |  |  | 2026-09-24
17 | 0 | Delivered baseline (maintain) | SG-02 | Signal Engine | Signal validation | Data gates before signals | Code-Derived | P0 | COMPLETED | 75 |  | EOD coverage guard; FII/DII hold | Maintain | pipeline/scheduler.py | a4a508b; 969f570 |  |  |  |  | 2026-09-24
18 | 0 | Delivered baseline (maintain) | SG-03 | Signal Engine | Signal ranking | Top-25 lists | Agreed-Spec | P0 | COMPLETED | 85 |  | Implemented | Maintain | scores/engine.py | dashboard lists |  |  |  |  | 2026-09-24
19 | 0 | Delivered baseline (maintain) | SG-05 | Signal Engine | Trade plan | Entry/stop/targets/R:R/horizon | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented | Maintain | scores/predictions.py | predictions.py |  |  |  |  | 2026-09-24
20 | 0 | Delivered baseline (maintain) | SG-06 | Signal Engine | Outcome tracking | Hit rate and P&L per signal | Agreed-Spec | P0 | COMPLETED | 80 |  | Implemented; corrected denominator | Maintain | scores/signal_log.py | cc8ce46 |  |  |  |  | 2026-09-24
21 | 0 | Delivered baseline (maintain) | SG-07 | Signal Engine | Signal provenance log | Immutable signal log | Code-Derived | P1 | COMPLETED | 80 |  | Append-only signal_log | Maintain | scores/signal_log.py | signal_log.py |  |  |  |  | 2026-09-24
22 | 0 | Delivered baseline (maintain) | BT-01 | Backtesting | Historical backtest | Bar-level backtest | Agreed-Spec | P0 | COMPLETED | 80 |  | 3 bar engines | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py | — |  |  |  |  | 2026-09-24
23 | 0 | Delivered baseline (maintain) | BT-10 | Backtesting | Win rate / profit factor / expectancy | Trade metrics | Agreed-Spec | P0 | COMPLETED | 90 |  | Implemented | Maintain | strategy/backtest_aggressive.py | metrics() |  |  |  |  | 2026-09-24
24 | 0 | Delivered baseline (maintain) | RK-02 | Risk Management | Max order value | Pre-trade limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
25 | 0 | Delivered baseline (maintain) | RK-03 | Risk Management | Max orders per day | Pre-trade limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
26 | 0 | Delivered baseline (maintain) | RK-04 | Risk Management | Max open positions | Position limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
27 | 0 | Delivered baseline (maintain) | RK-05 | Risk Management | Symbol exposure limit | Concentration limit | Quant-Research | P0 | COMPLETED | 90 |  | Enforced when configured | Set values in config.json | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
28 | 0 | Delivered baseline (maintain) | RK-14 | Risk Management | Crash-risk gating | CRI gate | Agreed-Spec | P0 | COMPLETED | 75 |  | SELL_CRI_DANGER + strategy use | Maintain | scores/engine.py | — |  |  |  |  | 2026-09-24
29 | 0 | Delivered baseline (maintain) | EX-03 | Execution | Position management | Persistent idempotent positions | Code-Derived | P0 | COMPLETED | 75 |  | reserve -> place -> apply | Maintain | strategy/positions.py | — |  |  |  |  | 2026-09-24
30 | 0 | Delivered baseline (maintain) | EX-04 | Execution | Entry/exit | Automated entry and exit | Agreed-Spec | P0 | COMPLETED | 70 |  | strategy/live.py | Maintain | strategy/live.py | — |  |  |  |  | 2026-09-24
31 | 0 | Delivered baseline (maintain) | EX-05 | Execution | Stop loss | Hard/ATR stops | Agreed-Spec | P0 | COMPLETED | 75 |  | Implemented | Maintain | strategy/aggressive.py | — |  |  |  |  | 2026-09-24
32 | 0 | Delivered baseline (maintain) | EX-06 | Execution | Trailing stop | ATR trailing stop | Quant-Research | P0 | COMPLETED | 80 |  | Implemented (4.0x ATR) | Maintain | strategy/aggressive.py | aggressive.py:57-66 |  |  |  |  | 2026-09-24
33 | 0 | Delivered baseline (maintain) | EX-07 | Execution | Profit booking / partial exit | Checkpoints and partial exits | Agreed-Spec | P1 | COMPLETED | 70 |  | Implemented in aggressive strategy | Maintain | strategy/aggressive.py | — |  |  |  |  | 2026-09-24
34 | 0 | Delivered baseline (maintain) | EX-13 | Execution | Paper trading | Virtual trading (FR-PT) | Agreed-Spec | P0 | COMPLETED | 85 |  | Paper broker with slippage | Maintain | orders/paper.py | tests/test_paper_broker.py |  |  |  |  | 2026-09-24
35 | 0 | Delivered baseline (maintain) | EX-14 | Execution | Live gating | PAPER default; explicit confirm | Agreed-Spec | P0 | COMPLETED | 85 |  | Implemented | Maintain | orders/environment.py | environment.py:37-57 |  |  |  |  | 2026-09-24
36 | 0 | Delivered baseline (maintain) | BR-01 | Broker Integration | Dhan | Data + orders | Agreed-Spec | P0 | COMPLETED | 80 |  | dhanhq integration | Maintain | data/dhan.py; orders/broker.py | — |  |  |  |  | 2026-09-24
37 | 0 | Delivered baseline (maintain) | BR-03 | Broker Integration | Broker abstraction | Routed execution clients | Quant-Research | P0 | COMPLETED | 75 |  | PAPER/SANDBOX/LIVE routing | Becomes multi-broker interface in ENT-15 | orders/environment.py | — |  |  |  |  | 2026-09-24
38 | 0 | Delivered baseline (maintain) | DB-01 | Dashboard | Market Health panel | Dashboard section | Agreed-Spec | P0 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
39 | 0 | Delivered baseline (maintain) | DB-02 | Dashboard | Global Markets panel | Dashboard section | Agreed-Spec | P1 | COMPLETED | 75 |  | Rendered; snapshot bug fixed | Maintain | dashboard/server.py | db7f506 |  |  |  |  | 2026-09-24
40 | 0 | Delivered baseline (maintain) | DB-03 | Dashboard | FII/DII panel | Dashboard section | Agreed-Spec | P1 | COMPLETED | 75 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
41 | 0 | Delivered baseline (maintain) | DB-05 | Dashboard | Sector Rotation | Dashboard section | Agreed-Spec | P1 | COMPLETED | 70 |  | Heatmap rendered | Maintain | dashboard/server.py | server.py:489 |  |  |  |  | 2026-09-24
42 | 0 | Delivered baseline (maintain) | DB-07 | Dashboard | Top 25 VPI | Dashboard section | Agreed-Spec | P0 | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | /api/scores |  |  |  |  | 2026-09-24
43 | 0 | Delivered baseline (maintain) | DB-08 | Dashboard | Buy Zone (ZPI) | Dashboard section | Agreed-Spec | P0 | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
44 | 0 | Delivered baseline (maintain) | DB-09 | Dashboard | Recovery (RRI) | Dashboard section | Agreed-Spec | P1 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
45 | 0 | Delivered baseline (maintain) | DB-10 | Dashboard | Momentum Reversal (MRI) | Dashboard section | Agreed-Spec | P1 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
46 | 0 | Delivered baseline (maintain) | DB-12 | Dashboard | Portfolio Health panel | Dashboard section | Agreed-Spec | P0 | COMPLETED | 80 |  | Rendered | Maintain | dashboard/server.py | /api/portfolio |  |  |  |  | 2026-09-24
47 | 0 | Delivered baseline (maintain) | DB-13 | Dashboard | Trade of the Day | Dashboard section | Agreed-Spec | P0 | COMPLETED | 85 |  | Rendered | Maintain | dashboard/server.py | /api/tod |  |  |  |  | 2026-09-24
48 | 0 | Delivered baseline (maintain) | DB-15 | Dashboard | Orders/signals panel | Orders tab | Code-Derived | P1 | COMPLETED | 70 |  | Rendered with PAPER status | Maintain | dashboard/server.py | /api/orders |  |  |  |  | 2026-09-24
49 | 0 | Delivered baseline (maintain) | DB-19 | Dashboard | Hosted read-only snapshot | bkesari viewer | Code-Derived | P1 | COMPLETED | 80 |  | publish_snapshot.py | Superseded by ENT-08 web app | publish_snapshot.py | — |  |  |  |  | 2026-09-24
50 | 0 | Delivered baseline (maintain) | API-01 | APIs | Internal REST | Dashboard API | Agreed-Spec | P1 | COMPLETED | 70 |  | 15 FastAPI routes | Maintain | dashboard/server.py | — |  |  |  |  | 2026-09-24
51 | 0 | Delivered baseline (maintain) | API-02 | APIs | Local API authentication | Auth on mutating routes | Agreed-Spec | P0 | COMPLETED | 80 |  | 127.0.0.1 bind + X-ATIP-Token | Replaced by per-user auth in SEC-02 | dashboard/security.py | 7191c71 |  |  |  |  | 2026-09-24
52 | 0 | Delivered baseline (maintain) | DBS-01 | Database | Schema | Operational schema | Agreed-Spec | P1 | COMPLETED | 75 |  | 19 SQLite tables | Migrations via DBS-04 | db/schema.py | — |  |  |  |  | 2026-09-24
53 | 0 | Delivered baseline (maintain) | DBS-02 | Database | Retention/purge | Data retention | Code-Derived | P2 | COMPLETED | 70 |  | db/purge.py | Maintain | db/purge.py | — |  |  |  |  | 2026-09-24
54 | 0 | Delivered baseline (maintain) | SEC-01 | Security | Credential handling | Secrets outside code | Agreed-Spec | P0 | COMPLETED | 70 |  | config.json outside repo | Vault in ENT-06 | atip_data/config.json | — |  |  |  |  | 2026-09-24
55 | 0 | Delivered baseline (maintain) | MON-07 | Monitoring | Feed health | WebSocket stall detection | Code-Derived | P1 | COMPLETED | 70 |  | Implemented | Maintain | data/dhan_ws.py | b303d7a |  |  |  |  | 2026-09-24
56 | 0 | Delivered baseline (maintain) | MON-08 | Monitoring | Diagnostics | Diagnostic tool | Code-Derived | P2 | COMPLETED | 65 |  | diagnose.py | Maintain | diagnose.py | — |  |  |  |  | 2026-09-24
57 | 0 | Delivered baseline (maintain) | OPS-01 | Deployment/Ops | Autostart/scheduling | Windows autostart | Code-Derived | P1 | COMPLETED | 75 |  | Task Scheduler + VBS | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml | — |  |  |  |  | 2026-09-24
58 | 0 | Delivered baseline (maintain) | OPS-07 | Deployment/Ops | Snapshot publishing | Hosted read-only view | Code-Derived | P2 | COMPLETED | 80 |  | Implemented | Maintain | publish_snapshot.py | — |  |  |  |  | 2026-09-24
59 | 1 | Foundation | DP-09 | Data Platform | India VIX | Real VIX series as MH/MSI/CRI input | Agreed-Spec | P0 | COMPLETED | 40 |  | Read from index snapshot with 15.0 fallback | Store daily VIX; remove silent default; flag missing | scores/engine.py; data/markets.py | engine.py:358 |  |  |  |  | 2026-09-24
60 | 1 | Foundation | DP-17 | Data Platform | Market breadth | Advance/decline; new highs/lows | Agreed-Spec | P0 | COMPLETED | 30 | DP-02 | Breadth input frozen (25.93) | Compute A/D and 52w highs/lows from prices_daily | scores/engine.py | Phase status Tier 3 |  |  |  |  | 2026-09-24
61 | 1 | Foundation | SC-09 | Alpha/Factor Engine | Market Health score | MH formula + regime label | Agreed-Spec | P0 | COMPLETED | 65 | DP-09; DP-17 | Implemented; breadth/VIX inputs frozen | Use real inputs; backfill market_health history | scores/engine.py | engine.py:354 |  |  |  |  | 2026-09-24
62 | 1 | Foundation | SC-08 | Alpha/Factor Engine | ACS | AI Confidence Score | Agreed-Spec | P0 | COMPLETED | 55 | SC-09 | Implemented; accuracy query leak; NewsConfidence frozen | Bound feedback query by date; real news confidence | scores/engine.py | engine.py:389 |  |  |  |  | 2026-09-24
63 | 1 | Foundation | MON-01 | Monitoring | Job logging | Accurate pipeline_log | Code-Derived | P0 | IN PROGRESS | 50 |  | Swallows exceptions; no end time; SUCCESS with 0 rows | Record failures, end time, row counts | pipeline/scheduler.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
64 | 1 | Foundation | MON-02 | Monitoring | Stalled-job detection | Heartbeat per job | Code-Derived | P0 | YET TO START | 5 | MON-01 |  | Expected-run table + missed-run check | pipeline/scheduler.py | news job silent 11 days |  |  |  |  | 2026-09-24
65 | 1 | Foundation | MON-03 | Monitoring | Failure alerting | Alerts on failure | Agreed-Spec | P0 | IN PROGRESS | 30 | MON-02 | Telegram path exists; unconfigured | Configure Telegram; alert on failure/stall | alerts/telegram.py | run_job |  |  |  |  | 2026-09-24
66 | 1 | Foundation | DB-14 | Dashboard | Alerts / morning brief | Telegram + 08:30 digest | Agreed-Spec | P1 | IN PROGRESS | 50 | MON-03 | Digest scheduled; channel unconfigured | Deliver digest; verify daily | alerts/telegram.py | scheduler.py:1032 |  |  |  |  | 2026-09-24
67 | 1 | Foundation | RK-15 | Risk Management | Risk alerts | Alerts on risk events | Agreed-Spec | P1 | IN PROGRESS | 40 | MON-03 | CRI alerts coded; channel unconfigured | Alert on halt, limit breach, CRI spike | alerts/telegram.py | — |  |  |  |  | 2026-09-24
68 | 1 | Foundation | MON-06 | Monitoring | Log rotation | Rotating logs | Code-Derived | P1 | YET TO START | 0 |  |  | RotatingFileHandler | main.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
69 | 1 | Foundation | DBS-06 | Database | Timestamp consistency | One timezone convention | Code-Derived | P1 | IN PROGRESS | 30 |  | IST and UTC mixed in same rows | Normalise; fix news recency | db/schema.py; data/news.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
70 | 1 | Foundation | NS-01 | News/Sentiment | News ingestion | Reliable daily news feed | Agreed-Spec | P0 | IN PROGRESS | 50 | MON-02 | ~1,249 rows; job stalled as of 09-21 | Fix job; add second source; health check | data/news.py | Phase status Tier 2 |  |  |  |  | 2026-09-24
71 | 1 | Foundation | OPS-03 | Deployment/Ops | Install/setup | Reproducible install | Code-Derived | P1 | IN PROGRESS | 50 |  | setup.py lists pandas-ta; omits ta | Fix requirements/setup; pin versions | setup.py; requirements.txt | Phase status Tier 3 |  |  |  |  | 2026-09-24
72 | 1 | Foundation | EX-01 | Execution | Order management tests | Tested order rule engine | Agreed-Spec | P0 | COMPLETED | 70 |  | orders/rules.py (944 lines) without tests | Unit tests for rules.py | orders/rules.py; tests/ | Phase status Phase 11 |  |  |  |  | 2026-09-24
73 | 1 | Foundation | OPS-02 | Deployment/Ops | CI + end-to-end test | Data->score->signal->order->P&L test | Code-Derived | P0 | COMPLETED | 70 | EX-01 | GitHub Actions; ~270 test functions; no E2E | Add E2E pipeline test | .github/workflows/tests.yml; tests/ | — |  |  |  |  | 2026-09-24
74 | 1 | Foundation | DP-15 | Data Platform | Fundamentals | ROE; ROCE; EPS; PEG; FCF; D/E | Agreed-Spec | P0 | IN PROGRESS | 30 |  | Screener.in fetcher; ingestion disabled | Your decision; enable; quarterly store; no 50.0 default | data/fundamentals.py; pipeline/scheduler.py | FUNDAMENTALS_ENABLED=False |  |  |  |  | 2026-09-24
75 | 1 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | FS formula per concept document | Agreed-Spec | P0 | IN PROGRESS | 20 | DP-15 | Default 50 when unparsed | Implement FS formula on real data | data/fundamentals.py | — |  |  |  |  | 2026-09-24
76 | 1 | Foundation | SC-02 | Alpha/Factor Engine | SPI | Stability Profit Index per QRH | Agreed-Spec | P0 | IN PROGRESS | 30 | SC-13 |  | Implement SPI formula separately from FS | scores/engine.py | engine.py:503 |  |  |  |  | 2026-09-24
77 | 1 | Foundation | SC-05 | Alpha/Factor Engine | CRI debt input | CRI per QRH incl. Debt | Agreed-Spec | P1 | COMPLETED | 75 | DP-15 | Implemented; Debt input missing | Feed Debt/Equity | scores/engine.py | engine.py:276 |  |  |  |  | 2026-09-24
78 | 1 | Foundation | SC-01 | Alpha/Factor Engine | VPI inputs | VPI per QRH | Agreed-Spec | P1 | COMPLETED | 80 | DP-15 | Implemented; FG/IS inputs weak | Real Fundamental Growth input | scores/engine.py | engine.py:222 |  |  |  |  | 2026-09-24
79 | 1 | Foundation | PF-01 | Portfolio | Portfolio ingestion | Zerodha/Dhan holdings sync | Agreed-Spec | P0 | IN PROGRESS | 60 |  | Kite holdings sync; Dhan holdings | Scheduled reliable sync + token handling | portfolio/zerodha.py; data/dhan.py | — |  |  |  |  | 2026-09-24
80 | 1 | Foundation | BR-04 | Broker Integration | Portfolio sync schedule | Real-time/daily sync (FR-BI-002) | Agreed-Spec | P0 | IN PROGRESS | 50 | PF-01 | Partial | Scheduled sync with alert on failure | pipeline/scheduler.py | — |  |  |  |  | 2026-09-24
81 | 1 | Foundation | PF-02 | Portfolio | Holdings & P&L | Holdings and P&L | Agreed-Spec | P0 | IN PROGRESS | 60 | PF-01 | portfolio_holdings with pnl | Realised + unrealised P&L | portfolio/ | zerodha.py:64 |  |  |  |  | 2026-09-24
82 | 1 | Foundation | PF-13 | Portfolio | Daily P&L series | Stored daily P&L (paper + live) | Code-Derived | P0 | YET TO START | 0 | PF-02 | None; realized_pnl cumulative only | Daily P&L table; EOD job | orders/paper.py | orders/risk.py docstring |  |  |  |  | 2026-09-24
83 | 1 | Foundation | RK-13 | Risk Management | Risk-based sizing wired to orders | FR-RM-001 position size | Agreed-Spec | P0 | IN PROGRESS | 25 |  | position_size_pct computed; not read | Use size in order path | scores/predictions.py; orders/rules.py | predictions.py:84 |  |  |  |  | 2026-09-24
84 | 1 | Foundation | RK-07 | Risk Management | Daily loss limit | Circuit breaker | Quant-Research | P0 | YET TO START | 0 | PF-13 | Deliberately absent | Limit on PF-13; auto-halt | orders/risk.py | — |  |  |  |  | 2026-09-24
85 | 1 | Foundation | RK-08 | Risk Management | Drawdown limit | Drawdown halt | Quant-Research | P0 | YET TO START | 0 | PF-13 |  | Peak-to-trough on PF-13; auto-halt | orders/risk.py | — |  |  |  |  | 2026-09-24
86 | 1 | Foundation | DBS-03 | Database | Backups | Automated backups | Agreed-Spec | P1 | IN PROGRESS | 40 |  | Manual pre-repair backups | Nightly integrity-checked backup + retention | db/ | atip_data/*.bak |  |  |  |  | 2026-09-24
87 | 1 | Foundation | DP-06 | Data Platform | Corporate actions open items | Split/bonus/demerger adjustment | Code-Derived | P2 | COMPLETED | 85 |  | NSE CA calendar; reconciliation; volume re-base | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py | 4416ac7 |  |  |  |  | 2026-09-24
88 | 1 | Foundation | TA-06 | Technical Analysis | Support/Resistance | S/R levels (ZPI/RRI inputs) | Agreed-Spec | P1 | UNCLEAR | 30 |  | Not verified statically | Confirm what ZPI/RRI use; implement pivot-based S/R | scores/engine.py | — |  |  |  |  | 2026-09-24
89 | 1 | Foundation | DP-19 | Data Platform | Data quality layer | Validation + DataQualityScore | Quant-Research | P1 | IN PROGRESS | 35 | MON-01 | Coverage/identical-bar/OHLC guards; no DQS | DQS table; outlier and timestamp checks | pipeline/scheduler.py | ba31981; 8526a9b |  |  |  |  | 2026-09-24
90 | 2 | Quant Research (data, factors, backtesting) | DBS-04 | Database | Schema migrations | Versioned migrations | Code-Derived | P0 | IN PROGRESS | 20 |  | CREATE IF NOT EXISTS only | Migration mechanism before new tables | db/schema.py | — |  |  |  |  | 2026-09-24
91 | 2 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | Live quotes + index feed (FR-MD-001) | Agreed-Spec | P1 | IN PROGRESS | 60 |  | Index WebSocket 09:00-15:45 + quote cache; stock tick feed never run | Stock-level live feed in production; failover | data/dhan_ws.py; data/dhan.py | dhan_ws.py session window/backoff |  |  |  |  | 2026-09-24
92 | 2 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | Stored 1/5/15-min bars | Agreed-Spec | P0 | IN PROGRESS | 20 | DBS-04 | Fetched every 30 min; nothing stored | Persist bars; retention policy | data/dhan.py; pipeline/scheduler.py | — |  |  |  |  | 2026-09-24
93 | 2 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | VWAP (TS weight 0.08) | Agreed-Spec | P1 | YET TO START | 5 | DP-03 | Weight seeded; never computed | Compute from intraday bars | data/technical.py | schema.py:322 |  |  |  |  | 2026-09-24
94 | 2 | Quant Research (data, factors, backtesting) | SC-12 | Alpha/Factor Engine | Technical Score VWAP input | TS formula complete | Agreed-Spec | P1 | COMPLETED | 75 | TA-03 | Implemented; VWAP weight dead | Include VWAP | data/technical.py | technical.py:307 |  |  |  |  | 2026-09-24
95 | 2 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | Volume by price; POC | Agreed-Spec | P1 | YET TO START | 0 | DP-03 |  | Implement on intraday bars | data/technical.py | — |  |  |  |  | 2026-09-24
96 | 2 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | Daily/weekly/intraday confluence | Agreed-Spec | P2 | YET TO START | 5 | DP-03 | Daily only | Resample timeframes | data/technical.py | — |  |  |  |  | 2026-09-24
97 | 2 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | Indicators for every history date | Quant-Research | P0 | IN PROGRESS | 30 |  | ~15 sessions deep | Backfill 426 sessions | data/technical.py | Phase status Phase 3 |  |  |  |  | 2026-09-24
98 | 2 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | (date, symbol, factor, value) | Quant-Research | P0 | IN PROGRESS | 30 | TA-12 | Composites stored; sub-components discarded | Persist sub-factors | scores/engine.py | — |  |  |  |  | 2026-09-24
99 | 2 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | Momentum; MR; trend; vol; volume; liquidity | Quant-Research | P0 | IN PROGRESS | 50 | AF-03 | Embedded inside composites | Extract as standalone factors | scores/engine.py | — |  |  |  |  | 2026-09-24
100 | 2 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | z-score; robust; winsorise; percentile | Quant-Research | P0 | IN PROGRESS | 15 | AF-03 | Min-max only | Per-factor normalisation config | scores/engine.py | — |  |  |  |  | 2026-09-24
101 | 2 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | ID; formula; lookback; version | Quant-Research | P0 | YET TO START | 5 | AF-03 |  | Registry table + API | — | — |  |  |  |  | 2026-09-24
102 | 2 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | Versioned score formulas | Agreed-Spec | P1 | IN PROGRESS | 25 | AF-01 | model_version + weights_hash on signal_log | Formula registry table | scores/signal_log.py | signal_log.py:144 |  |  |  |  | 2026-09-24
103 | 2 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | Factor/model/experiment tables | Quant-Research | P1 | YET TO START | 0 | DBS-04 |  | Create schema | db/schema.py | — |  |  |  |  | 2026-09-24
104 | 2 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | Rank IC; ICIR; hit-rate of IC | Quant-Research | P0 | YET TO START | 10 | AF-03 | Ad hoc only | IC engine vs forward returns | — | — |  |  |  |  | 2026-09-24
105 | 2 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | Decay by horizon | Quant-Research | P1 | YET TO START | 0 | QR-01 |  | Implement | — | — |  |  |  |  | 2026-09-24
106 | 2 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | Correlation matrix | Quant-Research | P1 | YET TO START | 0 | AF-03 |  | Implement | — | — |  |  |  |  | 2026-09-24
107 | 2 | Quant Research (data, factors, backtesting) | QR-04 | Quant Research | Statistical toolkit | Correlation; covariance; regression | Quant-Research | P1 | YET TO START | 5 | AF-03 | Univariate beta only | Stats module | — | technical.py:99 |  |  |  |  | 2026-09-24
108 | 2 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | Validation before production | Quant-Research | P1 | YET TO START | 0 | QR-01; QR-03 | Factor enters via seed code | Gate workflow + approval record | — | — |  |  |  |  | 2026-09-24
109 | 2 | Quant Research (data, factors, backtesting) | BT-16 | Backtesting | Dated equity curve / run records | Run registry with dated equity | Quant-Research | P0 | YET TO START | 5 |  |  | Dated trades + equity curve + run table | strategy/; scores/backtest.py | — |  |  |  |  | 2026-09-24
110 | 2 | Quant Research (data, factors, backtesting) | BT-08 | Backtesting | Portfolio-level backtest | Shared capital; sizing | Quant-Research | P0 | YET TO START | 5 | BT-16 | Independent per-trade notional | Portfolio simulator | — | backtest_history.py:139 |  |  |  |  | 2026-09-24
111 | 2 | Quant Research (data, factors, backtesting) | BT-09 | Backtesting | Drawdown analysis | Max DD on dated equity | Agreed-Spec | P0 | IN PROGRESS | 30 | BT-16 | DD in trade order (wrong) | Compute on equity curve | strategy/ | backtest_aggressive.py:206 |  |  |  |  | 2026-09-24
112 | 2 | Quant Research (data, factors, backtesting) | BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | Risk-adjusted metrics | Agreed-Spec | P0 | YET TO START | 0 | BT-16 |  | Implement | — | — |  |  |  |  | 2026-09-24
113 | 2 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | Tail metrics | Agreed-Spec | P1 | YET TO START | 0 | BT-16 |  | Implement | — | — |  |  |  |  | 2026-09-24
114 | 2 | Quant Research (data, factors, backtesting) | BT-05 | Backtesting | Itemised costs | Brokerage; STT; GST; stamp; SEBI fee; exchange fee | Agreed-Spec | P0 | IN PROGRESS | 35 |  | Single blended cost % | Indian cost model shared by backtest and paper | strategy/ | backtest_history.py:39 |  |  |  |  | 2026-09-24
115 | 2 | Quant Research (data, factors, backtesting) | BT-06 | Backtesting | Slippage in backtest | Slippage model | Agreed-Spec | P1 | IN PROGRESS | 30 | BT-05 | Paper broker only | Shared slippage model | orders/paper.py | paper.py:199 |  |  |  |  | 2026-09-24
116 | 2 | Quant Research (data, factors, backtesting) | BT-07 | Backtesting | Liquidity constraints | ADV/turnover floor + participation cap | Agreed-Spec | P1 | IN PROGRESS | 40 |  | One engine has floor | All engines | scores/backtest.py | backtest.py:61 |  |  |  |  | 2026-09-24
117 | 2 | Quant Research (data, factors, backtesting) | DP-18 | Data Platform | Survivorship-free universe | Point-in-time constituents | Agreed-Spec | P1 | COMPLETED | 80 |  | Current NIFTY 500 download | Store constituent history | data/index_constituents.py | — |  |  |  |  | 2026-09-24
118 | 2 | Quant Research (data, factors, backtesting) | BT-15 | Backtesting | Bias controls | Look-ahead; survivorship | Quant-Research | P1 | IN PROGRESS | 30 | DP-18 | Look-ahead handled in 2 places | Systematic checks | — | backtest.py:163-174 |  |  |  |  | 2026-09-24
119 | 2 | Quant Research (data, factors, backtesting) | BT-03 | Backtesting | In/out-of-sample | Split testing | Agreed-Spec | P0 | IN PROGRESS | 20 | BT-16 | Forward signal tracker only | Formal splits | — | — |  |  |  |  | 2026-09-24
120 | 2 | Quant Research (data, factors, backtesting) | BT-02 | Backtesting | Walk-forward | Rolling train/test (purged) | Agreed-Spec | P0 | YET TO START | 5 | BT-03 |  | Implement | — | — |  |  |  |  | 2026-09-24
121 | 2 | Quant Research (data, factors, backtesting) | BT-13 | Backtesting | Monte Carlo | Trade shuffle/bootstrap | Agreed-Spec | P1 | YET TO START | 0 | BT-16 |  | Implement | — | — |  |  |  |  | 2026-09-24
122 | 2 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | Optimiser | Agreed-Spec | P1 | IN PROGRESS | 20 | BT-02 | Manual sweep | Grid/Bayesian optimiser | — | aggressive.py:57 |  |  |  |  | 2026-09-24
123 | 2 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | Sensitivity analysis | Agreed-Spec | P1 | IN PROGRESS | 20 | BT-04 | Manual sweep | Neighbourhood analysis | strategy/aggressive.py | — |  |  |  |  | 2026-09-24
124 | 2 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | Deflated Sharpe; PBO; regime testing | Quant-Research | P1 | YET TO START | 0 | BT-02 |  | Implement | — | — |  |  |  |  | 2026-09-24
125 | 2 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | Seeded runs; experiment log | Quant-Research | P1 | YET TO START | 0 | DBS-07 |  | Experiment store | — | — |  |  |  |  | 2026-09-24
126 | 2 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | Trend strategy research | Agreed-Spec | P1 | IN PROGRESS | 30 | BT-02 | Aggressive exit + 3-policy backtest | Entry-side research | strategy/ | backtest_history.py |  |  |  |  | 2026-09-24
127 | 2 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | MR strategy research | Agreed-Spec | P1 | IN PROGRESS | 20 | BT-02 | RSI band inside VPI only | Standalone MR tests | scores/engine.py | — |  |  |  |  | 2026-09-24
128 | 2 | Quant Research (data, factors, backtesting) | QR-13 | Quant Research | Signal outcome research by regime | Hit rate by regime/ACS decile | Code-Derived | P1 | COMPLETED | 70 | ML-05 | success_report keyed on signal/threshold | Add regime/ACS buckets | scores/signal_log.py | signal_log.py:522 |  |  |  |  | 2026-09-24
129 | 2 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | 1y; 3y; rolling-60 beta (QRH) | Agreed-Spec | P2 | IN PROGRESS | 40 | TA-12 | 1y beta only | Add 3y and rolling beta | data/technical.py | technical.py:99 |  |  |  |  | 2026-09-24
130 | 2 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | Optional BRI (QRH) | Agreed-Spec | P2 | YET TO START | 0 | TA-09 |  | Define + implement | — | — |  |  |  |  | 2026-09-24
131 | 2 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | Ichimoku; Donchian; Keltner; SAR; MFI; CMF; HV | Quant-Research | P2 | YET TO START | 5 | TA-12 |  | Implement per research workbook | data/technical.py | — |  |  |  |  | 2026-09-24
132 | 2 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | Futures; options; OI; IV; PCR | Agreed-Spec | P1 | YET TO START | 0 | DBS-04 |  | NSE F&O bhavcopy + option chain store | — | — |  |  |  |  | 2026-09-24
133 | 2 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | Market Sentiment Index per QRH | Agreed-Spec | P1 | IN PROGRESS | 55 | DP-08 | Options/PCR frozen; news rule-based | Real PCR; AI news later | scores/engine.py | engine.py:374 |  |  |  |  | 2026-09-24
134 | 2 | Quant Research (data, factors, backtesting) | DP-10 | Data Platform | FII/DII history | FII/DII time series | Agreed-Spec | P2 | COMPLETED | 80 |  | Session flows; only 7 sessions history | Historical backfill source | data/bhavcopy.py | 969f570 |  |  |  |  | 2026-09-24
135 | 2 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | Pre-open GIFT Nifty | Agreed-Spec | P2 | IN PROGRESS | 60 |  | In index feed; shown on dashboard | Verify pre-market capture; store history | data/dhan.py | dhan.py:486 |  |  |  |  | 2026-09-24
136 | 2 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | Dashboard section | Agreed-Spec | P2 | IN PROGRESS | 60 | DP-11 | In index strip | Dedicated pre-open view | dashboard/server.py | — |  |  |  |  | 2026-09-24
137 | 2 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | Indices; FX; commodities; yields | Agreed-Spec | P2 | IN PROGRESS | 70 |  | 13 yfinance tickers | Bond yields; history depth | data/markets.py | markets.py:22-26 |  |  |  |  | 2026-09-24
138 | 2 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | Sector classification + sector indices | Agreed-Spec | P2 | IN PROGRESS | 60 |  | Industry via constituents | Sector index history; sector breadth | data/index_constituents.py | — |  |  |  |  | 2026-09-24
139 | 2 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | MF; promoter; insider; bulk/block | Agreed-Spec | P1 | IN PROGRESS | 25 |  | Bulk/block only | Promoter/SAST/PIT/MF feeds | data/bhavcopy.py | bhavcopy.py:67-124 |  |  |  |  | 2026-09-24
140 | 2 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | INS formula | Agreed-Spec | P1 | IN PROGRESS | 40 | DP-16 | FII + bulk only | Add MF/promoter/insider | scores/engine.py | engine.py:188 |  |  |  |  | 2026-09-24
141 | 2 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | Deal-flow signal | Agreed-Spec | P2 | IN PROGRESS | 40 | DP-16 | Feeds INS | Validate with IC | data/bhavcopy.py | bhavcopy.py:113 |  |  |  |  | 2026-09-24
142 | 3 | Strategy Engine | SG-04 | Signal Engine | Rich decision states | STRONG BUY..NO TRADE with reasons | Quant-Research | P0 | IN PROGRESS | 20 | BT-02 | WAIT as de-facto no-trade | Extended states + stored reasons | scores/engine.py | engine.py:499 |  |  |  |  | 2026-09-24
143 | 3 | Strategy Engine | SG-01 | Signal Engine | SELL calibration | BUY/SELL/HOLD/WAIT all reachable | Agreed-Spec | P0 | COMPLETED | 70 | BT-02 | SELL never fired | Backtest-based SELL thresholds | scores/engine.py | determine_signal |  |  |  |  | 2026-09-24
144 | 3 | Strategy Engine | SE-01 | Strategy Engine | Strategy library | Multiple strategies (FR-SB-004) | Agreed-Spec | P0 | IN PROGRESS | 20 | BT-16 | One strategy + order rules | Strategy interface + registry | strategy/ | — |  |  |  |  | 2026-09-24
145 | 3 | Strategy Engine | SE-02 | Strategy Engine | Strategy parameters | Parameter management | Agreed-Spec | P0 | IN PROGRESS | 35 | SE-01 | Aggressive params; order_rules | Param store per strategy with versions | strategy/; orders/rules.py | — |  |  |  |  | 2026-09-24
146 | 3 | Strategy Engine | SE-03 | Strategy Engine | Rule-based strategies | Rule engine | Agreed-Spec | P1 | IN PROGRESS | 50 | SE-01 | orders/rules.py rule engine | Generic rule definition format | orders/rules.py | — |  |  |  |  | 2026-09-24
147 | 3 | Strategy Engine | SE-06 | Strategy Engine | Multi-factor strategy | Composite-score entries | Agreed-Spec | P1 | IN PROGRESS | 40 | SE-01; QR-01 | BUY from ATIP composite | IC-weighted multi-factor strategy | scores/engine.py | engine.py:435 |  |  |  |  | 2026-09-24
148 | 3 | Strategy Engine | SE-04 | Strategy Engine | Quant strategies | Factor/stat strategies | Quant-Research | P1 | YET TO START | 5 | SE-01; QR-01 |  | Implement first quant strategies | — | — |  |  |  |  | 2026-09-24
149 | 3 | Strategy Engine | SE-09 | Strategy Engine | Strategy lifecycle | Idea -> research -> paper -> live -> retired | Quant-Research | P1 | YET TO START | 5 | SE-01 |  | State machine + gates | — | strategy_event 3 rows |  |  |  |  | 2026-09-24
150 | 3 | Strategy Engine | SE-11 | Strategy Engine | Strategy health | Rolling Sharpe/DD per strategy | Quant-Research | P1 | YET TO START | 0 | SE-09; BT-16 |  | Health scoring + alerts | — | — |  |  |  |  | 2026-09-24
151 | 3 | Strategy Engine | SE-07 | Strategy Engine | Strategy combination/ranking/selection | Allocator across strategies | Quant-Research | P1 | YET TO START | 5 | SE-11 |  | Allocator | — | — |  |  |  |  | 2026-09-24
152 | 3 | Strategy Engine | SE-08 | Strategy Engine | Regime-aware selection | Regime switches strategies | Quant-Research | P2 | IN PROGRESS | 15 | SE-07; ML-05 | Regime gates only | Regime-conditional allocation | scores/engine.py | — |  |  |  |  | 2026-09-24
153 | 3 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | Midday/pre-close scans on real data | Code-Derived | P2 | IN PROGRESS | 60 | DP-03 | Scheduled 12:30 and 14:45 | Use stored intraday bars | pipeline/scheduler.py | scheduler.py:1048 |  |  |  |  | 2026-09-24
154 | 3 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | Daily top-25 lists per concept document | Agreed-Spec | P1 | IN PROGRESS | 40 |  | CRI per-stock column only | Dedicated lists | dashboard/server.py | — |  |  |  |  | 2026-09-24
155 | 3 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | Dashboard section | Agreed-Spec | P1 | YET TO START | 10 | SE-11 |  | Panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
156 | 4 | AI/ML | ML-13 | AI/ML | Labels/targets | Outcome labels for training | Agreed-Spec | P0 | IN PROGRESS | 40 | AF-03 | predictions + accuracy_tracker | Label store with horizons | scores/ | — |  |  |  |  | 2026-09-24
157 | 4 | AI/ML | ML-07 | AI/ML | Feature selection | Automated selection | Quant-Research | P1 | YET TO START | 0 | ML-13; QR-01 |  | Implement | — | — |  |  |  |  | 2026-09-24
158 | 4 | AI/ML | ML-08 | AI/ML | Model validation | Purged CV; AUC; calibration | Agreed-Spec | P0 | YET TO START | 0 | ML-13; BT-02 |  | Validation framework | — | — |  |  |  |  | 2026-09-24
159 | 4 | AI/ML | ML-01 | AI/ML | Supervised ML | Classification/regression models | Agreed-Spec | P0 | YET TO START | 0 | ML-08 | None; no ML library | First model (e.g. gradient boosting) | — | grep sklearn = 0 |  |  |  |  | 2026-09-24
160 | 4 | AI/ML | ML-12 | AI/ML | Model registry/versioning | FR-ML-002 | Agreed-Spec | P0 | IN PROGRESS | 15 | ML-01; DBS-07 | Signal provenance only | Registry | scores/signal_log.py | — |  |  |  |  | 2026-09-24
161 | 4 | AI/ML | ML-11 | AI/ML | Ensemble models | Ensembles | Quant-Research | P1 | YET TO START | 0 | ML-01 |  | Implement | — | — |  |  |  |  | 2026-09-24
162 | 4 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | Drift alerts (FR-ML-001) | Agreed-Spec | P1 | YET TO START | 0 | ML-12 |  | Implement | — | — |  |  |  |  | 2026-09-24
163 | 4 | AI/ML | ML-10 | AI/ML | Explainability | FR-AI-003 | Agreed-Spec | P1 | IN PROGRESS | 40 | ML-01 | top_factor_1..3 | Model attribution | scores/engine.py | — |  |  |  |  | 2026-09-24
164 | 4 | AI/ML | ML-05 | AI/ML | Regime detection | Model-based regime + probability | Agreed-Spec | P0 | IN PROGRESS | 30 | SC-09 | 5-way threshold on MH | HMM/GMM; regime-conditional weights | scores/engine.py | compute_mh |  |  |  |  | 2026-09-24
165 | 4 | AI/ML | ML-03 | AI/ML | Unsupervised learning | Clustering | Agreed-Spec | P2 | YET TO START | 0 | AF-03 |  | Implement | — | — |  |  |  |  | 2026-09-24
166 | 4 | AI/ML | ML-06 | AI/ML | Anomaly detection | Data/market anomalies | Agreed-Spec | P2 | YET TO START | 0 | DP-19 |  | Implement | — | — |  |  |  |  | 2026-09-24
167 | 4 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | FR-SB-003 | Agreed-Spec | P1 | YET TO START | 0 | ML-01; SE-01 |  | ML-signal strategy through lifecycle | — | — |  |  |  |  | 2026-09-24
168 | 4 | AI/ML | NS-02 | News/Sentiment | News classification | Earnings/Orders/M&A/RBI/Govt/Global/Geopolitics | Agreed-Spec | P0 | IN PROGRESS | 30 |  | Claude classifier coded; key unset | Set key; taxonomy; cost cap | data/news.py | news.py:118-129 |  |  |  |  | 2026-09-24
169 | 4 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | Positive/neutral/negative + confidence | Agreed-Spec | P0 | IN PROGRESS | 40 | NS-02 | Rule-based; confidence frozen 50 | Model-based scoring | data/news.py | — |  |  |  |  | 2026-09-24
170 | 4 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | Decayed weighted sentiment | Quant-Research | P1 | YET TO START | 5 | NS-03 |  | Implement | data/news.py | — |  |  |  |  | 2026-09-24
171 | 4 | AI/ML | NS-04 | News/Sentiment | AI news summary | Summary for dashboard | Agreed-Spec | P1 | IN PROGRESS | 50 | NS-02 | Headline list | LLM summary | dashboard/server.py | /api/news |  |  |  |  | 2026-09-24
172 | 4 | AI/ML | DB-06 | Dashboard | AI News Summary panel | Dashboard section | Agreed-Spec | P1 | IN PROGRESS | 50 | NS-04 | News panel (rule-based) | Show AI summary | dashboard/server.py | — |  |  |  |  | 2026-09-24
173 | 4 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | Transcript sentiment | Agreed-Spec | P2 | YET TO START | 0 | NS-02 |  | Implement | — | — |  |  |  |  | 2026-09-24
174 | 4 | AI/ML | ML-02 | AI/ML | Deep learning | Neural models | Agreed-Spec | P2 | YET TO START | 0 | ML-08 |  | Only if validated benefit | — | — |  |  |  |  | 2026-09-24
175 | 4 | AI/ML | ML-04 | AI/ML | Reinforcement learning | RL where appropriate | Agreed-Spec | P2 | YET TO START | 0 | ML-08 |  | Low priority | — | — |  |  |  |  | 2026-09-24
176 | 4 | AI/ML | DB-18 | Dashboard | Quant/model panel | Factor IC; model health | Quant-Research | P2 | YET TO START | 0 | ML-12 |  | Panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
177 | 5 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | Allocation view | Agreed-Spec | P1 | IN PROGRESS | 30 | PF-02 | Partial via PHS | Sector exposure table | scores/portfolio_health.py | — |  |  |  |  | 2026-09-24
178 | 5 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | HHI; weight caps | Agreed-Spec | P1 | IN PROGRESS | 40 | PF-03 | Diversification term in PHS | Position-weight metrics | scores/portfolio_health.py | portfolio_health.py:127 |  |  |  |  | 2026-09-24
179 | 5 | Risk & Portfolio | PF-09 | Portfolio | Correlation | Holdings correlation | Agreed-Spec | P1 | YET TO START | 0 | QR-04 |  | Implement | — | — |  |  |  |  | 2026-09-24
180 | 5 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | Cluster limits | Quant-Research | P1 | YET TO START | 0 | PF-09 |  | Implement | orders/risk.py | — |  |  |  |  | 2026-09-24
181 | 5 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | Portfolio risk | Quant-Research | P1 | YET TO START | 0 | QR-04 |  | Implement | — | — |  |  |  |  | 2026-09-24
182 | 5 | Risk & Portfolio | RK-06 | Risk Management | Sector limits | Sector cap | Quant-Research | P1 | YET TO START | 0 | PF-03 |  | Pre-trade sector check | orders/risk.py | — |  |  |  |  | 2026-09-24
183 | 5 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | Vol-scaled exposure | Quant-Research | P1 | YET TO START | 0 | TA-12 |  | Implement | orders/risk.py | — |  |  |  |  | 2026-09-24
184 | 5 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | ADV participation cap | Quant-Research | P1 | YET TO START | 5 | DP-02 | None in order path | Pre-trade ADV check | orders/risk.py | — |  |  |  |  | 2026-09-24
185 | 5 | Risk & Portfolio | RK-18 | Risk Management | Strategy risk budget | Per-strategy limits | Quant-Research | P2 | YET TO START | 0 | SE-09 |  | Implement | orders/risk.py | — |  |  |  |  | 2026-09-24
186 | 5 | Risk & Portfolio | RK-01 | Risk Management | Kill switch scopes + auto-trigger | Global/strategy/symbol; auto on breach | Quant-Research | P0 | COMPLETED | 80 | RK-07; RK-08 | Global flag file + config | Per-strategy/symbol; auto-trigger | orders/risk.py | 71bff1b |  |  |  |  | 2026-09-24
187 | 5 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | Flatten all positions | Quant-Research | P0 | YET TO START | 5 | RK-01 |  | One-command flatten with confirm | orders/ | — |  |  |  |  | 2026-09-24
188 | 5 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | Vol target; risk parity; MV with costs; BL | Quant-Research | P1 | YET TO START | 0 | RK-12 |  | Covariance + optimiser | — | — |  |  |  |  | 2026-09-24
189 | 5 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | Rebalance proposals | Agreed-Spec | P1 | YET TO START | 0 | PF-10 |  | Implement | — | — |  |  |  |  | 2026-09-24
190 | 5 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | Risk contribution | Quant-Research | P2 | YET TO START | 0 | PF-10 |  | Implement | — | — |  |  |  |  | 2026-09-24
191 | 5 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | Return attribution | Quant-Research | P2 | YET TO START | 0 | PF-13 |  | Implement | — | — |  |  |  |  | 2026-09-24
192 | 5 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | FR-PO-004 | Agreed-Spec | P2 | YET TO START | 5 | PF-13 |  | Implement | — | — |  |  |  |  | 2026-09-24
193 | 5 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | Risk panel | Quant-Research | P1 | YET TO START | 5 | RK-12 |  | Panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
194 | 6 | Execution | EX-02 | Execution | Order types | Market/limit/SL/SL-M/GTT/bracket | Agreed-Spec | P0 | IN PROGRESS | 50 |  | Market + limit | Add SL/SL-M/GTT | orders/broker.py | — |  |  |  |  | 2026-09-24
195 | 6 | Execution | EX-08 | Execution | Order modify/cancel | FR-LT-002/003 | Agreed-Spec | P0 | UNCLEAR | 0 |  | Not verified | Confirm; implement | orders/broker.py | — |  |  |  |  | 2026-09-24
196 | 6 | Execution | BR-05 | Broker Integration | Execution reconciliation | Orders vs broker fills/positions | Agreed-Spec | P0 | IN PROGRESS | 30 |  | Partial reconcile code | EOD reconciliation job + alert | orders/ | — |  |  |  |  | 2026-09-24
197 | 6 | Execution | BR-06 | Broker Integration | Connection health | FR-BI-003 | Agreed-Spec | P1 | IN PROGRESS | 40 | MON-03 | broker-status route; WS stall detection | Health checks + alerts | dashboard/server.py | b303d7a |  |  |  |  | 2026-09-24
198 | 6 | Execution | RK-17 | Risk Management | Broker/operational risk | Token expiry; connection loss | Quant-Research | P1 | IN PROGRESS | 30 | BR-06 | broker-status route | Automated checks | dashboard/server.py | — |  |  |  |  | 2026-09-24
199 | 6 | Execution | BR-08 | Broker Integration | Sandbox | Broker sandbox environment | Code-Derived | P2 | IN PROGRESS | 30 |  | SANDBOX env defined | Verify sandbox path end-to-end | orders/environment.py | — |  |  |  |  | 2026-09-24
200 | 6 | Execution | EX-09 | Execution | Measured slippage | Slippage vs decision price | Quant-Research | P1 | YET TO START | 5 | PF-13 | Assumption only | Measure per fill | orders/ | — |  |  |  |  | 2026-09-24
201 | 6 | Execution | EX-10 | Execution | Execution analytics | Implementation shortfall; fill/reject rate | Quant-Research | P1 | IN PROGRESS | 10 | EX-09 | order_log raw data only | Analytics + panel | orders/ | — |  |  |  |  | 2026-09-24
202 | 6 | Execution | BR-02 | Broker Integration | Zerodha/Kite | Portfolio (+orders optional) | Agreed-Spec | P2 | IN PROGRESS | 50 |  | Holdings sync only | Token refresh; orders if wanted | portfolio/zerodha.py | — |  |  |  |  | 2026-09-24
203 | 6 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | Live P&L view | Agreed-Spec | P1 | IN PROGRESS | 25 | PF-13 | Dashboard partial | Live P&L panel | dashboard/server.py | — |  |  |  |  | 2026-09-24
204 | 6 | Execution | SEC-03 | Security | Audit logging | Immutable audit (FR-AT-001) | Agreed-Spec | P1 | IN PROGRESS | 50 |  | order_log; signal_log; pipeline_log | Tamper-evident unified audit | — | — |  |  |  |  | 2026-09-24
205 | 7 | Advanced Quant | DP-04 | Data Platform | Tick data | Tick capture store | Quant-Research | P2 | YET TO START | 5 | DBS-04 | live_ticks exists; 0 rows | Tick ingestion + storage | data/dhan.py | — |  |  |  |  | 2026-09-24
206 | 7 | Advanced Quant | DP-05 | Data Platform | Order book / depth | L2 depth; bid/ask | Quant-Research | P2 | YET TO START | 5 | DP-04 | FULL feed type defined (CLI only) | Depth capture + schema | data/dhan.py | dhan.py FULL=21 |  |  |  |  | 2026-09-24
207 | 7 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | OBI; spread; microprice | Quant-Research | P2 | YET TO START | 0 | DP-05 |  | Implement | — | — |  |  |  |  | 2026-09-24
208 | 7 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors | OI buildup; IV; PCR; skew | Quant-Research | P2 | YET TO START | 0 | DP-08 |  | Implement | — | — |  |  |  |  | 2026-09-24
209 | 7 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | IV/RV; vol breakout | Quant-Research | P2 | YET TO START | 0 | DP-08 |  | Implement | — | — |  |  |  |  | 2026-09-24
210 | 7 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | Pairs research | Quant-Research | P2 | YET TO START | 0 | QR-04 |  | Implement | — | — |  |  |  |  | 2026-09-24
211 | 7 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | Long-short research | Quant-Research | P2 | YET TO START | 0 | DP-08 | None (long-only cash) | Needs shorting via F&O | — | — |  |  |  |  | 2026-09-24
212 | 7 | Advanced Quant | QR-09 | Quant Research | Event-driven research | Earnings/CA event studies | Quant-Research | P2 | YET TO START | 5 | DP-06 | CA data exists; no event study | Abnormal-return engine | — | — |  |  |  |  | 2026-09-24
213 | 7 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | Piotroski; Altman; value z-composite | Quant-Research | P2 | YET TO START | 0 | DP-15 |  | Implement | — | — |  |  |  |  | 2026-09-24
214 | 7 | Advanced Quant | EX-11 | Execution | Execution algos | TWAP/VWAP/POV | Quant-Research | P2 | YET TO START | 0 | DP-03 |  | Implement | — | — |  |  |  |  | 2026-09-24
215 | 7 | Advanced Quant | EX-12 | Execution | Market impact model | Impact estimate | Quant-Research | P2 | YET TO START | 0 | DP-05 |  | Implement | — | — |  |  |  |  | 2026-09-24
216 | 7 | Advanced Quant | EX-15 | Execution | Latency telemetry | p50/p95/p99 | Quant-Research | P2 | YET TO START | 0 |  |  | Instrument data and order paths | — | — |  |  |  |  | 2026-09-24
217 | 7 | Advanced Quant | EX-16 | Execution | Event-driven OMS | Event bus signal->risk->order->fill | Quant-Research | P2 | YET TO START | 10 | EX-15 | Synchronous calls | Implement | — | — |  |  |  |  | 2026-09-24
218 | 7 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | Event engine shared with live | Quant-Research | P2 | YET TO START | 0 | EX-16 | Bar loops only | Implement | — | — |  |  |  |  | 2026-09-24
219 | 7 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | RBI rates; CPI; IIP; yields | Quant-Research | P2 | YET TO START | 0 |  |  | Macro connectors + calendar | — | — |  |  |  |  | 2026-09-24
220 | 7 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | Source abstraction | Quant-Research | P2 | YET TO START | 0 |  |  | DataSource interface | — | — |  |  |  |  | 2026-09-24
221 | 7 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | Web/social/search/etc. | Quant-Research | P2 | YET TO START | 0 | AD-01 |  | Add sources | — | — |  |  |  |  | 2026-09-24
222 | 7 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | Columnar PIT research store | Quant-Research | P2 | YET TO START | 5 |  | SQLite only | Parquet/DuckDB store | — | — |  |  |  |  | 2026-09-24
223 | 7 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | Commodities; FX; bonds; MF | Agreed-Spec | P2 | YET TO START | 0 |  | Global display tickers only | MCX/CDS/bond/MF feeds | — | — |  |  |  |  | 2026-09-24
224 | 8 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | Decay alerts | Quant-Research | P1 | YET TO START | 0 | QR-02; ML-09 |  | Implement | — | — |  |  |  |  | 2026-09-24
225 | 8 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | DR plan | Agreed-Spec | P1 | YET TO START | 5 | DBS-03 |  | Restore drills | — | — |  |  |  |  | 2026-09-24
226 | 8 | Production Hardening | SEC-04 | Security | Encryption | TLS 1.3; AES-256 at rest (SRS) | Agreed-Spec | P1 | YET TO START | 5 |  | None locally | Encrypt secrets and DB at rest | — | — |  |  |  |  | 2026-09-24
227 | 8 | Production Hardening | API-05 | APIs | API contracts/docs | Documented contracts | Agreed-Spec | P2 | IN PROGRESS | 30 |  | FastAPI defaults only | Written contracts | — | — |  |  |  |  | 2026-09-24
228 | 8 | Production Hardening | API-06 | APIs | Widget JSON schemas | QRH deliverable | Agreed-Spec | P2 | YET TO START | 5 |  |  | Define schemas | — | — |  |  |  |  | 2026-09-24
229 | 8 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | BRD..OPS documents with real content | Agreed-Spec | P1 | IN PROGRESS | 15 |  | Mostly 60-word templates | Author docs from as-built system | docs/ | OLd_Archives_ATIP/ATIP_Docs |  |  |  |  | 2026-09-24
230 | 9 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | Per-user data isolation; tenant model | Enterprise-SaaS | P0 | YET TO START | 0 | OPS-05 | Single-user local design | Architecture decision record; tenant-scoped schema | — | BRD-003; SRS 2 |  |  |  |  | 2026-09-24
231 | 9 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | PostgreSQL/time-series (SRS) | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-01 | SQLite | Migrate to Postgres | — | SRS 2 |  |  |  |  | 2026-09-24
232 | 9 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure | TLS; WAF; rate limits; zero trust | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-01 | Local-only by design (never exposed) | Security architecture before any exposure | — | SRS 5 |  |  |  |  | 2026-09-24
233 | 9 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | FR-AU-001/002; RBAC | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-07 | Single-user; none | Identity provider; roles; MFA | — | SRS Part III |  |  |  |  | 2026-09-24
234 | 9 | Enterprise SaaS (final objective) | ENT-05 | Security | Session management | Timeout; refresh tokens; revocation (FR-AU-003) | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | Single static token | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
235 | 9 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | Email; mobile; OAuth; Google; Apple (FR-UM-001) | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 |  | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
236 | 9 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | FR-UM-002 | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-02 |  | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
237 | 9 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | Broker OAuth; encrypted per-user tokens | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | One owner's config.json | Vault + broker OAuth | — | — |  |  |  |  | 2026-09-24
238 | 9 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | SEBI retail algo framework (broker/exchange algo approval); RA/IA registration if advice is offered | Enterprise-SaaS | P0 | YET TO START | 0 |  |  | Legal review before offering to other users | — | BRD-006 |  |  |  |  | 2026-09-24
239 | 9 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | FR-AT-002 | Enterprise-SaaS | P0 | YET TO START | 0 | ENT-14 |  | Implement controls from ENT-14 | — | SRS Part III |  |  |  |  | 2026-09-24
240 | 9 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | DPDP Act; consent; retention | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-14 |  | Privacy policy + controls | — | BRD-004 |  |  |  |  | 2026-09-24
241 | 9 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | Web UI for all users | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 | Single-user dashboard + read-only snapshot | Build web app | — | SRS 2 |  |  |  |  | 2026-09-24
242 | 9 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | Free/Premium/Enterprise (FR-UM-003) | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-02 |  | Plans + payment gateway | — | SRS Part III |  |  |  |  | 2026-09-24
243 | 9 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | FR-UM-004 | Enterprise-SaaS | P2 | YET TO START | 0 | ENT-05 |  | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
244 | 9 | Enterprise SaaS (final objective) | ENT-19 | Channels | Watchlists | BR-006 | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-08 |  | Implement | — | BRD-004 |  |  |  |  | 2026-09-24
245 | 9 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | FR-AL-001/002 | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-19 | Owner-only Telegram | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
246 | 9 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | Push; SMS; email; WhatsApp; in-app (FR-AL-003) | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-11 | Telegram only | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
247 | 9 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | Android + iOS | Enterprise-SaaS | P1 | YET TO START | 0 | API-03 |  | Build apps | — | SRS 2 |  |  |  |  | 2026-09-24
248 | 9 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | FR-API-001/003 | Enterprise-SaaS | P0 | YET TO START | 0 | SEC-02 |  | /v1 API with auth and rate limits | — | SRS Part III |  |  |  |  | 2026-09-24
249 | 9 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | FR-API-002 | Enterprise-SaaS | P2 | YET TO START | 0 | API-03 |  | Implement | — | SRS Part III |  |  |  |  | 2026-09-24
250 | 9 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | Angel/Groww/Upstox/CSV (FR-PO-002) | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-06 |  | Importers | — | SRS Part III |  |  |  |  | 2026-09-24
251 | 9 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | Angel/Upstox/Groww trading | Enterprise-SaaS | P1 | YET TO START | 0 | ENT-06; BR-03 |  | Adapters behind BR-03 interface | — | SRS Part III |  |  |  |  | 2026-09-24
252 | 9 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | MF; bonds; commodities; currency (FR-PO-003) | Enterprise-SaaS | P2 | YET TO START | 0 | DP-21; BR-07 | Equity cash only | Asset-specific execution/risk adapters | — | BRD-001 |  |  |  |  | 2026-09-24
253 | 9 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | Portfolio; tax; AI performance (FR-RP) | Enterprise-SaaS | P1 | YET TO START | 0 | PF-13 |  | Report generation + export | — | SRS Part III |  |  |  |  | 2026-09-24
254 | 9 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | User admin; system config (FR-AD) | Enterprise-SaaS | P1 | YET TO START | 0 | SEC-02 | config.json edited by hand | Admin console | — | SRS Part III |  |  |  |  | 2026-09-24
255 | 9 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | FR-SB-001/002 | Enterprise-SaaS | P2 | YET TO START | 0 | SE-01; ENT-08 |  | Visual builder on SE-01 interface | — | SRS Part III |  |  |  |  | 2026-09-24
256 | 9 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | NL assistant (SRS) | Enterprise-SaaS | P2 | YET TO START | 0 | ENT-08 |  | Implement | — | SRS 3 |  |  |  |  | 2026-09-24
257 | 9 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | Docker/Kubernetes on cloud (SRS) | Enterprise-SaaS | P0 | YET TO START | 0 | DBS-05; ENT-07 | Local Windows only | Containerise; IaC; environments | — | SRS 2 |  |  |  |  | 2026-09-24
258 | 9 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | 99.9%+ availability; horizontal scale; metrics/tracing | Enterprise-SaaS | P1 | YET TO START | 0 | OPS-04 | Single process | HA design + SLOs | — | SRS 4 |  |  |  |  | 2026-09-24