## Summary
ATIP features and waves: delivery status
Source: docs/ATIP_MASTER_TRACKER.csv (master, 277 features) on 2026-09-28. Production runs release ATIP-W24-RC1 (W1-W24, deployed 2026-09-28 11:31). W25 is merged and tagged ATIP-W25-RC1 but not yet deployed.
Delivery status | Features | Share | Meaning
DEPLOYED - VERIFIED |  |  | In the running production release and tested (W1/W2 automated tests or earlier verification).
DEPLOYED - AWAITING QA |  |  | In the running production release (ATIP-W24-RC1); smoke-checked only, independent QA pending.
DEVELOPED - NOT DEPLOYED |  |  | Built and merged to master (ATIP-W25-RC1) but NOT running: production has not been restarted onto it.
IN PROGRESS |  |  | Partly built (some code may be live); remaining work listed in 'Next action'.
YET TO START |  |  | Not built yet.
BLOCKED |  |  | Cannot proceed until an external dependency or owner decision is resolved.
TOTAL
By phase
Phase | Phase name | Deployed - verified | Deployed - awaiting QA | Developed - not deployed | In progress | Yet to start | Blocked | Total | Deployed %
0 | Delivered baseline (maintain)
1 | Foundation
2 | Quant Research (data, factors, backtesting)
3 | Strategy Engine
4 | AI/ML
5 | Risk & Portfolio
6 | Execution
7 | Advanced Quant
8 | Production Hardening
8 | Production hardening
9 | Enterprise SaaS (final objective)
10 | Wealth track (Waves 11-20)
TOTAL
How to use
Tabs: All Features (every row, filterable), Deployed, Developed not deployed, In Progress, Yet To Start (incl. blocked), Waves.
Yellow cells in 'All Features' are yours: Review Status (drop-down) and Reviewer Notes. Example: Issue found / 'VaR panel blank for PAPER book'.
All counts are formulas over 'All Features' (Delivery Status column G, Waves Involved column K): edit or filter there and the summary follows.
Deployed features that depend on a config switch stay OFF until you enable it (wealth.enabled, ml.enabled, quant.enabled, W25 limits).

## Waves
Wave | Scope | Commit | Deployment | Features | Deployed - verified | Deployed - awaiting QA | Developed - not deployed | In progress | Yet to start | Blocked | Wave status
Baseline | Delivered platform before the waves: data ingestion, scores, dashboard, alerts | - | Live | [7 empty] | DEPLOYED - VERIFIED
W1 | Foundation: job monitoring, alerts, P&L, loss limits, sizing, data quality | 3c13f63 | Live | [7 empty] | DEPLOYED - VERIFIED
W2 | Research / backtesting engine | ba4028f | Live | [7 empty] | DEPLOYED - VERIFIED
W3 | Strategy engine | d563978 | Live | [7 empty] | DEPLOYED - AWAITING QA
W4 | Risk engine + order management (paper) | d3b8715 | Live | [7 empty] | DEPLOYED - AWAITING QA
W5 | AI / ML framework | 123b340 | Live | [7 empty] | DEPLOYED - AWAITING QA
W6 | Advanced quant | cf1997d | Live | [7 empty] | DEPLOYED - AWAITING QA
W7 | Enterprise layer (users, tenants, RBAC, billing foundation) | 3e52bea | Live (enterprise.enabled off) | [7 empty] | DEPLOYED - AWAITING QA
W8 | Production hardening (health, backups, migrations, MFA, audit) | a7d7187 | Live | [7 empty] | DEPLOYED - AWAITING QA
W9 | Release readiness, live-trading master switch | 24943f3 | Live | [7 empty] | DEPLOYED - AWAITING QA
W11 | Investor DNA | 1da609f | Live (wealth.enabled off) | [7 empty] | DEPLOYED - AWAITING QA
W12 | Multi-asset wealth dashboard | 45f0b4b | Live | [7 empty] | DEPLOYED - AWAITING QA
W13 | Goal planning | 9680ee6 | Live | [7 empty] | DEPLOYED - AWAITING QA
W14 | Dynamic asset allocation | c790b95 | Live | [7 empty] | DEPLOYED - AWAITING QA
W15 | Rebalancing | 643ad57 | Live | [7 empty] | DEPLOYED - AWAITING QA
W15.5 | Investor performance attribution | 8210de6 | Live | [7 empty] | DEPLOYED - AWAITING QA
W16 | Explainable AI advisor | 4340cc8 | Live (narration off) | [7 empty] | DEPLOYED - AWAITING QA
W17 | Integrated intelligence | 8346d8d | Live | [7 empty] | DEPLOYED - AWAITING QA
W18 | QA suite + security fixes (70 tests written, not run) | 757116e | Live | [7 empty] | DEPLOYED - AWAITING QA
W19 | Beta / UAT tooling (UAT not executed) | 7c837be | Live | [7 empty] | DEPLOYED - AWAITING QA
W20 | Wealth hardening, migration 0005 | 11a8924 | Live | [7 empty] | DEPLOYED - AWAITING QA
W21 | Data & technical analysis | 52893af | Live | [7 empty] | DEPLOYED - AWAITING QA
W22 | Factor research platform | 609c6d6 | Live | [7 empty] | DEPLOYED - AWAITING QA
W23 | Research & backtesting depth | c00e6a7 | Live | [7 empty] | DEPLOYED - AWAITING QA
W24 | Machine learning (native GBM / RF / ensemble, validation, anomalies) | 0e648af | Live - release ATIP-W24-RC1, deployed 2026-09-28 11:31 | [7 empty] | DEPLOYED - AWAITING QA
W25 | Portfolio risk (VaR/ES, correlation, attribution, optimiser, limits, emergency exit) | 687b5ac | Merged to master + tagged ATIP-W25-RC1; NOT deployed (restart pending) | [7 empty] | DEVELOPED - NOT DEPLOYED
Note | A feature counts under every wave its tracker row names (implementation, evidence, notes, key files), so one feature can appear under several waves and the column does not add up to 277. W1/W2 work recorded without a wave tag counts as Baseline. The wealth track (W11-W20) is one tracker row per wave; its detail is in the W11-W20 handoffs.

## All Features
Seq | Phase | Phase Name | ID | Module | Feature | Delivery Status | Tracker Status | Completion % | Latest Wave | Waves Involved | Needs | Current Implementation | Next Action / Missing Work | Key Files | Last Updated | Review Status | Reviewer Notes
1 | 0 | Delivered baseline (maintain) | DP-02 | Data Platform | Daily OHLCV history | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | NSE Bhavcopy + Dhan; coverage/freshness/duplicate guards | Maintain | data/bhavcopy.py; data/dhan.py | 2026-09-24
2 | 0 | Delivered baseline (maintain) | DP-07 | Data Platform | Delivery data | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Full Bhavcopy nightly + backfill | Maintain | data/bhavcopy.py | 2026-09-24
3 | 0 | Delivered baseline (maintain) | DP-20 | Data Platform | Trading calendar | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | 2025-26 holidays + budget sessions | Add next year's holidays each December | utils/trading_calendar.py | 2026-09-24
4 | 0 | Delivered baseline (maintain) | TA-01 | Technical Analysis | Core indicators | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Computed and stored; MACD fixed and normalised | Maintain | data/technical.py | 2026-09-24
5 | 0 | Delivered baseline (maintain) | TA-02 | Technical Analysis | Extended oscillators | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Computed and stored | Maintain | data/technical.py | 2026-09-24
6 | 0 | Delivered baseline (maintain) | TA-05 | Technical Analysis | Fibonacci | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | 52-week 23.6/38.2/50/61.8 levels | Optional: swing-anchored levels | data/technical.py | 2026-09-24
7 | 0 | Delivered baseline (maintain) | TA-07 | Technical Analysis | Trend features | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Computed and stored | Maintain | data/technical.py | 2026-09-24
8 | 0 | Delivered baseline (maintain) | TA-08 | Technical Analysis | Relative strength | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | 20-day RS with date-matched benchmark | Sector-relative RS later (TA-08b in Phase 2 if wanted) | scores/engine.py | 2026-09-24
9 | 0 | Delivered baseline (maintain) | SC-03 | Alpha/Factor Engine | RRI | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented | Institutional input improves with SC-14 | scores/engine.py | 2026-09-24
10 | 0 | Delivered baseline (maintain) | SC-04 | Alpha/Factor Engine | MRI | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Implemented; MACD corrected | Maintain | scores/engine.py | 2026-09-24
11 | 0 | Delivered baseline (maintain) | SC-07 | Alpha/Factor Engine | ZPI | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented + delivery component | Maintain | scores/engine.py | 2026-09-24
12 | 0 | Delivered baseline (maintain) | SC-10 | Alpha/Factor Engine | Portfolio Health score | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py | 2026-09-24
13 | 0 | Delivered baseline (maintain) | PF-05 | Portfolio | Portfolio health | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented + dashboard | Maintain | scores/portfolio_health.py | 2026-09-24
14 | 0 | Delivered baseline (maintain) | SC-11 | Alpha/Factor Engine | Trade of the Day | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented; one TOD per session | Maintain | scores/engine.py | 2026-09-24
15 | 0 | Delivered baseline (maintain) | SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented; rank stored | Maintain | scores/engine.py | 2026-09-24
16 | 0 | Delivered baseline (maintain) | SC-17 | Alpha/Factor Engine | Configurable weights | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | weight_config table | Regime-specific rows used by ML-05 | db/schema.py | 2026-09-24
17 | 0 | Delivered baseline (maintain) | SG-02 | Signal Engine | Signal validation | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | EOD coverage guard; FII/DII hold | Maintain | pipeline/scheduler.py | 2026-09-24
18 | 0 | Delivered baseline (maintain) | SG-03 | Signal Engine | Signal ranking | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Implemented | Maintain | scores/engine.py | 2026-09-24
19 | 0 | Delivered baseline (maintain) | SG-05 | Signal Engine | Trade plan | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented | Maintain | scores/predictions.py | 2026-09-24
20 | 0 | Delivered baseline (maintain) | SG-06 | Signal Engine | Outcome tracking | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented; corrected denominator | Maintain | scores/signal_log.py | 2026-09-24
21 | 0 | Delivered baseline (maintain) | SG-07 | Signal Engine | Signal provenance log | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Append-only signal_log | Maintain | scores/signal_log.py | 2026-09-24
22 | 0 | Delivered baseline (maintain) | BT-01 | Backtesting | Historical backtest | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | 3 bar engines | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py | 2026-09-24
23 | 0 | Delivered baseline (maintain) | BT-10 | Backtesting | Win rate / profit factor / expectancy | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Implemented | Maintain | strategy/backtest_aggressive.py | 2026-09-24
24 | 0 | Delivered baseline (maintain) | RK-02 | Risk Management | Max order value | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Enforced when configured | Set values in config.json | orders/risk.py | 2026-09-24
25 | 0 | Delivered baseline (maintain) | RK-03 | Risk Management | Max orders per day | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Enforced when configured | Set values in config.json | orders/risk.py | 2026-09-24
26 | 0 | Delivered baseline (maintain) | RK-04 | Risk Management | Max open positions | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Enforced when configured | Set values in config.json | orders/risk.py | 2026-09-24
27 | 0 | Delivered baseline (maintain) | RK-05 | Risk Management | Symbol exposure limit | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Enforced when configured | Set values in config.json | orders/risk.py | 2026-09-24
28 | 0 | Delivered baseline (maintain) | RK-14 | Risk Management | Crash-risk gating | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | SELL_CRI_DANGER + strategy use | Maintain | scores/engine.py | 2026-09-24
29 | 0 | Delivered baseline (maintain) | EX-03 | Execution | Position management | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | reserve -> place -> apply | Maintain | strategy/positions.py | 2026-09-24
30 | 0 | Delivered baseline (maintain) | EX-04 | Execution | Entry/exit | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | strategy/live.py | Maintain | strategy/live.py | 2026-09-24
31 | 0 | Delivered baseline (maintain) | EX-05 | Execution | Stop loss | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented | Maintain | strategy/aggressive.py | 2026-09-24
32 | 0 | Delivered baseline (maintain) | EX-06 | Execution | Trailing stop | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented (4.0x ATR) | Maintain | strategy/aggressive.py | 2026-09-24
33 | 0 | Delivered baseline (maintain) | EX-07 | Execution | Profit booking / partial exit | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | Implemented in aggressive strategy | Maintain | strategy/aggressive.py | 2026-09-24
34 | 0 | Delivered baseline (maintain) | EX-13 | Execution | Paper trading | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Paper broker with slippage | Maintain | orders/paper.py | 2026-09-24
35 | 0 | Delivered baseline (maintain) | EX-14 | Execution | Live gating | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Implemented | Maintain | orders/environment.py | 2026-09-24
36 | 0 | Delivered baseline (maintain) | BR-01 | Broker Integration | Dhan | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | dhanhq integration | Maintain | data/dhan.py; orders/broker.py | 2026-09-24
37 | 0 | Delivered baseline (maintain) | BR-03 | Broker Integration | Broker abstraction | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | PAPER/SANDBOX/LIVE routing | Becomes multi-broker interface in ENT-15 | orders/environment.py | 2026-09-24
38 | 0 | Delivered baseline (maintain) | DB-01 | Dashboard | Market Health panel | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
39 | 0 | Delivered baseline (maintain) | DB-02 | Dashboard | Global Markets panel | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Rendered; snapshot bug fixed | Maintain | dashboard/server.py | 2026-09-24
40 | 0 | Delivered baseline (maintain) | DB-03 | Dashboard | FII/DII panel | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
41 | 0 | Delivered baseline (maintain) | DB-05 | Dashboard | Sector Rotation | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | Heatmap rendered | Maintain | dashboard/server.py | 2026-09-24
42 | 0 | Delivered baseline (maintain) | DB-07 | Dashboard | Top 25 VPI | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
43 | 0 | Delivered baseline (maintain) | DB-08 | Dashboard | Buy Zone (ZPI) | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
44 | 0 | Delivered baseline (maintain) | DB-09 | Dashboard | Recovery (RRI) | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
45 | 0 | Delivered baseline (maintain) | DB-10 | Dashboard | Momentum Reversal (MRI) | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
46 | 0 | Delivered baseline (maintain) | DB-12 | Dashboard | Portfolio Health panel | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
47 | 0 | Delivered baseline (maintain) | DB-13 | Dashboard | Trade of the Day | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | Rendered | Maintain | dashboard/server.py | 2026-09-24
48 | 0 | Delivered baseline (maintain) | DB-15 | Dashboard | Orders/signals panel | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | Rendered with PAPER status | Maintain | dashboard/server.py | 2026-09-24
49 | 0 | Delivered baseline (maintain) | DB-19 | Dashboard | Hosted read-only snapshot | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | publish_snapshot.py | Superseded by ENT-08 web app | publish_snapshot.py | 2026-09-24
50 | 0 | Delivered baseline (maintain) | API-01 | APIs | Internal REST | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | 15 FastAPI routes | Maintain | dashboard/server.py | 2026-09-24
51 | 0 | Delivered baseline (maintain) | API-02 | APIs | Local API authentication | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | 127.0.0.1 bind + X-ATIP-Token | Replaced by per-user auth in SEC-02 | dashboard/security.py | 2026-09-24
52 | 0 | Delivered baseline (maintain) | DBS-01 | Database | Schema | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | 19 SQLite tables | Migrations via DBS-04 | db/schema.py | 2026-09-24
53 | 0 | Delivered baseline (maintain) | DBS-02 | Database | Retention/purge | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | db/purge.py | Maintain | db/purge.py | 2026-09-24
54 | 0 | Delivered baseline (maintain) | SEC-01 | Security | Credential handling | DEPLOYED - VERIFIED | COMPLETED | 85% | W8 | ,W8, |  | Secrets abstraction (env > .env > atip_data/secrets > legacy config), presence/format validation, name-only access log, rotation dates, masking in logs | Move legacy plaintext keys out of config.json (owner action) | ops/secrets.py; ops/logs.py | 2026-09-25
55 | 0 | Delivered baseline (maintain) | MON-07 | Monitoring | Feed health | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | Implemented | Maintain | data/dhan_ws.py | 2026-09-24
56 | 0 | Delivered baseline (maintain) | MON-08 | Monitoring | Diagnostics | DEPLOYED - VERIFIED | COMPLETED | 80% | W8 | ,W8, |  | /health, /health/live¦ready¦database¦broker¦data¦scheduler¦ml (LIVE/READY/DEGRADED/FAILED); python -m ops status | Validate | ops/health.py; dashboard/ops_routes.py | 2026-09-25
57 | 0 | Delivered baseline (maintain) | OPS-01 | Deployment/Ops | Autostart/scheduling | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Task Scheduler + VBS | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml | 2026-09-24
58 | 0 | Delivered baseline (maintain) | OPS-07 | Deployment/Ops | Snapshot publishing | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented | Maintain | publish_snapshot.py | 2026-09-24
59 | 1 | Foundation | DP-09 | Data Platform | India VIX | DEPLOYED - VERIFIED | COMPLETED | 95% | Baseline | ,Baseline, |  | Daily INDIAVIX series in prices_daily (421 sessions 2025-01-13..; Dhan history + NSE close nightly); get_vix() = session feed then daily series; no 15.0 default | None for DP-09; VIX term structure/percentile features belong to later factor work | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py | 2026-09-24
60 | 1 | Foundation | DP-17 | Data Platform | Market breadth | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | breadth_series(): advances/declines; % advancing; A/D ratio; % above 200-DMA; 52-week new highs/lows over tracked universe; 80% coverage gate; stored in market_health | Survivorship-free universe (BT-15); sector-level breadth (DP-13) | scores/engine.py; db/schema.py | 2026-09-24
61 | 1 | Foundation | SC-09 | Alpha/Factor Engine | Market Health score | DEPLOYED - VERIFIED | COMPLETED | 90% | Baseline | ,Baseline, |  | Every MH input is real or left out (index_levels then daily index series; session-own FII/DII; global <=4 days; VIX; breadth); coverage + inputs stored; no score below 50% coverage; upsert keeps portfolio_health; 393 past sessions backfilled | FII/DII and global history only from 2026-07 (backfilled coverage avg 0.65); determine_signal still defaults a missing MH to 50; model-based regime is ML-05 | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py | 2026-09-24
62 | 1 | Foundation | SC-08 | Alpha/Factor Engine | ACS | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | HistoricalAccuracy = 90-day 5-session hit rate from outcomes known by the scored day (min 5); NewsConfidence only from AI-classified news with no look-ahead; missing inputs left out (no 50/60 stand-ins) | NewsConfidence stays absent until NS-02 (Anthropic key) classifies news | scores/engine.py; data/news.py; db/schema.py | 2026-09-24
63 | 1 | Foundation | MON-01 | Monitoring | Job logging | DEPLOYED - VERIFIED | COMPLETED | 90% | W1 | ,W1, |  | run_job records every run (start/end/duration/rows/status/error); returned FAILED is a failure; EMPTY status | Record failures, end time, row counts | pipeline/scheduler.py; db/schema.py | 2026-09-24
64 | 1 | Foundation | MON-02 | Monitoring | Stalled-job detection | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | pipeline/health.py expectations: MISSED/STALLED/FAILING/EMPTY; every 30 min | Expected-run table + missed-run check | pipeline/health.py; pipeline/scheduler.py | 2026-09-24
65 | 1 | Foundation | MON-03 | Monitoring | Failure alerting | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | alert_log + dashboard panel + Telegram when configured; daily de-dup; token scrubbed | Configure Telegram; alert on failure/stall | alerts/telegram.py; dashboard/server.py | 2026-09-24
66 | 1 | Foundation | DB-14 | Dashboard | Alerts / morning brief | DEPLOYED - VERIFIED | COMPLETED | 80% | W1 | ,W1, |  | Brief recorded for the dashboard + Telegram; pipeline-health section (outside W1, same tree) | Deliver digest; verify daily | alerts/telegram.py | 2026-09-24
67 | 1 | Foundation | RK-15 | Risk Management | Risk alerts | DEPLOYED - VERIFIED | COMPLETED | 80% | W1 | ,W1, |  | Alerts on halt/resume and on halted or limit-refused orders (outside W1, same tree) | Alert on halt, limit breach, CRI spike | orders/risk.py; orders/broker.py | 2026-09-24
68 | 1 | Foundation | MON-06 | Monitoring | Log rotation | DEPLOYED - VERIFIED | COMPLETED | 90% | W1 | ,W1, |  | SafeRotatingFileHandler 20 MB x 10, survives refused rename (outside W1, same tree) | RotatingFileHandler | main.py | 2026-09-24
69 | 1 | Foundation | DBS-06 | Database | Timestamp consistency | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | Convention documented (IST; created_at UTC); news UTC->IST; status query fixed; repair tool | Normalise; fix news recency | db/schema.py; data/news.py; tools/repair_news_timezone.py | 2026-09-24
70 | 1 | Foundation | NS-01 | News/Sentiment | News ingestion | DEPLOYED - VERIFIED | COMPLETED | 80% | W1 | ,W1, |  | News first + morning catch-up; de-dup; per-feed status; 4 more RSS feeds | Fix job; add second source; health check | data/news.py; pipeline/scheduler.py | 2026-09-24
71 | 1 | Foundation | OPS-03 | Deployment/Ops | Install/setup | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | ta not pandas-ta everywhere; requirements-dev.txt; CI httpx; config template; docs/DEV_SETUP.md | Fix requirements/setup; pin versions | setup.py; install.bat; requirements-dev.txt; docs/DEV_SETUP.md | 2026-09-24
72 | 1 | Foundation | EX-01 | Execution | Order management tests | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | orders/rules.py (944 lines) without tests | Unit tests for rules.py | orders/rules.py; tests/ | 2026-09-24
73 | 1 | Foundation | OPS-02 | Deployment/Ops | CI + end-to-end test | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | GitHub Actions; ~270 test functions; no E2E | Add E2E pipeline test | .github/workflows/tests.yml; tests/ | 2026-09-24
74 | 1 | Foundation | DP-15 | Data Platform | Fundamentals | IN PROGRESS | IN PROGRESS | 30% |  |  | Owner: Enable fundamentals ingestion | Screener.in fetcher; ingestion disabled | Your decision; enable; quarterly store; no 50.0 default | data/fundamentals.py; pipeline/scheduler.py | 2026-09-24
75 | 1 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | IN PROGRESS | IN PROGRESS | 20% |  |  | Development | Default 50 when unparsed | Implement FS formula on real data | data/fundamentals.py | 2026-09-24
76 | 1 | Foundation | SC-02 | Alpha/Factor Engine | SPI | IN PROGRESS | IN PROGRESS | 30% |  |  | Development |  | Implement SPI formula separately from FS | scores/engine.py | 2026-09-24
77 | 1 | Foundation | SC-05 | Alpha/Factor Engine | CRI debt input | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented; Debt input missing | Feed Debt/Equity | scores/engine.py | 2026-09-24
78 | 1 | Foundation | SC-01 | Alpha/Factor Engine | VPI inputs | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Implemented; FG/IS inputs weak | Real Fundamental Growth input | scores/engine.py | 2026-09-24
79 | 1 | Foundation | PF-01 | Portfolio | Portfolio ingestion | DEPLOYED - VERIFIED | COMPLETED | 80% | W1 | ,W1, |  | portfolio_sync records each attempt and reason (DH-901 named); qty/avg update; sold removed | Scheduled reliable sync + token handling | data/dhan.py; portfolio/zerodha.py | 2026-09-24
80 | 1 | Foundation | BR-04 | Broker Integration | Portfolio sync schedule | DEPLOYED - VERIFIED | COMPLETED | 80% | W1 | ,W1, |  | Morning catch-up re-sync; Zerodha SKIPPED when not connected; health expects SUCCESS | Scheduled sync with alert on failure | pipeline/scheduler.py; pipeline/health.py | 2026-09-24
81 | 1 | Foundation | PF-02 | Portfolio | Holdings & P&L | DEPLOYED - VERIFIED | COMPLETED | 80% | W1 | ,W1, |  | portfolio/pnl.py PAPER + LIVE books marked to market; /api/pnl | Realised + unrealised P&L | portfolio/pnl.py; dashboard/server.py | 2026-09-24
82 | 1 | Foundation | PF-13 | Portfolio | Daily P&L series | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | pnl_daily equity/day P&L/peak/drawdown per env; post-market daily_pnl job | Daily P&L table; EOD job | portfolio/pnl.py; db/schema.py | 2026-09-24
83 | 1 | Foundation | RK-13 | Risk Management | Risk-based sizing wired to orders | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | size_position() pure + size_for_account(); quantity_type RISK in order rules | Use size in order path | orders/risk.py; orders/rules.py | 2026-09-24
84 | 1 | Foundation | RK-07 | Risk Management | Daily loss limit | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | max_daily_loss_value blocks BUYs; unmeasurable blocks | Limit on PF-13; auto-halt | orders/risk.py | 2026-09-24
85 | 1 | Foundation | RK-08 | Risk Management | Drawdown limit | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | max_drawdown_pct blocks BUYs; unmeasurable blocks | Peak-to-trough on PF-13; auto-halt | orders/risk.py | 2026-09-24
86 | 1 | Foundation | DBS-03 | Database | Backups | DEPLOYED - VERIFIED | COMPLETED | 85% | W8 | ,W8, |  | ops/backup.py: daily online SQLite backup (19:15) VERIFIED by integrity_check + key-table counts + sha256 (ops_backup); 7 daily + 4 weekly retention of its own files only; restore to a NEW file; python -m ops backup/restore/verify | Off-machine copy of backups; restore drill | ops/backup.py; docs/BACKUP_RESTORE.md | 2026-09-25
87 | 1 | Foundation | DP-06 | Data Platform | Corporate actions open items | DEPLOYED - VERIFIED | COMPLETED | 85% | Baseline | ,Baseline, |  | NSE CA calendar; reconciliation; volume re-base | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py | 2026-09-24
88 | 1 | Foundation | TA-06 | Technical Analysis | Support/Resistance | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | ,W21, | Independent QA | W21: fractal pivots over 120 sessions, mean-anchored clusters, nearest confirmed support/resistance with touches and distance | QA; optionally feed the Technical Score SR component | data/technical_ext.py | 2026-09-27
89 | 1 | Foundation | DP-19 | Data Platform | Data quality layer | DEPLOYED - VERIFIED | COMPLETED | 85% | W1 | ,W1, |  | data/quality.py 12 checks + DQS per session; data_quality table; post-market; alert | DQS table; outlier and timestamp checks | data/quality.py; pipeline/scheduler.py | 2026-09-24
90 | 2 | Quant Research (data, factors, backtesting) | DBS-04 | Database | Schema migrations | DEPLOYED - VERIFIED | COMPLETED | 80% | W8 | ,W7,W8, |  | schema_migrations (version, checksum, applied_at, duration, status, rollback note); 0001 baseline, 0002 W8 tables, 0003 indexes, 0004 append-only audit triggers; drift detection; additive layer now runs once per process (W7-R8) | Down-migration scripts beyond rollback notes (policy: restore pre-release backup) | ops/migrations.py; db/schema.py | 2026-09-25
91 | 2 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | IN PROGRESS | IN PROGRESS | 60% |  |  | Development | Index WebSocket 09:00-15:45 + quote cache; stock tick feed never run | Stock-level live feed in production; failover | data/dhan_ws.py; data/dhan.py | 2026-09-24
92 | 2 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W21 | ,W21, | Independent QA | W21: intraday_bars stores the 30-min job's 15-min bars (was discarded); 90-day retention | QA; consider 5-min bars for session VWAP | data/dhan.py; db/schema.py; db/purge.py | 2026-09-27
93 | 2 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | ,W21, | Independent QA; Owner: technical.vwap_in_score | W21: vwap_20d, vwap_session (intraday bars), vwap_dev_pct in technical_ext; strategy feature vwap_dev_pct | Owner: technical.vwap_in_score (changes scores); QA | data/technical_ext.py; data/technical.py | 2026-09-27
94 | 2 | Quant Research (data, factors, backtesting) | SC-12 | Alpha/Factor Engine | Technical Score VWAP input | DEPLOYED - VERIFIED | COMPLETED | 75% | Baseline | ,Baseline, |  | Implemented; VWAP weight dead | Include VWAP | data/technical.py | 2026-09-24
95 | 2 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | ,W21, | Independent QA | W21: volume profile POC/VAH/VAL over 20 sessions (intraday or daily basis) | QA | data/technical_ext.py | 2026-09-27
96 | 2 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | ,W21, | Independent QA | W21: weekly RSI/trend, monthly trend, mtf_alignment -3..+3 | QA | data/technical_ext.py | 2026-09-27
97 | 2 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 70% | W21 | ,W21, | Independent QA; Owner: Run the indicator backfill | W21: python -m data.technical --backfill N (tracked universe, resumable) | Run the backfill (owner timing; copy first) | data/technical.py | 2026-09-27
98 | 2 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W22 | ,W22, | Independent QA | W22: score_components stores every ATIP index's sub-components per symbol/date (weighted_score label capture; scores unchanged) | QA | scores/engine.py; scores/formulas.py | 2026-09-27
99 | 2 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W22, | Independent QA | W22: 11 standalone factors: mean reversion, trend, volume, recovery, risk (BRI) | QA; research on full history | quant/factors.py | 2026-09-27
100 | 2 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W6 | ,W6, | Independent QA | W6 quant/normalize.py per-factor spec (winsorize/zscore/percentile/rank/minmax/sector/neutralize) -- tracker was stale | QA | quant/normalize.py | 2026-09-27
101 | 2 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W22 | ,W6,W22, | Independent QA | W6 registry quant_factor + factor sets + content-hash versioning (tracker was stale); W22 adds 11 factors | QA | quant/factors.py | 2026-09-27
102 | 2 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W22 | ,W22, | Independent QA | W22: formula_registry resolves each signal_log weights_hash to the full weight set + code version | QA | scores/formulas.py | 2026-09-27
103 | 2 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W22, | Independent QA | W22: research_study + research_link registry, frozen on conclusion | QA | quant/studies.py | 2026-09-27
104 | 2 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W6,W22, | Independent QA | W22: backfill_scores + research_report run IC for every factor | Run full-history backfill + report | quant/research.py | 2026-09-27
105 | 2 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W6,W22, | Independent QA | W22: IC decay 1/5/10/20 for every factor in research_report | Run on full history | quant/research.py | 2026-09-27
106 | 2 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W6,W22, | Independent QA | W22: redundancy report (pairs ¦rho¦>=0.7) in research_report | Run on full history | quant/research.py | 2026-09-27
107 | 2 | Quant Research (data, factors, backtesting) | QR-04 | Quant Research | Statistical toolkit | DEPLOYED - VERIFIED | COMPLETED | 75% | W6 | ,W6, |  | statarb (OLS, ADF, Engle-Granger, half-life, z) + normalize + volatility estimators | Validate | quant/statarb.py; quant/normalize.py; quant/volatility.py | 2026-09-25
108 | 2 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W22, | Independent QA; Owner: quant.require_approved_factors | W22: evidence-based approval gate, decision history, lifecycle enforcement behind quant.require_approved_factors | Owner: enable after review | quant/approval.py; strategy_engine/lifecycle.py | 2026-09-27
109 | 2 | Quant Research (data, factors, backtesting) | BT-16 | Backtesting | Dated equity curve / run records | DEPLOYED - VERIFIED | COMPLETED | 85% | W2 | ,W2, |  | backtest_run snapshot+hash, code version, data fingerprint; trades/equity/drawdowns tables | Dated trades + equity curve + run table | backtest/store.py; db/schema.py | 2026-09-24
110 | 2 | Quant Research (data, factors, backtesting) | BT-08 | Backtesting | Portfolio-level backtest | DEPLOYED - VERIFIED | COMPLETED | 85% | W2 | ,W1,W2, |  | Portfolio engine: cash, positions, sizing (W1 size_position), exposure, dated equity | Portfolio simulator | backtest/engine.py | 2026-09-24
111 | 2 | Quant Research (data, factors, backtesting) | BT-09 | Backtesting | Drawdown analysis | DEPLOYED - VERIFIED | COMPLETED | 90% | W2 | ,W2, |  | Drawdown series, max DD, episodes with duration/recovery on dated equity | Compute on equity curve | backtest/metrics.py | 2026-09-24
112 | 2 | Quant Research (data, factors, backtesting) | BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | DEPLOYED - VERIFIED | COMPLETED | 90% | W2 | ,W2, |  | Return, CAGR, vol, Sharpe, Sortino, Calmar, trade stats; conventions documented | Implement | backtest/metrics.py | 2026-09-24
113 | 2 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W23 | ,W23, | Independent QA | W23: historical VaR/CVaR 95/99, parametric VaR, skew, kurtosis in every backtest's metrics | QA | backtest/metrics.py | 2026-09-27
114 | 2 | Quant Research (data, factors, backtesting) | BT-05 | Backtesting | Itemised costs | DEPLOYED - VERIFIED | COMPLETED | 85% | W2 | ,W2, |  | Itemised NSE cost model (delivery/intraday/flat/zero), central config | Indian cost model shared by backtest and paper | backtest/costs.py; backtest/config.py | 2026-09-24
115 | 2 | Quant Research (data, factors, backtesting) | BT-06 | Backtesting | Slippage in backtest | DEPLOYED - VERIFIED | COMPLETED | 90% | W2 | ,W2, |  | none / fixed / pct slippage, default = paper broker 5 bps | Shared slippage model | backtest/slippage.py | 2026-09-24
116 | 2 | Quant Research (data, factors, backtesting) | BT-07 | Backtesting | Liquidity constraints | DEPLOYED - VERIFIED | COMPLETED | 85% | W2 | ,W2, |  | Volume participation cap/reject + prior-bar turnover floor | All engines | backtest/liquidity.py | 2026-09-24
117 | 2 | Quant Research (data, factors, backtesting) | DP-18 | Data Platform | Survivorship-free universe | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Current NIFTY 500 download | Store constituent history | data/index_constituents.py | 2026-09-24
118 | 2 | Quant Research (data, factors, backtesting) | BT-15 | Backtesting | Bias controls | DEPLOYED - VERIFIED | COMPLETED | 80% | W2 | ,W2, |  | Point-in-time view + LookAheadError, next-open fills, data/timestamp validation, survivorship flag | Systematic checks | backtest/data.py; backtest/engine.py | 2026-09-24
119 | 2 | Quant Research (data, factors, backtesting) | BT-03 | Backtesting | In/out-of-sample | DEPLOYED - VERIFIED | COMPLETED | 85% | W2 | ,W2, |  | Ordered non-overlapping research/validation/test; test needs allow_test; re-test flagged | Formal splits | backtest/periods.py; backtest/service.py | 2026-09-24
120 | 2 | Quant Research (data, factors, backtesting) | BT-02 | Backtesting | Walk-forward | DEPLOYED - VERIFIED | COMPLETED | 80% | W2 | ,W2, |  | Rolling windows, candidate selection on validation, stitched OOS; no optimiser | Implement | backtest/walkforward.py | 2026-09-24
121 | 2 | Quant Research (data, factors, backtesting) | BT-13 | Backtesting | Monte Carlo | DEPLOYED - VERIFIED | COMPLETED | 85% | W2 | ,W2, |  | Seeded trade shuffle + return bootstrap; percentiles, P(loss), disclaimer | Implement | backtest/montecarlo.py | 2026-09-24
122 | 2 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W23 | ,W23, | Independent QA | W23: grid / random / adaptive optimiser with trial runs, test-window refusal, Deflated Sharpe + overfit warning | QA; optional true Bayesian search | backtest/optimize.py | 2026-09-27
123 | 2 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W23 | ,W23, | Independent QA | W23: one-at-a-time sensitivity curves, stability, knife-edge flags, 2-D heat map | QA | backtest/sensitivity.py | 2026-09-27
124 | 2 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W23 | ,W23, | Independent QA | W23: robustness battery (costs x2, slippage x3, universe halves, period halves, regimes, Monte Carlo) with verdict | QA | backtest/robustness.py | 2026-09-27
125 | 2 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | ,W6,W22, | Independent QA | W6 experiments + W22 studies linking experiments/backtests/research | QA | quant/experiments.py; quant/studies.py | 2026-09-27
126 | 2 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 70% | W23 | ,W23, | Independent QA | W23: momentum breakout strategy + end-to-end study (optimise/validate/sensitivity/robustness/test) | Run full-universe study; review | backtest/strategies.py; backtest/study.py | 2026-09-27
127 | 2 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 70% | W23 | ,W23, | Independent QA | W23: RSI(2) mean-reversion strategy + study; 12-stock smoke: REJECTED out of sample | Run full-universe study; review | backtest/strategies.py; backtest/study.py | 2026-09-27
128 | 2 | Quant Research (data, factors, backtesting) | QR-13 | Quant Research | Signal outcome research by regime | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | success_report keyed on signal/threshold | Add regime/ACS buckets | scores/signal_log.py | 2026-09-24
129 | 2 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 70% | W21 | ,W21, | Independent QA; Owner: prices_daily retention >= 1,100 days | W21: beta_60, beta_downside, beta_long (>=500 sessions) | Owner: prices_daily retention >= 1,100 days for a 3-year beta | data/technical_ext.py | 2026-09-27
130 | 2 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 75% | W21 | ,W21, | Independent QA | W21: Beta Risk Index 0-100 (level, downside, instability); strategy feature bri | QA; decide if it joins a composite | data/technical_ext.py | 2026-09-27
131 | 2 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | ,W21, | Independent QA | W21: Supertrend, Ichimoku, Keltner, Donchian, MFI, CMF, ROC, Aroon, PSAR; stoch/Williams %R/CCI now computed | QA | data/technical_ext.py; data/technical.py | 2026-09-27
132 | 2 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | YET TO START | YET TO START | 0% |  |  | Owner: Derivatives data source | None | NSE F&O bhavcopy + option chain store | — | 2026-09-24
133 | 2 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | IN PROGRESS | IN PROGRESS | 55% |  |  | Development | Options/PCR frozen; news rule-based | Real PCR; AI news later | scores/engine.py | 2026-09-24
134 | 2 | Quant Research (data, factors, backtesting) | DP-10 | Data Platform | FII/DII history | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Session flows; only 7 sessions history | Historical backfill source | data/bhavcopy.py | 2026-09-24
135 | 2 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 75% | W21 | ,W21, | Independent QA | W21: daily GIFTNIFTY close from index_levels into prices_daily | Pre-open panel (DB-04) | data/market_series.py | 2026-09-27
136 | 2 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | IN PROGRESS | IN PROGRESS | 60% |  |  | Development | In index strip | Dedicated pre-open view | dashboard/server.py | 2026-09-24
137 | 2 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | IN PROGRESS | IN PROGRESS | 70% |  |  | Development | 13 yfinance tickers | Bond yields; history depth | data/markets.py | 2026-09-24
138 | 2 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | ,W21, | Independent QA | W21: 8 sector index series in the daily Dhan sync + sector_breadth table | Run --backfill-sectors; QA | data/market_series.py; data/dhan.py | 2026-09-27
139 | 2 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | IN PROGRESS | IN PROGRESS | 25% |  |  | Development | Bulk/block only | Promoter/SAST/PIT/MF feeds | data/bhavcopy.py | 2026-09-24
140 | 2 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | IN PROGRESS | IN PROGRESS | 40% |  |  | Development | FII + bulk only | Add MF/promoter/insider | scores/engine.py | 2026-09-24
141 | 2 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | IN PROGRESS | IN PROGRESS | 40% |  |  | Development | Feeds INS | Validate with IC | data/bhavcopy.py | 2026-09-24
142 | 3 | Strategy Engine | SG-04 | Signal Engine | Rich decision states | DEPLOYED - VERIFIED | COMPLETED | 80% | W3 | ,W3, |  | Decision states BUY/ADD/HOLD/REDUCE/EXIT/SELL/NO_ACTION/BLOCKED_BY_RISK with reasons; PositionIntent | Extended states + stored reasons | strategy_engine/decisions.py | 2026-09-24
143 | 3 | Strategy Engine | SG-01 | Signal Engine | SELL calibration | DEPLOYED - VERIFIED | COMPLETED | 70% | Baseline | ,Baseline, |  | SELL never fired | Backtest-based SELL thresholds | scores/engine.py | 2026-09-24
144 | 3 | Strategy Engine | SE-01 | Strategy Engine | Strategy library | DEPLOYED - VERIFIED | COMPLETED | 85% | W3 | ,W3, |  | Versioned JSON definitions + DB registry (id, name, description, category, version, status, owner, created/updated, priority, weight); VERSION/LIFECYCLE events; 9 library strategies | Strategy interface + registry | strategy_engine/definition.py; registry.py | 2026-09-24
145 | 3 | Strategy Engine | SE-02 | Strategy Engine | Strategy parameters | DEPLOYED - VERIFIED | COMPLETED | 85% | W3 | ,W3, |  | ParamSpec name/type/default/min/max/allowed/required/description; validated on resolve; stored per version in strategy_parameter | Param store per strategy with versions | strategy_engine/params.py; registry.py | 2026-09-24
146 | 3 | Strategy Engine | SE-03 | Strategy Engine | Rule-based strategies | DEPLOYED - VERIFIED | COMPLETED | 85% | W3 | ,W3, |  | Rule language all/any/not/min-of, 11 operators incl. crosses; rule kind | Generic rule definition format | strategy_engine/rules.py; kinds.py | 2026-09-24
147 | 3 | Strategy Engine | SE-06 | Strategy Engine | Multi-factor strategy | DEPLOYED - VERIFIED | COMPLETED | 85% | W3 | ,W3, |  | multi_factor kind: weights, scaling, thresholds, confirmations, coverage, ranking | IC-weighted multi-factor strategy | strategy_engine/kinds.py | 2026-09-24
148 | 3 | Strategy Engine | SE-04 | Strategy Engine | Quant strategies | DEPLOYED - VERIFIED | COMPLETED | 75% | W3 | ,W3, |  | quant_rank kind + point-in-time feature catalogue (framework only) | Implement first quant strategies | strategy_engine/kinds.py; features.py | 2026-09-24
149 | 3 | Strategy Engine | SE-09 | Strategy Engine | Strategy lifecycle | DEPLOYED - VERIFIED | COMPLETED | 85% | W3 | ,W3, |  | 12 states incl. DRAFT/ACTIVE/PAUSED/DISABLED/RETIRED/ARCHIVED; allowed transitions; backtest evidence for ACTIVE/VALIDATION/APPROVED; strategy_engine_event audit | State machine + gates | strategy_engine/lifecycle.py | 2026-09-24
150 | 3 | Strategy Engine | SE-11 | Strategy Engine | Strategy health | DEPLOYED - VERIFIED | COMPLETED | 75% | W3 | ,W3, |  | HEALTHY/WARNING/ERROR/STALE/DISABLED; last execution, last signal, signal frequency, error count, performance reference, data availability, parameter validity | Health scoring + alerts | strategy_engine/health.py | 2026-09-24
151 | 3 | Strategy Engine | SE-07 | Strategy Engine | Strategy combination/ranking/selection | DEPLOYED - VERIFIED | COMPLETED | 75% | W3 | ,W3, |  | composite kind (vote/weighted/priority/regime_select) + cross-strategy combine(): priority, weighting, vote, conflict -> WAIT, NO_TRADE veto; enable/disable via lifecycle and mapping | Allocator | strategy_engine/selection.py; kinds.py | 2026-09-24
152 | 3 | Strategy Engine | SE-08 | Strategy Engine | Regime-aware selection | DEPLOYED - VERIFIED | COMPLETED | 75% | W3 | ,W3, |  | Configurable regime mapping STRONG_BULL/BULL/NEUTRAL/BEAR/HIGH_RISK (+DEFAULT) -> strategies or NO_TRADE; Market Health regime provider; default mapping seeded | Regime-conditional allocation | strategy_engine/selection.py; regime.py; library/regime_mapping.json | 2026-09-24
153 | 3 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | IN PROGRESS | IN PROGRESS | 60% |  |  | Development | Scheduled 12:30 and 14:45 | Use stored intraday bars | pipeline/scheduler.py | 2026-09-24
154 | 3 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | IN PROGRESS | IN PROGRESS | 40% |  |  | Development | CRI per-stock column only | Dedicated lists | dashboard/server.py | 2026-09-24
155 | 3 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | IN PROGRESS | IN PROGRESS | 30% | W4 | ,W4, | Development | /strategies list shows latest signals; per-strategy P&L from W4 fills on /trading | Performance panel | dashboard/strategy_page.py; dashboard/execution_page.py | 2026-09-25
156 | 4 | AI/ML | ML-13 | AI/ML | Labels/targets | DEPLOYED - VERIFIED | COMPLETED | 85% | W5 | ,W5, |  | ml/labels.py: direction, binary_return, forward_return, return_rank, volatility_regime, market_regime, signal_outcome; ml_label definitions; computed only from bars after t | Validate | ml/labels.py | 2026-09-25
157 | 4 | AI/ML | ML-07 | AI/ML | Feature selection | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | ,W5,W24, | Independent QA | W24: importance-stability selection -> new feature-set version | QA | ml/selection.py | 2026-09-27
158 | 4 | AI/ML | ML-08 | AI/ML | Model validation | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W24 | ,W5,W24, | Independent QA | W24: purged expanding walk-forward reports vs baselines, IC, calibration, verdict | QA | ml/validation.py | 2026-09-27
159 | 4 | AI/ML | ML-01 | AI/ML | Supervised ML | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | ,W5,W24, | Independent QA | W24: native numpy GBM + random forest; bootstrap trains + validates first models (TRAINED, not ACTIVE); real-data smoke: NO_EDGE on 5-day direction | Richer features / labels; full-universe validation | ml/trees.py; ml/presets.py | 2026-09-27
160 | 4 | AI/ML | ML-12 | AI/ML | Model registry/versioning | DEPLOYED - VERIFIED | COMPLETED | 85% | W5 | ,W5, |  | ml_model / ml_model_version with feature-set, dataset, config and artifact hashes; immutable artifacts; lifecycle | Validate | ml/registry.py; ml/artifacts.py | 2026-09-25
161 | 4 | AI/ML | ML-11 | AI/ML | Ensemble models | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | ,W5,W24, | Independent QA | W24: ensemble model type blended by held-out loss | QA | ml/trees.py | 2026-09-27
162 | 4 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | ,W5,W24, | Independent QA | W24: drift (PSI share) + realised decay alerts, ml_health_check, monitor rule | QA | ml/decay.py; ops/monitor.py | 2026-09-27
163 | 4 | AI/ML | ML-10 | AI/ML | Explainability | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 85% | W24 | ,W5,W24, | Independent QA | W24: exact path contributions for trees, gain importances, out-of-sample permutation importance | QA | ml/trees.py; ml/validation.py | 2026-09-27
164 | 4 | AI/ML | ML-05 | AI/ML | Regime detection | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | ,W5,W24, | Independent QA; Owner: Regime provider (after evidence) | W24: market_regime model preset validated + trained (NO_EDGE on smoke) | Owner decides regime provider after evidence | ml/presets.py | 2026-09-27
165 | 4 | AI/ML | ML-03 | AI/ML | Unsupervised learning | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | ,W24, | Independent QA | W24: k-means++ factor clusters with profiles; return PCA | QA | ml/unsupervised.py | 2026-09-27
166 | 4 | AI/ML | ML-06 | AI/ML | Anomaly detection | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | ,W24, | Independent QA; Owner: ml.anomalies_enabled | W24: robust-z + multivariate anomaly scan, CA-explained, post-market (flag off) | Owner: ml.anomalies_enabled | ml/unsupervised.py | 2026-09-27
167 | 4 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | IN PROGRESS | IN PROGRESS | 60% | W5 | ,W4,W5, | Owner: Activate a model (after evidence) | ml_* strategy features (point in time, out of sample); ml_direction / atip_ml_blend (DRAFT); W4 risk check ml_model_active blocks signals of non-ACTIVE models | Activate once a model is ACTIVE | ml/strategy_features.py; execution/risk_engine.py; strategy_engine/library/50_*,51_* | 2026-09-25
168 | 4 | AI/ML | NS-02 | News/Sentiment | News classification | IN PROGRESS | IN PROGRESS | 30% |  |  | Owner: Working Anthropic API key (current key 401) | Claude classifier coded; key unset | Set key; taxonomy; cost cap | data/news.py | 2026-09-24
169 | 4 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | IN PROGRESS | IN PROGRESS | 40% |  |  | Development | Rule-based; confidence frozen 50 | Model-based scoring | data/news.py | 2026-09-24
170 | 4 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | YET TO START | YET TO START | 5% |  |  | Development | None | Implement | data/news.py | 2026-09-24
171 | 4 | AI/ML | NS-04 | News/Sentiment | AI news summary | IN PROGRESS | IN PROGRESS | 50% |  |  | Development | Headline list | LLM summary | dashboard/server.py | 2026-09-24
172 | 4 | AI/ML | DB-06 | Dashboard | AI News Summary panel | IN PROGRESS | IN PROGRESS | 50% |  |  | Development | News panel (rule-based) | Show AI summary | dashboard/server.py | 2026-09-24
173 | 4 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | YET TO START | YET TO START | 0% |  |  | Development | None | Implement | — | 2026-09-24
174 | 4 | AI/ML | ML-02 | AI/ML | Deep learning | YET TO START | YET TO START | 0% |  |  | Development | None | Only if validated benefit | — | 2026-09-24
175 | 4 | AI/ML | ML-04 | AI/ML | Reinforcement learning | YET TO START | YET TO START | 0% |  |  | Development | None | Low priority | — | 2026-09-24
176 | 4 | AI/ML | DB-18 | Dashboard | Quant/model panel | IN PROGRESS | IN PROGRESS | 40% | W5 | ,W5, | Development | /ml page: models, versions, lifecycle, predictions, feature sets, datasets, training runs | Monitoring charts | dashboard/ml_page.py | 2026-09-25
177 | 5 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 90% | W25 | ,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: portfolio/risk.py book_snapshot for PAPER and LIVE books (weights, % equity, sector exposure); /api/risk/portfolio; /trading Portfolio risk panel | Independent QA | portfolio/risk.py; dashboard/portfolio_risk_routes.py | 2026-09-28
178 | 5 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 90% | W25 | ,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: concentration() max/top-5 weight, HHI, effective N, sector HHI; in /api/risk/portfolio and snapshots | Independent QA | portfolio/risk.py | 2026-09-28
179 | 5 | Risk & Portfolio | PF-09 | Portfolio | Correlation | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 90% | W25 | ,W6,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: portfolio correlation matrix, weighted avg pairwise correlation, high pairs, diversification ratio; heatmap on /trading | Independent QA | portfolio/risk.py; dashboard/execution_page.py | 2026-09-28
180 | 5 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit (off) | W25: W4 limit max_avg_correlation (value-weighted correlation of the new symbol with the held book; fail closed); analytics in /api/risk/portfolio | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; portfolio/limits.py | 2026-09-28
181 | 5 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit / enable snapshot (off) | W25: historical / parametric / Monte Carlo VaR and ES, 95/99%, 1 and 10 days; W4 limit max_portfolio_var_pct (post-trade); snapshot job + VaR alert (off by default) | Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | portfolio/risk.py; portfolio/limits.py; execution/risk_engine.py | 2026-09-28
182 | 5 | Risk & Portfolio | RK-06 | Risk Management | Sector limits | DEPLOYED - VERIFIED | COMPLETED | 80% | W4 | ,W4, |  | max_sector_exposure_pct in the W4 risk engine (NSE industry from cached Nifty 500 list; fails closed when unavailable) | Validate | execution/risk_engine.py; execution/positions.py | 2026-09-25
183 | 5 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit (off) | W25: W4 limit max_symbol_volatility_pct (annualised 60-session vol; fail closed) | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; execution/config.py; portfolio/limits.py | 2026-09-28
184 | 5 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W1,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit (off) | W25: W4 cap max_adv_participation_pct (qty <= % of 20-session ADV) and W1 risk_limits.max_adv_participation_pct (BUY and SELL, unmeasurable -> refused) | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; orders/risk.py; portfolio/limits.py | 2026-09-28
185 | 5 | Risk & Portfolio | RK-18 | Risk Management | Strategy risk budget | DEPLOYED - VERIFIED | COMPLETED | 75% | W4 | ,W4, |  | max_strategy_exposure_pct + strategy_drawdown_limit_pct from per-strategy fill attribution | Per-strategy capital budgets | execution/risk_engine.py; execution/positions.py | 2026-09-25
186 | 5 | Risk & Portfolio | RK-01 | Risk Management | Kill switch scopes + auto-trigger | DEPLOYED - VERIFIED | COMPLETED | 80% | Baseline | ,Baseline, |  | Global flag file + config | Per-strategy/symbol; auto-trigger | orders/risk.py | 2026-09-24
187 | 5 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: portfolio/emergency.py plan + confirm code (10 min) -> kill switch ON, cancel open W4 orders, sell PAPER book; LIVE = sell list only, never an order; /api/risk/emergency-exit (risk:approve); dashboard button | Independent QA | portfolio/emergency.py; dashboard/portfolio_risk_routes.py | 2026-09-28
188 | 5 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W6,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: portfolio/optimize.py min_variance / mean_variance / max_sharpe / risk_parity; long-only, max/min weight, sector caps (FISTA + exact Dykstra projection); shrunk covariance; frontier; stored runs | Independent QA; expected-return model review | portfolio/optimize.py | 2026-09-28
189 | 5 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 80% | W25 | ,W6,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: rebalance_plan (NEW/ADD/REDUCE/EXIT/HOLD, band, min trade, costs, turnover); portfolio strategy kind reweight_band_pct emits ADD/REDUCE with exact quantity | Independent QA; backtest engine still trades whole positions | portfolio/optimize.py; strategy_engine/kinds.py; strategy_engine/engine.py | 2026-09-28
190 | 5 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: risk_attribution per position / sector variance share, component VaR, beta, systematic vs idiosyncratic | Independent QA | portfolio/risk.py | 2026-09-28
191 | 5 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 75% | W25 | ,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: holdings-based contribution by position / sector, beta-alpha split vs NIFTY50, Brinson allocation/selection vs equal-weighted universe | Independent QA; trade-based attribution needs a LIVE trade ledger | portfolio/risk.py | 2026-09-28
192 | 5 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 70% | W25 | ,W15.5,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: CAGR from pnl_daily equity; PAPER book + per-position XIRR from paper fills (wealth ledger XIRR in W15.5) | Independent QA; LIVE XIRR needs a trade ledger | portfolio/risk.py; wealth/perf/metrics.py | 2026-09-28
193 | 5 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | DEVELOPED - NOT DEPLOYED | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | ,W4,W25, | Independent QA; Deploy (restart onto ATIP-W25-RC1) | W25: /trading Portfolio risk panels: KPIs, VaR/ES table, concentration, risk contribution, correlation heatmap, performance attribution, emergency exit | Independent QA | dashboard/execution_page.py | 2026-09-28
194 | 6 | Execution | EX-02 | Execution | Order types | IN PROGRESS | IN PROGRESS | 60% | W4 | ,W4, | Development | W4 OMS: MARKET and LIMIT through the paper adapter; order type from config | Stop-loss / stop-limit order types | execution/order_manager.py; execution/adapters.py | 2026-09-25
195 | 6 | Execution | EX-08 | Execution | Order modify/cancel | IN PROGRESS | IN PROGRESS | 50% | W4 | ,W4, | Development | Cancel with explicit CANCEL_PENDING state; status refresh; no modify | Order modify | execution/order_manager.py | 2026-09-25
196 | 6 | Execution | BR-05 | Broker Integration | Execution reconciliation | IN PROGRESS | IN PROGRESS | 30% |  |  | Development | Partial reconcile code | EOD reconciliation job + alert | orders/ | 2026-09-24
197 | 6 | Execution | BR-06 | Broker Integration | Connection health | IN PROGRESS | IN PROGRESS | 40% |  |  | Development | broker-status route; WS stall detection | Health checks + alerts | dashboard/server.py | 2026-09-24
198 | 6 | Execution | RK-17 | Risk Management | Broker/operational risk | IN PROGRESS | IN PROGRESS | 50% | W4 | ,W4, | Development | Kill switch + live-trading gate + broker failure -> FAILED order state with context | Broker health / stale-data checks | execution/config.py; execution/order_manager.py | 2026-09-25
199 | 6 | Execution | BR-08 | Broker Integration | Sandbox | IN PROGRESS | IN PROGRESS | 30% |  |  | Development | SANDBOX env defined | Verify sandbox path end-to-end | orders/environment.py | 2026-09-24
200 | 6 | Execution | EX-09 | Execution | Measured slippage | IN PROGRESS | IN PROGRESS | 30% | W4 | ,W4, | Development | Fill price and decision reference price stored per order/fill (slippage derivable) | Slippage metric + report | execution/order_manager.py | 2026-09-25
201 | 6 | Execution | EX-10 | Execution | Execution analytics | IN PROGRESS | IN PROGRESS | 30% | W4 | ,W4, | Development | oms_order / oms_order_event / oms_execution / oms_fill audit tables and APIs | Fill-rate / slippage / rejection analytics | execution/* | 2026-09-25
202 | 6 | Execution | BR-02 | Broker Integration | Zerodha/Kite | IN PROGRESS | IN PROGRESS | 50% |  |  | Development | Holdings sync only | Token refresh; orders if wanted | portfolio/zerodha.py | 2026-09-24
203 | 6 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | IN PROGRESS | IN PROGRESS | 25% |  |  | Development | Dashboard partial | Live P&L panel | dashboard/server.py | 2026-09-24
204 | 6 | Execution | SEC-03 | Security | Audit logging | IN PROGRESS | IN PROGRESS | 85% | W8 | ,W8, | Development | enterprise_audit hash chain (prev_hash/row_hash, verify_chain) + append-only triggers on enterprise_audit and oms_order_event; mutating API requests audited even with the enterprise layer off; config changes and secret rotations audited | Export / retention; off-box audit copy | enterprise/audit.py; ops/migrations.py; ops/http.py | 2026-09-25
205 | 7 | Advanced Quant | DP-04 | Data Platform | Tick data | YET TO START | YET TO START | 5% |  |  | Development | live_ticks exists; 0 rows | Tick ingestion + storage | data/dhan.py | 2026-09-24
206 | 7 | Advanced Quant | DP-05 | Data Platform | Order book / depth | YET TO START | YET TO START | 5% |  |  | Development | FULL feed type defined (CLI only) | Depth capture + schema | data/dhan.py | 2026-09-24
207 | 7 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | IN PROGRESS | IN PROGRESS | 25% | W6 | ,W6, | Development | Intraday features from live_quotes; tick/depth pending | Tick / depth feed | quant/microstructure.py | 2026-09-25
208 | 7 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors | BLOCKED | BLOCKED | 20% | W6 | ,W6, | Owner: Derivatives data source | Black-Scholes / greeks / IV / basis maths + schema; no derivatives data | Derivatives data source | quant/derivatives.py | 2026-09-25
209 | 7 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | IN PROGRESS | IN PROGRESS | 40% | W6 | ,W6, | Development | Volatility estimators and regime; IV needs options data | Options data | quant/volatility.py | 2026-09-25
210 | 7 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | IN PROGRESS | IN PROGRESS | 70% | W6 | ,W3,W6, | Development | Pairs registry, spreads, cointegration screen, W3 pairs kind (short leg not executable) | Shortable instrument | quant/statarb.py; quant/pairs.py; strategy_engine/kinds.py | 2026-09-25
211 | 7 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | IN PROGRESS | IN PROGRESS | 65% | W6 | ,W6, | Development | Cross-sectional ranking + portfolio kind with dollar/beta/sector neutrality (shorts not executable) | Shortable instrument | quant/engine.py; quant/portfolio.py; strategy_engine/kinds.py | 2026-09-25
212 | 7 | Advanced Quant | QR-09 | Quant Research | Event-driven research | IN PROGRESS | IN PROGRESS | 45% | W6 | ,W6, | Development | market_event from corporate_actions + bulk_deals; ev_* strategy features; typed interface for pending sources | Earnings/dividend/macro sources | quant/events.py | 2026-09-25
213 | 7 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | IN PROGRESS | IN PROGRESS | 50% | W6 | ,W6, | Development | Value/quality/growth factors + vqm / vqmg composites (fundamental_data empty) | Fundamentals ingestion | quant/factors.py; quant/composite.py | 2026-09-25
214 | 7 | Advanced Quant | EX-11 | Execution | Execution algos | YET TO START | YET TO START | 0% |  |  | Development | None | Implement | — | 2026-09-24
215 | 7 | Advanced Quant | EX-12 | Execution | Market impact model | YET TO START | YET TO START | 0% |  |  | Development | None | Implement | — | 2026-09-24
216 | 7 | Advanced Quant | EX-15 | Execution | Latency telemetry | YET TO START | YET TO START | 0% |  |  | Development | None | Instrument data and order paths | — | 2026-09-24
217 | 7 | Advanced Quant | EX-16 | Execution | Event-driven OMS | YET TO START | YET TO START | 10% |  |  | Development | Synchronous calls | Implement | — | 2026-09-24
218 | 7 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | YET TO START | YET TO START | 0% |  |  | Development | Bar loops only | Implement | — | 2026-09-24
219 | 7 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | YET TO START | YET TO START | 0% |  |  | Development | None | Macro connectors + calendar | — | 2026-09-24
220 | 7 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | YET TO START | YET TO START | 0% |  |  | Development | None | DataSource interface | — | 2026-09-24
221 | 7 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | YET TO START | YET TO START | 0% |  |  | Development | None | Add sources | — | 2026-09-24
222 | 7 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | YET TO START | YET TO START | 5% |  |  | Development | SQLite only | Parquet/DuckDB store | — | 2026-09-24
223 | 7 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | YET TO START | YET TO START | 0% |  |  | Development | Global display tickers only | MCX/CDS/bond/MF feeds | — | 2026-09-24
224 | 8 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | ,W24, | Independent QA | W24: model + factor IC decay monitoring with alerts | Needs factor history (W22 backfill) | ml/decay.py | 2026-09-27
225 | 8 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | IN PROGRESS | IN PROGRESS | 60% | W8 | ,W8, | Development | Verified daily backups + retention; DR runbook with RPO 24 h / RTO ~10 min; pre-release backup procedure | Off-site backup target; scheduled restore drill; backup encryption | ops/backup.py; docs/DISASTER_RECOVERY.md | 2026-09-25
226 | 8 | Production Hardening | SEC-04 | Security | Encryption | IN PROGRESS | IN PROGRESS | 50% | W8 | ,W8, | Development | AES-256-GCM field encryption (ops/crypto.py, key from ATIP_ENCRYPTION_KEY, AAD-bound, no plaintext fallback); used for MFA secrets; sensitive-field classification; TLS 1.3 reverse-proxy architecture documented (ATIP stays on 127.0.0.1) | Encrypt broker credentials (ENT-06); key rotation re-encryption; TLS only with ENT-07 | ops/crypto.py; docs/SECURITY_ARCHITECTURE.md | 2026-09-25
227 | 8 | Production Hardening | API-05 | APIs | API contracts/docs | IN PROGRESS | IN PROGRESS | 40% | W8 | ,W8, | Development | Error envelope + codes, versioning, pagination, idempotency and security headers documented | Generated API reference | docs/PRODUCTION_ARCHITECTURE.md; ops/errors.py | 2026-09-25
228 | 8 | Production Hardening | API-06 | APIs | Widget JSON schemas | YET TO START | YET TO START | 5% |  |  | Development | None | Define schemas | — | 2026-09-24
229 | 8 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | IN PROGRESS | IN PROGRESS | 60% | W8 | ,W8, | Development | W8 set: production architecture, security, observability, DR, backup/restore, deployment, rollback, operations runbook, production configuration | User guide; API reference | docs/ | 2026-09-25
230 | 9 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | IN PROGRESS | IN PROGRESS | 60% | W7 | ,W3,W6,W7, | Development | Tenants + lifecycle + limits; tenant_id on tenant-owned W3-W6 tables; middleware isolation (single-resource 404, list filtering, create stamping); single shared paper book | Per-tenant paper books / broker accounts; SQL-level scoping | enterprise/tenants.py; enterprise/authz.py; db/schema.py | 2026-09-25
231 | 9 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | YET TO START | YET TO START | 0% |  |  | Owner: Move to Postgres | SQLite | Migrate to Postgres | — | 2026-09-24
232 | 9 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure | BLOCKED | BLOCKED | 5% | W7 | ,W7, | Owner: Security architecture + decision to expose | Not implemented by design: W7 keeps the 127.0.0.1 bind; exposure needs TLS, MFA, rate limiting, security review | Owner decision + security architecture | dashboard/security.py | 2026-09-25
233 | 9 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | IN PROGRESS | IN PROGRESS | 85% | W8 | ,W8, | Development | Users + 8 roles + 27 permissions, per-tenant roles, route->permission middleware; W8 TOTP MFA (enroll/confirm/disable, admin reset, login otp, encrypted secret, replay-refusing) | WebAuthn / recovery codes | enterprise/mfa.py; enterprise/users.py; enterprise/authz.py | 2026-09-25
234 | 9 | Enterprise SaaS (final objective) | ENT-05 | Security | Session management | DEPLOYED - VERIFIED | COMPLETED | 90% | W8 | ,W8, |  | Sessions (digest-only, expiry, revoke) + W8 refresh tokens: rotation on every use, reuse detection revokes the family and all sessions, HttpOnly cookie scoped to /api/auth/refresh | Validate | enterprise/users.py; dashboard/enterprise_routes.py | 2026-09-25
235 | 9 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | IN PROGRESS | IN PROGRESS | 70% | W7 | ,W7, | Development | Admin-created users (must change password), optional self-registration (PENDING + own FREE-trial tenant), activation, reset tokens; no e-mail | E-mail verification | enterprise/users.py; dashboard/enterprise_routes.py | 2026-09-25
236 | 9 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | IN PROGRESS | IN PROGRESS | 65% | W7 | ,W4,W7, | Development | Profile + preferences; tenant/user trading profiles (trading enabled, modes, brokers, assets, strategies, capital, order value) — tighten W4 only | Per-user capital accounting | enterprise/profiles.py; execution/risk_engine.py | 2026-09-25
237 | 9 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | YET TO START | YET TO START | 0% | W7 | ,W7, | Owner: Broker credential vault design | Not built: per-user broker credential vault (Claude does not handle credentials) | Design with the owner | — | 2026-09-25
238 | 9 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | YET TO START | YET TO START | 0% |  |  | Owner: Legal / SEBI review | None | Legal review before offering to other users | — | 2026-09-24
239 | 9 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | YET TO START | YET TO START | 0% |  |  | Development | None | Implement controls from ENT-14 | — | 2026-09-24
240 | 9 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | YET TO START | YET TO START | 0% |  |  | Development | None | Privacy policy + controls | — | 2026-09-24
241 | 9 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | IN PROGRESS | IN PROGRESS | 40% | W7 | ,W7, | Development | Multi-user sign-in (/login, /account, /admin) on the existing dashboard; still local-only | Blocked on ENT-07 for any exposure | dashboard/enterprise_*.py | 2026-09-25
242 | 9 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | IN PROGRESS | IN PROGRESS | 45% | W7 | ,W7, | Owner: Payment gateway | Plans (limits/features, no invented prices), subscriptions, usage metering, DRAFT invoices; no payment gateway | Payment gateway (owner decision) | enterprise/billing.py | 2026-09-25
243 | 9 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | IN PROGRESS | IN PROGRESS | 40% | W7 | ,W7, | Development | Multiple concurrent sessions per user with IP/user agent; revoke all | Device management UI | enterprise/users.py | 2026-09-25
244 | 9 | Enterprise SaaS (final objective) | ENT-19 | Channels | Watchlists | DEPLOYED - VERIFIED | COMPLETED | 75% | W7 | ,W7, |  | Per-user / shared watchlists | Validate | enterprise/workspace.py | 2026-09-25
245 | 9 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | IN PROGRESS | IN PROGRESS | 55% | W7 | ,W3,W6,W7, | Development | Per-user alert rules on any W3/W6 feature, evaluated post-market into notifications; AI alerts via ml_* features | Intraday evaluation | enterprise/workspace.py | 2026-09-25
246 | 9 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | IN PROGRESS | IN PROGRESS | 45% | W7 | ,W7, | Development | In-app inbox + preferences; Telegram (owner bot, default tenant only); no e-mail/SMS/push | E-mail / push channels | enterprise/notifications.py | 2026-09-25
247 | 9 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | YET TO START | YET TO START | 0% |  |  | Owner: Mobile apps | None | Build apps | — | 2026-09-24
248 | 9 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | IN PROGRESS | IN PROGRESS | 55% | W8 | ,W8, | Development | API keys with scopes; W8 /api/v1/* alias of the current API (API-Version header), pagination/sort/filter on v1 lists, standard error envelope, request ids | Per-route v1 contract (OpenAPI) and deprecation policy | ops/http.py; ops/errors.py | 2026-09-25
249 | 9 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | IN PROGRESS | IN PROGRESS | 60% | W8 | ,W8, | Development | Inbound POST /api/webhooks/{source}: HMAC-SHA256 signature, 300 s replay window, event-id dedupe; outbound signed delivery with backoff retry, DEAD letter, per-host circuit breaker | Business consumers (billing / broker postbacks); endpoint admin UI | ops/webhooks.py; dashboard/ops_routes.py | 2026-09-25
250 | 9 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | YET TO START | YET TO START | 0% |  |  | Development | None | Importers | — | 2026-09-24
251 | 9 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | YET TO START | YET TO START | 0% |  |  | Development | None | Adapters behind BR-03 interface | — | 2026-09-24
252 | 9 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | YET TO START | YET TO START | 0% |  |  | Development | Equity cash only | Asset-specific execution/risk adapters | — | 2026-09-24
253 | 9 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | IN PROGRESS | IN PROGRESS | 30% | W7 | ,W7, | Development | Saved report definitions (tenant-owned); rendering reuses existing pages/APIs | Report rendering / export | enterprise/workspace.py | 2026-09-25
254 | 9 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | IN PROGRESS | IN PROGRESS | 60% | W7 | ,W7, | Development | /admin: users, tenants, roles, plans, audit; admin API | Richer console | dashboard/enterprise_page.py; dashboard/enterprise_routes.py | 2026-09-25
255 | 9 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | YET TO START | YET TO START | 0% |  |  | Development | None | Visual builder on SE-01 interface | — | 2026-09-24
256 | 9 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | YET TO START | YET TO START | 0% |  |  | Development | None | Implement | — | 2026-09-24
257 | 9 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | YET TO START | YET TO START | 0% |  |  | Owner: Cloud deployment | Local Windows only | Containerise; IaC; environments | — | 2026-09-24
258 | 9 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | IN PROGRESS | IN PROGRESS | 35% | W8 | ,W8, | Development | Observability: JSON logs with request/correlation ids and secret masking, Prometheus-format metrics, health endpoints, monitoring rules; scalability path documented | HA / horizontal scale (needs DBS-05 Postgres) | ops/logs.py; ops/metrics.py; ops/health.py; docs/OBSERVABILITY.md | 2026-09-25
259 | 8 | Production hardening | SEC-06 | Security | API security hardening | DEPLOYED - VERIFIED | COMPLETED | 80% | W8 | ,W8, |  | OpsMiddleware: 2 MB limit (413), JSON content-type/parse checks (415/400), optional token-bucket rate limit (429), nosniff/DENY/no-referrer/COOP/Permissions-Policy, no-store on auth/account/admin, HSTS only with TLS, CORS only when origins configured | Enable rate limiting in production config | ops/http.py | 2026-09-25
260 | 8 | Production hardening | OPS-08 | Deployment/Ops | Configuration management | DEPLOYED - VERIFIED | COMPLETED | 80% | W8 | ,W8, |  | ATIP_ENV / environment (development/test/staging/production), config.<env>.json overlay, ATIP__SECTION__KEY overrides, validation (production refuses to start on errors), fingerprint + ops_config_version + audit of changed keys, feature flags | Validate | ops/config.py; ops/startup.py | 2026-09-25
261 | 8 | Production hardening | OPS-09 | Deployment/Ops | Scheduler hardening | DEPLOYED - VERIFIED | COMPLETED | 80% | W8 | ,W8, |  | ops_job_lock per job name (stale-owner takeover), scheduler heartbeat every 60 s, SKIPPED run when another runner holds the job, job metrics | Validate | ops/jobs.py; pipeline/scheduler.py | 2026-09-25
262 | 8 | Production hardening | OPS-10 | Deployment/Ops | Resilience + idempotency | IN PROGRESS | IN PROGRESS | 60% | W8 | ,W8, | Development | ops/resilience.py primitives (orders marked non-idempotent: never retried); Idempotency-Key on mutating API (orders from /trading keyed per decision/order) | Wrap existing data-source calls with breakers/retry | ops/resilience.py; ops/idempotency.py | 2026-09-25
263 | 8 | Production hardening | MON-09 | Monitoring | Operational alerting | DEPLOYED - VERIFIED | COMPLETED | 75% | W8 | ,W1,W8, |  | ops_monitor every 15 min, 12 rules, FIRING/RESOLVED state with 6 h re-notify, delivered via the W1 alert channel (alert_log + Telegram when configured) | Tune thresholds after observation | ops/monitor.py | 2026-09-25
264 | 8 | Production hardening | RK-19 | Risk | Stale-data trade protection | DEPLOYED - VERIFIED | COMPLETED | 80% | W8 | ,W8, |  | Risk check market_data_fresh (BUY rejected when last bar > 2 sessions behind); LIVE orders validated against the NSE session; live gate additionally requires environment production | Validate | execution/risk_engine.py; execution/order_manager.py; execution/config.py | 2026-09-25
265 | 8 | Production hardening | OPS-11 | Deployment/Ops | Release management & deployment | IN PROGRESS | IN PROGRESS | 80% | W9 | ,W9, | Development | Tag ATIP-W9-RC2; ops/release.py preflight/manifest/postcheck/record; deploy/deploy_release.ps1 + rollback_release.ps1 (dry-run default); requirements.lock.txt; release docs | Authorized deployment + first executed rollback drill | ops/release.py; deploy/; docs/PRODUCTION_DEPLOYMENT.md | 2026-09-26
266 | 8 | Production hardening | RK-20 | Risk | Unified live-trading master switch | DEPLOYED - VERIFIED | COMPLETED | 90% | W9 | ,W1,W4,W9, |  | W1 real orders (order rules, aggressive strategy) also require execution.live_trading_enabled + environment production (BLOCKED_LIVE_DISABLED otherwise); W4 gate + Dhan adapter refusal unchanged | Validate | orders/broker.py; ops/trading_safety.py | 2026-09-26
267 | 10 | Wealth track (Waves 11-20) | INV-001 | Wealth | Investor DNA | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W11 | ,W11, | Independent QA | W11: Risk capacity / tolerance / requirement, horizon, behaviour, personality | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/dna.py | 2026-09-26
268 | 10 | Wealth track (Waves 11-20) | WLT-001 | Wealth | Multi-asset wealth dashboard | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W12 | ,W12, | Independent QA | W12: Unified holdings, net worth, allocation, concentration, overlay | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/holdings.py; wealth/assets.py | 2026-09-26
269 | 10 | Wealth track (Waves 11-20) | GOL-001 | Wealth | Goal planning engine | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W13 | ,W13, | Independent QA | W13: Corpus, contributions, CAGR, shortfall, Monte Carlo, scenarios | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/goals.py | 2026-09-26
270 | 10 | Wealth track (Waves 11-20) | AAL-001 | Wealth | Dynamic asset allocation | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W14 | ,W14, | Independent QA | W14: Strategic + tactical from DNA, goals, regime, ATIP signals | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/allocation.py | 2026-09-26
271 | 10 | Wealth track (Waves 11-20) | RBL-001 | Wealth | Portfolio rebalancing | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W15 | ,W15, | Independent QA | W15: Drift, triggers, cost-aware plans (tax-neutral) | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/rebalance.py | 2026-09-26
272 | 10 | Wealth track (Waves 11-20) | PERF-001 | Wealth | Investor performance attribution | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W15.5 | ,W15.5, | Independent QA | W15.5: Model / executable / actual / benchmark; attribution; audit; export | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/perf/ | 2026-09-26
273 | 10 | Wealth track (Waves 11-20) | AIA-001 | Wealth | AI investment advisor | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W16 | ,W16, | Independent QA | W16: Evidence-backed, suitability-checked; optional Claude narration | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/advisor.py | 2026-09-26
274 | 10 | Wealth track (Waves 11-20) | INT-001 | Wealth | Integrated intelligence | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W17 | ,W17, | Independent QA | W17: Investor cycle, overview, modes, signal suitability | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/integrated.py | 2026-09-26
275 | 10 | Wealth track (Waves 11-20) | QA-001 | Wealth | Wealth QA / security / performance | IN PROGRESS | IN PROGRESS | 60% | W18 | ,W18, | Development | W18: 70-test suite, security review (S1/S2 fixed), performance | Independent testing (ChatGPT) + UAT; merge after authorization | tests/test_wealth_*.py | 2026-09-26
276 | 10 | Wealth track (Waves 11-20) | UAT-001 | Wealth | Beta / UAT | IN PROGRESS | IN PROGRESS | 60% | W19 | ,W19, | Development | W19: Personas, persona view, feedback, UAT plan | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/uat.py | 2026-09-26
277 | 10 | Wealth track (Waves 11-20) | REL-001 | Wealth | Wealth production hardening | DEPLOYED - AWAITING QA | IMPLEMENTED BUT NOT VERIFIED | 80% | W20 | ,W20, | Independent QA | W20: Migration 0005, /health/wealth, monitor, backup, docs, RC | Independent testing (ChatGPT) + UAT; merge after authorization | ops/migrations.py; wealth/health.py | 2026-09-26

## Deployed
Seq | Phase Name | ID | Module | Feature | Delivery Status | Completion % | Waves | Current Implementation | Next Action / Missing Work | Needs
1 | Delivered baseline (maintain) | DP-02 | Data Platform | Daily OHLCV history | DEPLOYED - VERIFIED | 90% | Baseline | NSE Bhavcopy + Dhan; coverage/freshness/duplicate guards | Maintain
2 | Delivered baseline (maintain) | DP-07 | Data Platform | Delivery data | DEPLOYED - VERIFIED | 90% | Baseline | Full Bhavcopy nightly + backfill | Maintain
3 | Delivered baseline (maintain) | DP-20 | Data Platform | Trading calendar | DEPLOYED - VERIFIED | 90% | Baseline | 2025-26 holidays + budget sessions | Add next year's holidays each December
4 | Delivered baseline (maintain) | TA-01 | Technical Analysis | Core indicators | DEPLOYED - VERIFIED | 90% | Baseline | Computed and stored; MACD fixed and normalised | Maintain
5 | Delivered baseline (maintain) | TA-02 | Technical Analysis | Extended oscillators | DEPLOYED - VERIFIED | 80% | Baseline | Computed and stored | Maintain
6 | Delivered baseline (maintain) | TA-05 | Technical Analysis | Fibonacci | DEPLOYED - VERIFIED | 80% | Baseline | 52-week 23.6/38.2/50/61.8 levels | Optional: swing-anchored levels
7 | Delivered baseline (maintain) | TA-07 | Technical Analysis | Trend features | DEPLOYED - VERIFIED | 80% | Baseline | Computed and stored | Maintain
8 | Delivered baseline (maintain) | TA-08 | Technical Analysis | Relative strength | DEPLOYED - VERIFIED | 80% | Baseline | 20-day RS with date-matched benchmark | Sector-relative RS later (TA-08b in Phase 2 if wanted)
9 | Delivered baseline (maintain) | SC-03 | Alpha/Factor Engine | RRI | DEPLOYED - VERIFIED | 75% | Baseline | Implemented | Institutional input improves with SC-14
10 | Delivered baseline (maintain) | SC-04 | Alpha/Factor Engine | MRI | DEPLOYED - VERIFIED | 85% | Baseline | Implemented; MACD corrected | Maintain
11 | Delivered baseline (maintain) | SC-07 | Alpha/Factor Engine | ZPI | DEPLOYED - VERIFIED | 80% | Baseline | Implemented + delivery component | Maintain
12 | Delivered baseline (maintain) | SC-10 | Alpha/Factor Engine | Portfolio Health score | DEPLOYED - VERIFIED | 75% | Baseline | Implemented | Correlation/drawdown inputs come with PF-09 and PF-13
13 | Delivered baseline (maintain) | PF-05 | Portfolio | Portfolio health | DEPLOYED - VERIFIED | 75% | Baseline | Implemented + dashboard | Maintain
14 | Delivered baseline (maintain) | SC-11 | Alpha/Factor Engine | Trade of the Day | DEPLOYED - VERIFIED | 80% | Baseline | Implemented; one TOD per session | Maintain
15 | Delivered baseline (maintain) | SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | DEPLOYED - VERIFIED | 80% | Baseline | Implemented; rank stored | Maintain
16 | Delivered baseline (maintain) | SC-17 | Alpha/Factor Engine | Configurable weights | DEPLOYED - VERIFIED | 80% | Baseline | weight_config table | Regime-specific rows used by ML-05
17 | Delivered baseline (maintain) | SG-02 | Signal Engine | Signal validation | DEPLOYED - VERIFIED | 75% | Baseline | EOD coverage guard; FII/DII hold | Maintain
18 | Delivered baseline (maintain) | SG-03 | Signal Engine | Signal ranking | DEPLOYED - VERIFIED | 85% | Baseline | Implemented | Maintain
19 | Delivered baseline (maintain) | SG-05 | Signal Engine | Trade plan | DEPLOYED - VERIFIED | 75% | Baseline | Implemented | Maintain
20 | Delivered baseline (maintain) | SG-06 | Signal Engine | Outcome tracking | DEPLOYED - VERIFIED | 80% | Baseline | Implemented; corrected denominator | Maintain
21 | Delivered baseline (maintain) | SG-07 | Signal Engine | Signal provenance log | DEPLOYED - VERIFIED | 80% | Baseline | Append-only signal_log | Maintain
22 | Delivered baseline (maintain) | BT-01 | Backtesting | Historical backtest | DEPLOYED - VERIFIED | 80% | Baseline | 3 bar engines | Extended by Phase 2 items
23 | Delivered baseline (maintain) | BT-10 | Backtesting | Win rate / profit factor / expectancy | DEPLOYED - VERIFIED | 90% | Baseline | Implemented | Maintain
24 | Delivered baseline (maintain) | RK-02 | Risk Management | Max order value | DEPLOYED - VERIFIED | 90% | Baseline | Enforced when configured | Set values in config.json
25 | Delivered baseline (maintain) | RK-03 | Risk Management | Max orders per day | DEPLOYED - VERIFIED | 90% | Baseline | Enforced when configured | Set values in config.json
26 | Delivered baseline (maintain) | RK-04 | Risk Management | Max open positions | DEPLOYED - VERIFIED | 90% | Baseline | Enforced when configured | Set values in config.json
27 | Delivered baseline (maintain) | RK-05 | Risk Management | Symbol exposure limit | DEPLOYED - VERIFIED | 90% | Baseline | Enforced when configured | Set values in config.json
28 | Delivered baseline (maintain) | RK-14 | Risk Management | Crash-risk gating | DEPLOYED - VERIFIED | 75% | Baseline | SELL_CRI_DANGER + strategy use | Maintain
29 | Delivered baseline (maintain) | EX-03 | Execution | Position management | DEPLOYED - VERIFIED | 75% | Baseline | reserve -> place -> apply | Maintain
30 | Delivered baseline (maintain) | EX-04 | Execution | Entry/exit | DEPLOYED - VERIFIED | 70% | Baseline | strategy/live.py | Maintain
31 | Delivered baseline (maintain) | EX-05 | Execution | Stop loss | DEPLOYED - VERIFIED | 75% | Baseline | Implemented | Maintain
32 | Delivered baseline (maintain) | EX-06 | Execution | Trailing stop | DEPLOYED - VERIFIED | 80% | Baseline | Implemented (4.0x ATR) | Maintain
33 | Delivered baseline (maintain) | EX-07 | Execution | Profit booking / partial exit | DEPLOYED - VERIFIED | 70% | Baseline | Implemented in aggressive strategy | Maintain
34 | Delivered baseline (maintain) | EX-13 | Execution | Paper trading | DEPLOYED - VERIFIED | 85% | Baseline | Paper broker with slippage | Maintain
35 | Delivered baseline (maintain) | EX-14 | Execution | Live gating | DEPLOYED - VERIFIED | 85% | Baseline | Implemented | Maintain
36 | Delivered baseline (maintain) | BR-01 | Broker Integration | Dhan | DEPLOYED - VERIFIED | 80% | Baseline | dhanhq integration | Maintain
37 | Delivered baseline (maintain) | BR-03 | Broker Integration | Broker abstraction | DEPLOYED - VERIFIED | 75% | Baseline | PAPER/SANDBOX/LIVE routing | Becomes multi-broker interface in ENT-15
38 | Delivered baseline (maintain) | DB-01 | Dashboard | Market Health panel | DEPLOYED - VERIFIED | 80% | Baseline | Rendered | Maintain
39 | Delivered baseline (maintain) | DB-02 | Dashboard | Global Markets panel | DEPLOYED - VERIFIED | 75% | Baseline | Rendered; snapshot bug fixed | Maintain
40 | Delivered baseline (maintain) | DB-03 | Dashboard | FII/DII panel | DEPLOYED - VERIFIED | 75% | Baseline | Rendered | Maintain
41 | Delivered baseline (maintain) | DB-05 | Dashboard | Sector Rotation | DEPLOYED - VERIFIED | 70% | Baseline | Heatmap rendered | Maintain
42 | Delivered baseline (maintain) | DB-07 | Dashboard | Top 25 VPI | DEPLOYED - VERIFIED | 85% | Baseline | Rendered | Maintain
43 | Delivered baseline (maintain) | DB-08 | Dashboard | Buy Zone (ZPI) | DEPLOYED - VERIFIED | 85% | Baseline | Rendered | Maintain
44 | Delivered baseline (maintain) | DB-09 | Dashboard | Recovery (RRI) | DEPLOYED - VERIFIED | 80% | Baseline | Rendered | Maintain
45 | Delivered baseline (maintain) | DB-10 | Dashboard | Momentum Reversal (MRI) | DEPLOYED - VERIFIED | 80% | Baseline | Rendered | Maintain
46 | Delivered baseline (maintain) | DB-12 | Dashboard | Portfolio Health panel | DEPLOYED - VERIFIED | 80% | Baseline | Rendered | Maintain
47 | Delivered baseline (maintain) | DB-13 | Dashboard | Trade of the Day | DEPLOYED - VERIFIED | 85% | Baseline | Rendered | Maintain
48 | Delivered baseline (maintain) | DB-15 | Dashboard | Orders/signals panel | DEPLOYED - VERIFIED | 70% | Baseline | Rendered with PAPER status | Maintain
49 | Delivered baseline (maintain) | DB-19 | Dashboard | Hosted read-only snapshot | DEPLOYED - VERIFIED | 80% | Baseline | publish_snapshot.py | Superseded by ENT-08 web app
50 | Delivered baseline (maintain) | API-01 | APIs | Internal REST | DEPLOYED - VERIFIED | 70% | Baseline | 15 FastAPI routes | Maintain
51 | Delivered baseline (maintain) | API-02 | APIs | Local API authentication | DEPLOYED - VERIFIED | 80% | Baseline | 127.0.0.1 bind + X-ATIP-Token | Replaced by per-user auth in SEC-02
52 | Delivered baseline (maintain) | DBS-01 | Database | Schema | DEPLOYED - VERIFIED | 75% | Baseline | 19 SQLite tables | Migrations via DBS-04
53 | Delivered baseline (maintain) | DBS-02 | Database | Retention/purge | DEPLOYED - VERIFIED | 70% | Baseline | db/purge.py | Maintain
54 | Delivered baseline (maintain) | SEC-01 | Security | Credential handling | DEPLOYED - VERIFIED | 85% | W8 | Secrets abstraction (env > .env > atip_data/secrets > legacy config), presence/format validation, name-only access log, rotation dates, masking in logs | Move legacy plaintext keys out of config.json (owner action)
55 | Delivered baseline (maintain) | MON-07 | Monitoring | Feed health | DEPLOYED - VERIFIED | 70% | Baseline | Implemented | Maintain
56 | Delivered baseline (maintain) | MON-08 | Monitoring | Diagnostics | DEPLOYED - VERIFIED | 80% | W8 | /health, /health/live¦ready¦database¦broker¦data¦scheduler¦ml (LIVE/READY/DEGRADED/FAILED); python -m ops status | Validate
57 | Delivered baseline (maintain) | OPS-01 | Deployment/Ops | Autostart/scheduling | DEPLOYED - VERIFIED | 75% | Baseline | Task Scheduler + VBS | Replaced by cloud deploy in OPS-04
58 | Delivered baseline (maintain) | OPS-07 | Deployment/Ops | Snapshot publishing | DEPLOYED - VERIFIED | 80% | Baseline | Implemented | Maintain
59 | Foundation | DP-09 | Data Platform | India VIX | DEPLOYED - VERIFIED | 95% | Baseline | Daily INDIAVIX series in prices_daily (421 sessions 2025-01-13..; Dhan history + NSE close nightly); get_vix() = session feed then daily series; no 15.0 default | None for DP-09; VIX term structure/percentile features belong to later factor work
60 | Foundation | DP-17 | Data Platform | Market breadth | DEPLOYED - VERIFIED | 90% | Baseline | breadth_series(): advances/declines; % advancing; A/D ratio; % above 200-DMA; 52-week new highs/lows over tracked universe; 80% coverage gate; stored in market_health | Survivorship-free universe (BT-15); sector-level breadth (DP-13)
61 | Foundation | SC-09 | Alpha/Factor Engine | Market Health score | DEPLOYED - VERIFIED | 90% | Baseline | Every MH input is real or left out (index_levels then daily index series; session-own FII/DII; global <=4 days; VIX; breadth); coverage + inputs stored; no score below 50% coverage; upsert keeps portfolio_health; 393 past sessions backfilled | FII/DII and global history only from 2026-07 (backfilled coverage avg 0.65); determine_signal still defaults a missing MH to 50; model-based regime is ML-05
62 | Foundation | SC-08 | Alpha/Factor Engine | ACS | DEPLOYED - VERIFIED | 85% | Baseline | HistoricalAccuracy = 90-day 5-session hit rate from outcomes known by the scored day (min 5); NewsConfidence only from AI-classified news with no look-ahead; missing inputs left out (no 50/60 stand-ins) | NewsConfidence stays absent until NS-02 (Anthropic key) classifies news
63 | Foundation | MON-01 | Monitoring | Job logging | DEPLOYED - VERIFIED | 90% | W1 | run_job records every run (start/end/duration/rows/status/error); returned FAILED is a failure; EMPTY status | Record failures, end time, row counts
64 | Foundation | MON-02 | Monitoring | Stalled-job detection | DEPLOYED - VERIFIED | 85% | W1 | pipeline/health.py expectations: MISSED/STALLED/FAILING/EMPTY; every 30 min | Expected-run table + missed-run check
65 | Foundation | MON-03 | Monitoring | Failure alerting | DEPLOYED - VERIFIED | 85% | W1 | alert_log + dashboard panel + Telegram when configured; daily de-dup; token scrubbed | Configure Telegram; alert on failure/stall
66 | Foundation | DB-14 | Dashboard | Alerts / morning brief | DEPLOYED - VERIFIED | 80% | W1 | Brief recorded for the dashboard + Telegram; pipeline-health section (outside W1, same tree) | Deliver digest; verify daily
67 | Foundation | RK-15 | Risk Management | Risk alerts | DEPLOYED - VERIFIED | 80% | W1 | Alerts on halt/resume and on halted or limit-refused orders (outside W1, same tree) | Alert on halt, limit breach, CRI spike
68 | Foundation | MON-06 | Monitoring | Log rotation | DEPLOYED - VERIFIED | 90% | W1 | SafeRotatingFileHandler 20 MB x 10, survives refused rename (outside W1, same tree) | RotatingFileHandler
69 | Foundation | DBS-06 | Database | Timestamp consistency | DEPLOYED - VERIFIED | 85% | W1 | Convention documented (IST; created_at UTC); news UTC->IST; status query fixed; repair tool | Normalise; fix news recency
70 | Foundation | NS-01 | News/Sentiment | News ingestion | DEPLOYED - VERIFIED | 80% | W1 | News first + morning catch-up; de-dup; per-feed status; 4 more RSS feeds | Fix job; add second source; health check
71 | Foundation | OPS-03 | Deployment/Ops | Install/setup | DEPLOYED - VERIFIED | 85% | W1 | ta not pandas-ta everywhere; requirements-dev.txt; CI httpx; config template; docs/DEV_SETUP.md | Fix requirements/setup; pin versions
72 | Foundation | EX-01 | Execution | Order management tests | DEPLOYED - VERIFIED | 70% | Baseline | orders/rules.py (944 lines) without tests | Unit tests for rules.py
73 | Foundation | OPS-02 | Deployment/Ops | CI + end-to-end test | DEPLOYED - VERIFIED | 70% | Baseline | GitHub Actions; ~270 test functions; no E2E | Add E2E pipeline test
77 | Foundation | SC-05 | Alpha/Factor Engine | CRI debt input | DEPLOYED - VERIFIED | 75% | Baseline | Implemented; Debt input missing | Feed Debt/Equity
78 | Foundation | SC-01 | Alpha/Factor Engine | VPI inputs | DEPLOYED - VERIFIED | 80% | Baseline | Implemented; FG/IS inputs weak | Real Fundamental Growth input
79 | Foundation | PF-01 | Portfolio | Portfolio ingestion | DEPLOYED - VERIFIED | 80% | W1 | portfolio_sync records each attempt and reason (DH-901 named); qty/avg update; sold removed | Scheduled reliable sync + token handling
80 | Foundation | BR-04 | Broker Integration | Portfolio sync schedule | DEPLOYED - VERIFIED | 80% | W1 | Morning catch-up re-sync; Zerodha SKIPPED when not connected; health expects SUCCESS | Scheduled sync with alert on failure
81 | Foundation | PF-02 | Portfolio | Holdings & P&L | DEPLOYED - VERIFIED | 80% | W1 | portfolio/pnl.py PAPER + LIVE books marked to market; /api/pnl | Realised + unrealised P&L
82 | Foundation | PF-13 | Portfolio | Daily P&L series | DEPLOYED - VERIFIED | 85% | W1 | pnl_daily equity/day P&L/peak/drawdown per env; post-market daily_pnl job | Daily P&L table; EOD job
83 | Foundation | RK-13 | Risk Management | Risk-based sizing wired to orders | DEPLOYED - VERIFIED | 85% | W1 | size_position() pure + size_for_account(); quantity_type RISK in order rules | Use size in order path
84 | Foundation | RK-07 | Risk Management | Daily loss limit | DEPLOYED - VERIFIED | 85% | W1 | max_daily_loss_value blocks BUYs; unmeasurable blocks | Limit on PF-13; auto-halt
85 | Foundation | RK-08 | Risk Management | Drawdown limit | DEPLOYED - VERIFIED | 85% | W1 | max_drawdown_pct blocks BUYs; unmeasurable blocks | Peak-to-trough on PF-13; auto-halt
86 | Foundation | DBS-03 | Database | Backups | DEPLOYED - VERIFIED | 85% | W8 | ops/backup.py: daily online SQLite backup (19:15) VERIFIED by integrity_check + key-table counts + sha256 (ops_backup); 7 daily + 4 weekly retention of its own files only; restore to a NEW file; python -m ops backup/restore/verify | Off-machine copy of backups; restore drill
87 | Foundation | DP-06 | Data Platform | Corporate actions open items | DEPLOYED - VERIFIED | 85% | Baseline | NSE CA calendar; reconciliation; volume re-base | TVSMOTOR scheme; renamed symbols
88 | Foundation | TA-06 | Technical Analysis | Support/Resistance | DEPLOYED - AWAITING QA | 80% | W21 | W21: fractal pivots over 120 sessions, mean-anchored clusters, nearest confirmed support/resistance with touches and distance | QA; optionally feed the Technical Score SR component | Independent QA
89 | Foundation | DP-19 | Data Platform | Data quality layer | DEPLOYED - VERIFIED | 85% | W1 | data/quality.py 12 checks + DQS per session; data_quality table; post-market; alert | DQS table; outlier and timestamp checks
90 | Quant Research (data, factors, backtesting) | DBS-04 | Database | Schema migrations | DEPLOYED - VERIFIED | 80% | W7,W8 | schema_migrations (version, checksum, applied_at, duration, status, rollback note); 0001 baseline, 0002 W8 tables, 0003 indexes, 0004 append-only audit triggers; drift detection; additive layer now runs once per process (W7-R8) | Down-migration scripts beyond rollback notes (policy: restore pre-release backup)
92 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | DEPLOYED - AWAITING QA | 85% | W21 | W21: intraday_bars stores the 30-min job's 15-min bars (was discarded); 90-day retention | QA; consider 5-min bars for session VWAP | Independent QA
93 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | DEPLOYED - AWAITING QA | 80% | W21 | W21: vwap_20d, vwap_session (intraday bars), vwap_dev_pct in technical_ext; strategy feature vwap_dev_pct | Owner: technical.vwap_in_score (changes scores); QA | Independent QA; Owner: technical.vwap_in_score
94 | Quant Research (data, factors, backtesting) | SC-12 | Alpha/Factor Engine | Technical Score VWAP input | DEPLOYED - VERIFIED | 75% | Baseline | Implemented; VWAP weight dead | Include VWAP
95 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | DEPLOYED - AWAITING QA | 80% | W21 | W21: volume profile POC/VAH/VAL over 20 sessions (intraday or daily basis) | QA | Independent QA
96 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | DEPLOYED - AWAITING QA | 80% | W21 | W21: weekly RSI/trend, monthly trend, mtf_alignment -3..+3 | QA | Independent QA
97 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | DEPLOYED - AWAITING QA | 70% | W21 | W21: python -m data.technical --backfill N (tracked universe, resumable) | Run the backfill (owner timing; copy first) | Independent QA; Owner: Run the indicator backfill
98 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | DEPLOYED - AWAITING QA | 85% | W22 | W22: score_components stores every ATIP index's sub-components per symbol/date (weighted_score label capture; scores unchanged) | QA | Independent QA
99 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | DEPLOYED - AWAITING QA | 80% | W22 | W22: 11 standalone factors: mean reversion, trend, volume, recovery, risk (BRI) | QA; research on full history | Independent QA
100 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | DEPLOYED - AWAITING QA | 85% | W6 | W6 quant/normalize.py per-factor spec (winsorize/zscore/percentile/rank/minmax/sector/neutralize) -- tracker was stale | QA | Independent QA
101 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | DEPLOYED - AWAITING QA | 85% | W6,W22 | W6 registry quant_factor + factor sets + content-hash versioning (tracker was stale); W22 adds 11 factors | QA | Independent QA
102 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | DEPLOYED - AWAITING QA | 85% | W22 | W22: formula_registry resolves each signal_log weights_hash to the full weight set + code version | QA | Independent QA
103 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | DEPLOYED - AWAITING QA | 80% | W22 | W22: research_study + research_link registry, frozen on conclusion | QA | Independent QA
104 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | DEPLOYED - AWAITING QA | 80% | W6,W22 | W22: backfill_scores + research_report run IC for every factor | Run full-history backfill + report | Independent QA
105 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | DEPLOYED - AWAITING QA | 80% | W6,W22 | W22: IC decay 1/5/10/20 for every factor in research_report | Run on full history | Independent QA
106 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | DEPLOYED - AWAITING QA | 80% | W6,W22 | W22: redundancy report (pairs ¦rho¦>=0.7) in research_report | Run on full history | Independent QA
107 | Quant Research (data, factors, backtesting) | QR-04 | Quant Research | Statistical toolkit | DEPLOYED - VERIFIED | 75% | W6 | statarb (OLS, ADF, Engle-Granger, half-life, z) + normalize + volatility estimators | Validate
108 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | DEPLOYED - AWAITING QA | 80% | W22 | W22: evidence-based approval gate, decision history, lifecycle enforcement behind quant.require_approved_factors | Owner: enable after review | Independent QA; Owner: quant.require_approved_factors
109 | Quant Research (data, factors, backtesting) | BT-16 | Backtesting | Dated equity curve / run records | DEPLOYED - VERIFIED | 85% | W2 | backtest_run snapshot+hash, code version, data fingerprint; trades/equity/drawdowns tables | Dated trades + equity curve + run table
110 | Quant Research (data, factors, backtesting) | BT-08 | Backtesting | Portfolio-level backtest | DEPLOYED - VERIFIED | 85% | W1,W2 | Portfolio engine: cash, positions, sizing (W1 size_position), exposure, dated equity | Portfolio simulator
111 | Quant Research (data, factors, backtesting) | BT-09 | Backtesting | Drawdown analysis | DEPLOYED - VERIFIED | 90% | W2 | Drawdown series, max DD, episodes with duration/recovery on dated equity | Compute on equity curve
112 | Quant Research (data, factors, backtesting) | BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | DEPLOYED - VERIFIED | 90% | W2 | Return, CAGR, vol, Sharpe, Sortino, Calmar, trade stats; conventions documented | Implement
113 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | DEPLOYED - AWAITING QA | 85% | W23 | W23: historical VaR/CVaR 95/99, parametric VaR, skew, kurtosis in every backtest's metrics | QA | Independent QA
114 | Quant Research (data, factors, backtesting) | BT-05 | Backtesting | Itemised costs | DEPLOYED - VERIFIED | 85% | W2 | Itemised NSE cost model (delivery/intraday/flat/zero), central config | Indian cost model shared by backtest and paper
115 | Quant Research (data, factors, backtesting) | BT-06 | Backtesting | Slippage in backtest | DEPLOYED - VERIFIED | 90% | W2 | none / fixed / pct slippage, default = paper broker 5 bps | Shared slippage model
116 | Quant Research (data, factors, backtesting) | BT-07 | Backtesting | Liquidity constraints | DEPLOYED - VERIFIED | 85% | W2 | Volume participation cap/reject + prior-bar turnover floor | All engines
117 | Quant Research (data, factors, backtesting) | DP-18 | Data Platform | Survivorship-free universe | DEPLOYED - VERIFIED | 80% | Baseline | Current NIFTY 500 download | Store constituent history
118 | Quant Research (data, factors, backtesting) | BT-15 | Backtesting | Bias controls | DEPLOYED - VERIFIED | 80% | W2 | Point-in-time view + LookAheadError, next-open fills, data/timestamp validation, survivorship flag | Systematic checks
119 | Quant Research (data, factors, backtesting) | BT-03 | Backtesting | In/out-of-sample | DEPLOYED - VERIFIED | 85% | W2 | Ordered non-overlapping research/validation/test; test needs allow_test; re-test flagged | Formal splits
120 | Quant Research (data, factors, backtesting) | BT-02 | Backtesting | Walk-forward | DEPLOYED - VERIFIED | 80% | W2 | Rolling windows, candidate selection on validation, stitched OOS; no optimiser | Implement
121 | Quant Research (data, factors, backtesting) | BT-13 | Backtesting | Monte Carlo | DEPLOYED - VERIFIED | 85% | W2 | Seeded trade shuffle + return bootstrap; percentiles, P(loss), disclaimer | Implement
122 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | DEPLOYED - AWAITING QA | 80% | W23 | W23: grid / random / adaptive optimiser with trial runs, test-window refusal, Deflated Sharpe + overfit warning | QA; optional true Bayesian search | Independent QA
123 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | DEPLOYED - AWAITING QA | 80% | W23 | W23: one-at-a-time sensitivity curves, stability, knife-edge flags, 2-D heat map | QA | Independent QA
124 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | DEPLOYED - AWAITING QA | 80% | W23 | W23: robustness battery (costs x2, slippage x3, universe halves, period halves, regimes, Monte Carlo) with verdict | QA | Independent QA
125 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | DEPLOYED - AWAITING QA | 80% | W6,W22 | W6 experiments + W22 studies linking experiments/backtests/research | QA | Independent QA
126 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | DEPLOYED - AWAITING QA | 70% | W23 | W23: momentum breakout strategy + end-to-end study (optimise/validate/sensitivity/robustness/test) | Run full-universe study; review | Independent QA
127 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | DEPLOYED - AWAITING QA | 70% | W23 | W23: RSI(2) mean-reversion strategy + study; 12-stock smoke: REJECTED out of sample | Run full-universe study; review | Independent QA
128 | Quant Research (data, factors, backtesting) | QR-13 | Quant Research | Signal outcome research by regime | DEPLOYED - VERIFIED | 70% | Baseline | success_report keyed on signal/threshold | Add regime/ACS buckets
129 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | DEPLOYED - AWAITING QA | 70% | W21 | W21: beta_60, beta_downside, beta_long (>=500 sessions) | Owner: prices_daily retention >= 1,100 days for a 3-year beta | Independent QA; Owner: prices_daily retention >= 1,100 days
130 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | DEPLOYED - AWAITING QA | 75% | W21 | W21: Beta Risk Index 0-100 (level, downside, instability); strategy feature bri | QA; decide if it joins a composite | Independent QA
131 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | DEPLOYED - AWAITING QA | 80% | W21 | W21: Supertrend, Ichimoku, Keltner, Donchian, MFI, CMF, ROC, Aroon, PSAR; stoch/Williams %R/CCI now computed | QA | Independent QA
134 | Quant Research (data, factors, backtesting) | DP-10 | Data Platform | FII/DII history | DEPLOYED - VERIFIED | 80% | Baseline | Session flows; only 7 sessions history | Historical backfill source
135 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | DEPLOYED - AWAITING QA | 75% | W21 | W21: daily GIFTNIFTY close from index_levels into prices_daily | Pre-open panel (DB-04) | Independent QA
138 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | DEPLOYED - AWAITING QA | 80% | W21 | W21: 8 sector index series in the daily Dhan sync + sector_breadth table | Run --backfill-sectors; QA | Independent QA
142 | Strategy Engine | SG-04 | Signal Engine | Rich decision states | DEPLOYED - VERIFIED | 80% | W3 | Decision states BUY/ADD/HOLD/REDUCE/EXIT/SELL/NO_ACTION/BLOCKED_BY_RISK with reasons; PositionIntent | Extended states + stored reasons
143 | Strategy Engine | SG-01 | Signal Engine | SELL calibration | DEPLOYED - VERIFIED | 70% | Baseline | SELL never fired | Backtest-based SELL thresholds
144 | Strategy Engine | SE-01 | Strategy Engine | Strategy library | DEPLOYED - VERIFIED | 85% | W3 | Versioned JSON definitions + DB registry (id, name, description, category, version, status, owner, created/updated, priority, weight); VERSION/LIFECYCLE events; 9 library strategies | Strategy interface + registry
145 | Strategy Engine | SE-02 | Strategy Engine | Strategy parameters | DEPLOYED - VERIFIED | 85% | W3 | ParamSpec name/type/default/min/max/allowed/required/description; validated on resolve; stored per version in strategy_parameter | Param store per strategy with versions
146 | Strategy Engine | SE-03 | Strategy Engine | Rule-based strategies | DEPLOYED - VERIFIED | 85% | W3 | Rule language all/any/not/min-of, 11 operators incl. crosses; rule kind | Generic rule definition format
147 | Strategy Engine | SE-06 | Strategy Engine | Multi-factor strategy | DEPLOYED - VERIFIED | 85% | W3 | multi_factor kind: weights, scaling, thresholds, confirmations, coverage, ranking | IC-weighted multi-factor strategy
148 | Strategy Engine | SE-04 | Strategy Engine | Quant strategies | DEPLOYED - VERIFIED | 75% | W3 | quant_rank kind + point-in-time feature catalogue (framework only) | Implement first quant strategies
149 | Strategy Engine | SE-09 | Strategy Engine | Strategy lifecycle | DEPLOYED - VERIFIED | 85% | W3 | 12 states incl. DRAFT/ACTIVE/PAUSED/DISABLED/RETIRED/ARCHIVED; allowed transitions; backtest evidence for ACTIVE/VALIDATION/APPROVED; strategy_engine_event audit | State machine + gates
150 | Strategy Engine | SE-11 | Strategy Engine | Strategy health | DEPLOYED - VERIFIED | 75% | W3 | HEALTHY/WARNING/ERROR/STALE/DISABLED; last execution, last signal, signal frequency, error count, performance reference, data availability, parameter validity | Health scoring + alerts
151 | Strategy Engine | SE-07 | Strategy Engine | Strategy combination/ranking/selection | DEPLOYED - VERIFIED | 75% | W3 | composite kind (vote/weighted/priority/regime_select) + cross-strategy combine(): priority, weighting, vote, conflict -> WAIT, NO_TRADE veto; enable/disable via lifecycle and mapping | Allocator
152 | Strategy Engine | SE-08 | Strategy Engine | Regime-aware selection | DEPLOYED - VERIFIED | 75% | W3 | Configurable regime mapping STRONG_BULL/BULL/NEUTRAL/BEAR/HIGH_RISK (+DEFAULT) -> strategies or NO_TRADE; Market Health regime provider; default mapping seeded | Regime-conditional allocation
156 | AI/ML | ML-13 | AI/ML | Labels/targets | DEPLOYED - VERIFIED | 85% | W5 | ml/labels.py: direction, binary_return, forward_return, return_rank, volatility_regime, market_regime, signal_outcome; ml_label definitions; computed only from bars after t | Validate
157 | AI/ML | ML-07 | AI/ML | Feature selection | DEPLOYED - AWAITING QA | 80% | W5,W24 | W24: importance-stability selection -> new feature-set version | QA | Independent QA
158 | AI/ML | ML-08 | AI/ML | Model validation | DEPLOYED - AWAITING QA | 85% | W5,W24 | W24: purged expanding walk-forward reports vs baselines, IC, calibration, verdict | QA | Independent QA
159 | AI/ML | ML-01 | AI/ML | Supervised ML | DEPLOYED - AWAITING QA | 80% | W5,W24 | W24: native numpy GBM + random forest; bootstrap trains + validates first models (TRAINED, not ACTIVE); real-data smoke: NO_EDGE on 5-day direction | Richer features / labels; full-universe validation | Independent QA
160 | AI/ML | ML-12 | AI/ML | Model registry/versioning | DEPLOYED - VERIFIED | 85% | W5 | ml_model / ml_model_version with feature-set, dataset, config and artifact hashes; immutable artifacts; lifecycle | Validate
161 | AI/ML | ML-11 | AI/ML | Ensemble models | DEPLOYED - AWAITING QA | 80% | W5,W24 | W24: ensemble model type blended by held-out loss | QA | Independent QA
162 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | DEPLOYED - AWAITING QA | 80% | W5,W24 | W24: drift (PSI share) + realised decay alerts, ml_health_check, monitor rule | QA | Independent QA
163 | AI/ML | ML-10 | AI/ML | Explainability | DEPLOYED - AWAITING QA | 85% | W5,W24 | W24: exact path contributions for trees, gain importances, out-of-sample permutation importance | QA | Independent QA
164 | AI/ML | ML-05 | AI/ML | Regime detection | DEPLOYED - AWAITING QA | 75% | W5,W24 | W24: market_regime model preset validated + trained (NO_EDGE on smoke) | Owner decides regime provider after evidence | Independent QA; Owner: Regime provider (after evidence)
165 | AI/ML | ML-03 | AI/ML | Unsupervised learning | DEPLOYED - AWAITING QA | 75% | W24 | W24: k-means++ factor clusters with profiles; return PCA | QA | Independent QA
166 | AI/ML | ML-06 | AI/ML | Anomaly detection | DEPLOYED - AWAITING QA | 75% | W24 | W24: robust-z + multivariate anomaly scan, CA-explained, post-market (flag off) | Owner: ml.anomalies_enabled | Independent QA; Owner: ml.anomalies_enabled
182 | Risk & Portfolio | RK-06 | Risk Management | Sector limits | DEPLOYED - VERIFIED | 80% | W4 | max_sector_exposure_pct in the W4 risk engine (NSE industry from cached Nifty 500 list; fails closed when unavailable) | Validate
185 | Risk & Portfolio | RK-18 | Risk Management | Strategy risk budget | DEPLOYED - VERIFIED | 75% | W4 | max_strategy_exposure_pct + strategy_drawdown_limit_pct from per-strategy fill attribution | Per-strategy capital budgets
186 | Risk & Portfolio | RK-01 | Risk Management | Kill switch scopes + auto-trigger | DEPLOYED - VERIFIED | 80% | Baseline | Global flag file + config | Per-strategy/symbol; auto-trigger
224 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | DEPLOYED - AWAITING QA | 75% | W24 | W24: model + factor IC decay monitoring with alerts | Needs factor history (W22 backfill) | Independent QA
234 | Enterprise SaaS (final objective) | ENT-05 | Security | Session management | DEPLOYED - VERIFIED | 90% | W8 | Sessions (digest-only, expiry, revoke) + W8 refresh tokens: rotation on every use, reuse detection revokes the family and all sessions, HttpOnly cookie scoped to /api/auth/refresh | Validate
244 | Enterprise SaaS (final objective) | ENT-19 | Channels | Watchlists | DEPLOYED - VERIFIED | 75% | W7 | Per-user / shared watchlists | Validate
259 | Production hardening | SEC-06 | Security | API security hardening | DEPLOYED - VERIFIED | 80% | W8 | OpsMiddleware: 2 MB limit (413), JSON content-type/parse checks (415/400), optional token-bucket rate limit (429), nosniff/DENY/no-referrer/COOP/Permissions-Policy, no-store on auth/account/admin, HSTS only with TLS, CORS only when origins configured | Enable rate limiting in production config
260 | Production hardening | OPS-08 | Deployment/Ops | Configuration management | DEPLOYED - VERIFIED | 80% | W8 | ATIP_ENV / environment (development/test/staging/production), config.<env>.json overlay, ATIP__SECTION__KEY overrides, validation (production refuses to start on errors), fingerprint + ops_config_version + audit of changed keys, feature flags | Validate
261 | Production hardening | OPS-09 | Deployment/Ops | Scheduler hardening | DEPLOYED - VERIFIED | 80% | W8 | ops_job_lock per job name (stale-owner takeover), scheduler heartbeat every 60 s, SKIPPED run when another runner holds the job, job metrics | Validate
263 | Production hardening | MON-09 | Monitoring | Operational alerting | DEPLOYED - VERIFIED | 75% | W1,W8 | ops_monitor every 15 min, 12 rules, FIRING/RESOLVED state with 6 h re-notify, delivered via the W1 alert channel (alert_log + Telegram when configured) | Tune thresholds after observation
264 | Production hardening | RK-19 | Risk | Stale-data trade protection | DEPLOYED - VERIFIED | 80% | W8 | Risk check market_data_fresh (BUY rejected when last bar > 2 sessions behind); LIVE orders validated against the NSE session; live gate additionally requires environment production | Validate
266 | Production hardening | RK-20 | Risk | Unified live-trading master switch | DEPLOYED - VERIFIED | 90% | W1,W4,W9 | W1 real orders (order rules, aggressive strategy) also require execution.live_trading_enabled + environment production (BLOCKED_LIVE_DISABLED otherwise); W4 gate + Dhan adapter refusal unchanged | Validate
267 | Wealth track (Waves 11-20) | INV-001 | Wealth | Investor DNA | DEPLOYED - AWAITING QA | 80% | W11 | W11: Risk capacity / tolerance / requirement, horizon, behaviour, personality | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
268 | Wealth track (Waves 11-20) | WLT-001 | Wealth | Multi-asset wealth dashboard | DEPLOYED - AWAITING QA | 80% | W12 | W12: Unified holdings, net worth, allocation, concentration, overlay | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
269 | Wealth track (Waves 11-20) | GOL-001 | Wealth | Goal planning engine | DEPLOYED - AWAITING QA | 80% | W13 | W13: Corpus, contributions, CAGR, shortfall, Monte Carlo, scenarios | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
270 | Wealth track (Waves 11-20) | AAL-001 | Wealth | Dynamic asset allocation | DEPLOYED - AWAITING QA | 80% | W14 | W14: Strategic + tactical from DNA, goals, regime, ATIP signals | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
271 | Wealth track (Waves 11-20) | RBL-001 | Wealth | Portfolio rebalancing | DEPLOYED - AWAITING QA | 80% | W15 | W15: Drift, triggers, cost-aware plans (tax-neutral) | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
272 | Wealth track (Waves 11-20) | PERF-001 | Wealth | Investor performance attribution | DEPLOYED - AWAITING QA | 80% | W15.5 | W15.5: Model / executable / actual / benchmark; attribution; audit; export | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
273 | Wealth track (Waves 11-20) | AIA-001 | Wealth | AI investment advisor | DEPLOYED - AWAITING QA | 80% | W16 | W16: Evidence-backed, suitability-checked; optional Claude narration | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
274 | Wealth track (Waves 11-20) | INT-001 | Wealth | Integrated intelligence | DEPLOYED - AWAITING QA | 80% | W17 | W17: Investor cycle, overview, modes, signal suitability | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
277 | Wealth track (Waves 11-20) | REL-001 | Wealth | Wealth production hardening | DEPLOYED - AWAITING QA | 80% | W20 | W20: Migration 0005, /health/wealth, monitor, backup, docs, RC | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA

## Developed not deployed
Seq | Phase Name | ID | Module | Feature | Delivery Status | Completion % | Waves | Current Implementation | Next Action / Missing Work | Needs
177 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | DEVELOPED - NOT DEPLOYED | 90% | W4,W25 | W25: portfolio/risk.py book_snapshot for PAPER and LIVE books (weights, % equity, sector exposure); /api/risk/portfolio; /trading Portfolio risk panel | Independent QA | Independent QA; Deploy (restart onto ATIP-W25-RC1)
178 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | DEVELOPED - NOT DEPLOYED | 90% | W25 | W25: concentration() max/top-5 weight, HHI, effective N, sector HHI; in /api/risk/portfolio and snapshots | Independent QA | Independent QA; Deploy (restart onto ATIP-W25-RC1)
179 | Risk & Portfolio | PF-09 | Portfolio | Correlation | DEVELOPED - NOT DEPLOYED | 90% | W6,W25 | W25: portfolio correlation matrix, weighted avg pairwise correlation, high pairs, diversification ratio; heatmap on /trading | Independent QA | Independent QA; Deploy (restart onto ATIP-W25-RC1)
180 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | DEVELOPED - NOT DEPLOYED | 85% | W4,W25 | W25: W4 limit max_avg_correlation (value-weighted correlation of the new symbol with the held book; fail closed); analytics in /api/risk/portfolio | Independent QA; owner sets the limit (default off) | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit (off)
181 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | DEVELOPED - NOT DEPLOYED | 85% | W4,W25 | W25: historical / parametric / Monte Carlo VaR and ES, 95/99%, 1 and 10 days; W4 limit max_portfolio_var_pct (post-trade); snapshot job + VaR alert (off by default) | Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit / enable snapshot (off)
183 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | DEVELOPED - NOT DEPLOYED | 85% | W4,W25 | W25: W4 limit max_symbol_volatility_pct (annualised 60-session vol; fail closed) | Independent QA; owner sets the limit (default off) | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit (off)
184 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | DEVELOPED - NOT DEPLOYED | 85% | W1,W4,W25 | W25: W4 cap max_adv_participation_pct (qty <= % of 20-session ADV) and W1 risk_limits.max_adv_participation_pct (BUY and SELL, unmeasurable -> refused) | Independent QA; owner sets the limit (default off) | Independent QA; Deploy (restart onto ATIP-W25-RC1); Owner: Set limit (off)
187 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | DEVELOPED - NOT DEPLOYED | 85% | W4,W25 | W25: portfolio/emergency.py plan + confirm code (10 min) -> kill switch ON, cancel open W4 orders, sell PAPER book; LIVE = sell list only, never an order; /api/risk/emergency-exit (risk:approve); dashboard button | Independent QA | Independent QA; Deploy (restart onto ATIP-W25-RC1)
188 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | DEVELOPED - NOT DEPLOYED | 85% | W6,W25 | W25: portfolio/optimize.py min_variance / mean_variance / max_sharpe / risk_parity; long-only, max/min weight, sector caps (FISTA + exact Dykstra projection); shrunk covariance; frontier; stored runs | Independent QA; expected-return model review | Independent QA; Deploy (restart onto ATIP-W25-RC1)
189 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | DEVELOPED - NOT DEPLOYED | 80% | W6,W25 | W25: rebalance_plan (NEW/ADD/REDUCE/EXIT/HOLD, band, min trade, costs, turnover); portfolio strategy kind reweight_band_pct emits ADD/REDUCE with exact quantity | Independent QA; backtest engine still trades whole positions | Independent QA; Deploy (restart onto ATIP-W25-RC1)
190 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | DEVELOPED - NOT DEPLOYED | 85% | W25 | W25: risk_attribution per position / sector variance share, component VaR, beta, systematic vs idiosyncratic | Independent QA | Independent QA; Deploy (restart onto ATIP-W25-RC1)
191 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | DEVELOPED - NOT DEPLOYED | 75% | W25 | W25: holdings-based contribution by position / sector, beta-alpha split vs NIFTY50, Brinson allocation/selection vs equal-weighted universe | Independent QA; trade-based attribution needs a LIVE trade ledger | Independent QA; Deploy (restart onto ATIP-W25-RC1)
192 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | DEVELOPED - NOT DEPLOYED | 70% | W15.5,W25 | W25: CAGR from pnl_daily equity; PAPER book + per-position XIRR from paper fills (wealth ledger XIRR in W15.5) | Independent QA; LIVE XIRR needs a trade ledger | Independent QA; Deploy (restart onto ATIP-W25-RC1)
193 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | DEVELOPED - NOT DEPLOYED | 85% | W4,W25 | W25: /trading Portfolio risk panels: KPIs, VaR/ES table, concentration, risk contribution, correlation heatmap, performance attribution, emergency exit | Independent QA | Independent QA; Deploy (restart onto ATIP-W25-RC1)

## In Progress
Seq | Phase Name | ID | Module | Feature | Delivery Status | Completion % | Waves | Current Implementation | Next Action / Missing Work | Needs
74 | Foundation | DP-15 | Data Platform | Fundamentals | IN PROGRESS | 30% |  | Screener.in fetcher; ingestion disabled | Your decision; enable; quarterly store; no 50.0 default | Owner: Enable fundamentals ingestion
75 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | IN PROGRESS | 20% |  | Default 50 when unparsed | Implement FS formula on real data | Development
76 | Foundation | SC-02 | Alpha/Factor Engine | SPI | IN PROGRESS | 30% |  |  | Implement SPI formula separately from FS | Development
91 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | IN PROGRESS | 60% |  | Index WebSocket 09:00-15:45 + quote cache; stock tick feed never run | Stock-level live feed in production; failover | Development
133 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | IN PROGRESS | 55% |  | Options/PCR frozen; news rule-based | Real PCR; AI news later | Development
136 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | IN PROGRESS | 60% |  | In index strip | Dedicated pre-open view | Development
137 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | IN PROGRESS | 70% |  | 13 yfinance tickers | Bond yields; history depth | Development
139 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | IN PROGRESS | 25% |  | Bulk/block only | Promoter/SAST/PIT/MF feeds | Development
140 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | IN PROGRESS | 40% |  | FII + bulk only | Add MF/promoter/insider | Development
141 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | IN PROGRESS | 40% |  | Feeds INS | Validate with IC | Development
153 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | IN PROGRESS | 60% |  | Scheduled 12:30 and 14:45 | Use stored intraday bars | Development
154 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | IN PROGRESS | 40% |  | CRI per-stock column only | Dedicated lists | Development
155 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | IN PROGRESS | 30% | W4 | /strategies list shows latest signals; per-strategy P&L from W4 fills on /trading | Performance panel | Development
167 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | IN PROGRESS | 60% | W4,W5 | ml_* strategy features (point in time, out of sample); ml_direction / atip_ml_blend (DRAFT); W4 risk check ml_model_active blocks signals of non-ACTIVE models | Activate once a model is ACTIVE | Owner: Activate a model (after evidence)
168 | AI/ML | NS-02 | News/Sentiment | News classification | IN PROGRESS | 30% |  | Claude classifier coded; key unset | Set key; taxonomy; cost cap | Owner: Working Anthropic API key (current key 401)
169 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | IN PROGRESS | 40% |  | Rule-based; confidence frozen 50 | Model-based scoring | Development
171 | AI/ML | NS-04 | News/Sentiment | AI news summary | IN PROGRESS | 50% |  | Headline list | LLM summary | Development
172 | AI/ML | DB-06 | Dashboard | AI News Summary panel | IN PROGRESS | 50% |  | News panel (rule-based) | Show AI summary | Development
176 | AI/ML | DB-18 | Dashboard | Quant/model panel | IN PROGRESS | 40% | W5 | /ml page: models, versions, lifecycle, predictions, feature sets, datasets, training runs | Monitoring charts | Development
194 | Execution | EX-02 | Execution | Order types | IN PROGRESS | 60% | W4 | W4 OMS: MARKET and LIMIT through the paper adapter; order type from config | Stop-loss / stop-limit order types | Development
195 | Execution | EX-08 | Execution | Order modify/cancel | IN PROGRESS | 50% | W4 | Cancel with explicit CANCEL_PENDING state; status refresh; no modify | Order modify | Development
196 | Execution | BR-05 | Broker Integration | Execution reconciliation | IN PROGRESS | 30% |  | Partial reconcile code | EOD reconciliation job + alert | Development
197 | Execution | BR-06 | Broker Integration | Connection health | IN PROGRESS | 40% |  | broker-status route; WS stall detection | Health checks + alerts | Development
198 | Execution | RK-17 | Risk Management | Broker/operational risk | IN PROGRESS | 50% | W4 | Kill switch + live-trading gate + broker failure -> FAILED order state with context | Broker health / stale-data checks | Development
199 | Execution | BR-08 | Broker Integration | Sandbox | IN PROGRESS | 30% |  | SANDBOX env defined | Verify sandbox path end-to-end | Development
200 | Execution | EX-09 | Execution | Measured slippage | IN PROGRESS | 30% | W4 | Fill price and decision reference price stored per order/fill (slippage derivable) | Slippage metric + report | Development
201 | Execution | EX-10 | Execution | Execution analytics | IN PROGRESS | 30% | W4 | oms_order / oms_order_event / oms_execution / oms_fill audit tables and APIs | Fill-rate / slippage / rejection analytics | Development
202 | Execution | BR-02 | Broker Integration | Zerodha/Kite | IN PROGRESS | 50% |  | Holdings sync only | Token refresh; orders if wanted | Development
203 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | IN PROGRESS | 25% |  | Dashboard partial | Live P&L panel | Development
204 | Execution | SEC-03 | Security | Audit logging | IN PROGRESS | 85% | W8 | enterprise_audit hash chain (prev_hash/row_hash, verify_chain) + append-only triggers on enterprise_audit and oms_order_event; mutating API requests audited even with the enterprise layer off; config changes and secret rotations audited | Export / retention; off-box audit copy | Development
207 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | IN PROGRESS | 25% | W6 | Intraday features from live_quotes; tick/depth pending | Tick / depth feed | Development
209 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | IN PROGRESS | 40% | W6 | Volatility estimators and regime; IV needs options data | Options data | Development
210 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | IN PROGRESS | 70% | W3,W6 | Pairs registry, spreads, cointegration screen, W3 pairs kind (short leg not executable) | Shortable instrument | Development
211 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | IN PROGRESS | 65% | W6 | Cross-sectional ranking + portfolio kind with dollar/beta/sector neutrality (shorts not executable) | Shortable instrument | Development
212 | Advanced Quant | QR-09 | Quant Research | Event-driven research | IN PROGRESS | 45% | W6 | market_event from corporate_actions + bulk_deals; ev_* strategy features; typed interface for pending sources | Earnings/dividend/macro sources | Development
213 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | IN PROGRESS | 50% | W6 | Value/quality/growth factors + vqm / vqmg composites (fundamental_data empty) | Fundamentals ingestion | Development
225 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | IN PROGRESS | 60% | W8 | Verified daily backups + retention; DR runbook with RPO 24 h / RTO ~10 min; pre-release backup procedure | Off-site backup target; scheduled restore drill; backup encryption | Development
226 | Production Hardening | SEC-04 | Security | Encryption | IN PROGRESS | 50% | W8 | AES-256-GCM field encryption (ops/crypto.py, key from ATIP_ENCRYPTION_KEY, AAD-bound, no plaintext fallback); used for MFA secrets; sensitive-field classification; TLS 1.3 reverse-proxy architecture documented (ATIP stays on 127.0.0.1) | Encrypt broker credentials (ENT-06); key rotation re-encryption; TLS only with ENT-07 | Development
227 | Production Hardening | API-05 | APIs | API contracts/docs | IN PROGRESS | 40% | W8 | Error envelope + codes, versioning, pagination, idempotency and security headers documented | Generated API reference | Development
229 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | IN PROGRESS | 60% | W8 | W8 set: production architecture, security, observability, DR, backup/restore, deployment, rollback, operations runbook, production configuration | User guide; API reference | Development
230 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | IN PROGRESS | 60% | W3,W6,W7 | Tenants + lifecycle + limits; tenant_id on tenant-owned W3-W6 tables; middleware isolation (single-resource 404, list filtering, create stamping); single shared paper book | Per-tenant paper books / broker accounts; SQL-level scoping | Development
233 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | IN PROGRESS | 85% | W8 | Users + 8 roles + 27 permissions, per-tenant roles, route->permission middleware; W8 TOTP MFA (enroll/confirm/disable, admin reset, login otp, encrypted secret, replay-refusing) | WebAuthn / recovery codes | Development
235 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | IN PROGRESS | 70% | W7 | Admin-created users (must change password), optional self-registration (PENDING + own FREE-trial tenant), activation, reset tokens; no e-mail | E-mail verification | Development
236 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | IN PROGRESS | 65% | W4,W7 | Profile + preferences; tenant/user trading profiles (trading enabled, modes, brokers, assets, strategies, capital, order value) — tighten W4 only | Per-user capital accounting | Development
241 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | IN PROGRESS | 40% | W7 | Multi-user sign-in (/login, /account, /admin) on the existing dashboard; still local-only | Blocked on ENT-07 for any exposure | Development
242 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | IN PROGRESS | 45% | W7 | Plans (limits/features, no invented prices), subscriptions, usage metering, DRAFT invoices; no payment gateway | Payment gateway (owner decision) | Owner: Payment gateway
243 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | IN PROGRESS | 40% | W7 | Multiple concurrent sessions per user with IP/user agent; revoke all | Device management UI | Development
245 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | IN PROGRESS | 55% | W3,W6,W7 | Per-user alert rules on any W3/W6 feature, evaluated post-market into notifications; AI alerts via ml_* features | Intraday evaluation | Development
246 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | IN PROGRESS | 45% | W7 | In-app inbox + preferences; Telegram (owner bot, default tenant only); no e-mail/SMS/push | E-mail / push channels | Development
248 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | IN PROGRESS | 55% | W8 | API keys with scopes; W8 /api/v1/* alias of the current API (API-Version header), pagination/sort/filter on v1 lists, standard error envelope, request ids | Per-route v1 contract (OpenAPI) and deprecation policy | Development
249 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | IN PROGRESS | 60% | W8 | Inbound POST /api/webhooks/{source}: HMAC-SHA256 signature, 300 s replay window, event-id dedupe; outbound signed delivery with backoff retry, DEAD letter, per-host circuit breaker | Business consumers (billing / broker postbacks); endpoint admin UI | Development
253 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | IN PROGRESS | 30% | W7 | Saved report definitions (tenant-owned); rendering reuses existing pages/APIs | Report rendering / export | Development
254 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | IN PROGRESS | 60% | W7 | /admin: users, tenants, roles, plans, audit; admin API | Richer console | Development
258 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | IN PROGRESS | 35% | W8 | Observability: JSON logs with request/correlation ids and secret masking, Prometheus-format metrics, health endpoints, monitoring rules; scalability path documented | HA / horizontal scale (needs DBS-05 Postgres) | Development
262 | Production hardening | OPS-10 | Deployment/Ops | Resilience + idempotency | IN PROGRESS | 60% | W8 | ops/resilience.py primitives (orders marked non-idempotent: never retried); Idempotency-Key on mutating API (orders from /trading keyed per decision/order) | Wrap existing data-source calls with breakers/retry | Development
265 | Production hardening | OPS-11 | Deployment/Ops | Release management & deployment | IN PROGRESS | 80% | W9 | Tag ATIP-W9-RC2; ops/release.py preflight/manifest/postcheck/record; deploy/deploy_release.ps1 + rollback_release.ps1 (dry-run default); requirements.lock.txt; release docs | Authorized deployment + first executed rollback drill | Development
275 | Wealth track (Waves 11-20) | QA-001 | Wealth | Wealth QA / security / performance | IN PROGRESS | 60% | W18 | W18: 70-test suite, security review (S1/S2 fixed), performance | Independent testing (ChatGPT) + UAT; merge after authorization | Development
276 | Wealth track (Waves 11-20) | UAT-001 | Wealth | Beta / UAT | IN PROGRESS | 60% | W19 | W19: Personas, persona view, feedback, UAT plan | Independent testing (ChatGPT) + UAT; merge after authorization | Development

## Yet To Start
Seq | Phase Name | ID | Module | Feature | Delivery Status | Completion % | Waves | Current Implementation | Next Action / Missing Work | Needs
132 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | YET TO START | 0% |  | None | NSE F&O bhavcopy + option chain store | Owner: Derivatives data source
170 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | YET TO START | 5% |  | None | Implement | Development
173 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | YET TO START | 0% |  | None | Implement | Development
174 | AI/ML | ML-02 | AI/ML | Deep learning | YET TO START | 0% |  | None | Only if validated benefit | Development
175 | AI/ML | ML-04 | AI/ML | Reinforcement learning | YET TO START | 0% |  | None | Low priority | Development
205 | Advanced Quant | DP-04 | Data Platform | Tick data | YET TO START | 5% |  | live_ticks exists; 0 rows | Tick ingestion + storage | Development
206 | Advanced Quant | DP-05 | Data Platform | Order book / depth | YET TO START | 5% |  | FULL feed type defined (CLI only) | Depth capture + schema | Development
208 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors | BLOCKED | 20% | W6 | Black-Scholes / greeks / IV / basis maths + schema; no derivatives data | Derivatives data source | Owner: Derivatives data source
214 | Advanced Quant | EX-11 | Execution | Execution algos | YET TO START | 0% |  | None | Implement | Development
215 | Advanced Quant | EX-12 | Execution | Market impact model | YET TO START | 0% |  | None | Implement | Development
216 | Advanced Quant | EX-15 | Execution | Latency telemetry | YET TO START | 0% |  | None | Instrument data and order paths | Development
217 | Advanced Quant | EX-16 | Execution | Event-driven OMS | YET TO START | 10% |  | Synchronous calls | Implement | Development
218 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | YET TO START | 0% |  | Bar loops only | Implement | Development
219 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | YET TO START | 0% |  | None | Macro connectors + calendar | Development
220 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | YET TO START | 0% |  | None | DataSource interface | Development
221 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | YET TO START | 0% |  | None | Add sources | Development
222 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | YET TO START | 5% |  | SQLite only | Parquet/DuckDB store | Development
223 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | YET TO START | 0% |  | Global display tickers only | MCX/CDS/bond/MF feeds | Development
228 | Production Hardening | API-06 | APIs | Widget JSON schemas | YET TO START | 5% |  | None | Define schemas | Development
231 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | YET TO START | 0% |  | SQLite | Migrate to Postgres | Owner: Move to Postgres
232 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure | BLOCKED | 5% | W7 | Not implemented by design: W7 keeps the 127.0.0.1 bind; exposure needs TLS, MFA, rate limiting, security review | Owner decision + security architecture | Owner: Security architecture + decision to expose
237 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | YET TO START | 0% | W7 | Not built: per-user broker credential vault (Claude does not handle credentials) | Design with the owner | Owner: Broker credential vault design
238 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | YET TO START | 0% |  | None | Legal review before offering to other users | Owner: Legal / SEBI review
239 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | YET TO START | 0% |  | None | Implement controls from ENT-14 | Development
240 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | YET TO START | 0% |  | None | Privacy policy + controls | Development
247 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | YET TO START | 0% |  | None | Build apps | Owner: Mobile apps
250 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | YET TO START | 0% |  | None | Importers | Development
251 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | YET TO START | 0% |  | None | Adapters behind BR-03 interface | Development
252 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | YET TO START | 0% |  | Equity cash only | Asset-specific execution/risk adapters | Development
255 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | YET TO START | 0% |  | None | Visual builder on SE-01 interface | Development
256 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | YET TO START | 0% |  | None | Implement | Development
257 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | YET TO START | 0% |  | Local Windows only | Containerise; IaC; environments | Owner: Cloud deployment