## Features
Seq | ID | Phase | Module | Feature | Status | Detailed status | Completion % | Reason / Remarks | Key files
1 | DP-02 | Delivered baseline (maintain) | Data Platform | Daily OHLCV history | Implemented | Completed | 90 | Maintain | data/bhavcopy.py; data/dhan.py
2 | DP-07 | Delivered baseline (maintain) | Data Platform | Delivery data | Implemented | Completed | 90 | Maintain | data/bhavcopy.py
3 | DP-20 | Delivered baseline (maintain) | Data Platform | Trading calendar | Implemented | Completed | 90 | Add next year's holidays each December | utils/trading_calendar.py
4 | TA-01 | Delivered baseline (maintain) | Technical Analysis | Core indicators | Implemented | Completed | 90 | Maintain | data/technical.py
5 | TA-02 | Delivered baseline (maintain) | Technical Analysis | Extended oscillators | Implemented | Completed | 80 | Maintain | data/technical.py
6 | TA-05 | Delivered baseline (maintain) | Technical Analysis | Fibonacci | Implemented | Completed | 80 | Optional: swing-anchored levels | data/technical.py
7 | TA-07 | Delivered baseline (maintain) | Technical Analysis | Trend features | Implemented | Completed | 80 | Maintain | data/technical.py
8 | TA-08 | Delivered baseline (maintain) | Technical Analysis | Relative strength | Implemented | Completed | 80 | Sector-relative RS later (TA-08b in Phase 2 if wanted) | scores/engine.py
9 | SC-03 | Delivered baseline (maintain) | Alpha/Factor Engine | RRI | Implemented | Completed | 75 | Institutional input improves with SC-14 | scores/engine.py
10 | SC-04 | Delivered baseline (maintain) | Alpha/Factor Engine | MRI | Implemented | Completed | 85 | Maintain | scores/engine.py
11 | SC-07 | Delivered baseline (maintain) | Alpha/Factor Engine | ZPI | Implemented | Completed | 80 | Maintain | scores/engine.py
12 | SC-10 | Delivered baseline (maintain) | Alpha/Factor Engine | Portfolio Health score | Implemented | Completed | 75 | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py
13 | PF-05 | Delivered baseline (maintain) | Portfolio | Portfolio health | Implemented | Completed | 75 | Maintain | scores/portfolio_health.py
14 | SC-11 | Delivered baseline (maintain) | Alpha/Factor Engine | Trade of the Day | Implemented | Completed | 80 | Maintain | scores/engine.py
15 | SC-15 | Delivered baseline (maintain) | Alpha/Factor Engine | Overall ATIP score + rank | Implemented | Completed | 80 | Maintain | scores/engine.py
16 | SC-17 | Delivered baseline (maintain) | Alpha/Factor Engine | Configurable weights | Implemented | Completed | 80 | Regime-specific rows used by ML-05 | db/schema.py
17 | SG-02 | Delivered baseline (maintain) | Signal Engine | Signal validation | Implemented | Completed | 75 | Maintain | pipeline/scheduler.py
18 | SG-03 | Delivered baseline (maintain) | Signal Engine | Signal ranking | Implemented | Completed | 85 | Maintain | scores/engine.py
19 | SG-05 | Delivered baseline (maintain) | Signal Engine | Trade plan | Implemented | Completed | 75 | Maintain | scores/predictions.py
20 | SG-06 | Delivered baseline (maintain) | Signal Engine | Outcome tracking | Implemented | Completed | 80 | Maintain | scores/signal_log.py
21 | SG-07 | Delivered baseline (maintain) | Signal Engine | Signal provenance log | Implemented | Completed | 80 | Maintain | scores/signal_log.py
22 | BT-01 | Delivered baseline (maintain) | Backtesting | Historical backtest | Implemented | Completed | 80 | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py
23 | BT-10 | Delivered baseline (maintain) | Backtesting | Win rate / profit factor / expectancy | Implemented | Completed | 90 | Maintain | strategy/backtest_aggressive.py
24 | RK-02 | Delivered baseline (maintain) | Risk Management | Max order value | Implemented | Completed | 90 | Set values in config.json | orders/risk.py
25 | RK-03 | Delivered baseline (maintain) | Risk Management | Max orders per day | Implemented | Completed | 90 | Set values in config.json | orders/risk.py
26 | RK-04 | Delivered baseline (maintain) | Risk Management | Max open positions | Implemented | Completed | 90 | Set values in config.json | orders/risk.py
27 | RK-05 | Delivered baseline (maintain) | Risk Management | Symbol exposure limit | Implemented | Completed | 90 | Set values in config.json | orders/risk.py
28 | RK-14 | Delivered baseline (maintain) | Risk Management | Crash-risk gating | Implemented | Completed | 75 | Maintain | scores/engine.py
29 | EX-03 | Delivered baseline (maintain) | Execution | Position management | Implemented | Completed | 75 | Maintain | strategy/positions.py
30 | EX-04 | Delivered baseline (maintain) | Execution | Entry/exit | Implemented | Completed | 70 | Maintain | strategy/live.py
31 | EX-05 | Delivered baseline (maintain) | Execution | Stop loss | Implemented | Completed | 75 | Maintain | strategy/aggressive.py
32 | EX-06 | Delivered baseline (maintain) | Execution | Trailing stop | Implemented | Completed | 80 | Maintain | strategy/aggressive.py
33 | EX-07 | Delivered baseline (maintain) | Execution | Profit booking / partial exit | Implemented | Completed | 70 | Maintain | strategy/aggressive.py
34 | EX-13 | Delivered baseline (maintain) | Execution | Paper trading | Implemented | Completed | 85 | Maintain | orders/paper.py
35 | EX-14 | Delivered baseline (maintain) | Execution | Live gating | Implemented | Completed | 85 | Maintain | orders/environment.py
36 | BR-01 | Delivered baseline (maintain) | Broker Integration | Dhan | Implemented | Completed | 80 | Maintain | data/dhan.py; orders/broker.py
37 | BR-03 | Delivered baseline (maintain) | Broker Integration | Broker abstraction | Implemented | Completed | 75 | Becomes multi-broker interface in ENT-15 | orders/environment.py
38 | DB-01 | Delivered baseline (maintain) | Dashboard | Market Health panel | Implemented | Completed | 80 | Maintain | dashboard/server.py
39 | DB-02 | Delivered baseline (maintain) | Dashboard | Global Markets panel | Implemented | Completed | 75 | Maintain | dashboard/server.py
40 | DB-03 | Delivered baseline (maintain) | Dashboard | FII/DII panel | Implemented | Completed | 75 | Maintain | dashboard/server.py
41 | DB-05 | Delivered baseline (maintain) | Dashboard | Sector Rotation | Implemented | Completed | 70 | Maintain | dashboard/server.py
42 | DB-07 | Delivered baseline (maintain) | Dashboard | Top 25 VPI | Implemented | Completed | 85 | Maintain | dashboard/server.py
43 | DB-08 | Delivered baseline (maintain) | Dashboard | Buy Zone (ZPI) | Implemented | Completed | 85 | Maintain | dashboard/server.py
44 | DB-09 | Delivered baseline (maintain) | Dashboard | Recovery (RRI) | Implemented | Completed | 80 | Maintain | dashboard/server.py
45 | DB-10 | Delivered baseline (maintain) | Dashboard | Momentum Reversal (MRI) | Implemented | Completed | 80 | Maintain | dashboard/server.py
46 | DB-12 | Delivered baseline (maintain) | Dashboard | Portfolio Health panel | Implemented | Completed | 80 | Maintain | dashboard/server.py
47 | DB-13 | Delivered baseline (maintain) | Dashboard | Trade of the Day | Implemented | Completed | 85 | Maintain | dashboard/server.py
48 | DB-15 | Delivered baseline (maintain) | Dashboard | Orders/signals panel | Implemented | Completed | 70 | Maintain | dashboard/server.py
49 | DB-19 | Delivered baseline (maintain) | Dashboard | Hosted read-only snapshot | Implemented | Completed | 80 | Superseded by ENT-08 web app | publish_snapshot.py
50 | API-01 | Delivered baseline (maintain) | APIs | Internal REST | Implemented | Completed | 70 | Maintain | dashboard/server.py
51 | API-02 | Delivered baseline (maintain) | APIs | Local API authentication | Implemented | Completed | 80 | Replaced by per-user auth in SEC-02 | dashboard/security.py
52 | DBS-01 | Delivered baseline (maintain) | Database | Schema | Implemented | Completed | 75 | Migrations via DBS-04 | db/schema.py
53 | DBS-02 | Delivered baseline (maintain) | Database | Retention/purge | Implemented | Completed | 70 | Maintain | db/purge.py
54 | SEC-01 | Delivered baseline (maintain) | Security | Credential handling | Implemented | Completed | 85 | Move legacy plaintext keys out of config.json (owner action) | ops/secrets.py; ops/logs.py
55 | MON-07 | Delivered baseline (maintain) | Monitoring | Feed health | Implemented | Completed | 70 | Maintain | data/dhan_ws.py
56 | MON-08 | Delivered baseline (maintain) | Monitoring | Diagnostics | Implemented | Completed | 80 | Validate | ops/health.py; dashboard/ops_routes.py
57 | OPS-01 | Delivered baseline (maintain) | Deployment/Ops | Autostart/scheduling | Implemented | Completed | 75 | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml
58 | OPS-07 | Delivered baseline (maintain) | Deployment/Ops | Snapshot publishing | Implemented | Completed | 80 | Maintain | publish_snapshot.py
59 | DP-09 | Foundation | Data Platform | India VIX | Implemented | Completed | 95 | None for DP-09; VIX term structure/percentile features belong to later factor work | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py
60 | DP-17 | Foundation | Data Platform | Market breadth | Implemented | Completed | 90 | Survivorship-free universe (BT-15); sector-level breadth (DP-13) | scores/engine.py; db/schema.py
61 | SC-09 | Foundation | Alpha/Factor Engine | Market Health score | Implemented | Completed | 90 | FII/DII and global history only from 2026-07 (backfilled coverage avg 0.65); determine_signal still defaults a missing MH to 50; model-based regime is ML-05 | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py
62 | SC-08 | Foundation | Alpha/Factor Engine | ACS | Implemented | Completed | 85 | NewsConfidence stays absent until NS-02 (Anthropic key) classifies news | scores/engine.py; data/news.py; db/schema.py
63 | MON-01 | Foundation | Monitoring | Job logging | Implemented | Completed | 90 | Record failures, end time, row counts | pipeline/scheduler.py; db/schema.py
64 | MON-02 | Foundation | Monitoring | Stalled-job detection | Implemented | Completed | 85 | Expected-run table + missed-run check | pipeline/health.py; pipeline/scheduler.py
65 | MON-03 | Foundation | Monitoring | Failure alerting | Implemented | Completed | 85 | Configure Telegram; alert on failure/stall | alerts/telegram.py; dashboard/server.py
66 | DB-14 | Foundation | Dashboard | Alerts / morning brief | Implemented | Completed | 80 | Deliver digest; verify daily | alerts/telegram.py
67 | RK-15 | Foundation | Risk Management | Risk alerts | Implemented | Completed | 80 | Alert on halt, limit breach, CRI spike | orders/risk.py; orders/broker.py
68 | MON-06 | Foundation | Monitoring | Log rotation | Implemented | Completed | 90 | RotatingFileHandler | main.py
69 | DBS-06 | Foundation | Database | Timestamp consistency | Implemented | Completed | 85 | Normalise; fix news recency | db/schema.py; data/news.py; tools/repair_news_timezone.py
70 | NS-01 | Foundation | News/Sentiment | News ingestion | Implemented | Completed | 80 | Fix job; add second source; health check | data/news.py; pipeline/scheduler.py
71 | OPS-03 | Foundation | Deployment/Ops | Install/setup | Implemented | Completed | 85 | Fix requirements/setup; pin versions | setup.py; install.bat; requirements-dev.txt; docs/DEV_SETUP.md
72 | EX-01 | Foundation | Execution | Order management tests | Implemented | Completed | 70 | Unit tests for rules.py | orders/rules.py; tests/
73 | OPS-02 | Foundation | Deployment/Ops | CI + end-to-end test | Implemented | Completed | 70 | Add E2E pipeline test | .github/workflows/tests.yml; tests/
77 | SC-05 | Foundation | Alpha/Factor Engine | CRI debt input | Implemented | Completed | 75 | Feed Debt/Equity | scores/engine.py
78 | SC-01 | Foundation | Alpha/Factor Engine | VPI inputs | Implemented | Completed | 80 | Real Fundamental Growth input | scores/engine.py
79 | PF-01 | Foundation | Portfolio | Portfolio ingestion | Implemented | Completed | 80 | Scheduled reliable sync + token handling | data/dhan.py; portfolio/zerodha.py
80 | BR-04 | Foundation | Broker Integration | Portfolio sync schedule | Implemented | Completed | 80 | Scheduled sync with alert on failure | pipeline/scheduler.py; pipeline/health.py
81 | PF-02 | Foundation | Portfolio | Holdings & P&L | Implemented | Completed | 80 | Realised + unrealised P&L | portfolio/pnl.py; dashboard/server.py
82 | PF-13 | Foundation | Portfolio | Daily P&L series | Implemented | Completed | 85 | Daily P&L table; EOD job | portfolio/pnl.py; db/schema.py
83 | RK-13 | Foundation | Risk Management | Risk-based sizing wired to orders | Implemented | Completed | 85 | Use size in order path | orders/risk.py; orders/rules.py
84 | RK-07 | Foundation | Risk Management | Daily loss limit | Implemented | Completed | 85 | Limit on PF-13; auto-halt | orders/risk.py
85 | RK-08 | Foundation | Risk Management | Drawdown limit | Implemented | Completed | 85 | Peak-to-trough on PF-13; auto-halt | orders/risk.py
86 | DBS-03 | Foundation | Database | Backups | Implemented | Completed | 85 | Off-machine copy of backups; restore drill | ops/backup.py; docs/BACKUP_RESTORE.md
87 | DP-06 | Foundation | Data Platform | Corporate actions open items | Implemented | Completed | 85 | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py
88 | TA-06 | Foundation | Technical Analysis | Support/Resistance | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA; optionally feed the Technical Score SR component | data/technical_ext.py
89 | DP-19 | Foundation | Data Platform | Data quality layer | Implemented | Completed | 85 | DQS table; outlier and timestamp checks | data/quality.py; pipeline/scheduler.py
90 | DBS-04 | Quant Research (data, factors, backtesting) | Database | Schema migrations | Implemented | Completed | 80 | Down-migration scripts beyond rollback notes (policy: restore pre-release backup) | ops/migrations.py; db/schema.py
92 | DP-03 | Quant Research (data, factors, backtesting) | Data Platform | Intraday bars | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA; consider 5-min bars for session VWAP | data/dhan.py; db/schema.py; db/purge.py
93 | TA-03 | Quant Research (data, factors, backtesting) | Technical Analysis | VWAP | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Owner: technical.vwap_in_score (changes scores); QA | data/technical_ext.py; data/technical.py
94 | SC-12 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Technical Score VWAP input | Implemented | Completed | 75 | Include VWAP | data/technical.py
95 | TA-04 | Quant Research (data, factors, backtesting) | Technical Analysis | Volume Profile | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | data/technical_ext.py
96 | TA-10 | Quant Research (data, factors, backtesting) | Technical Analysis | Multi-timeframe analysis | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | data/technical_ext.py
97 | TA-12 | Quant Research (data, factors, backtesting) | Technical Analysis | Full-history indicator panel | Implemented | Implemented But Not Verified | 70 | Built; awaiting independent testing. Run the backfill (owner timing; copy first) | data/technical.py
98 | AF-03 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Factor panel persistence | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | scores/engine.py; scores/formulas.py
99 | AF-04 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Standalone factor families | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA; research on full history | quant/factors.py
100 | AF-02 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Normalisation contract | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | quant/normalize.py
101 | AF-01 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Factor library/registry | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | quant/factors.py
102 | SC-18 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Formula registry/versioning | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | scores/formulas.py
103 | DBS-07 | Quant Research (data, factors, backtesting) | Database | Research registry tables | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | quant/studies.py
104 | QR-01 | Quant Research (data, factors, backtesting) | Quant Research | Information coefficient | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Run full-history backfill + report | quant/research.py
105 | QR-02 | Quant Research (data, factors, backtesting) | Quant Research | IC decay / half-life | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Run on full history | quant/research.py
106 | QR-03 | Quant Research (data, factors, backtesting) | Quant Research | Factor correlation/redundancy | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Run on full history | quant/research.py
107 | QR-04 | Quant Research (data, factors, backtesting) | Quant Research | Statistical toolkit | Implemented | Completed | 75 | Validate | quant/statarb.py; quant/normalize.py; quant/volatility.py
108 | AF-08 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Factor approval gate | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Owner: enable after review | quant/approval.py; strategy_engine/lifecycle.py
109 | BT-16 | Quant Research (data, factors, backtesting) | Backtesting | Dated equity curve / run records | Implemented | Completed | 85 | Dated trades + equity curve + run table | backtest/store.py; db/schema.py
110 | BT-08 | Quant Research (data, factors, backtesting) | Backtesting | Portfolio-level backtest | Implemented | Completed | 85 | Portfolio simulator | backtest/engine.py
111 | BT-09 | Quant Research (data, factors, backtesting) | Backtesting | Drawdown analysis | Implemented | Completed | 90 | Compute on equity curve | backtest/metrics.py
112 | BT-11 | Quant Research (data, factors, backtesting) | Backtesting | Sharpe/Sortino/CAGR/Calmar | Implemented | Completed | 90 | Implement | backtest/metrics.py
113 | BT-12 | Quant Research (data, factors, backtesting) | Backtesting | VaR/CVaR in backtest | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | backtest/metrics.py
114 | BT-05 | Quant Research (data, factors, backtesting) | Backtesting | Itemised costs | Implemented | Completed | 85 | Indian cost model shared by backtest and paper | backtest/costs.py; backtest/config.py
115 | BT-06 | Quant Research (data, factors, backtesting) | Backtesting | Slippage in backtest | Implemented | Completed | 90 | Shared slippage model | backtest/slippage.py
116 | BT-07 | Quant Research (data, factors, backtesting) | Backtesting | Liquidity constraints | Implemented | Completed | 85 | All engines | backtest/liquidity.py
117 | DP-18 | Quant Research (data, factors, backtesting) | Data Platform | Survivorship-free universe | Implemented | Completed | 80 | Store constituent history | data/index_constituents.py
118 | BT-15 | Quant Research (data, factors, backtesting) | Backtesting | Bias controls | Implemented | Completed | 80 | Systematic checks | backtest/data.py; backtest/engine.py
119 | BT-03 | Quant Research (data, factors, backtesting) | Backtesting | In/out-of-sample | Implemented | Completed | 85 | Formal splits | backtest/periods.py; backtest/service.py
120 | BT-02 | Quant Research (data, factors, backtesting) | Backtesting | Walk-forward | Implemented | Completed | 80 | Implement | backtest/walkforward.py
121 | BT-13 | Quant Research (data, factors, backtesting) | Backtesting | Monte Carlo | Implemented | Completed | 85 | Implement | backtest/montecarlo.py
122 | BT-04 | Quant Research (data, factors, backtesting) | Backtesting | Parameter optimisation | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA; optional true Bayesian search | backtest/optimize.py
123 | QR-11 | Quant Research (data, factors, backtesting) | Quant Research | Parameter sensitivity | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | backtest/sensitivity.py
124 | BT-14 | Quant Research (data, factors, backtesting) | Backtesting | Robustness | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | backtest/robustness.py
125 | QR-12 | Quant Research (data, factors, backtesting) | Quant Research | Reproducibility / experiment tracking | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | quant/experiments.py; quant/studies.py
126 | QR-07 | Quant Research (data, factors, backtesting) | Quant Research | Momentum/trend research | Implemented | Implemented But Not Verified | 70 | Built; awaiting independent testing. Run full-universe study; review | backtest/strategies.py; backtest/study.py
127 | QR-08 | Quant Research (data, factors, backtesting) | Quant Research | Mean-reversion research | Implemented | Implemented But Not Verified | 70 | Built; awaiting independent testing. Run full-universe study; review | backtest/strategies.py; backtest/study.py
128 | QR-13 | Quant Research (data, factors, backtesting) | Quant Research | Signal outcome research by regime | Implemented | Completed | 70 | Add regime/ACS buckets | scores/signal_log.py
129 | TA-09 | Quant Research (data, factors, backtesting) | Technical Analysis | Beta 3y / rolling 60 | Implemented | Implemented But Not Verified | 70 | Built; awaiting independent testing. Owner: prices_daily retention >= 1,100 days for a 3-year beta | data/technical_ext.py
130 | SC-16 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Beta Risk Index | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. QA; decide if it joins a composite | data/technical_ext.py
131 | TA-11 | Quant Research (data, factors, backtesting) | Technical Analysis | Extended indicator catalogue | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | data/technical_ext.py; data/technical.py
134 | DP-10 | Quant Research (data, factors, backtesting) | Data Platform | FII/DII history | Implemented | Completed | 80 | Historical backfill source | data/bhavcopy.py
135 | DP-11 | Quant Research (data, factors, backtesting) | Data Platform | GIFT Nifty | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. Pre-open panel (DB-04) | data/market_series.py
138 | DP-13 | Quant Research (data, factors, backtesting) | Data Platform | Sector data | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Run --backfill-sectors; QA | data/market_series.py; data/dhan.py
142 | SG-04 | Strategy Engine | Signal Engine | Rich decision states | Implemented | Completed | 80 | Extended states + stored reasons | strategy_engine/decisions.py
143 | SG-01 | Strategy Engine | Signal Engine | SELL calibration | Implemented | Completed | 70 | Backtest-based SELL thresholds | scores/engine.py
144 | SE-01 | Strategy Engine | Strategy Engine | Strategy library | Implemented | Completed | 85 | Strategy interface + registry | strategy_engine/definition.py; registry.py
145 | SE-02 | Strategy Engine | Strategy Engine | Strategy parameters | Implemented | Completed | 85 | Param store per strategy with versions | strategy_engine/params.py; registry.py
146 | SE-03 | Strategy Engine | Strategy Engine | Rule-based strategies | Implemented | Completed | 85 | Generic rule definition format | strategy_engine/rules.py; kinds.py
147 | SE-06 | Strategy Engine | Strategy Engine | Multi-factor strategy | Implemented | Completed | 85 | IC-weighted multi-factor strategy | strategy_engine/kinds.py
148 | SE-04 | Strategy Engine | Strategy Engine | Quant strategies | Implemented | Completed | 75 | Implement first quant strategies | strategy_engine/kinds.py; features.py
149 | SE-09 | Strategy Engine | Strategy Engine | Strategy lifecycle | Implemented | Completed | 85 | State machine + gates | strategy_engine/lifecycle.py
150 | SE-11 | Strategy Engine | Strategy Engine | Strategy health | Implemented | Completed | 75 | Health scoring + alerts | strategy_engine/health.py
151 | SE-07 | Strategy Engine | Strategy Engine | Strategy combination/ranking/selection | Implemented | Completed | 75 | Allocator | strategy_engine/selection.py; kinds.py
152 | SE-08 | Strategy Engine | Strategy Engine | Regime-aware selection | Implemented | Completed | 75 | Regime-conditional allocation | strategy_engine/selection.py; regime.py; library/regime_mapping.json
156 | ML-13 | AI/ML | AI/ML | Labels/targets | Implemented | Completed | 85 | Validate | ml/labels.py
157 | ML-07 | AI/ML | AI/ML | Feature selection | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | ml/selection.py
158 | ML-08 | AI/ML | AI/ML | Model validation | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | ml/validation.py
159 | ML-01 | AI/ML | AI/ML | Supervised ML | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Richer features / labels; full-universe validation | ml/trees.py; ml/presets.py
160 | ML-12 | AI/ML | AI/ML | Model registry/versioning | Implemented | Completed | 85 | Validate | ml/registry.py; ml/artifacts.py
161 | ML-11 | AI/ML | AI/ML | Ensemble models | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | ml/trees.py
162 | ML-09 | AI/ML | AI/ML | Model monitoring/drift | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. QA | ml/decay.py; ops/monitor.py
163 | ML-10 | AI/ML | AI/ML | Explainability | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. QA | ml/trees.py; ml/validation.py
164 | ML-05 | AI/ML | AI/ML | Regime detection | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. Owner decides regime provider after evidence | ml/presets.py
165 | ML-03 | AI/ML | AI/ML | Unsupervised learning | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. QA | ml/unsupervised.py
166 | ML-06 | AI/ML | AI/ML | Anomaly detection | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. Owner: ml.anomalies_enabled | ml/unsupervised.py
177 | PF-03 | Risk & Portfolio | Portfolio | Exposure / sector allocation | Implemented | Implemented But Not Verified | 90 | Built; awaiting independent testing. Independent QA | portfolio/risk.py; dashboard/portfolio_risk_routes.py
178 | PF-04 | Risk & Portfolio | Portfolio | Concentration/diversification | Implemented | Implemented But Not Verified | 90 | Built; awaiting independent testing. Independent QA | portfolio/risk.py
179 | PF-09 | Risk & Portfolio | Portfolio | Correlation | Implemented | Implemented But Not Verified | 90 | Built; awaiting independent testing. Independent QA | portfolio/risk.py; dashboard/execution_page.py
180 | RK-11 | Risk & Portfolio | Risk Management | Correlation risk | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA; owner sets the limit (default off) | execution/risk_engine.py; portfolio/limits.py
181 | RK-12 | Risk & Portfolio | Risk Management | Portfolio VaR/ES | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | portfolio/risk.py; portfolio/limits.py; execution/risk_engine.py
182 | RK-06 | Risk & Portfolio | Risk Management | Sector limits | Implemented | Completed | 80 | Validate | execution/risk_engine.py; execution/positions.py
183 | RK-09 | Risk & Portfolio | Risk Management | Volatility limits | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA; owner sets the limit (default off) | execution/risk_engine.py; execution/config.py; portfolio/limits.py
184 | RK-10 | Risk & Portfolio | Risk Management | Liquidity limits | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA; owner sets the limit (default off) | execution/risk_engine.py; orders/risk.py; portfolio/limits.py
185 | RK-18 | Risk & Portfolio | Risk Management | Strategy risk budget | Implemented | Completed | 75 | Per-strategy capital budgets | execution/risk_engine.py; execution/positions.py
186 | RK-01 | Risk & Portfolio | Risk Management | Kill switch scopes + auto-trigger | Implemented | Completed | 80 | Per-strategy/symbol; auto-trigger | orders/risk.py
187 | RK-16 | Risk & Portfolio | Risk Management | Emergency exit | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA | portfolio/emergency.py; dashboard/portfolio_risk_routes.py
188 | PF-10 | Risk & Portfolio | Portfolio | Portfolio optimisation | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA; expected-return model review | portfolio/optimize.py
189 | PF-06 | Risk & Portfolio | Portfolio | Rebalancing | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent QA; backtest engine still trades whole positions | portfolio/optimize.py; strategy_engine/kinds.py; strategy_engine/engine.py
190 | PF-07 | Risk & Portfolio | Portfolio | Risk attribution | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA | portfolio/risk.py
191 | PF-08 | Risk & Portfolio | Portfolio | Performance attribution | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. Independent QA; trade-based attribution needs a LIVE trade ledger | portfolio/risk.py
192 | PF-11 | Risk & Portfolio | Portfolio | CAGR/XIRR analytics | Implemented | Implemented But Not Verified | 70 | Built; awaiting independent testing. Independent QA; LIVE XIRR needs a trade ledger | portfolio/risk.py; wealth/perf/metrics.py
193 | DB-17 | Risk & Portfolio | Dashboard | Risk dashboard | Implemented | Implemented But Not Verified | 85 | Built; awaiting independent testing. Independent QA | dashboard/execution_page.py
224 | MON-05 | Production Hardening | Monitoring | Model/factor decay monitoring | Implemented | Implemented But Not Verified | 75 | Built; awaiting independent testing. Needs factor history (W22 backfill) | ml/decay.py
234 | ENT-05 | Enterprise SaaS (final objective) | Security | Session management | Implemented | Completed | 90 | Validate | enterprise/users.py; dashboard/enterprise_routes.py
244 | ENT-19 | Enterprise SaaS (final objective) | Channels | Watchlists | Implemented | Completed | 75 | Validate | enterprise/workspace.py
259 | SEC-06 | Production hardening | Security | API security hardening | Implemented | Completed | 80 | Enable rate limiting in production config | ops/http.py
260 | OPS-08 | Production hardening | Deployment/Ops | Configuration management | Implemented | Completed | 80 | Validate | ops/config.py; ops/startup.py
261 | OPS-09 | Production hardening | Deployment/Ops | Scheduler hardening | Implemented | Completed | 80 | Validate | ops/jobs.py; pipeline/scheduler.py
263 | MON-09 | Production hardening | Monitoring | Operational alerting | Implemented | Completed | 75 | Tune thresholds after observation | ops/monitor.py
264 | RK-19 | Production hardening | Risk | Stale-data trade protection | Implemented | Completed | 80 | Validate | execution/risk_engine.py; execution/order_manager.py; execution/config.py
266 | RK-20 | Production hardening | Risk | Unified live-trading master switch | Implemented | Completed | 90 | Validate | orders/broker.py; ops/trading_safety.py
267 | INV-001 | Wealth track (Waves 11-20) | Wealth | Investor DNA | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/dna.py
268 | WLT-001 | Wealth track (Waves 11-20) | Wealth | Multi-asset wealth dashboard | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/holdings.py; wealth/assets.py
269 | GOL-001 | Wealth track (Waves 11-20) | Wealth | Goal planning engine | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/goals.py
270 | AAL-001 | Wealth track (Waves 11-20) | Wealth | Dynamic asset allocation | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/allocation.py
271 | RBL-001 | Wealth track (Waves 11-20) | Wealth | Portfolio rebalancing | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/rebalance.py
272 | PERF-001 | Wealth track (Waves 11-20) | Wealth | Investor performance attribution | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/perf/
273 | AIA-001 | Wealth track (Waves 11-20) | Wealth | AI investment advisor | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/advisor.py
274 | INT-001 | Wealth track (Waves 11-20) | Wealth | Integrated intelligence | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | wealth/integrated.py
277 | REL-001 | Wealth track (Waves 11-20) | Wealth | Wealth production hardening | Implemented | Implemented But Not Verified | 80 | Built; awaiting independent testing. Independent testing (ChatGPT) + UAT; merge after authorization | ops/migrations.py; wealth/health.py
74 | DP-15 | Foundation | Data Platform | Fundamentals | In progress | In Progress | 30 | Your decision; enable; quarterly store; no 50.0 default | data/fundamentals.py; pipeline/scheduler.py
75 | SC-13 | Foundation | Alpha/Factor Engine | Fundamental Score | In progress | In Progress | 20 | Implement FS formula on real data | data/fundamentals.py
76 | SC-02 | Foundation | Alpha/Factor Engine | SPI | In progress | In Progress | 30 | Implement SPI formula separately from FS | scores/engine.py
91 | DP-01 | Quant Research (data, factors, backtesting) | Data Platform | Live market data | In progress | In Progress | 60 | Stock-level live feed in production; failover | data/dhan_ws.py; data/dhan.py
133 | SC-06 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | MSI | In progress | In Progress | 55 | Real PCR; AI news later | scores/engine.py
136 | DB-04 | Quant Research (data, factors, backtesting) | Dashboard | GIFT Nifty panel | In progress | In Progress | 60 | Dedicated pre-open view | dashboard/server.py
137 | DP-12 | Quant Research (data, factors, backtesting) | Data Platform | Global markets | In progress | In Progress | 70 | Bond yields; history depth | data/markets.py
139 | DP-16 | Quant Research (data, factors, backtesting) | Data Platform | Institutional data | In progress | In Progress | 25 | Promoter/SAST/PIT/MF feeds | data/bhavcopy.py
140 | SC-14 | Quant Research (data, factors, backtesting) | Alpha/Factor Engine | Institutional Score | In progress | In Progress | 40 | Add MF/promoter/insider | scores/engine.py
141 | AD-03 | Quant Research (data, factors, backtesting) | Alternative Data | Bulk/block deal signal | In progress | In Progress | 40 | Validate with IC | data/bhavcopy.py
153 | SG-08 | Strategy Engine | Signal Engine | Intraday scans | In progress | In Progress | 60 | Use stored intraday bars | pipeline/scheduler.py
154 | DB-11 | Strategy Engine | Dashboard | Crash Risk + Top 25 SPI/MSI lists | In progress | In Progress | 40 | Dedicated lists | dashboard/server.py
155 | DB-16 | Strategy Engine | Dashboard | Strategy performance panel | In progress | In Progress | 30 | Performance panel | dashboard/strategy_page.py; dashboard/execution_page.py
167 | SE-05 | AI/ML | Strategy Engine | AI-driven strategies | In progress | In Progress | 60 | Activate once a model is ACTIVE | ml/strategy_features.py; execution/risk_engine.py; strategy_engine/library/50_*,51_*
168 | NS-02 | AI/ML | News/Sentiment | News classification | In progress | In Progress | 30 | Set key; taxonomy; cost cap | data/news.py
169 | NS-03 | AI/ML | News/Sentiment | Sentiment + confidence | In progress | In Progress | 40 | Model-based scoring | data/news.py
171 | NS-04 | AI/ML | News/Sentiment | AI news summary | In progress | In Progress | 50 | LLM summary | dashboard/server.py
172 | DB-06 | AI/ML | Dashboard | AI News Summary panel | In progress | In Progress | 50 | Show AI summary | dashboard/server.py
176 | DB-18 | AI/ML | Dashboard | Quant/model panel | In progress | In Progress | 40 | Monitoring charts | dashboard/ml_page.py
194 | EX-02 | Execution | Execution | Order types | In progress | In Progress | 60 | Stop-loss / stop-limit order types | execution/order_manager.py; execution/adapters.py
195 | EX-08 | Execution | Execution | Order modify/cancel | In progress | In Progress | 50 | Order modify | execution/order_manager.py
196 | BR-05 | Execution | Broker Integration | Execution reconciliation | In progress | In Progress | 30 | EOD reconciliation job + alert | orders/
197 | BR-06 | Execution | Broker Integration | Connection health | In progress | In Progress | 40 | Health checks + alerts | dashboard/server.py
198 | RK-17 | Execution | Risk Management | Broker/operational risk | In progress | In Progress | 50 | Broker health / stale-data checks | execution/config.py; execution/order_manager.py
199 | BR-08 | Execution | Broker Integration | Sandbox | In progress | In Progress | 30 | Verify sandbox path end-to-end | orders/environment.py
200 | EX-09 | Execution | Execution | Measured slippage | In progress | In Progress | 30 | Slippage metric + report | execution/order_manager.py
201 | EX-10 | Execution | Execution | Execution analytics | In progress | In Progress | 30 | Fill-rate / slippage / rejection analytics | execution/*
202 | BR-02 | Execution | Broker Integration | Zerodha/Kite | In progress | In Progress | 50 | Token refresh; orders if wanted | portfolio/zerodha.py
203 | MON-04 | Execution | Monitoring | Live strategy/P&L monitoring | In progress | In Progress | 25 | Live P&L panel | dashboard/server.py
204 | SEC-03 | Execution | Security | Audit logging | In progress | In Progress | 85 | Export / retention; off-box audit copy | enterprise/audit.py; ops/migrations.py; ops/http.py
207 | AF-07 | Advanced Quant | Alpha/Factor Engine | Microstructure factors | In progress | In Progress | 25 | Tick / depth feed | quant/microstructure.py
209 | QR-10 | Advanced Quant | Quant Research | Volatility strategies | In progress | In Progress | 40 | Options data | quant/volatility.py
210 | QR-05 | Advanced Quant | Quant Research | Stat-arb / pairs / cointegration | In progress | In Progress | 70 | Shortable instrument | quant/statarb.py; quant/pairs.py; strategy_engine/kinds.py
211 | QR-06 | Advanced Quant | Quant Research | Cross-sectional / market-neutral | In progress | In Progress | 65 | Shortable instrument | quant/engine.py; quant/portfolio.py; strategy_engine/kinds.py
212 | QR-09 | Advanced Quant | Quant Research | Event-driven research | In progress | In Progress | 45 | Earnings/dividend/macro sources | quant/events.py
213 | AF-05 | Advanced Quant | Alpha/Factor Engine | Value/quality composites | In progress | In Progress | 50 | Fundamentals ingestion | quant/factors.py; quant/composite.py
225 | OPS-06 | Production Hardening | Deployment/Ops | DR / backup automation | In progress | In Progress | 60 | Off-site backup target; scheduled restore drill; backup encryption | ops/backup.py; docs/DISASTER_RECOVERY.md
226 | SEC-04 | Production Hardening | Security | Encryption | In progress | In Progress | 50 | Encrypt broker credentials (ENT-06); key rotation re-encryption; TLS only with ENT-07 | ops/crypto.py; docs/SECURITY_ARCHITECTURE.md
227 | API-05 | Production Hardening | APIs | API contracts/docs | In progress | In Progress | 40 | Generated API reference | docs/PRODUCTION_ARCHITECTURE.md; ops/errors.py
229 | OPS-05 | Production Hardening | Deployment/Ops | Documentation set | In progress | In Progress | 60 | User guide; API reference | docs/
230 | ENT-01 | Enterprise SaaS (final objective) | Enterprise Platform | Multi-tenant architecture | In progress | In Progress | 60 | Per-tenant paper books / broker accounts; SQL-level scoping | enterprise/tenants.py; enterprise/authz.py; db/schema.py
233 | SEC-02 | Enterprise SaaS (final objective) | Security | Users / RBAC / MFA | In progress | In Progress | 85 | WebAuthn / recovery codes | enterprise/mfa.py; enterprise/users.py; enterprise/authz.py
235 | ENT-02 | Enterprise SaaS (final objective) | User Management | User registration/onboarding | In progress | In Progress | 70 | E-mail verification | enterprise/users.py; dashboard/enterprise_routes.py
236 | ENT-03 | Enterprise SaaS (final objective) | User Management | User profile + risk profile | In progress | In Progress | 65 | Per-user capital accounting | enterprise/profiles.py; execution/risk_engine.py
241 | ENT-08 | Enterprise SaaS (final objective) | Channels | Multi-user web app | In progress | In Progress | 40 | Blocked on ENT-07 for any exposure | dashboard/enterprise_*.py
242 | ENT-04 | Enterprise SaaS (final objective) | User Management | Subscriptions & billing | In progress | In Progress | 45 | Payment gateway (owner decision) | enterprise/billing.py
243 | ENT-18 | Enterprise SaaS (final objective) | User Management | Multi-device login | In progress | In Progress | 40 | Device management UI | enterprise/users.py
245 | ENT-11 | Enterprise SaaS (final objective) | Channels | Per-user price & AI alerts | In progress | In Progress | 55 | Intraday evaluation | enterprise/workspace.py
246 | ENT-10 | Enterprise SaaS (final objective) | Channels | Notification channels | In progress | In Progress | 45 | E-mail / push channels | enterprise/notifications.py
248 | API-03 | Enterprise SaaS (final objective) | APIs | Versioned public API | In progress | In Progress | 55 | Per-route v1 contract (OpenAPI) and deprecation policy | ops/http.py; ops/errors.py
249 | API-04 | Enterprise SaaS (final objective) | APIs | Webhooks | In progress | In Progress | 60 | Business consumers (billing / broker postbacks); endpoint admin UI | ops/webhooks.py; dashboard/ops_routes.py
253 | ENT-12 | Enterprise SaaS (final objective) | Reporting | Reports | In progress | In Progress | 30 | Report rendering / export | enterprise/workspace.py
254 | ENT-13 | Enterprise SaaS (final objective) | Administration | Administration console | In progress | In Progress | 60 | Richer console | dashboard/enterprise_page.py; dashboard/enterprise_routes.py
258 | ENT-16 | Enterprise SaaS (final objective) | Deployment/Ops | Scalability, HA & observability | In progress | In Progress | 35 | HA / horizontal scale (needs DBS-05 Postgres) | ops/logs.py; ops/metrics.py; ops/health.py; docs/OBSERVABILITY.md
262 | OPS-10 | Production hardening | Deployment/Ops | Resilience + idempotency | In progress | In Progress | 60 | Wrap existing data-source calls with breakers/retry | ops/resilience.py; ops/idempotency.py
265 | OPS-11 | Production hardening | Deployment/Ops | Release management & deployment | In progress | In Progress | 80 | Authorized deployment + first executed rollback drill | ops/release.py; deploy/; docs/PRODUCTION_DEPLOYMENT.md
275 | QA-001 | Wealth track (Waves 11-20) | Wealth | Wealth QA / security / performance | In progress | In Progress | 60 | Independent testing (ChatGPT) + UAT; merge after authorization | tests/test_wealth_*.py
276 | UAT-001 | Wealth track (Waves 11-20) | Wealth | Beta / UAT | In progress | In Progress | 60 | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/uat.py
208 | AF-06 | Advanced Quant | Alpha/Factor Engine | Derivatives factors | Blocked | Blocked | 20 | BLOCKED: Derivatives data source | quant/derivatives.py
232 | ENT-07 | Enterprise SaaS (final objective) | Security | Secure internet exposure | Blocked | Blocked | 5 | BLOCKED: Owner decision + security architecture | dashboard/security.py
132 | DP-08 | Quant Research (data, factors, backtesting) | Data Platform | Derivatives data | Not started | Yet To Start | 0 | NSE F&O bhavcopy + option chain store | —
170 | NS-05 | AI/ML | News/Sentiment | Novelty/decay/source weighting | Not started | Yet To Start | 5 | Implement | data/news.py
173 | NS-06 | AI/ML | News/Sentiment | Earnings call / announcement NLP | Not started | Yet To Start | 0 | Implement | —
174 | ML-02 | AI/ML | AI/ML | Deep learning | Not started | Yet To Start | 0 | Only if validated benefit | —
175 | ML-04 | AI/ML | AI/ML | Reinforcement learning | Not started | Yet To Start | 0 | Low priority | —
205 | DP-04 | Advanced Quant | Data Platform | Tick data | Not started | Yet To Start | 5 | Tick ingestion + storage | data/dhan.py
206 | DP-05 | Advanced Quant | Data Platform | Order book / depth | Not started | Yet To Start | 5 | Depth capture + schema | data/dhan.py
214 | EX-11 | Advanced Quant | Execution | Execution algos | Not started | Yet To Start | 0 | Implement | —
215 | EX-12 | Advanced Quant | Execution | Market impact model | Not started | Yet To Start | 0 | Implement | —
216 | EX-15 | Advanced Quant | Execution | Latency telemetry | Not started | Yet To Start | 0 | Instrument data and order paths | —
217 | EX-16 | Advanced Quant | Execution | Event-driven OMS | Not started | Yet To Start | 10 | Implement | —
218 | BT-17 | Advanced Quant | Backtesting | Event-driven backtester | Not started | Yet To Start | 0 | Implement | —
219 | DP-14 | Advanced Quant | Data Platform | Macroeconomic data | Not started | Yet To Start | 0 | Macro connectors + calendar | —
220 | AD-01 | Advanced Quant | Alternative Data | Alt-data framework | Not started | Yet To Start | 0 | DataSource interface | —
221 | AD-02 | Advanced Quant | Alternative Data | Alt-data sources | Not started | Yet To Start | 0 | Add sources | —
222 | DP-22 | Advanced Quant | Data Platform | Point-in-time data lake | Not started | Yet To Start | 5 | Parquet/DuckDB store | —
223 | DP-21 | Advanced Quant | Data Platform | Multi-asset data | Not started | Yet To Start | 0 | MCX/CDS/bond/MF feeds | —
228 | API-06 | Production Hardening | APIs | Widget JSON schemas | Not started | Yet To Start | 5 | Define schemas | —
231 | DBS-05 | Enterprise SaaS (final objective) | Database | Scalable database | Not started | Yet To Start | 0 | Migrate to Postgres | —
237 | ENT-06 | Enterprise SaaS (final objective) | Security | Per-user broker credential vault | Not started | Yet To Start | 0 | Design with the owner | —
238 | ENT-14 | Enterprise SaaS (final objective) | Compliance | Regulatory approvals | Not started | Yet To Start | 0 | Legal review before offering to other users | —
239 | SEC-05 | Enterprise SaaS (final objective) | Security | Compliance monitoring | Not started | Yet To Start | 0 | Implement controls from ENT-14 | —
240 | ENT-17 | Enterprise SaaS (final objective) | Compliance | Data privacy | Not started | Yet To Start | 0 | Privacy policy + controls | —
247 | ENT-09 | Enterprise SaaS (final objective) | Channels | Mobile apps | Not started | Yet To Start | 0 | Build apps | —
250 | PF-12 | Enterprise SaaS (final objective) | Portfolio | Multi-broker import | Not started | Yet To Start | 0 | Importers | —
251 | BR-07 | Enterprise SaaS (final objective) | Broker Integration | Additional brokers | Not started | Yet To Start | 0 | Adapters behind BR-03 interface | —
252 | ENT-15 | Enterprise SaaS (final objective) | Execution | Multi-asset trading | Not started | Yet To Start | 0 | Asset-specific execution/risk adapters | —
255 | SE-10 | Enterprise SaaS (final objective) | Strategy Engine | No/low-code strategy builder | Not started | Yet To Start | 0 | Visual builder on SE-01 interface | —
256 | ML-16 | Enterprise SaaS (final objective) | AI/ML | AI chat assistant | Not started | Yet To Start | 0 | Implement | —
257 | OPS-04 | Enterprise SaaS (final objective) | Deployment/Ops | Cloud deployment | Not started | Yet To Start | 0 | Containerise; IaC; environments | —

## Summary
Status | Count
Implemented | 187
In progress | 58
Blocked | 2
Not started | 30
Total | 277