## Summary
ATIP feature status tracker
Source: docs/ATIP_MASTER_TRACKER.csv (dev branch, incl. W25) as of 2026-09-28; production release ATIP-W24-RC1 deployed 2026-09-28 11:31; W25 built, not deployed.
Phase | Phase name | Completed | Built, needs QA | In progress | Yet to start | Blocked | Unclear | Total | Done or built % | Avg completion %
0 | Delivered baseline (maintain)
1 | Foundation
2 | Quant Research (data, factors, backtesting)
3 | Strategy Engine
4 | AI/ML
5 | Risk & Portfolio
6 | Execution
7 | Advanced Quant
8 | Production Hardening
8 | Production hardening
9 | Enterprise SaaS (final objective)
10 | Wealth track (Waves 11-20)
TOTAL
Other counts
Features needing independent QA (built, not verified)
Features waiting on an owner decision
Owner decisions still open
Reviewed OK
Reviewed with an issue
Open issues
How to use this workbook
Yellow cells are yours to fill: 'All Features' columns Review Status (drop-down) and Reviewer Notes; 'Owner Decisions' columns Your decision and Date.
Example: Review Status = Issue found; Reviewer Notes = 'Goal Monte Carlo slow with 20 goals (8 s) - retest after fix'.
Status meanings: COMPLETED = built (W1/W2 tested); IMPLEMENTED BUT NOT VERIFIED = built and smoke-run, awaiting independent QA; IN PROGRESS = partly built; YET TO START = not built.
Every count above is a live formula over 'All Features': filter or edit that sheet and the summary updates.
'Deployed' means the code is in the running production release ATIP-W24-RC1; new features stay off until their config switch is enabled (see Owner Decisions).
Note on J4: Share of the phase's features that are COMPLETED or built awaiting QA.

## All Features
Seq | Phase | Phase Name | ID | Module | Feature | Status | Completion % | Wave | Deployed | Needs | Current Implementation | Next Action / Missing Work | Key Files | Depends On | Last Updated | Review Status | Reviewer Notes
1 | 0 | Delivered baseline (maintain) | DP-02 | Data Platform | Daily OHLCV history | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | NSE Bhavcopy + Dhan; coverage/freshness/duplicate guards | Maintain | data/bhavcopy.py; data/dhan.py |  | 2026-09-24
2 | 0 | Delivered baseline (maintain) | DP-07 | Data Platform | Delivery data | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Full Bhavcopy nightly + backfill | Maintain | data/bhavcopy.py |  | 2026-09-24
3 | 0 | Delivered baseline (maintain) | DP-20 | Data Platform | Trading calendar | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | 2025-26 holidays + budget sessions | Add next year's holidays each December | utils/trading_calendar.py |  | 2026-09-24
4 | 0 | Delivered baseline (maintain) | TA-01 | Technical Analysis | Core indicators | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Computed and stored; MACD fixed and normalised | Maintain | data/technical.py |  | 2026-09-24
5 | 0 | Delivered baseline (maintain) | TA-02 | Technical Analysis | Extended oscillators | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Computed and stored | Maintain | data/technical.py |  | 2026-09-24
6 | 0 | Delivered baseline (maintain) | TA-05 | Technical Analysis | Fibonacci | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | 52-week 23.6/38.2/50/61.8 levels | Optional: swing-anchored levels | data/technical.py |  | 2026-09-24
7 | 0 | Delivered baseline (maintain) | TA-07 | Technical Analysis | Trend features | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Computed and stored | Maintain | data/technical.py |  | 2026-09-24
8 | 0 | Delivered baseline (maintain) | TA-08 | Technical Analysis | Relative strength | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | 20-day RS with date-matched benchmark | Sector-relative RS later (TA-08b in Phase 2 if wanted) | scores/engine.py |  | 2026-09-24
9 | 0 | Delivered baseline (maintain) | SC-03 | Alpha/Factor Engine | RRI | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented | Institutional input improves with SC-14 | scores/engine.py |  | 2026-09-24
10 | 0 | Delivered baseline (maintain) | SC-04 | Alpha/Factor Engine | MRI | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Implemented; MACD corrected | Maintain | scores/engine.py |  | 2026-09-24
11 | 0 | Delivered baseline (maintain) | SC-07 | Alpha/Factor Engine | ZPI | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented + delivery component | Maintain | scores/engine.py |  | 2026-09-24
12 | 0 | Delivered baseline (maintain) | SC-10 | Alpha/Factor Engine | Portfolio Health score | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented | Correlation/drawdown inputs come with PF-09 and PF-13 | scores/portfolio_health.py |  | 2026-09-24
13 | 0 | Delivered baseline (maintain) | PF-05 | Portfolio | Portfolio health | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented + dashboard | Maintain | scores/portfolio_health.py |  | 2026-09-24
14 | 0 | Delivered baseline (maintain) | SC-11 | Alpha/Factor Engine | Trade of the Day | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented; one TOD per session | Maintain | scores/engine.py |  | 2026-09-24
15 | 0 | Delivered baseline (maintain) | SC-15 | Alpha/Factor Engine | Overall ATIP score + rank | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented; rank stored | Maintain | scores/engine.py |  | 2026-09-24
16 | 0 | Delivered baseline (maintain) | SC-17 | Alpha/Factor Engine | Configurable weights | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | weight_config table | Regime-specific rows used by ML-05 | db/schema.py |  | 2026-09-24
17 | 0 | Delivered baseline (maintain) | SG-02 | Signal Engine | Signal validation | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | EOD coverage guard; FII/DII hold | Maintain | pipeline/scheduler.py |  | 2026-09-24
18 | 0 | Delivered baseline (maintain) | SG-03 | Signal Engine | Signal ranking | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | scores/engine.py |  | 2026-09-24
19 | 0 | Delivered baseline (maintain) | SG-05 | Signal Engine | Trade plan | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | scores/predictions.py |  | 2026-09-24
20 | 0 | Delivered baseline (maintain) | SG-06 | Signal Engine | Outcome tracking | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented; corrected denominator | Maintain | scores/signal_log.py |  | 2026-09-24
21 | 0 | Delivered baseline (maintain) | SG-07 | Signal Engine | Signal provenance log | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Append-only signal_log | Maintain | scores/signal_log.py |  | 2026-09-24
22 | 0 | Delivered baseline (maintain) | BT-01 | Backtesting | Historical backtest | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | 3 bar engines | Extended by Phase 2 items | scores/backtest.py; strategy/backtest_*.py |  | 2026-09-24
23 | 0 | Delivered baseline (maintain) | BT-10 | Backtesting | Win rate / profit factor / expectancy | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | strategy/backtest_aggressive.py |  | 2026-09-24
24 | 0 | Delivered baseline (maintain) | RK-02 | Risk Management | Max order value | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Enforced when configured | Set values in config.json | orders/risk.py |  | 2026-09-24
25 | 0 | Delivered baseline (maintain) | RK-03 | Risk Management | Max orders per day | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Enforced when configured | Set values in config.json | orders/risk.py |  | 2026-09-24
26 | 0 | Delivered baseline (maintain) | RK-04 | Risk Management | Max open positions | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Enforced when configured | Set values in config.json | orders/risk.py |  | 2026-09-24
27 | 0 | Delivered baseline (maintain) | RK-05 | Risk Management | Symbol exposure limit | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Enforced when configured | Set values in config.json | orders/risk.py |  | 2026-09-24
28 | 0 | Delivered baseline (maintain) | RK-14 | Risk Management | Crash-risk gating | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | SELL_CRI_DANGER + strategy use | Maintain | scores/engine.py |  | 2026-09-24
29 | 0 | Delivered baseline (maintain) | EX-03 | Execution | Position management | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | reserve -> place -> apply | Maintain | strategy/positions.py |  | 2026-09-24
30 | 0 | Delivered baseline (maintain) | EX-04 | Execution | Entry/exit | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | strategy/live.py | Maintain | strategy/live.py |  | 2026-09-24
31 | 0 | Delivered baseline (maintain) | EX-05 | Execution | Stop loss | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | strategy/aggressive.py |  | 2026-09-24
32 | 0 | Delivered baseline (maintain) | EX-06 | Execution | Trailing stop | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented (4.0x ATR) | Maintain | strategy/aggressive.py |  | 2026-09-24
33 | 0 | Delivered baseline (maintain) | EX-07 | Execution | Profit booking / partial exit | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | Implemented in aggressive strategy | Maintain | strategy/aggressive.py |  | 2026-09-24
34 | 0 | Delivered baseline (maintain) | EX-13 | Execution | Paper trading | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Paper broker with slippage | Maintain | orders/paper.py |  | 2026-09-24
35 | 0 | Delivered baseline (maintain) | EX-14 | Execution | Live gating | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | orders/environment.py |  | 2026-09-24
36 | 0 | Delivered baseline (maintain) | BR-01 | Broker Integration | Dhan | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | dhanhq integration | Maintain | data/dhan.py; orders/broker.py |  | 2026-09-24
37 | 0 | Delivered baseline (maintain) | BR-03 | Broker Integration | Broker abstraction | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | PAPER/SANDBOX/LIVE routing | Becomes multi-broker interface in ENT-15 | orders/environment.py |  | 2026-09-24
38 | 0 | Delivered baseline (maintain) | DB-01 | Dashboard | Market Health panel | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
39 | 0 | Delivered baseline (maintain) | DB-02 | Dashboard | Global Markets panel | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Rendered; snapshot bug fixed | Maintain | dashboard/server.py |  | 2026-09-24
40 | 0 | Delivered baseline (maintain) | DB-03 | Dashboard | FII/DII panel | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
41 | 0 | Delivered baseline (maintain) | DB-05 | Dashboard | Sector Rotation | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | Heatmap rendered | Maintain | dashboard/server.py |  | 2026-09-24
42 | 0 | Delivered baseline (maintain) | DB-07 | Dashboard | Top 25 VPI | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
43 | 0 | Delivered baseline (maintain) | DB-08 | Dashboard | Buy Zone (ZPI) | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
44 | 0 | Delivered baseline (maintain) | DB-09 | Dashboard | Recovery (RRI) | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
45 | 0 | Delivered baseline (maintain) | DB-10 | Dashboard | Momentum Reversal (MRI) | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
46 | 0 | Delivered baseline (maintain) | DB-12 | Dashboard | Portfolio Health panel | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
47 | 0 | Delivered baseline (maintain) | DB-13 | Dashboard | Trade of the Day | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Rendered | Maintain | dashboard/server.py |  | 2026-09-24
48 | 0 | Delivered baseline (maintain) | DB-15 | Dashboard | Orders/signals panel | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | Rendered with PAPER status | Maintain | dashboard/server.py |  | 2026-09-24
49 | 0 | Delivered baseline (maintain) | DB-19 | Dashboard | Hosted read-only snapshot | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | publish_snapshot.py | Superseded by ENT-08 web app | publish_snapshot.py |  | 2026-09-24
50 | 0 | Delivered baseline (maintain) | API-01 | APIs | Internal REST | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | 15 FastAPI routes | Maintain | dashboard/server.py |  | 2026-09-24
51 | 0 | Delivered baseline (maintain) | API-02 | APIs | Local API authentication | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | 127.0.0.1 bind + X-ATIP-Token | Replaced by per-user auth in SEC-02 | dashboard/security.py |  | 2026-09-24
52 | 0 | Delivered baseline (maintain) | DBS-01 | Database | Schema | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | 19 SQLite tables | Migrations via DBS-04 | db/schema.py |  | 2026-09-24
53 | 0 | Delivered baseline (maintain) | DBS-02 | Database | Retention/purge | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | db/purge.py | Maintain | db/purge.py |  | 2026-09-24
54 | 0 | Delivered baseline (maintain) | SEC-01 | Security | Credential handling | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Secrets abstraction (env > .env > atip_data/secrets > legacy config), presence/format validation, name-only access log, rotation dates, masking in logs | Move legacy plaintext keys out of config.json (owner action) | ops/secrets.py; ops/logs.py |  | 2026-09-25
55 | 0 | Delivered baseline (maintain) | MON-07 | Monitoring | Feed health | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | data/dhan_ws.py |  | 2026-09-24
56 | 0 | Delivered baseline (maintain) | MON-08 | Monitoring | Diagnostics | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | /health, /health/live¦ready¦database¦broker¦data¦scheduler¦ml (LIVE/READY/DEGRADED/FAILED); python -m ops status | Validate | ops/health.py; dashboard/ops_routes.py |  | 2026-09-25
57 | 0 | Delivered baseline (maintain) | OPS-01 | Deployment/Ops | Autostart/scheduling | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Task Scheduler + VBS | Replaced by cloud deploy in OPS-04 | start_atip.bat; ATIP_TaskScheduler.xml |  | 2026-09-24
58 | 0 | Delivered baseline (maintain) | OPS-07 | Deployment/Ops | Snapshot publishing | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented | Maintain | publish_snapshot.py |  | 2026-09-24
59 | 1 | Foundation | DP-09 | Data Platform | India VIX | COMPLETED | 95% |  | Live (ATIP-W24-RC1) |  | Daily INDIAVIX series in prices_daily (421 sessions 2025-01-13..; Dhan history + NSE close nightly); get_vix() = session feed then daily series; no 15.0 default | None for DP-09; VIX term structure/percentile features belong to later factor work | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py |  | 2026-09-24
60 | 1 | Foundation | DP-17 | Data Platform | Market breadth | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | breadth_series(): advances/declines; % advancing; A/D ratio; % above 200-DMA; 52-week new highs/lows over tracked universe; 80% coverage gate; stored in market_health | Survivorship-free universe (BT-15); sector-level breadth (DP-13) | scores/engine.py; db/schema.py | DP-02 | 2026-09-24
61 | 1 | Foundation | SC-09 | Alpha/Factor Engine | Market Health score | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Every MH input is real or left out (index_levels then daily index series; session-own FII/DII; global <=4 days; VIX; breadth); coverage + inputs stored; no score below 50% coverage; upsert keeps portfolio_health; 393 past sessions backfilled | FII/DII and global history only from 2026-07 (backfilled coverage avg 0.65); determine_signal still defaults a missing MH to 50; model-based regime is ML-05 | scores/engine.py; data/dhan.py; data/bhavcopy.py; pipeline/scheduler.py; main.py | DP-09; DP-17 | 2026-09-24
62 | 1 | Foundation | SC-08 | Alpha/Factor Engine | ACS | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | HistoricalAccuracy = 90-day 5-session hit rate from outcomes known by the scored day (min 5); NewsConfidence only from AI-classified news with no look-ahead; missing inputs left out (no 50/60 stand-ins) | NewsConfidence stays absent until NS-02 (Anthropic key) classifies news | scores/engine.py; data/news.py; db/schema.py | SC-09 | 2026-09-24
63 | 1 | Foundation | MON-01 | Monitoring | Job logging | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | run_job records every run (start/end/duration/rows/status/error); returned FAILED is a failure; EMPTY status | Record failures, end time, row counts | pipeline/scheduler.py; db/schema.py |  | 2026-09-24
64 | 1 | Foundation | MON-02 | Monitoring | Stalled-job detection | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | pipeline/health.py expectations: MISSED/STALLED/FAILING/EMPTY; every 30 min | Expected-run table + missed-run check | pipeline/health.py; pipeline/scheduler.py | MON-01 | 2026-09-24
65 | 1 | Foundation | MON-03 | Monitoring | Failure alerting | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | alert_log + dashboard panel + Telegram when configured; daily de-dup; token scrubbed | Configure Telegram; alert on failure/stall | alerts/telegram.py; dashboard/server.py | MON-02 | 2026-09-24
66 | 1 | Foundation | DB-14 | Dashboard | Alerts / morning brief | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Brief recorded for the dashboard + Telegram; pipeline-health section (outside W1, same tree) | Deliver digest; verify daily | alerts/telegram.py | MON-03 | 2026-09-24
67 | 1 | Foundation | RK-15 | Risk Management | Risk alerts | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Alerts on halt/resume and on halted or limit-refused orders (outside W1, same tree) | Alert on halt, limit breach, CRI spike | orders/risk.py; orders/broker.py | MON-03 | 2026-09-24
68 | 1 | Foundation | MON-06 | Monitoring | Log rotation | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | SafeRotatingFileHandler 20 MB x 10, survives refused rename (outside W1, same tree) | RotatingFileHandler | main.py |  | 2026-09-24
69 | 1 | Foundation | DBS-06 | Database | Timestamp consistency | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Convention documented (IST; created_at UTC); news UTC->IST; status query fixed; repair tool | Normalise; fix news recency | db/schema.py; data/news.py; tools/repair_news_timezone.py |  | 2026-09-24
70 | 1 | Foundation | NS-01 | News/Sentiment | News ingestion | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | News first + morning catch-up; de-dup; per-feed status; 4 more RSS feeds | Fix job; add second source; health check | data/news.py; pipeline/scheduler.py | MON-02 | 2026-09-24
71 | 1 | Foundation | OPS-03 | Deployment/Ops | Install/setup | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | ta not pandas-ta everywhere; requirements-dev.txt; CI httpx; config template; docs/DEV_SETUP.md | Fix requirements/setup; pin versions | setup.py; install.bat; requirements-dev.txt; docs/DEV_SETUP.md |  | 2026-09-24
72 | 1 | Foundation | EX-01 | Execution | Order management tests | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | orders/rules.py (944 lines) without tests | Unit tests for rules.py | orders/rules.py; tests/ |  | 2026-09-24
73 | 1 | Foundation | OPS-02 | Deployment/Ops | CI + end-to-end test | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | GitHub Actions; ~270 test functions; no E2E | Add E2E pipeline test | .github/workflows/tests.yml; tests/ | EX-01 | 2026-09-24
74 | 1 | Foundation | DP-15 | Data Platform | Fundamentals | IN PROGRESS | 30% |  | — | Owner: Enable fundamentals ingestion (Screener.in) | Screener.in fetcher; ingestion disabled | Your decision; enable; quarterly store; no 50.0 default | data/fundamentals.py; pipeline/scheduler.py |  | 2026-09-24
75 | 1 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | IN PROGRESS | 20% |  | — | Development | Default 50 when unparsed | Implement FS formula on real data | data/fundamentals.py | DP-15 | 2026-09-24
76 | 1 | Foundation | SC-02 | Alpha/Factor Engine | SPI | IN PROGRESS | 30% |  | — | Development |  | Implement SPI formula separately from FS | scores/engine.py | SC-13 | 2026-09-24
77 | 1 | Foundation | SC-05 | Alpha/Factor Engine | CRI debt input | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented; Debt input missing | Feed Debt/Equity | scores/engine.py | DP-15 | 2026-09-24
78 | 1 | Foundation | SC-01 | Alpha/Factor Engine | VPI inputs | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Implemented; FG/IS inputs weak | Real Fundamental Growth input | scores/engine.py | DP-15 | 2026-09-24
79 | 1 | Foundation | PF-01 | Portfolio | Portfolio ingestion | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | portfolio_sync records each attempt and reason (DH-901 named); qty/avg update; sold removed | Scheduled reliable sync + token handling | data/dhan.py; portfolio/zerodha.py |  | 2026-09-24
80 | 1 | Foundation | BR-04 | Broker Integration | Portfolio sync schedule | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Morning catch-up re-sync; Zerodha SKIPPED when not connected; health expects SUCCESS | Scheduled sync with alert on failure | pipeline/scheduler.py; pipeline/health.py | PF-01 | 2026-09-24
81 | 1 | Foundation | PF-02 | Portfolio | Holdings & P&L | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | portfolio/pnl.py PAPER + LIVE books marked to market; /api/pnl | Realised + unrealised P&L | portfolio/pnl.py; dashboard/server.py | PF-01 | 2026-09-24
82 | 1 | Foundation | PF-13 | Portfolio | Daily P&L series | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | pnl_daily equity/day P&L/peak/drawdown per env; post-market daily_pnl job | Daily P&L table; EOD job | portfolio/pnl.py; db/schema.py | PF-02 | 2026-09-24
83 | 1 | Foundation | RK-13 | Risk Management | Risk-based sizing wired to orders | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | size_position() pure + size_for_account(); quantity_type RISK in order rules | Use size in order path | orders/risk.py; orders/rules.py |  | 2026-09-24
84 | 1 | Foundation | RK-07 | Risk Management | Daily loss limit | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | max_daily_loss_value blocks BUYs; unmeasurable blocks | Limit on PF-13; auto-halt | orders/risk.py | PF-13 | 2026-09-24
85 | 1 | Foundation | RK-08 | Risk Management | Drawdown limit | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | max_drawdown_pct blocks BUYs; unmeasurable blocks | Peak-to-trough on PF-13; auto-halt | orders/risk.py | PF-13 | 2026-09-24
86 | 1 | Foundation | DBS-03 | Database | Backups | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | ops/backup.py: daily online SQLite backup (19:15) VERIFIED by integrity_check + key-table counts + sha256 (ops_backup); 7 daily + 4 weekly retention of its own files only; restore to a NEW file; python -m ops backup/restore/verify | Off-machine copy of backups; restore drill | ops/backup.py; docs/BACKUP_RESTORE.md |  | 2026-09-25
87 | 1 | Foundation | DP-06 | Data Platform | Corporate actions open items | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | NSE CA calendar; reconciliation; volume re-base | TVSMOTOR scheme; renamed symbols | data/corporate_actions.py |  | 2026-09-24
88 | 1 | Foundation | TA-06 | Technical Analysis | Support/Resistance | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: fractal pivots over 120 sessions, mean-anchored clusters, nearest confirmed support/resistance with touches and distance | QA; optionally feed the Technical Score SR component | data/technical_ext.py |  | 2026-09-27
89 | 1 | Foundation | DP-19 | Data Platform | Data quality layer | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | data/quality.py 12 checks + DQS per session; data_quality table; post-market; alert | DQS table; outlier and timestamp checks | data/quality.py; pipeline/scheduler.py | MON-01 | 2026-09-24
90 | 2 | Quant Research (data, factors, backtesting) | DBS-04 | Database | Schema migrations | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | schema_migrations (version, checksum, applied_at, duration, status, rollback note); 0001 baseline, 0002 W8 tables, 0003 indexes, 0004 append-only audit triggers; drift detection; additive layer now runs once per process (W7-R8) | Down-migration scripts beyond rollback notes (policy: restore pre-release backup) | ops/migrations.py; db/schema.py |  | 2026-09-25
91 | 2 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | IN PROGRESS | 60% |  | — | Development | Index WebSocket 09:00-15:45 + quote cache; stock tick feed never run | Stock-level live feed in production; failover | data/dhan_ws.py; data/dhan.py |  | 2026-09-24
92 | 2 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | IMPLEMENTED BUT NOT VERIFIED | 85% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: intraday_bars stores the 30-min job's 15-min bars (was discarded); 90-day retention | QA; consider 5-min bars for session VWAP | data/dhan.py; db/schema.py; db/purge.py | DBS-04 | 2026-09-27
93 | 2 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | Live (ATIP-W24-RC1) | Independent QA; Owner: technical.vwap_in_score (changes scores) | W21: vwap_20d, vwap_session (intraday bars), vwap_dev_pct in technical_ext; strategy feature vwap_dev_pct | Owner: technical.vwap_in_score (changes scores); QA | data/technical_ext.py; data/technical.py | DP-03 | 2026-09-27
94 | 2 | Quant Research (data, factors, backtesting) | SC-12 | Alpha/Factor Engine | Technical Score VWAP input | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Implemented; VWAP weight dead | Include VWAP | data/technical.py | TA-03 | 2026-09-24
95 | 2 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: volume profile POC/VAH/VAL over 20 sessions (intraday or daily basis) | QA | data/technical_ext.py | DP-03 | 2026-09-27
96 | 2 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: weekly RSI/trend, monthly trend, mtf_alignment -3..+3 | QA | data/technical_ext.py | DP-03 | 2026-09-27
97 | 2 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | IMPLEMENTED BUT NOT VERIFIED | 70% | W21 | Live (ATIP-W24-RC1) | Independent QA; Owner: When to run the indicator backfill | W21: python -m data.technical --backfill N (tracked universe, resumable) | Run the backfill (owner timing; copy first) | data/technical.py |  | 2026-09-27
98 | 2 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | IMPLEMENTED BUT NOT VERIFIED | 85% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: score_components stores every ATIP index's sub-components per symbol/date (weighted_score label capture; scores unchanged) | QA | scores/engine.py; scores/formulas.py | TA-12 | 2026-09-27
99 | 2 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: 11 standalone factors: mean reversion, trend, volume, recovery, risk (BRI) | QA; research on full history | quant/factors.py | AF-03 | 2026-09-27
100 | 2 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | IMPLEMENTED BUT NOT VERIFIED | 85% |  | Live (ATIP-W24-RC1) | Independent QA | W6 quant/normalize.py per-factor spec (winsorize/zscore/percentile/rank/minmax/sector/neutralize) -- tracker was stale | QA | quant/normalize.py | AF-03 | 2026-09-27
101 | 2 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | IMPLEMENTED BUT NOT VERIFIED | 85% |  | Live (ATIP-W24-RC1) | Independent QA | W6 registry quant_factor + factor sets + content-hash versioning (tracker was stale); W22 adds 11 factors | QA | quant/factors.py | AF-03 | 2026-09-27
102 | 2 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | IMPLEMENTED BUT NOT VERIFIED | 85% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: formula_registry resolves each signal_log weights_hash to the full weight set + code version | QA | scores/formulas.py | AF-01 | 2026-09-27
103 | 2 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: research_study + research_link registry, frozen on conclusion | QA | quant/studies.py | DBS-04 | 2026-09-27
104 | 2 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: backfill_scores + research_report run IC for every factor | Run full-history backfill + report | quant/research.py | AF-03 | 2026-09-27
105 | 2 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: IC decay 1/5/10/20 for every factor in research_report | Run on full history | quant/research.py | QR-01 | 2026-09-27
106 | 2 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | Live (ATIP-W24-RC1) | Independent QA | W22: redundancy report (pairs ¦rho¦>=0.7) in research_report | Run on full history | quant/research.py | AF-03 | 2026-09-27
107 | 2 | Quant Research (data, factors, backtesting) | QR-04 | Quant Research | Statistical toolkit | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | statarb (OLS, ADF, Engle-Granger, half-life, z) + normalize + volatility estimators | Validate | quant/statarb.py; quant/normalize.py; quant/volatility.py | AF-03 | 2026-09-25
108 | 2 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | IMPLEMENTED BUT NOT VERIFIED | 80% | W22 | Live (ATIP-W24-RC1) | Independent QA; Owner: quant.require_approved_factors | W22: evidence-based approval gate, decision history, lifecycle enforcement behind quant.require_approved_factors | Owner: enable after review | quant/approval.py; strategy_engine/lifecycle.py | QR-01; QR-03 | 2026-09-27
109 | 2 | Quant Research (data, factors, backtesting) | BT-16 | Backtesting | Dated equity curve / run records | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | backtest_run snapshot+hash, code version, data fingerprint; trades/equity/drawdowns tables | Dated trades + equity curve + run table | backtest/store.py; db/schema.py |  | 2026-09-24
110 | 2 | Quant Research (data, factors, backtesting) | BT-08 | Backtesting | Portfolio-level backtest | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Portfolio engine: cash, positions, sizing (W1 size_position), exposure, dated equity | Portfolio simulator | backtest/engine.py | BT-16 | 2026-09-24
111 | 2 | Quant Research (data, factors, backtesting) | BT-09 | Backtesting | Drawdown analysis | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Drawdown series, max DD, episodes with duration/recovery on dated equity | Compute on equity curve | backtest/metrics.py | BT-16 | 2026-09-24
112 | 2 | Quant Research (data, factors, backtesting) | BT-11 | Backtesting | Sharpe/Sortino/CAGR/Calmar | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Return, CAGR, vol, Sharpe, Sortino, Calmar, trade stats; conventions documented | Implement | backtest/metrics.py | BT-16 | 2026-09-24
113 | 2 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | IMPLEMENTED BUT NOT VERIFIED | 85% | W23 | Live (ATIP-W24-RC1) | Independent QA | W23: historical VaR/CVaR 95/99, parametric VaR, skew, kurtosis in every backtest's metrics | QA | backtest/metrics.py | BT-16 | 2026-09-27
114 | 2 | Quant Research (data, factors, backtesting) | BT-05 | Backtesting | Itemised costs | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Itemised NSE cost model (delivery/intraday/flat/zero), central config | Indian cost model shared by backtest and paper | backtest/costs.py; backtest/config.py |  | 2026-09-24
115 | 2 | Quant Research (data, factors, backtesting) | BT-06 | Backtesting | Slippage in backtest | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | none / fixed / pct slippage, default = paper broker 5 bps | Shared slippage model | backtest/slippage.py | BT-05 | 2026-09-24
116 | 2 | Quant Research (data, factors, backtesting) | BT-07 | Backtesting | Liquidity constraints | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Volume participation cap/reject + prior-bar turnover floor | All engines | backtest/liquidity.py |  | 2026-09-24
117 | 2 | Quant Research (data, factors, backtesting) | DP-18 | Data Platform | Survivorship-free universe | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Current NIFTY 500 download | Store constituent history | data/index_constituents.py |  | 2026-09-24
118 | 2 | Quant Research (data, factors, backtesting) | BT-15 | Backtesting | Bias controls | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Point-in-time view + LookAheadError, next-open fills, data/timestamp validation, survivorship flag | Systematic checks | backtest/data.py; backtest/engine.py | DP-18 | 2026-09-24
119 | 2 | Quant Research (data, factors, backtesting) | BT-03 | Backtesting | In/out-of-sample | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Ordered non-overlapping research/validation/test; test needs allow_test; re-test flagged | Formal splits | backtest/periods.py; backtest/service.py | BT-16 | 2026-09-24
120 | 2 | Quant Research (data, factors, backtesting) | BT-02 | Backtesting | Walk-forward | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Rolling windows, candidate selection on validation, stitched OOS; no optimiser | Implement | backtest/walkforward.py | BT-03 | 2026-09-24
121 | 2 | Quant Research (data, factors, backtesting) | BT-13 | Backtesting | Monte Carlo | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Seeded trade shuffle + return bootstrap; percentiles, P(loss), disclaimer | Implement | backtest/montecarlo.py | BT-16 | 2026-09-24
122 | 2 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | IMPLEMENTED BUT NOT VERIFIED | 80% | W23 | Live (ATIP-W24-RC1) | Independent QA | W23: grid / random / adaptive optimiser with trial runs, test-window refusal, Deflated Sharpe + overfit warning | QA; optional true Bayesian search | backtest/optimize.py | BT-02 | 2026-09-27
123 | 2 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | IMPLEMENTED BUT NOT VERIFIED | 80% | W23 | Live (ATIP-W24-RC1) | Independent QA | W23: one-at-a-time sensitivity curves, stability, knife-edge flags, 2-D heat map | QA | backtest/sensitivity.py | BT-04 | 2026-09-27
124 | 2 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | IMPLEMENTED BUT NOT VERIFIED | 80% | W23 | Live (ATIP-W24-RC1) | Independent QA | W23: robustness battery (costs x2, slippage x3, universe halves, period halves, regimes, Monte Carlo) with verdict | QA | backtest/robustness.py | BT-02 | 2026-09-27
125 | 2 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | IMPLEMENTED BUT NOT VERIFIED | 80% |  | Live (ATIP-W24-RC1) | Independent QA | W6 experiments + W22 studies linking experiments/backtests/research | QA | quant/experiments.py; quant/studies.py | DBS-07 | 2026-09-27
126 | 2 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | IMPLEMENTED BUT NOT VERIFIED | 70% | W23 | Live (ATIP-W24-RC1) | Independent QA | W23: momentum breakout strategy + end-to-end study (optimise/validate/sensitivity/robustness/test) | Run full-universe study; review | backtest/strategies.py; backtest/study.py | BT-02 | 2026-09-27
127 | 2 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | IMPLEMENTED BUT NOT VERIFIED | 70% | W23 | Live (ATIP-W24-RC1) | Independent QA | W23: RSI(2) mean-reversion strategy + study; 12-stock smoke: REJECTED out of sample | Run full-universe study; review | backtest/strategies.py; backtest/study.py | BT-02 | 2026-09-27
128 | 2 | Quant Research (data, factors, backtesting) | QR-13 | Quant Research | Signal outcome research by regime | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | success_report keyed on signal/threshold | Add regime/ACS buckets | scores/signal_log.py | ML-05 | 2026-09-24
129 | 2 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | IMPLEMENTED BUT NOT VERIFIED | 70% | W21 | Live (ATIP-W24-RC1) | Independent QA; Owner: prices_daily retention >= 1,100 days | W21: beta_60, beta_downside, beta_long (>=500 sessions) | Owner: prices_daily retention >= 1,100 days for a 3-year beta | data/technical_ext.py | TA-12 | 2026-09-27
130 | 2 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | IMPLEMENTED BUT NOT VERIFIED | 75% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: Beta Risk Index 0-100 (level, downside, instability); strategy feature bri | QA; decide if it joins a composite | data/technical_ext.py | TA-09 | 2026-09-27
131 | 2 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: Supertrend, Ichimoku, Keltner, Donchian, MFI, CMF, ROC, Aroon, PSAR; stoch/Williams %R/CCI now computed | QA | data/technical_ext.py; data/technical.py | TA-12 | 2026-09-27
132 | 2 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | YET TO START | 0% |  | — | Owner: Choose a derivatives data source | None | NSE F&O bhavcopy + option chain store | — | DBS-04 | 2026-09-24
133 | 2 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | IN PROGRESS | 55% |  | — | Development | Options/PCR frozen; news rule-based | Real PCR; AI news later | scores/engine.py | DP-08 | 2026-09-24
134 | 2 | Quant Research (data, factors, backtesting) | DP-10 | Data Platform | FII/DII history | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Session flows; only 7 sessions history | Historical backfill source | data/bhavcopy.py |  | 2026-09-24
135 | 2 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | IMPLEMENTED BUT NOT VERIFIED | 75% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: daily GIFTNIFTY close from index_levels into prices_daily | Pre-open panel (DB-04) | data/market_series.py |  | 2026-09-27
136 | 2 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | IN PROGRESS | 60% |  | — | Development | In index strip | Dedicated pre-open view | dashboard/server.py | DP-11 | 2026-09-24
137 | 2 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | IN PROGRESS | 70% |  | — | Development | 13 yfinance tickers | Bond yields; history depth | data/markets.py |  | 2026-09-24
138 | 2 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | IMPLEMENTED BUT NOT VERIFIED | 80% | W21 | Live (ATIP-W24-RC1) | Independent QA | W21: 8 sector index series in the daily Dhan sync + sector_breadth table | Run --backfill-sectors; QA | data/market_series.py; data/dhan.py |  | 2026-09-27
139 | 2 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | IN PROGRESS | 25% |  | — | Development | Bulk/block only | Promoter/SAST/PIT/MF feeds | data/bhavcopy.py |  | 2026-09-24
140 | 2 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | IN PROGRESS | 40% |  | — | Development | FII + bulk only | Add MF/promoter/insider | scores/engine.py | DP-16 | 2026-09-24
141 | 2 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | IN PROGRESS | 40% |  | — | Development | Feeds INS | Validate with IC | data/bhavcopy.py | DP-16 | 2026-09-24
142 | 3 | Strategy Engine | SG-04 | Signal Engine | Rich decision states | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Decision states BUY/ADD/HOLD/REDUCE/EXIT/SELL/NO_ACTION/BLOCKED_BY_RISK with reasons; PositionIntent | Extended states + stored reasons | strategy_engine/decisions.py | BT-02 | 2026-09-24
143 | 3 | Strategy Engine | SG-01 | Signal Engine | SELL calibration | COMPLETED | 70% |  | Live (ATIP-W24-RC1) |  | SELL never fired | Backtest-based SELL thresholds | scores/engine.py | BT-02 | 2026-09-24
144 | 3 | Strategy Engine | SE-01 | Strategy Engine | Strategy library | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Versioned JSON definitions + DB registry (id, name, description, category, version, status, owner, created/updated, priority, weight); VERSION/LIFECYCLE events; 9 library strategies | Strategy interface + registry | strategy_engine/definition.py; registry.py | BT-16 | 2026-09-24
145 | 3 | Strategy Engine | SE-02 | Strategy Engine | Strategy parameters | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | ParamSpec name/type/default/min/max/allowed/required/description; validated on resolve; stored per version in strategy_parameter | Param store per strategy with versions | strategy_engine/params.py; registry.py | SE-01 | 2026-09-24
146 | 3 | Strategy Engine | SE-03 | Strategy Engine | Rule-based strategies | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | Rule language all/any/not/min-of, 11 operators incl. crosses; rule kind | Generic rule definition format | strategy_engine/rules.py; kinds.py | SE-01 | 2026-09-24
147 | 3 | Strategy Engine | SE-06 | Strategy Engine | Multi-factor strategy | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | multi_factor kind: weights, scaling, thresholds, confirmations, coverage, ranking | IC-weighted multi-factor strategy | strategy_engine/kinds.py | SE-01; QR-01 | 2026-09-24
148 | 3 | Strategy Engine | SE-04 | Strategy Engine | Quant strategies | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | quant_rank kind + point-in-time feature catalogue (framework only) | Implement first quant strategies | strategy_engine/kinds.py; features.py | SE-01; QR-01 | 2026-09-24
149 | 3 | Strategy Engine | SE-09 | Strategy Engine | Strategy lifecycle | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | 12 states incl. DRAFT/ACTIVE/PAUSED/DISABLED/RETIRED/ARCHIVED; allowed transitions; backtest evidence for ACTIVE/VALIDATION/APPROVED; strategy_engine_event audit | State machine + gates | strategy_engine/lifecycle.py | SE-01 | 2026-09-24
150 | 3 | Strategy Engine | SE-11 | Strategy Engine | Strategy health | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | HEALTHY/WARNING/ERROR/STALE/DISABLED; last execution, last signal, signal frequency, error count, performance reference, data availability, parameter validity | Health scoring + alerts | strategy_engine/health.py | SE-09; BT-16 | 2026-09-24
151 | 3 | Strategy Engine | SE-07 | Strategy Engine | Strategy combination/ranking/selection | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | composite kind (vote/weighted/priority/regime_select) + cross-strategy combine(): priority, weighting, vote, conflict -> WAIT, NO_TRADE veto; enable/disable via lifecycle and mapping | Allocator | strategy_engine/selection.py; kinds.py | SE-11 | 2026-09-24
152 | 3 | Strategy Engine | SE-08 | Strategy Engine | Regime-aware selection | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Configurable regime mapping STRONG_BULL/BULL/NEUTRAL/BEAR/HIGH_RISK (+DEFAULT) -> strategies or NO_TRADE; Market Health regime provider; default mapping seeded | Regime-conditional allocation | strategy_engine/selection.py; regime.py; library/regime_mapping.json | SE-07; ML-05 | 2026-09-24
153 | 3 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | IN PROGRESS | 60% |  | — | Development | Scheduled 12:30 and 14:45 | Use stored intraday bars | pipeline/scheduler.py | DP-03 | 2026-09-24
154 | 3 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | IN PROGRESS | 40% |  | — | Development | CRI per-stock column only | Dedicated lists | dashboard/server.py |  | 2026-09-24
155 | 3 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | IN PROGRESS | 30% |  | — | Development | /strategies list shows latest signals; per-strategy P&L from W4 fills on /trading | Performance panel | dashboard/strategy_page.py; dashboard/execution_page.py | SE-11 | 2026-09-25
156 | 4 | AI/ML | ML-13 | AI/ML | Labels/targets | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | ml/labels.py: direction, binary_return, forward_return, return_rank, volatility_regime, market_regime, signal_outcome; ml_label definitions; computed only from bars after t | Validate | ml/labels.py | AF-03 | 2026-09-25
157 | 4 | AI/ML | ML-07 | AI/ML | Feature selection | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: importance-stability selection -> new feature-set version | QA | ml/selection.py | ML-13; QR-01 | 2026-09-27
158 | 4 | AI/ML | ML-08 | AI/ML | Model validation | IMPLEMENTED BUT NOT VERIFIED | 85% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: purged expanding walk-forward reports vs baselines, IC, calibration, verdict | QA | ml/validation.py | ML-13; BT-02 | 2026-09-27
159 | 4 | AI/ML | ML-01 | AI/ML | Supervised ML | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: native numpy GBM + random forest; bootstrap trains + validates first models (TRAINED, not ACTIVE); real-data smoke: NO_EDGE on 5-day direction | Richer features / labels; full-universe validation | ml/trees.py; ml/presets.py | ML-08 | 2026-09-27
160 | 4 | AI/ML | ML-12 | AI/ML | Model registry/versioning | COMPLETED | 85% |  | Live (ATIP-W24-RC1) |  | ml_model / ml_model_version with feature-set, dataset, config and artifact hashes; immutable artifacts; lifecycle | Validate | ml/registry.py; ml/artifacts.py | ML-01; DBS-07 | 2026-09-25
161 | 4 | AI/ML | ML-11 | AI/ML | Ensemble models | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: ensemble model type blended by held-out loss | QA | ml/trees.py | ML-01 | 2026-09-27
162 | 4 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | IMPLEMENTED BUT NOT VERIFIED | 80% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: drift (PSI share) + realised decay alerts, ml_health_check, monitor rule | QA | ml/decay.py; ops/monitor.py | ML-12 | 2026-09-27
163 | 4 | AI/ML | ML-10 | AI/ML | Explainability | IMPLEMENTED BUT NOT VERIFIED | 85% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: exact path contributions for trees, gain importances, out-of-sample permutation importance | QA | ml/trees.py; ml/validation.py | ML-01 | 2026-09-27
164 | 4 | AI/ML | ML-05 | AI/ML | Regime detection | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | Live (ATIP-W24-RC1) | Independent QA; Owner: Regime provider (after evidence) | W24: market_regime model preset validated + trained (NO_EDGE on smoke) | Owner decides regime provider after evidence | ml/presets.py | SC-09 | 2026-09-27
165 | 4 | AI/ML | ML-03 | AI/ML | Unsupervised learning | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: k-means++ factor clusters with profiles; return PCA | QA | ml/unsupervised.py | AF-03 | 2026-09-27
166 | 4 | AI/ML | ML-06 | AI/ML | Anomaly detection | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | Live (ATIP-W24-RC1) | Independent QA; Owner: ml.anomalies_enabled | W24: robust-z + multivariate anomaly scan, CA-explained, post-market (flag off) | Owner: ml.anomalies_enabled | ml/unsupervised.py | DP-19 | 2026-09-27
167 | 4 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | IN PROGRESS | 60% |  | — | Owner: Activate a model (after evidence) | ml_* strategy features (point in time, out of sample); ml_direction / atip_ml_blend (DRAFT); W4 risk check ml_model_active blocks signals of non-ACTIVE models | Activate once a model is ACTIVE | ml/strategy_features.py; execution/risk_engine.py; strategy_engine/library/50_*,51_* | ML-01; SE-01 | 2026-09-25
168 | 4 | AI/ML | NS-02 | News/Sentiment | News classification | IN PROGRESS | 30% |  | — | Owner: Provide a working Anthropic API key (current key 401) | Claude classifier coded; key unset | Set key; taxonomy; cost cap | data/news.py |  | 2026-09-24
169 | 4 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | IN PROGRESS | 40% |  | — | Development | Rule-based; confidence frozen 50 | Model-based scoring | data/news.py | NS-02 | 2026-09-24
170 | 4 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | YET TO START | 5% |  | — | Development | None | Implement | data/news.py | NS-03 | 2026-09-24
171 | 4 | AI/ML | NS-04 | News/Sentiment | AI news summary | IN PROGRESS | 50% |  | — | Development | Headline list | LLM summary | dashboard/server.py | NS-02 | 2026-09-24
172 | 4 | AI/ML | DB-06 | Dashboard | AI News Summary panel | IN PROGRESS | 50% |  | — | Development | News panel (rule-based) | Show AI summary | dashboard/server.py | NS-04 | 2026-09-24
173 | 4 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | YET TO START | 0% |  | — | Development | None | Implement | — | NS-02 | 2026-09-24
174 | 4 | AI/ML | ML-02 | AI/ML | Deep learning | YET TO START | 0% |  | — | Development | None | Only if validated benefit | — | ML-08 | 2026-09-24
175 | 4 | AI/ML | ML-04 | AI/ML | Reinforcement learning | YET TO START | 0% |  | — | Development | None | Low priority | — | ML-08 | 2026-09-24
176 | 4 | AI/ML | DB-18 | Dashboard | Quant/model panel | IN PROGRESS | 40% |  | — | Development | /ml page: models, versions, lifecycle, predictions, feature sets, datasets, training runs | Monitoring charts | dashboard/ml_page.py | ML-12 | 2026-09-25
177 | 5 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | IMPLEMENTED BUT NOT VERIFIED | 90% | W25 | Branch w25 (not deployed) | Independent QA | W25: portfolio/risk.py book_snapshot for PAPER and LIVE books (weights, % equity, sector exposure); /api/risk/portfolio; /trading Portfolio risk panel | Independent QA | portfolio/risk.py; dashboard/portfolio_risk_routes.py | PF-02 | 2026-09-28
178 | 5 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | IMPLEMENTED BUT NOT VERIFIED | 90% | W25 | Branch w25 (not deployed) | Independent QA | W25: concentration() max/top-5 weight, HHI, effective N, sector HHI; in /api/risk/portfolio and snapshots | Independent QA | portfolio/risk.py | PF-03 | 2026-09-28
179 | 5 | Risk & Portfolio | PF-09 | Portfolio | Correlation | IMPLEMENTED BUT NOT VERIFIED | 90% | W25 | Branch w25 (not deployed) | Independent QA | W25: portfolio correlation matrix, weighted avg pairwise correlation, high pairs, diversification ratio; heatmap on /trading | Independent QA | portfolio/risk.py; dashboard/execution_page.py | QR-04 | 2026-09-28
180 | 5 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: W4 limit max_avg_correlation (value-weighted correlation of the new symbol with the held book; fail closed); analytics in /api/risk/portfolio | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; portfolio/limits.py | PF-09 | 2026-09-28
181 | 5 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: historical / parametric / Monte Carlo VaR and ES, 95/99%, 1 and 10 days; W4 limit max_portfolio_var_pct (post-trade); snapshot job + VaR alert (off by default) | Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | portfolio/risk.py; portfolio/limits.py; execution/risk_engine.py | QR-04 | 2026-09-28
182 | 5 | Risk & Portfolio | RK-06 | Risk Management | Sector limits | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | max_sector_exposure_pct in the W4 risk engine (NSE industry from cached Nifty 500 list; fails closed when unavailable) | Validate | execution/risk_engine.py; execution/positions.py | PF-03 | 2026-09-25
183 | 5 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: W4 limit max_symbol_volatility_pct (annualised 60-session vol; fail closed) | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; execution/config.py; portfolio/limits.py | TA-12 | 2026-09-28
184 | 5 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: W4 cap max_adv_participation_pct (qty <= % of 20-session ADV) and W1 risk_limits.max_adv_participation_pct (BUY and SELL, unmeasurable -> refused) | Independent QA; owner sets the limit (default off) | execution/risk_engine.py; orders/risk.py; portfolio/limits.py | DP-02 | 2026-09-28
185 | 5 | Risk & Portfolio | RK-18 | Risk Management | Strategy risk budget | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | max_strategy_exposure_pct + strategy_drawdown_limit_pct from per-strategy fill attribution | Per-strategy capital budgets | execution/risk_engine.py; execution/positions.py | SE-09 | 2026-09-25
186 | 5 | Risk & Portfolio | RK-01 | Risk Management | Kill switch scopes + auto-trigger | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Global flag file + config | Per-strategy/symbol; auto-trigger | orders/risk.py | RK-07; RK-08 | 2026-09-24
187 | 5 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: portfolio/emergency.py plan + confirm code (10 min) -> kill switch ON, cancel open W4 orders, sell PAPER book; LIVE = sell list only, never an order; /api/risk/emergency-exit (risk:approve); dashboard button | Independent QA | portfolio/emergency.py; dashboard/portfolio_risk_routes.py | RK-01 | 2026-09-28
188 | 5 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: portfolio/optimize.py min_variance / mean_variance / max_sharpe / risk_parity; long-only, max/min weight, sector caps (FISTA + exact Dykstra projection); shrunk covariance; frontier; stored runs | Independent QA; expected-return model review | portfolio/optimize.py | RK-12 | 2026-09-28
189 | 5 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | IMPLEMENTED BUT NOT VERIFIED | 80% | W25 | Branch w25 (not deployed) | Independent QA | W25: rebalance_plan (NEW/ADD/REDUCE/EXIT/HOLD, band, min trade, costs, turnover); portfolio strategy kind reweight_band_pct emits ADD/REDUCE with exact quantity | Independent QA; backtest engine still trades whole positions | portfolio/optimize.py; strategy_engine/kinds.py; strategy_engine/engine.py | PF-10 | 2026-09-28
190 | 5 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: risk_attribution per position / sector variance share, component VaR, beta, systematic vs idiosyncratic | Independent QA | portfolio/risk.py | PF-10 | 2026-09-28
191 | 5 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | IMPLEMENTED BUT NOT VERIFIED | 75% | W25 | Branch w25 (not deployed) | Independent QA | W25: holdings-based contribution by position / sector, beta-alpha split vs NIFTY50, Brinson allocation/selection vs equal-weighted universe | Independent QA; trade-based attribution needs a LIVE trade ledger | portfolio/risk.py | PF-13 | 2026-09-28
192 | 5 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | IMPLEMENTED BUT NOT VERIFIED | 70% | W25 | Branch w25 (not deployed) | Independent QA | W25: CAGR from pnl_daily equity; PAPER book + per-position XIRR from paper fills (wealth ledger XIRR in W15.5) | Independent QA; LIVE XIRR needs a trade ledger | portfolio/risk.py; wealth/perf/metrics.py | PF-13 | 2026-09-28
193 | 5 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | IMPLEMENTED BUT NOT VERIFIED | 85% | W25 | Branch w25 (not deployed) | Independent QA | W25: /trading Portfolio risk panels: KPIs, VaR/ES table, concentration, risk contribution, correlation heatmap, performance attribution, emergency exit | Independent QA | dashboard/execution_page.py | RK-12 | 2026-09-28
194 | 6 | Execution | EX-02 | Execution | Order types | IN PROGRESS | 60% |  | — | Development | W4 OMS: MARKET and LIMIT through the paper adapter; order type from config | Stop-loss / stop-limit order types | execution/order_manager.py; execution/adapters.py |  | 2026-09-25
195 | 6 | Execution | EX-08 | Execution | Order modify/cancel | IN PROGRESS | 50% |  | — | Development | Cancel with explicit CANCEL_PENDING state; status refresh; no modify | Order modify | execution/order_manager.py |  | 2026-09-25
196 | 6 | Execution | BR-05 | Broker Integration | Execution reconciliation | IN PROGRESS | 30% |  | — | Development | Partial reconcile code | EOD reconciliation job + alert | orders/ |  | 2026-09-24
197 | 6 | Execution | BR-06 | Broker Integration | Connection health | IN PROGRESS | 40% |  | — | Development | broker-status route; WS stall detection | Health checks + alerts | dashboard/server.py | MON-03 | 2026-09-24
198 | 6 | Execution | RK-17 | Risk Management | Broker/operational risk | IN PROGRESS | 50% |  | — | Development | Kill switch + live-trading gate + broker failure -> FAILED order state with context | Broker health / stale-data checks | execution/config.py; execution/order_manager.py | BR-06 | 2026-09-25
199 | 6 | Execution | BR-08 | Broker Integration | Sandbox | IN PROGRESS | 30% |  | — | Development | SANDBOX env defined | Verify sandbox path end-to-end | orders/environment.py |  | 2026-09-24
200 | 6 | Execution | EX-09 | Execution | Measured slippage | IN PROGRESS | 30% |  | — | Development | Fill price and decision reference price stored per order/fill (slippage derivable) | Slippage metric + report | execution/order_manager.py | PF-13 | 2026-09-25
201 | 6 | Execution | EX-10 | Execution | Execution analytics | IN PROGRESS | 30% |  | — | Development | oms_order / oms_order_event / oms_execution / oms_fill audit tables and APIs | Fill-rate / slippage / rejection analytics | execution/* | EX-09 | 2026-09-25
202 | 6 | Execution | BR-02 | Broker Integration | Zerodha/Kite | IN PROGRESS | 50% |  | — | Development | Holdings sync only | Token refresh; orders if wanted | portfolio/zerodha.py |  | 2026-09-24
203 | 6 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | IN PROGRESS | 25% |  | — | Development | Dashboard partial | Live P&L panel | dashboard/server.py | PF-13 | 2026-09-24
204 | 6 | Execution | SEC-03 | Security | Audit logging | IN PROGRESS | 85% |  | — | Development | enterprise_audit hash chain (prev_hash/row_hash, verify_chain) + append-only triggers on enterprise_audit and oms_order_event; mutating API requests audited even with the enterprise layer off; config changes and secret rotations audited | Export / retention; off-box audit copy | enterprise/audit.py; ops/migrations.py; ops/http.py |  | 2026-09-25
205 | 7 | Advanced Quant | DP-04 | Data Platform | Tick data | YET TO START | 5% |  | — | Development | live_ticks exists; 0 rows | Tick ingestion + storage | data/dhan.py | DBS-04 | 2026-09-24
206 | 7 | Advanced Quant | DP-05 | Data Platform | Order book / depth | YET TO START | 5% |  | — | Development | FULL feed type defined (CLI only) | Depth capture + schema | data/dhan.py | DP-04 | 2026-09-24
207 | 7 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | IN PROGRESS | 25% |  | — | Development | Intraday features from live_quotes; tick/depth pending | Tick / depth feed | quant/microstructure.py | DP-05 | 2026-09-25
208 | 7 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors | BLOCKED | 20% |  | — | Owner: Derivatives data source | Black-Scholes / greeks / IV / basis maths + schema; no derivatives data | Derivatives data source | quant/derivatives.py | DP-08 | 2026-09-25
209 | 7 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | IN PROGRESS | 40% |  | — | Development | Volatility estimators and regime; IV needs options data | Options data | quant/volatility.py | DP-08 | 2026-09-25
210 | 7 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | IN PROGRESS | 70% |  | — | Development | Pairs registry, spreads, cointegration screen, W3 pairs kind (short leg not executable) | Shortable instrument | quant/statarb.py; quant/pairs.py; strategy_engine/kinds.py | QR-04 | 2026-09-25
211 | 7 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | IN PROGRESS | 65% |  | — | Development | Cross-sectional ranking + portfolio kind with dollar/beta/sector neutrality (shorts not executable) | Shortable instrument | quant/engine.py; quant/portfolio.py; strategy_engine/kinds.py | DP-08 | 2026-09-25
212 | 7 | Advanced Quant | QR-09 | Quant Research | Event-driven research | IN PROGRESS | 45% |  | — | Development | market_event from corporate_actions + bulk_deals; ev_* strategy features; typed interface for pending sources | Earnings/dividend/macro sources | quant/events.py | DP-06 | 2026-09-25
213 | 7 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | IN PROGRESS | 50% |  | — | Development | Value/quality/growth factors + vqm / vqmg composites (fundamental_data empty) | Fundamentals ingestion | quant/factors.py; quant/composite.py | DP-15 | 2026-09-25
214 | 7 | Advanced Quant | EX-11 | Execution | Execution algos | YET TO START | 0% |  | — | Development | None | Implement | — | DP-03 | 2026-09-24
215 | 7 | Advanced Quant | EX-12 | Execution | Market impact model | YET TO START | 0% |  | — | Development | None | Implement | — | DP-05 | 2026-09-24
216 | 7 | Advanced Quant | EX-15 | Execution | Latency telemetry | YET TO START | 0% |  | — | Development | None | Instrument data and order paths | — |  | 2026-09-24
217 | 7 | Advanced Quant | EX-16 | Execution | Event-driven OMS | YET TO START | 10% |  | — | Development | Synchronous calls | Implement | — | EX-15 | 2026-09-24
218 | 7 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | YET TO START | 0% |  | — | Development | Bar loops only | Implement | — | EX-16 | 2026-09-24
219 | 7 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | YET TO START | 0% |  | — | Development | None | Macro connectors + calendar | — |  | 2026-09-24
220 | 7 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | YET TO START | 0% |  | — | Development | None | DataSource interface | — |  | 2026-09-24
221 | 7 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | YET TO START | 0% |  | — | Development | None | Add sources | — | AD-01 | 2026-09-24
222 | 7 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | YET TO START | 5% |  | — | Development | SQLite only | Parquet/DuckDB store | — |  | 2026-09-24
223 | 7 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | YET TO START | 0% |  | — | Development | Global display tickers only | MCX/CDS/bond/MF feeds | — |  | 2026-09-24
224 | 8 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | IMPLEMENTED BUT NOT VERIFIED | 75% | W24 | Live (ATIP-W24-RC1) | Independent QA | W24: model + factor IC decay monitoring with alerts | Needs factor history (W22 backfill) | ml/decay.py | QR-02; ML-09 | 2026-09-27
225 | 8 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | IN PROGRESS | 60% |  | — | Development | Verified daily backups + retention; DR runbook with RPO 24 h / RTO ~10 min; pre-release backup procedure | Off-site backup target; scheduled restore drill; backup encryption | ops/backup.py; docs/DISASTER_RECOVERY.md | DBS-03 | 2026-09-25
226 | 8 | Production Hardening | SEC-04 | Security | Encryption | IN PROGRESS | 50% |  | — | Development | AES-256-GCM field encryption (ops/crypto.py, key from ATIP_ENCRYPTION_KEY, AAD-bound, no plaintext fallback); used for MFA secrets; sensitive-field classification; TLS 1.3 reverse-proxy architecture documented (ATIP stays on 127.0.0.1) | Encrypt broker credentials (ENT-06); key rotation re-encryption; TLS only with ENT-07 | ops/crypto.py; docs/SECURITY_ARCHITECTURE.md |  | 2026-09-25
227 | 8 | Production Hardening | API-05 | APIs | API contracts/docs | IN PROGRESS | 40% |  | — | Development | Error envelope + codes, versioning, pagination, idempotency and security headers documented | Generated API reference | docs/PRODUCTION_ARCHITECTURE.md; ops/errors.py |  | 2026-09-25
228 | 8 | Production Hardening | API-06 | APIs | Widget JSON schemas | YET TO START | 5% |  | — | Development | None | Define schemas | — |  | 2026-09-24
229 | 8 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | IN PROGRESS | 60% |  | — | Development | W8 set: production architecture, security, observability, DR, backup/restore, deployment, rollback, operations runbook, production configuration | User guide; API reference | docs/ |  | 2026-09-25
230 | 9 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | IN PROGRESS | 60% |  | — | Development | Tenants + lifecycle + limits; tenant_id on tenant-owned W3-W6 tables; middleware isolation (single-resource 404, list filtering, create stamping); single shared paper book | Per-tenant paper books / broker accounts; SQL-level scoping | enterprise/tenants.py; enterprise/authz.py; db/schema.py | OPS-05 | 2026-09-25
231 | 9 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | YET TO START | 0% |  | — | Owner: Move to Postgres | SQLite | Migrate to Postgres | — | ENT-01 | 2026-09-24
232 | 9 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure | BLOCKED | 5% |  | — | Owner: Security architecture + decision to expose | Not implemented by design: W7 keeps the 127.0.0.1 bind; exposure needs TLS, MFA, rate limiting, security review | Owner decision + security architecture | dashboard/security.py | ENT-01 | 2026-09-25
233 | 9 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | IN PROGRESS | 85% |  | — | Development | Users + 8 roles + 27 permissions, per-tenant roles, route->permission middleware; W8 TOTP MFA (enroll/confirm/disable, admin reset, login otp, encrypted secret, replay-refusing) | WebAuthn / recovery codes | enterprise/mfa.py; enterprise/users.py; enterprise/authz.py | ENT-07 | 2026-09-25
234 | 9 | Enterprise SaaS (final objective) | ENT-05 | Security | Session management | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | Sessions (digest-only, expiry, revoke) + W8 refresh tokens: rotation on every use, reuse detection revokes the family and all sessions, HttpOnly cookie scoped to /api/auth/refresh | Validate | enterprise/users.py; dashboard/enterprise_routes.py | SEC-02 | 2026-09-25
235 | 9 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | IN PROGRESS | 70% |  | — | Development | Admin-created users (must change password), optional self-registration (PENDING + own FREE-trial tenant), activation, reset tokens; no e-mail | E-mail verification | enterprise/users.py; dashboard/enterprise_routes.py | SEC-02 | 2026-09-25
236 | 9 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | IN PROGRESS | 65% |  | — | Development | Profile + preferences; tenant/user trading profiles (trading enabled, modes, brokers, assets, strategies, capital, order value) — tighten W4 only | Per-user capital accounting | enterprise/profiles.py; execution/risk_engine.py | ENT-02 | 2026-09-25
237 | 9 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | YET TO START | 0% |  | — | Owner: Design broker credential vault | Not built: per-user broker credential vault (Claude does not handle credentials) | Design with the owner | — | SEC-02 | 2026-09-25
238 | 9 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | YET TO START | 0% |  | — | Owner: Legal / SEBI review | None | Legal review before offering to other users | — |  | 2026-09-24
239 | 9 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | YET TO START | 0% |  | — | Development | None | Implement controls from ENT-14 | — | ENT-14 | 2026-09-24
240 | 9 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | YET TO START | 0% |  | — | Development | None | Privacy policy + controls | — | ENT-14 | 2026-09-24
241 | 9 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | IN PROGRESS | 40% |  | — | Development | Multi-user sign-in (/login, /account, /admin) on the existing dashboard; still local-only | Blocked on ENT-07 for any exposure | dashboard/enterprise_*.py | SEC-02 | 2026-09-25
242 | 9 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | IN PROGRESS | 45% |  | — | Owner: Payment gateway | Plans (limits/features, no invented prices), subscriptions, usage metering, DRAFT invoices; no payment gateway | Payment gateway (owner decision) | enterprise/billing.py | ENT-02 | 2026-09-25
243 | 9 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | IN PROGRESS | 40% |  | — | Development | Multiple concurrent sessions per user with IP/user agent; revoke all | Device management UI | enterprise/users.py | ENT-05 | 2026-09-25
244 | 9 | Enterprise SaaS (final objective) | ENT-19 | Channels | Watchlists | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | Per-user / shared watchlists | Validate | enterprise/workspace.py | ENT-08 | 2026-09-25
245 | 9 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | IN PROGRESS | 55% |  | — | Development | Per-user alert rules on any W3/W6 feature, evaluated post-market into notifications; AI alerts via ml_* features | Intraday evaluation | enterprise/workspace.py | ENT-19 | 2026-09-25
246 | 9 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | IN PROGRESS | 45% |  | — | Development | In-app inbox + preferences; Telegram (owner bot, default tenant only); no e-mail/SMS/push | E-mail / push channels | enterprise/notifications.py | ENT-11 | 2026-09-25
247 | 9 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | YET TO START | 0% |  | — | Owner: Mobile apps | None | Build apps | — | API-03 | 2026-09-24
248 | 9 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | IN PROGRESS | 55% |  | — | Development | API keys with scopes; W8 /api/v1/* alias of the current API (API-Version header), pagination/sort/filter on v1 lists, standard error envelope, request ids | Per-route v1 contract (OpenAPI) and deprecation policy | ops/http.py; ops/errors.py | SEC-02 | 2026-09-25
249 | 9 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | IN PROGRESS | 60% |  | — | Development | Inbound POST /api/webhooks/{source}: HMAC-SHA256 signature, 300 s replay window, event-id dedupe; outbound signed delivery with backoff retry, DEAD letter, per-host circuit breaker | Business consumers (billing / broker postbacks); endpoint admin UI | ops/webhooks.py; dashboard/ops_routes.py | API-03 | 2026-09-25
250 | 9 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | YET TO START | 0% |  | — | Development | None | Importers | — | ENT-06 | 2026-09-24
251 | 9 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | YET TO START | 0% |  | — | Development | None | Adapters behind BR-03 interface | — | ENT-06; BR-03 | 2026-09-24
252 | 9 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | YET TO START | 0% |  | — | Development | Equity cash only | Asset-specific execution/risk adapters | — | DP-21; BR-07 | 2026-09-24
253 | 9 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | IN PROGRESS | 30% |  | — | Development | Saved report definitions (tenant-owned); rendering reuses existing pages/APIs | Report rendering / export | enterprise/workspace.py | PF-13 | 2026-09-25
254 | 9 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | IN PROGRESS | 60% |  | — | Development | /admin: users, tenants, roles, plans, audit; admin API | Richer console | dashboard/enterprise_page.py; dashboard/enterprise_routes.py | SEC-02 | 2026-09-25
255 | 9 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | YET TO START | 0% |  | — | Development | None | Visual builder on SE-01 interface | — | SE-01; ENT-08 | 2026-09-24
256 | 9 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | YET TO START | 0% |  | — | Development | None | Implement | — | ENT-08 | 2026-09-24
257 | 9 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | YET TO START | 0% |  | — | Owner: Cloud deployment | Local Windows only | Containerise; IaC; environments | — | DBS-05; ENT-07 | 2026-09-24
258 | 9 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | IN PROGRESS | 35% |  | — | Development | Observability: JSON logs with request/correlation ids and secret masking, Prometheus-format metrics, health endpoints, monitoring rules; scalability path documented | HA / horizontal scale (needs DBS-05 Postgres) | ops/logs.py; ops/metrics.py; ops/health.py; docs/OBSERVABILITY.md | OPS-04 | 2026-09-25
259 | 8 | Production hardening | SEC-06 | Security | API security hardening | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | OpsMiddleware: 2 MB limit (413), JSON content-type/parse checks (415/400), optional token-bucket rate limit (429), nosniff/DENY/no-referrer/COOP/Permissions-Policy, no-store on auth/account/admin, HSTS only with TLS, CORS only when origins configured | Enable rate limiting in production config | ops/http.py |  | 2026-09-25
260 | 8 | Production hardening | OPS-08 | Deployment/Ops | Configuration management | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | ATIP_ENV / environment (development/test/staging/production), config.<env>.json overlay, ATIP__SECTION__KEY overrides, validation (production refuses to start on errors), fingerprint + ops_config_version + audit of changed keys, feature flags | Validate | ops/config.py; ops/startup.py |  | 2026-09-25
261 | 8 | Production hardening | OPS-09 | Deployment/Ops | Scheduler hardening | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | ops_job_lock per job name (stale-owner takeover), scheduler heartbeat every 60 s, SKIPPED run when another runner holds the job, job metrics | Validate | ops/jobs.py; pipeline/scheduler.py |  | 2026-09-25
262 | 8 | Production hardening | OPS-10 | Deployment/Ops | Resilience + idempotency | IN PROGRESS | 60% |  | — | Development | ops/resilience.py primitives (orders marked non-idempotent: never retried); Idempotency-Key on mutating API (orders from /trading keyed per decision/order) | Wrap existing data-source calls with breakers/retry | ops/resilience.py; ops/idempotency.py |  | 2026-09-25
263 | 8 | Production hardening | MON-09 | Monitoring | Operational alerting | COMPLETED | 75% |  | Live (ATIP-W24-RC1) |  | ops_monitor every 15 min, 12 rules, FIRING/RESOLVED state with 6 h re-notify, delivered via the W1 alert channel (alert_log + Telegram when configured) | Tune thresholds after observation | ops/monitor.py |  | 2026-09-25
264 | 8 | Production hardening | RK-19 | Risk | Stale-data trade protection | COMPLETED | 80% |  | Live (ATIP-W24-RC1) |  | Risk check market_data_fresh (BUY rejected when last bar > 2 sessions behind); LIVE orders validated against the NSE session; live gate additionally requires environment production | Validate | execution/risk_engine.py; execution/order_manager.py; execution/config.py |  | 2026-09-25
265 | 8 | Production hardening | OPS-11 | Deployment/Ops | Release management & deployment | IN PROGRESS | 80% |  | — | Development | Tag ATIP-W9-RC2; ops/release.py preflight/manifest/postcheck/record; deploy/deploy_release.ps1 + rollback_release.ps1 (dry-run default); requirements.lock.txt; release docs | Authorized deployment + first executed rollback drill | ops/release.py; deploy/; docs/PRODUCTION_DEPLOYMENT.md |  | 2026-09-26
266 | 8 | Production hardening | RK-20 | Risk | Unified live-trading master switch | COMPLETED | 90% |  | Live (ATIP-W24-RC1) |  | W1 real orders (order rules, aggressive strategy) also require execution.live_trading_enabled + environment production (BLOCKED_LIVE_DISABLED otherwise); W4 gate + Dhan adapter refusal unchanged | Validate | orders/broker.py; ops/trading_safety.py |  | 2026-09-26
267 | 10 | Wealth track (Waves 11-20) | INV-001 | Wealth | Investor DNA | IMPLEMENTED BUT NOT VERIFIED | 80% | W11 | Live (ATIP-W24-RC1) | Independent QA | W11: Risk capacity / tolerance / requirement, horizon, behaviour, personality | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/dna.py |  | 2026-09-26
268 | 10 | Wealth track (Waves 11-20) | WLT-001 | Wealth | Multi-asset wealth dashboard | IMPLEMENTED BUT NOT VERIFIED | 80% | W12 | Live (ATIP-W24-RC1) | Independent QA | W12: Unified holdings, net worth, allocation, concentration, overlay | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/holdings.py; wealth/assets.py | INV-001 | 2026-09-26
269 | 10 | Wealth track (Waves 11-20) | GOL-001 | Wealth | Goal planning engine | IMPLEMENTED BUT NOT VERIFIED | 80% | W13 | Live (ATIP-W24-RC1) | Independent QA | W13: Corpus, contributions, CAGR, shortfall, Monte Carlo, scenarios | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/goals.py | INV-001; WLT-001 | 2026-09-26
270 | 10 | Wealth track (Waves 11-20) | AAL-001 | Wealth | Dynamic asset allocation | IMPLEMENTED BUT NOT VERIFIED | 80% | W14 | Live (ATIP-W24-RC1) | Independent QA | W14: Strategic + tactical from DNA, goals, regime, ATIP signals | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/allocation.py | INV-001; GOL-001 | 2026-09-26
271 | 10 | Wealth track (Waves 11-20) | RBL-001 | Wealth | Portfolio rebalancing | IMPLEMENTED BUT NOT VERIFIED | 80% | W15 | Live (ATIP-W24-RC1) | Independent QA | W15: Drift, triggers, cost-aware plans (tax-neutral) | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/rebalance.py | WLT-001; AAL-001 | 2026-09-26
272 | 10 | Wealth track (Waves 11-20) | PERF-001 | Wealth | Investor performance attribution | IMPLEMENTED BUT NOT VERIFIED | 80% | W15.5 | Live (ATIP-W24-RC1) | Independent QA | W15.5: Model / executable / actual / benchmark; attribution; audit; export | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/perf/ | RBL-001 | 2026-09-26
273 | 10 | Wealth track (Waves 11-20) | AIA-001 | Wealth | AI investment advisor | IMPLEMENTED BUT NOT VERIFIED | 80% | W16 | Live (ATIP-W24-RC1) | Independent QA | W16: Evidence-backed, suitability-checked; optional Claude narration | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/advisor.py | PERF-001 | 2026-09-26
274 | 10 | Wealth track (Waves 11-20) | INT-001 | Wealth | Integrated intelligence | IMPLEMENTED BUT NOT VERIFIED | 80% | W17 | Live (ATIP-W24-RC1) | Independent QA | W17: Investor cycle, overview, modes, signal suitability | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/integrated.py | AIA-001 | 2026-09-26
275 | 10 | Wealth track (Waves 11-20) | QA-001 | Wealth | Wealth QA / security / performance | IN PROGRESS | 60% | W18 | Live (ATIP-W24-RC1) | Development | W18: 70-test suite, security review (S1/S2 fixed), performance | Independent testing (ChatGPT) + UAT; merge after authorization | tests/test_wealth_*.py | INT-001 | 2026-09-26
276 | 10 | Wealth track (Waves 11-20) | UAT-001 | Wealth | Beta / UAT | IN PROGRESS | 60% | W19 | Live (ATIP-W24-RC1) | Development | W19: Personas, persona view, feedback, UAT plan | Independent testing (ChatGPT) + UAT; merge after authorization | wealth/uat.py | QA-001 | 2026-09-26
277 | 10 | Wealth track (Waves 11-20) | REL-001 | Wealth | Wealth production hardening | IMPLEMENTED BUT NOT VERIFIED | 80% | W20 | Live (ATIP-W24-RC1) | Independent QA | W20: Migration 0005, /health/wealth, monitor, backup, docs, RC | Independent testing (ChatGPT) + UAT; merge after authorization | ops/migrations.py; wealth/health.py | UAT-001 | 2026-09-26

## Built - Needs QA
Seq | Phase Name | ID | Module | Feature | Completion % | Wave | Current Implementation | Next Action / Missing Work | Needs
88 | Foundation | TA-06 | Technical Analysis | Support/Resistance | 80% | W21 | W21: fractal pivots over 120 sessions, mean-anchored clusters, nearest confirmed support/resistance with touches and distance | QA; optionally feed the Technical Score SR component | Independent QA
92 | Quant Research (data, factors, backtesting) | DP-03 | Data Platform | Intraday bars | 85% | W21 | W21: intraday_bars stores the 30-min job's 15-min bars (was discarded); 90-day retention | QA; consider 5-min bars for session VWAP | Independent QA
93 | Quant Research (data, factors, backtesting) | TA-03 | Technical Analysis | VWAP | 80% | W21 | W21: vwap_20d, vwap_session (intraday bars), vwap_dev_pct in technical_ext; strategy feature vwap_dev_pct | Owner: technical.vwap_in_score (changes scores); QA | Independent QA; Owner: technical.vwap_in_score (changes scores)
95 | Quant Research (data, factors, backtesting) | TA-04 | Technical Analysis | Volume Profile | 80% | W21 | W21: volume profile POC/VAH/VAL over 20 sessions (intraday or daily basis) | QA | Independent QA
96 | Quant Research (data, factors, backtesting) | TA-10 | Technical Analysis | Multi-timeframe analysis | 80% | W21 | W21: weekly RSI/trend, monthly trend, mtf_alignment -3..+3 | QA | Independent QA
97 | Quant Research (data, factors, backtesting) | TA-12 | Technical Analysis | Full-history indicator panel | 70% | W21 | W21: python -m data.technical --backfill N (tracked universe, resumable) | Run the backfill (owner timing; copy first) | Independent QA; Owner: When to run the indicator backfill
98 | Quant Research (data, factors, backtesting) | AF-03 | Alpha/Factor Engine | Factor panel persistence | 85% | W22 | W22: score_components stores every ATIP index's sub-components per symbol/date (weighted_score label capture; scores unchanged) | QA | Independent QA
99 | Quant Research (data, factors, backtesting) | AF-04 | Alpha/Factor Engine | Standalone factor families | 80% | W22 | W22: 11 standalone factors: mean reversion, trend, volume, recovery, risk (BRI) | QA; research on full history | Independent QA
100 | Quant Research (data, factors, backtesting) | AF-02 | Alpha/Factor Engine | Normalisation contract | 85% |  | W6 quant/normalize.py per-factor spec (winsorize/zscore/percentile/rank/minmax/sector/neutralize) -- tracker was stale | QA | Independent QA
101 | Quant Research (data, factors, backtesting) | AF-01 | Alpha/Factor Engine | Factor library/registry | 85% |  | W6 registry quant_factor + factor sets + content-hash versioning (tracker was stale); W22 adds 11 factors | QA | Independent QA
102 | Quant Research (data, factors, backtesting) | SC-18 | Alpha/Factor Engine | Formula registry/versioning | 85% | W22 | W22: formula_registry resolves each signal_log weights_hash to the full weight set + code version | QA | Independent QA
103 | Quant Research (data, factors, backtesting) | DBS-07 | Database | Research registry tables | 80% | W22 | W22: research_study + research_link registry, frozen on conclusion | QA | Independent QA
104 | Quant Research (data, factors, backtesting) | QR-01 | Quant Research | Information coefficient | 80% | W22 | W22: backfill_scores + research_report run IC for every factor | Run full-history backfill + report | Independent QA
105 | Quant Research (data, factors, backtesting) | QR-02 | Quant Research | IC decay / half-life | 80% | W22 | W22: IC decay 1/5/10/20 for every factor in research_report | Run on full history | Independent QA
106 | Quant Research (data, factors, backtesting) | QR-03 | Quant Research | Factor correlation/redundancy | 80% | W22 | W22: redundancy report (pairs ¦rho¦>=0.7) in research_report | Run on full history | Independent QA
108 | Quant Research (data, factors, backtesting) | AF-08 | Alpha/Factor Engine | Factor approval gate | 80% | W22 | W22: evidence-based approval gate, decision history, lifecycle enforcement behind quant.require_approved_factors | Owner: enable after review | Independent QA; Owner: quant.require_approved_factors
113 | Quant Research (data, factors, backtesting) | BT-12 | Backtesting | VaR/CVaR in backtest | 85% | W23 | W23: historical VaR/CVaR 95/99, parametric VaR, skew, kurtosis in every backtest's metrics | QA | Independent QA
122 | Quant Research (data, factors, backtesting) | BT-04 | Backtesting | Parameter optimisation | 80% | W23 | W23: grid / random / adaptive optimiser with trial runs, test-window refusal, Deflated Sharpe + overfit warning | QA; optional true Bayesian search | Independent QA
123 | Quant Research (data, factors, backtesting) | QR-11 | Quant Research | Parameter sensitivity | 80% | W23 | W23: one-at-a-time sensitivity curves, stability, knife-edge flags, 2-D heat map | QA | Independent QA
124 | Quant Research (data, factors, backtesting) | BT-14 | Backtesting | Robustness | 80% | W23 | W23: robustness battery (costs x2, slippage x3, universe halves, period halves, regimes, Monte Carlo) with verdict | QA | Independent QA
125 | Quant Research (data, factors, backtesting) | QR-12 | Quant Research | Reproducibility / experiment tracking | 80% |  | W6 experiments + W22 studies linking experiments/backtests/research | QA | Independent QA
126 | Quant Research (data, factors, backtesting) | QR-07 | Quant Research | Momentum/trend research | 70% | W23 | W23: momentum breakout strategy + end-to-end study (optimise/validate/sensitivity/robustness/test) | Run full-universe study; review | Independent QA
127 | Quant Research (data, factors, backtesting) | QR-08 | Quant Research | Mean-reversion research | 70% | W23 | W23: RSI(2) mean-reversion strategy + study; 12-stock smoke: REJECTED out of sample | Run full-universe study; review | Independent QA
129 | Quant Research (data, factors, backtesting) | TA-09 | Technical Analysis | Beta 3y / rolling 60 | 70% | W21 | W21: beta_60, beta_downside, beta_long (>=500 sessions) | Owner: prices_daily retention >= 1,100 days for a 3-year beta | Independent QA; Owner: prices_daily retention >= 1,100 days
130 | Quant Research (data, factors, backtesting) | SC-16 | Alpha/Factor Engine | Beta Risk Index | 75% | W21 | W21: Beta Risk Index 0-100 (level, downside, instability); strategy feature bri | QA; decide if it joins a composite | Independent QA
131 | Quant Research (data, factors, backtesting) | TA-11 | Technical Analysis | Extended indicator catalogue | 80% | W21 | W21: Supertrend, Ichimoku, Keltner, Donchian, MFI, CMF, ROC, Aroon, PSAR; stoch/Williams %R/CCI now computed | QA | Independent QA
135 | Quant Research (data, factors, backtesting) | DP-11 | Data Platform | GIFT Nifty | 75% | W21 | W21: daily GIFTNIFTY close from index_levels into prices_daily | Pre-open panel (DB-04) | Independent QA
138 | Quant Research (data, factors, backtesting) | DP-13 | Data Platform | Sector data | 80% | W21 | W21: 8 sector index series in the daily Dhan sync + sector_breadth table | Run --backfill-sectors; QA | Independent QA
157 | AI/ML | ML-07 | AI/ML | Feature selection | 80% | W24 | W24: importance-stability selection -> new feature-set version | QA | Independent QA
158 | AI/ML | ML-08 | AI/ML | Model validation | 85% | W24 | W24: purged expanding walk-forward reports vs baselines, IC, calibration, verdict | QA | Independent QA
159 | AI/ML | ML-01 | AI/ML | Supervised ML | 80% | W24 | W24: native numpy GBM + random forest; bootstrap trains + validates first models (TRAINED, not ACTIVE); real-data smoke: NO_EDGE on 5-day direction | Richer features / labels; full-universe validation | Independent QA
161 | AI/ML | ML-11 | AI/ML | Ensemble models | 80% | W24 | W24: ensemble model type blended by held-out loss | QA | Independent QA
162 | AI/ML | ML-09 | AI/ML | Model monitoring/drift | 80% | W24 | W24: drift (PSI share) + realised decay alerts, ml_health_check, monitor rule | QA | Independent QA
163 | AI/ML | ML-10 | AI/ML | Explainability | 85% | W24 | W24: exact path contributions for trees, gain importances, out-of-sample permutation importance | QA | Independent QA
164 | AI/ML | ML-05 | AI/ML | Regime detection | 75% | W24 | W24: market_regime model preset validated + trained (NO_EDGE on smoke) | Owner decides regime provider after evidence | Independent QA; Owner: Regime provider (after evidence)
165 | AI/ML | ML-03 | AI/ML | Unsupervised learning | 75% | W24 | W24: k-means++ factor clusters with profiles; return PCA | QA | Independent QA
166 | AI/ML | ML-06 | AI/ML | Anomaly detection | 75% | W24 | W24: robust-z + multivariate anomaly scan, CA-explained, post-market (flag off) | Owner: ml.anomalies_enabled | Independent QA; Owner: ml.anomalies_enabled
177 | Risk & Portfolio | PF-03 | Portfolio | Exposure / sector allocation | 90% | W25 | W25: portfolio/risk.py book_snapshot for PAPER and LIVE books (weights, % equity, sector exposure); /api/risk/portfolio; /trading Portfolio risk panel | Independent QA | Independent QA
178 | Risk & Portfolio | PF-04 | Portfolio | Concentration/diversification | 90% | W25 | W25: concentration() max/top-5 weight, HHI, effective N, sector HHI; in /api/risk/portfolio and snapshots | Independent QA | Independent QA
179 | Risk & Portfolio | PF-09 | Portfolio | Correlation | 90% | W25 | W25: portfolio correlation matrix, weighted avg pairwise correlation, high pairs, diversification ratio; heatmap on /trading | Independent QA | Independent QA
180 | Risk & Portfolio | RK-11 | Risk Management | Correlation risk | 85% | W25 | W25: W4 limit max_avg_correlation (value-weighted correlation of the new symbol with the held book; fail closed); analytics in /api/risk/portfolio | Independent QA; owner sets the limit (default off) | Independent QA
181 | Risk & Portfolio | RK-12 | Risk Management | Portfolio VaR/ES | 85% | W25 | W25: historical / parametric / Monte Carlo VaR and ES, 95/99%, 1 and 10 days; W4 limit max_portfolio_var_pct (post-trade); snapshot job + VaR alert (off by default) | Independent QA; owner sets limit / enables portfolio_risk.snapshot_enabled | Independent QA
183 | Risk & Portfolio | RK-09 | Risk Management | Volatility limits | 85% | W25 | W25: W4 limit max_symbol_volatility_pct (annualised 60-session vol; fail closed) | Independent QA; owner sets the limit (default off) | Independent QA
184 | Risk & Portfolio | RK-10 | Risk Management | Liquidity limits | 85% | W25 | W25: W4 cap max_adv_participation_pct (qty <= % of 20-session ADV) and W1 risk_limits.max_adv_participation_pct (BUY and SELL, unmeasurable -> refused) | Independent QA; owner sets the limit (default off) | Independent QA
187 | Risk & Portfolio | RK-16 | Risk Management | Emergency exit | 85% | W25 | W25: portfolio/emergency.py plan + confirm code (10 min) -> kill switch ON, cancel open W4 orders, sell PAPER book; LIVE = sell list only, never an order; /api/risk/emergency-exit (risk:approve); dashboard button | Independent QA | Independent QA
188 | Risk & Portfolio | PF-10 | Portfolio | Portfolio optimisation | 85% | W25 | W25: portfolio/optimize.py min_variance / mean_variance / max_sharpe / risk_parity; long-only, max/min weight, sector caps (FISTA + exact Dykstra projection); shrunk covariance; frontier; stored runs | Independent QA; expected-return model review | Independent QA
189 | Risk & Portfolio | PF-06 | Portfolio | Rebalancing | 80% | W25 | W25: rebalance_plan (NEW/ADD/REDUCE/EXIT/HOLD, band, min trade, costs, turnover); portfolio strategy kind reweight_band_pct emits ADD/REDUCE with exact quantity | Independent QA; backtest engine still trades whole positions | Independent QA
190 | Risk & Portfolio | PF-07 | Portfolio | Risk attribution | 85% | W25 | W25: risk_attribution per position / sector variance share, component VaR, beta, systematic vs idiosyncratic | Independent QA | Independent QA
191 | Risk & Portfolio | PF-08 | Portfolio | Performance attribution | 75% | W25 | W25: holdings-based contribution by position / sector, beta-alpha split vs NIFTY50, Brinson allocation/selection vs equal-weighted universe | Independent QA; trade-based attribution needs a LIVE trade ledger | Independent QA
192 | Risk & Portfolio | PF-11 | Portfolio | CAGR/XIRR analytics | 70% | W25 | W25: CAGR from pnl_daily equity; PAPER book + per-position XIRR from paper fills (wealth ledger XIRR in W15.5) | Independent QA; LIVE XIRR needs a trade ledger | Independent QA
193 | Risk & Portfolio | DB-17 | Dashboard | Risk dashboard | 85% | W25 | W25: /trading Portfolio risk panels: KPIs, VaR/ES table, concentration, risk contribution, correlation heatmap, performance attribution, emergency exit | Independent QA | Independent QA
224 | Production Hardening | MON-05 | Monitoring | Model/factor decay monitoring | 75% | W24 | W24: model + factor IC decay monitoring with alerts | Needs factor history (W22 backfill) | Independent QA
267 | Wealth track (Waves 11-20) | INV-001 | Wealth | Investor DNA | 80% | W11 | W11: Risk capacity / tolerance / requirement, horizon, behaviour, personality | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
268 | Wealth track (Waves 11-20) | WLT-001 | Wealth | Multi-asset wealth dashboard | 80% | W12 | W12: Unified holdings, net worth, allocation, concentration, overlay | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
269 | Wealth track (Waves 11-20) | GOL-001 | Wealth | Goal planning engine | 80% | W13 | W13: Corpus, contributions, CAGR, shortfall, Monte Carlo, scenarios | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
270 | Wealth track (Waves 11-20) | AAL-001 | Wealth | Dynamic asset allocation | 80% | W14 | W14: Strategic + tactical from DNA, goals, regime, ATIP signals | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
271 | Wealth track (Waves 11-20) | RBL-001 | Wealth | Portfolio rebalancing | 80% | W15 | W15: Drift, triggers, cost-aware plans (tax-neutral) | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
272 | Wealth track (Waves 11-20) | PERF-001 | Wealth | Investor performance attribution | 80% | W15.5 | W15.5: Model / executable / actual / benchmark; attribution; audit; export | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
273 | Wealth track (Waves 11-20) | AIA-001 | Wealth | AI investment advisor | 80% | W16 | W16: Evidence-backed, suitability-checked; optional Claude narration | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
274 | Wealth track (Waves 11-20) | INT-001 | Wealth | Integrated intelligence | 80% | W17 | W17: Investor cycle, overview, modes, signal suitability | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA
277 | Wealth track (Waves 11-20) | REL-001 | Wealth | Wealth production hardening | 80% | W20 | W20: Migration 0005, /health/wealth, monitor, backup, docs, RC | Independent testing (ChatGPT) + UAT; merge after authorization | Independent QA

## In Progress
Seq | Phase Name | ID | Module | Feature | Completion % | Wave | Current Implementation | Next Action / Missing Work | Needs
74 | Foundation | DP-15 | Data Platform | Fundamentals | 30% |  | Screener.in fetcher; ingestion disabled | Your decision; enable; quarterly store; no 50.0 default | Owner: Enable fundamentals ingestion (Screener.in)
75 | Foundation | SC-13 | Alpha/Factor Engine | Fundamental Score | 20% |  | Default 50 when unparsed | Implement FS formula on real data | Development
76 | Foundation | SC-02 | Alpha/Factor Engine | SPI | 30% |  |  | Implement SPI formula separately from FS | Development
91 | Quant Research (data, factors, backtesting) | DP-01 | Data Platform | Live market data | 60% |  | Index WebSocket 09:00-15:45 + quote cache; stock tick feed never run | Stock-level live feed in production; failover | Development
133 | Quant Research (data, factors, backtesting) | SC-06 | Alpha/Factor Engine | MSI | 55% |  | Options/PCR frozen; news rule-based | Real PCR; AI news later | Development
136 | Quant Research (data, factors, backtesting) | DB-04 | Dashboard | GIFT Nifty panel | 60% |  | In index strip | Dedicated pre-open view | Development
137 | Quant Research (data, factors, backtesting) | DP-12 | Data Platform | Global markets | 70% |  | 13 yfinance tickers | Bond yields; history depth | Development
139 | Quant Research (data, factors, backtesting) | DP-16 | Data Platform | Institutional data | 25% |  | Bulk/block only | Promoter/SAST/PIT/MF feeds | Development
140 | Quant Research (data, factors, backtesting) | SC-14 | Alpha/Factor Engine | Institutional Score | 40% |  | FII + bulk only | Add MF/promoter/insider | Development
141 | Quant Research (data, factors, backtesting) | AD-03 | Alternative Data | Bulk/block deal signal | 40% |  | Feeds INS | Validate with IC | Development
153 | Strategy Engine | SG-08 | Signal Engine | Intraday scans | 60% |  | Scheduled 12:30 and 14:45 | Use stored intraday bars | Development
154 | Strategy Engine | DB-11 | Dashboard | Crash Risk + Top 25 SPI/MSI lists | 40% |  | CRI per-stock column only | Dedicated lists | Development
155 | Strategy Engine | DB-16 | Dashboard | Strategy performance panel | 30% |  | /strategies list shows latest signals; per-strategy P&L from W4 fills on /trading | Performance panel | Development
167 | AI/ML | SE-05 | Strategy Engine | AI-driven strategies | 60% |  | ml_* strategy features (point in time, out of sample); ml_direction / atip_ml_blend (DRAFT); W4 risk check ml_model_active blocks signals of non-ACTIVE models | Activate once a model is ACTIVE | Owner: Activate a model (after evidence)
168 | AI/ML | NS-02 | News/Sentiment | News classification | 30% |  | Claude classifier coded; key unset | Set key; taxonomy; cost cap | Owner: Provide a working Anthropic API key (current key 401)
169 | AI/ML | NS-03 | News/Sentiment | Sentiment + confidence | 40% |  | Rule-based; confidence frozen 50 | Model-based scoring | Development
171 | AI/ML | NS-04 | News/Sentiment | AI news summary | 50% |  | Headline list | LLM summary | Development
172 | AI/ML | DB-06 | Dashboard | AI News Summary panel | 50% |  | News panel (rule-based) | Show AI summary | Development
176 | AI/ML | DB-18 | Dashboard | Quant/model panel | 40% |  | /ml page: models, versions, lifecycle, predictions, feature sets, datasets, training runs | Monitoring charts | Development
194 | Execution | EX-02 | Execution | Order types | 60% |  | W4 OMS: MARKET and LIMIT through the paper adapter; order type from config | Stop-loss / stop-limit order types | Development
195 | Execution | EX-08 | Execution | Order modify/cancel | 50% |  | Cancel with explicit CANCEL_PENDING state; status refresh; no modify | Order modify | Development
196 | Execution | BR-05 | Broker Integration | Execution reconciliation | 30% |  | Partial reconcile code | EOD reconciliation job + alert | Development
197 | Execution | BR-06 | Broker Integration | Connection health | 40% |  | broker-status route; WS stall detection | Health checks + alerts | Development
198 | Execution | RK-17 | Risk Management | Broker/operational risk | 50% |  | Kill switch + live-trading gate + broker failure -> FAILED order state with context | Broker health / stale-data checks | Development
199 | Execution | BR-08 | Broker Integration | Sandbox | 30% |  | SANDBOX env defined | Verify sandbox path end-to-end | Development
200 | Execution | EX-09 | Execution | Measured slippage | 30% |  | Fill price and decision reference price stored per order/fill (slippage derivable) | Slippage metric + report | Development
201 | Execution | EX-10 | Execution | Execution analytics | 30% |  | oms_order / oms_order_event / oms_execution / oms_fill audit tables and APIs | Fill-rate / slippage / rejection analytics | Development
202 | Execution | BR-02 | Broker Integration | Zerodha/Kite | 50% |  | Holdings sync only | Token refresh; orders if wanted | Development
203 | Execution | MON-04 | Monitoring | Live strategy/P&L monitoring | 25% |  | Dashboard partial | Live P&L panel | Development
204 | Execution | SEC-03 | Security | Audit logging | 85% |  | enterprise_audit hash chain (prev_hash/row_hash, verify_chain) + append-only triggers on enterprise_audit and oms_order_event; mutating API requests audited even with the enterprise layer off; config changes and secret rotations audited | Export / retention; off-box audit copy | Development
207 | Advanced Quant | AF-07 | Alpha/Factor Engine | Microstructure factors | 25% |  | Intraday features from live_quotes; tick/depth pending | Tick / depth feed | Development
209 | Advanced Quant | QR-10 | Quant Research | Volatility strategies | 40% |  | Volatility estimators and regime; IV needs options data | Options data | Development
210 | Advanced Quant | QR-05 | Quant Research | Stat-arb / pairs / cointegration | 70% |  | Pairs registry, spreads, cointegration screen, W3 pairs kind (short leg not executable) | Shortable instrument | Development
211 | Advanced Quant | QR-06 | Quant Research | Cross-sectional / market-neutral | 65% |  | Cross-sectional ranking + portfolio kind with dollar/beta/sector neutrality (shorts not executable) | Shortable instrument | Development
212 | Advanced Quant | QR-09 | Quant Research | Event-driven research | 45% |  | market_event from corporate_actions + bulk_deals; ev_* strategy features; typed interface for pending sources | Earnings/dividend/macro sources | Development
213 | Advanced Quant | AF-05 | Alpha/Factor Engine | Value/quality composites | 50% |  | Value/quality/growth factors + vqm / vqmg composites (fundamental_data empty) | Fundamentals ingestion | Development
225 | Production Hardening | OPS-06 | Deployment/Ops | DR / backup automation | 60% |  | Verified daily backups + retention; DR runbook with RPO 24 h / RTO ~10 min; pre-release backup procedure | Off-site backup target; scheduled restore drill; backup encryption | Development
226 | Production Hardening | SEC-04 | Security | Encryption | 50% |  | AES-256-GCM field encryption (ops/crypto.py, key from ATIP_ENCRYPTION_KEY, AAD-bound, no plaintext fallback); used for MFA secrets; sensitive-field classification; TLS 1.3 reverse-proxy architecture documented (ATIP stays on 127.0.0.1) | Encrypt broker credentials (ENT-06); key rotation re-encryption; TLS only with ENT-07 | Development
227 | Production Hardening | API-05 | APIs | API contracts/docs | 40% |  | Error envelope + codes, versioning, pagination, idempotency and security headers documented | Generated API reference | Development
229 | Production Hardening | OPS-05 | Deployment/Ops | Documentation set | 60% |  | W8 set: production architecture, security, observability, DR, backup/restore, deployment, rollback, operations runbook, production configuration | User guide; API reference | Development
230 | Enterprise SaaS (final objective) | ENT-01 | Enterprise Platform | Multi-tenant architecture | 60% |  | Tenants + lifecycle + limits; tenant_id on tenant-owned W3-W6 tables; middleware isolation (single-resource 404, list filtering, create stamping); single shared paper book | Per-tenant paper books / broker accounts; SQL-level scoping | Development
233 | Enterprise SaaS (final objective) | SEC-02 | Security | Users / RBAC / MFA | 85% |  | Users + 8 roles + 27 permissions, per-tenant roles, route->permission middleware; W8 TOTP MFA (enroll/confirm/disable, admin reset, login otp, encrypted secret, replay-refusing) | WebAuthn / recovery codes | Development
235 | Enterprise SaaS (final objective) | ENT-02 | User Management | User registration/onboarding | 70% |  | Admin-created users (must change password), optional self-registration (PENDING + own FREE-trial tenant), activation, reset tokens; no e-mail | E-mail verification | Development
236 | Enterprise SaaS (final objective) | ENT-03 | User Management | User profile + risk profile | 65% |  | Profile + preferences; tenant/user trading profiles (trading enabled, modes, brokers, assets, strategies, capital, order value) — tighten W4 only | Per-user capital accounting | Development
241 | Enterprise SaaS (final objective) | ENT-08 | Channels | Multi-user web app | 40% |  | Multi-user sign-in (/login, /account, /admin) on the existing dashboard; still local-only | Blocked on ENT-07 for any exposure | Development
242 | Enterprise SaaS (final objective) | ENT-04 | User Management | Subscriptions & billing | 45% |  | Plans (limits/features, no invented prices), subscriptions, usage metering, DRAFT invoices; no payment gateway | Payment gateway (owner decision) | Owner: Payment gateway
243 | Enterprise SaaS (final objective) | ENT-18 | User Management | Multi-device login | 40% |  | Multiple concurrent sessions per user with IP/user agent; revoke all | Device management UI | Development
245 | Enterprise SaaS (final objective) | ENT-11 | Channels | Per-user price & AI alerts | 55% |  | Per-user alert rules on any W3/W6 feature, evaluated post-market into notifications; AI alerts via ml_* features | Intraday evaluation | Development
246 | Enterprise SaaS (final objective) | ENT-10 | Channels | Notification channels | 45% |  | In-app inbox + preferences; Telegram (owner bot, default tenant only); no e-mail/SMS/push | E-mail / push channels | Development
248 | Enterprise SaaS (final objective) | API-03 | APIs | Versioned public API | 55% |  | API keys with scopes; W8 /api/v1/* alias of the current API (API-Version header), pagination/sort/filter on v1 lists, standard error envelope, request ids | Per-route v1 contract (OpenAPI) and deprecation policy | Development
249 | Enterprise SaaS (final objective) | API-04 | APIs | Webhooks | 60% |  | Inbound POST /api/webhooks/{source}: HMAC-SHA256 signature, 300 s replay window, event-id dedupe; outbound signed delivery with backoff retry, DEAD letter, per-host circuit breaker | Business consumers (billing / broker postbacks); endpoint admin UI | Development
253 | Enterprise SaaS (final objective) | ENT-12 | Reporting | Reports | 30% |  | Saved report definitions (tenant-owned); rendering reuses existing pages/APIs | Report rendering / export | Development
254 | Enterprise SaaS (final objective) | ENT-13 | Administration | Administration console | 60% |  | /admin: users, tenants, roles, plans, audit; admin API | Richer console | Development
258 | Enterprise SaaS (final objective) | ENT-16 | Deployment/Ops | Scalability, HA & observability | 35% |  | Observability: JSON logs with request/correlation ids and secret masking, Prometheus-format metrics, health endpoints, monitoring rules; scalability path documented | HA / horizontal scale (needs DBS-05 Postgres) | Development
262 | Production hardening | OPS-10 | Deployment/Ops | Resilience + idempotency | 60% |  | ops/resilience.py primitives (orders marked non-idempotent: never retried); Idempotency-Key on mutating API (orders from /trading keyed per decision/order) | Wrap existing data-source calls with breakers/retry | Development
265 | Production hardening | OPS-11 | Deployment/Ops | Release management & deployment | 80% |  | Tag ATIP-W9-RC2; ops/release.py preflight/manifest/postcheck/record; deploy/deploy_release.ps1 + rollback_release.ps1 (dry-run default); requirements.lock.txt; release docs | Authorized deployment + first executed rollback drill | Development
275 | Wealth track (Waves 11-20) | QA-001 | Wealth | Wealth QA / security / performance | 60% | W18 | W18: 70-test suite, security review (S1/S2 fixed), performance | Independent testing (ChatGPT) + UAT; merge after authorization | Development
276 | Wealth track (Waves 11-20) | UAT-001 | Wealth | Beta / UAT | 60% | W19 | W19: Personas, persona view, feedback, UAT plan | Independent testing (ChatGPT) + UAT; merge after authorization | Development

## Yet To Start
Seq | Phase Name | ID | Module | Feature | Completion % | Wave | Current Implementation | Next Action / Missing Work | Needs
132 | Quant Research (data, factors, backtesting) | DP-08 | Data Platform | Derivatives data | 0% |  | None | NSE F&O bhavcopy + option chain store | Owner: Choose a derivatives data source
170 | AI/ML | NS-05 | News/Sentiment | Novelty/decay/source weighting | 5% |  | None | Implement | Development
173 | AI/ML | NS-06 | News/Sentiment | Earnings call / announcement NLP | 0% |  | None | Implement | Development
174 | AI/ML | ML-02 | AI/ML | Deep learning | 0% |  | None | Only if validated benefit | Development
175 | AI/ML | ML-04 | AI/ML | Reinforcement learning | 0% |  | None | Low priority | Development
205 | Advanced Quant | DP-04 | Data Platform | Tick data | 5% |  | live_ticks exists; 0 rows | Tick ingestion + storage | Development
206 | Advanced Quant | DP-05 | Data Platform | Order book / depth | 5% |  | FULL feed type defined (CLI only) | Depth capture + schema | Development
214 | Advanced Quant | EX-11 | Execution | Execution algos | 0% |  | None | Implement | Development
215 | Advanced Quant | EX-12 | Execution | Market impact model | 0% |  | None | Implement | Development
216 | Advanced Quant | EX-15 | Execution | Latency telemetry | 0% |  | None | Instrument data and order paths | Development
217 | Advanced Quant | EX-16 | Execution | Event-driven OMS | 10% |  | Synchronous calls | Implement | Development
218 | Advanced Quant | BT-17 | Backtesting | Event-driven backtester | 0% |  | Bar loops only | Implement | Development
219 | Advanced Quant | DP-14 | Data Platform | Macroeconomic data | 0% |  | None | Macro connectors + calendar | Development
220 | Advanced Quant | AD-01 | Alternative Data | Alt-data framework | 0% |  | None | DataSource interface | Development
221 | Advanced Quant | AD-02 | Alternative Data | Alt-data sources | 0% |  | None | Add sources | Development
222 | Advanced Quant | DP-22 | Data Platform | Point-in-time data lake | 5% |  | SQLite only | Parquet/DuckDB store | Development
223 | Advanced Quant | DP-21 | Data Platform | Multi-asset data | 0% |  | Global display tickers only | MCX/CDS/bond/MF feeds | Development
228 | Production Hardening | API-06 | APIs | Widget JSON schemas | 5% |  | None | Define schemas | Development
231 | Enterprise SaaS (final objective) | DBS-05 | Database | Scalable database | 0% |  | SQLite | Migrate to Postgres | Owner: Move to Postgres
237 | Enterprise SaaS (final objective) | ENT-06 | Security | Per-user broker credential vault | 0% |  | Not built: per-user broker credential vault (Claude does not handle credentials) | Design with the owner | Owner: Design broker credential vault
238 | Enterprise SaaS (final objective) | ENT-14 | Compliance | Regulatory approvals | 0% |  | None | Legal review before offering to other users | Owner: Legal / SEBI review
239 | Enterprise SaaS (final objective) | SEC-05 | Security | Compliance monitoring | 0% |  | None | Implement controls from ENT-14 | Development
240 | Enterprise SaaS (final objective) | ENT-17 | Compliance | Data privacy | 0% |  | None | Privacy policy + controls | Development
247 | Enterprise SaaS (final objective) | ENT-09 | Channels | Mobile apps | 0% |  | None | Build apps | Owner: Mobile apps
250 | Enterprise SaaS (final objective) | PF-12 | Portfolio | Multi-broker import | 0% |  | None | Importers | Development
251 | Enterprise SaaS (final objective) | BR-07 | Broker Integration | Additional brokers | 0% |  | None | Adapters behind BR-03 interface | Development
252 | Enterprise SaaS (final objective) | ENT-15 | Execution | Multi-asset trading | 0% |  | Equity cash only | Asset-specific execution/risk adapters | Development
255 | Enterprise SaaS (final objective) | SE-10 | Strategy Engine | No/low-code strategy builder | 0% |  | None | Visual builder on SE-01 interface | Development
256 | Enterprise SaaS (final objective) | ML-16 | AI/ML | AI chat assistant | 0% |  | None | Implement | Development
257 | Enterprise SaaS (final objective) | OPS-04 | Deployment/Ops | Cloud deployment | 0% |  | Local Windows only | Containerise; IaC; environments | Owner: Cloud deployment
208 | Advanced Quant | AF-06 | Alpha/Factor Engine | Derivatives factors (BLOCKED) | 0.2 |  | Black-Scholes / greeks / IV / basis maths + schema; no derivatives data | Derivatives data source | Owner: Derivatives data source
232 | Enterprise SaaS (final objective) | ENT-07 | Security | Secure internet exposure (BLOCKED) | 0.05 |  | Not implemented by design: W7 keeps the 127.0.0.1 bind; exposure needs TLS, MFA, rate limiting, security review | Owner decision + security architecture | Owner: Security architecture + decision to expose

## Owner Decisions
# | Decision | Affects | Default now | Why it matters | Your decision | Date
1 | Turn on the scheduled investor cycle (wealth.enabled) | W11-W17 | off | Daily snapshots, allocation, goal and rebalance checks, wealth alerts. Save your Investor DNA first.
2 | Enable Claude narration of the advisor (wealth.advisor_llm_enabled) | W16 | off | Sends your holdings/goals evidence pack to Anthropic; needs a working API key.
3 | Provide a working Anthropic API key | NS-02..04, W16 | key returns 401 | News classification/summary and advisor narration are all blocked; the news catch-up is slow while every call fails.
4 | VWAP inside the Technical Score (technical.vwap_in_score) | TA-03 | off | Changes every Technical Score, ATIP score and signal.
5 | prices_daily retention >= 1,100 days | TA-09 | 600 days | Needed for a true 3-year beta; roughly doubles the database.
6 | Run the technical backfill (python -m data.technical --backfill 426) | TA-12 | not run | Heavy; off-hours, on a copy first.
7 | Run the factor backfill + research report | QR-01..03, AF-08, MON-05 | 25 sessions only | ~40 s per session for 13 factors; several hours for full history.
8 | Require approved factors for strategies (quant.require_approved_factors) | AF-08 | off | Blocks promotion of strategies that use unapproved factors.
9 | Daily anomaly scan (ml.anomalies_enabled) | ML-06 | off | Flags unusual price/volume days.
10 | Activate an ML model / choose the ML regime provider | SE-05, ML-05 | none active | Validation shows NO_EDGE today: keep off until a report shows EDGE.
11 | Set the W25 pre-trade limits (volatility / ADV / correlation / portfolio VaR) and portfolio_risk.snapshot_enabled | RK-09..12 | all off | New pre-trade limits and the daily risk snapshot; suggested start: ADV 5%, VaR alert 2% of equity.
12 | Deploy W25 (portfolio risk) | W25 | branch only | Merge w25-portfolio-risk to master and deploy with deploy_release.ps1.
13 | Enable fundamentals ingestion | DP-15, SC-13, SC-02, AF-05 | disabled | Unlocks the fundamental score, SPI and value/quality factors.
14 | Choose a derivatives data source | DP-08, AF-06, QR-10, SC-06 | none | Options/futures analytics and PCR are blocked without it.
15 | Fix the Dhan intraday bar fetch (dhan_15min_bars fails with 0 rows) | DP-03, TA-03 session VWAP | failing since 2026-09-25 or earlier | Storage is live; no bars arrive until the broker intraday call works (subscription?).
16 | Security architecture + decision to expose ATIP | ENT-07, ENT-08, OPS-04 | localhost only | Gate for any multi-user / internet use.
17 | Payment gateway; legal / SEBI review | ENT-04, ENT-14 | not started | Needed before offering ATIP to others.

## Open Issues
ID | Issue | Where | Severity | Status | Seen
OPS-DH15 | dhan_15min_bars job fails every run (0 rows) -- intraday bars cannot be stored | data/dhan.py / broker | Medium | OPEN | 2026-09-25
KD-001 | Anthropic API key returns 401 (news classifier, advisor narration) | .env / config | Medium | OPEN | 2026-09-28
W8-R4 | 7 secrets still in config.json plaintext | atip_data/config.json | Medium | OPEN | 2026-09-28
WLT-1 | LIVE ledger sells inferred at the close until contract notes are entered | wealth/perf/ledger.py | Medium | OPEN | 2026-09-26
WLT-3 | DNA / allocation / scenario methodology not validated against outcomes | wealth/ | Medium | OPEN | 2026-09-26
ML-EDGE | First ML models show NO_EDGE out of sample on 5-day direction | ml/ | Info | OPEN | 2026-09-28
QA-ALL | W3-W24 not independently tested; 70-test wealth suite written, not run | tests/ | High | OPEN | 2026-09-28

## Waves & Deployment
Wave | Scope | Commit | In master | Deployed | Testing
W1 | Foundation: job monitoring, alerts, P&L, loss limits, sizing, data quality | 3c13f63 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | COMPLETED
W2 | Research / backtesting | ba4028f | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | COMPLETED
W3 | Strategy engine | d563978 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W4 | Risk and execution (paper) | d3b8715 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W5 | AI / ML framework | 123b340 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W6 | Advanced quant | cf1997d | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W7 | Enterprise layer | 3e52bea | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W8 | Production hardening | a7d7187 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W9 | Release readiness, live-trading master switch | 24943f3 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W11 | Investor DNA | 1da609f | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W12 | Multi-asset wealth dashboard | 45f0b4b | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W13 | Goal planning | 9680ee6 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W14 | Dynamic asset allocation | c790b95 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W15 | Rebalancing | 643ad57 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W15.5 | Performance attribution | 8210de6 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W16 | Explainable advisor | 4340cc8 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Not verified
W17 | Integrated intelligence | 8346d8d | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Smoke only
W18 | QA suite + security fixes | 757116e | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Suite not run
W19 | UAT tooling | 7c837be | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | UAT not done
W20 | Wealth hardening, migration 0005 | 11a8924 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Smoke only
W21 | Data & technical analysis | 52893af | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Smoke only
W22 | Factor research platform | 609c6d6 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Smoke only
W23 | Research & backtesting depth | c00e6a7 | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Smoke only
W24 | Machine learning | 0e648af | yes | Live since 2026-09-28 11:31 (ATIP-W24-RC1) | Smoke only
W25 | Portfolio risk: exposure, VaR/ES, correlation, attribution, optimiser, limits, emergency exit | 687b5ac | no (branch w25-portfolio-risk) | Not deployed - needs your authorization | Smoke only